## MEMO
WHEN YOU INSERT THE QUANTITY PLEASE CHECK THE UNIT RATE SINCE SOME ITEMS RATE HAVE BEEN REVISED I`LL SEND U ANY REVISED RATE THEN U`LL CHOOSE THE ONE U WANT FOR THIS PAYMENT

## certificate
Contract No -
¾¡õÁ Ue¡` ¨[kƒ 16
CERTIFICATE OF PAYMENT No 15
e^¨<
| Project | DESSIE UCBP WWTP LOT 1 &2 NETWORK |  |  |  |  | Amount (Birr)
| x¨< |  |  |  | Main contract |  | 13219003.02
| Location | DESSIE |  |  | Supplementary contract |  | 16676057.32
[5 empty] | price adjustment |  | 6265671.42
| ›W]¨< S/u?ƒ |  |  |  | Variation Order |  | 2414403.13
| Owner | GIZ IS |  |  |  | vat 15% | 5786270.2335
¾e^ }s^ß
| Contractor | TRUST CONSTRUCTION |  |  | Total sum |  | 44361405.1235
›T"] SN”Ç=c
| consultant | MH ENGINEERING | [5 empty] | 15886770.77
Amount (Birr)
| ›v] uJ’¨< ¾¡õÁ c’É ØÁo SW[ƒ cŸ ³_ }s^Û ¾c^¨< c^ | [5 empty] | 39582211.3294 |  |  | 88.5
As per the attached statement the value of work executed to date is
}../VAT 15%/
[6 empty] | ÖpLL/TOTAL/ | 39582211.3294 | 141.6
| lØ` | k” | ¾Ñ”²u< M¡ w` | vat | Deduction | Amount (Birr)
| No | Date | Amount Br. |  | œckÉV ¾}ŸðK | 15759338.78
| 1 | Advance | 2643800.6 |  | Previous payment
|  | Advance | 2035059.24 |  | p“i |  |  |  | 274314.59
|  | Advance | 1174956.7
| 2 |  | 255208.54 | 48489.62 | Rebate 4%
| 3 |  | 423577.62 | 80479.75 | SÁ¹ | 1979110.5665
| 4 |  | 82540.68 | 23296 | Retention 5%
| 5 |  | 167561.53 | 33512.3 | SkÝ | [5 empty] | 20763292.2
| 6 |  | 113447.07 | 22689.42 | Penalty | [5 empty] | -18818919.1294
| 7 |  | 339070.94 | 67814.19 | ¾pÉT>Á ¡õÁ | 7560202.3639 |  |  |  |  | 6053576.9072
| 8 |  | 1283629.14 | 256725.82 | P.Advance Repayment20%
| 9 |  | 1665233.53 | 414950.22
| 10 |  | 951845.57 | 208372.5
| 11 |  | 6775944.39 | 1226685.8 | K?L
| 12 |  | 3701279.77 | 731478.21 | Others
[5 empty] | ÉU` | 25298651.7104
|  |  | 15759338.78 | 3114493.83 | Total
ÖpLL ለ}s^ß ¾T>ŸðM Ñ”²w
| Amount of advance taken birr |  | 5853816.54 |  | Total sum due to the contractor
| This payment repaid advance |  | 7560202.3639
| Out standing advance repayment |  | -1706385.8239
VAT PAYMENT
| Total Executed Amount |  | 39582211.3294
| Total 15 % VAT |  | 5937331.6994
| Previous VAT |  | 2363900.817
| Net VAT Payable on this paym. |  | 3573430.8824
| Total pay.to cont.inc.15%VAT |  | 3573430.8824
We certify that the contractor is now entitled to the sum of Three Million Eighty Five Thousand Sixty Two & 59/100 Birr Only
| ___________________ |  |  |  | __________________
| }[ÒÓጧM |  |  |  | çÉsM
| Certified |  |  |  | Approved

## Sheet1 (hidden)
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Emergency Storage Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
3 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
3.1 Excavation and earth work
Pit excavation ( Rock)
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 2
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Imhot Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
6 |  |  |  | 15/04/2011
|  |  |  | Number | Dimension | Quantity
6.1 Excavation and earth work
Pit excavation ( Rock)
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 3
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Emergency Storage Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
3 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
3.1.2 Pit excavation to a depth exceeding 1500mm but not
exceeding 3000mm ( Rock)
At=14.4*37.00=537.98 | 532.8
Ab=10.94*33.54=325.4 | 366.49
V=1/3h(At + Ab + √ At * Ab )
V=1/3*1.00(532.8+ 366.49+ √532.8*366.49)
V= 447.06M3 | [5 empty] | 447.06
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 4
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Emergency Storage Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
3 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
3.1.3Pit excavation to a depth exceeding 3000mm but not
exceeding 4500mm | (Rock)
At=10.94*33.54=366.93
Ab=9.2*31.8=292.56
V=1/3h(At + Ab + √ At * Ab )
V=1/3*.5(366.93+ 292.56+ √366.93*292.56)
V=164.52M3 | [5 empty] | 164.52
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 5
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Imhot Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
6 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
6.1.2 Pit excavation to a depth exceeding 1500mm but not
exceeding 3000mm | (Rock)
At=28.64*35.44=1015.00
Ab=25.18*31.98=805.26
V=1/3h(At + Ab + √ At * Ab )
V=1/3*1.00(1015+ 805.26+ √1015*805.26)
V=908.11M3 | [5 empty] | 908.11
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 6
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Imhot Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
6 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
6.1.3 Pit excavation to a depth exceeding 3000mm but not
exceeding 4500mm | (Rock)
At=25.18*31.98=805.26
Ab=19.98*26.78=535.06
V=1/3h(At + Ab + √ At * Ab )
V=1/3*1.5(805.26 + 535.06+ √805.26*535.06)
V=998.36M3 | [5 empty] | 1996.72
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 7
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Imhot Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
6 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
6.1.4 Pit excavation to a depth exceeding 4500mm but not
exceeding 6000mm | (Rock)
At=19.78*26.78=529.71
Ab=*14.78*21.58=318.95
V=1/3h(At + Ab + √ At * Ab )
V=1/3*1.5(529.71+ 318.95+ √529.71*318.95)
V=629.85M3 | [5 empty] | 629.85
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 8
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Imhot Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
6 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
6.1.5 Pit excavation to a depth exceeding 6000mm but not
exceeding 7500mm
At=14.78*21.58=318.95
Ab=9.58*16.38=156.92
V=1/3h(At + Ab + √ At * Ab )
V=1/3*1.5(318.95.+ 156.92+ √318.95*156.92)
V=349.79M3 | [5 empty] | 349.79
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction Plc |  |  |  | 1 |  | 9
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Semera |  |  | 1 | Imhot Tank
Item No: (only one item per sheet |  | Prepared by: |  | Date:
6 |  |  |  | 15/04/2011
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
6.1.6 Pit excavation to a depth exceeding 7500mm but not
exceeding 9000mm
At=9.58*16.38=156.92
Ab=8.2*15.00=123
V=1/3h(At + Ab + √ At * Ab )
V=1/3*.4(156.92+ 123+ √156.92*123)
V=55.85M3 | [5 empty] | 55.85
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GTZ-IS SM:

## SUMMARY
TRUST CONSTRUCTION
PROJECT: DESSIE UCBP WWTP
CONTRACTOR: TRUST CONSTRUCTION | [14 empty] | 1678066.9973
CONSULTANT: MH ENGINEERING PLC | [14 empty] | 1678066.9973
CLIENT : GIZ IS
Item | Description |  |  |  | unit | rate | Qty. |  |  |  | Amount ( Birr)
[7 empty] | Contract | Previous | Current | To-Date | Contract | Previous | Current | To-Date
LOT-1
1.SITE PREPARATION
1.1.1 | Site clearing |  |  |  | Ha | 11363.68 | 0.97 | 0.95 |  | 0.95 | 11022.7696 | 10795.496 | 0 | 10795.496
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.2 | Trench excavation |  |  |  | m3 | 26.17 | 218.03 | 940.5 |  | 940.5 | 5705.8451 | 24612.885 |  | 24612.885
0
1.1.3 | Bulk excavation all over the water threatment plant area |  |  |  | m3 | 26.11 | 17019.7 | 4799.07 |  | 4799.07 | 444384.367 | 125303.7177 | 0 | 125303.7177
[11 empty] | 0 | 0 | 0
1.1.4 | Load and cart awy surplus excavated material |  |  |  | m3 | 34.69 | 23706.02 | 9273.77 |  | 9273.77 | 822361.8338 | 321707.0813 | 0 | 321707.0813
1.1.5 | Backfill around Retaining Wall |  |  |  | m3 | 134.37 |  | 560.5 |  | 560.5 |  | 75314.385 | 0 | 75314.385
[10 empty] | 0 |  |  |  | 0
| 1.2 CONCRETE WORK | [8 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
1.2.1 | 50mm lean concrete quality c-5 | [8 empty] | 0 |  |  |  | 0
| a) Under strip foundation |  |  |  | M2 | 26.11 | 102.78 | 627 |  | 627 | 2683.5858 | 16370.97 | 0 | 16370.97
0
1.2.2 | Reinforced concrete quality c-25 | [12 empty] | 0
| a) In strip foundation |  |  |  | M3 | 1098.8 | 10.28 | 94.05 |  | 94.05 | 11295.664 | 103342.14 | 0 | 103342.14
1.2.3 | Provide,cut and fix in position of form work
| a) To strip foundation |  |  |  | M2 | 58.19 | 17.25 | 57 |  | 57 | 1003.7775 | 3316.83 | 0 | 3316.83
1.2.4 | Mild steel reinforcement
| a) Dia 8mm deformed bar |  |  |  | kg | 2.56 | 477.12 | 2551.95 |  | 2551.95 | 1221.4272 | 6532.992 | 0 | 6532.992
1.2 MASONRY WORK
1.2.1 | Average 1200mm thick hard trachytic
roughly dressed stone masonry retaining
| wall bedded in cement mortar 1:3 |  |  |  | M3 | 578.54 | 154.17 | 506.9 |  | 506.9 | 89193.5118 | 293261.926 | 0 | 293261.926
[10 empty] | 0 | 0 | 0 | 0 | 0
| Total carried to summary | [8 empty] | 19411.69 | 1388872.7818 | 980558.423 | 0 | 980558.423
3 EMERGENCY RETENTION TANK
3.1 EXCAVATION & EARTH WORK
3.1.1 | Pit excavation in ordinary soil for retention tank
| to a depth not exceeding 1500mm |  |  |  | M3 | 26.17 | 240.29 | 1651.78 |  | 1651.78 | 6288.3893 | 43227.0826 | 0 | 43227.0826
3.1.2 | Ditto but to a depth exceeding 1500mm but
| not exceeding 3000mm |  |  |  | M3 | 48.12 | 240.29 | 545.67 |  | 545.67 | 11562.7548 | 26257.6404 | 0 | 26257.6404
[10 empty] | 0 |  | 0 | 0 | 0
3.1.3 | Ditto as but to a depth exceeding 3000mm | [8 empty] | 0 |  | 0 | 0 | 0
| but not exceeding 4500mm |  |  |  | M3 | 72.18 | 48.06 | 327.4 |  | 327.4 | 3468.9708 | 23631.732 | 0 | 23631.732
[11 empty] | 0 | 0 | 0 | 0
[13 empty] | 0 | 0
3.1.4 | Fill around RC wall in non expansive excavated | [8 empty] | 0 |  | 0 | 0 | 0
| material from site |  |  |  | M3 | 34.11 | 239.58 | 0 | 0 | 0 | 8172.0738 | 0 | 0 | 0
[10 empty] | 0 |  | 0 | 0 | 0
3.1.5 | Load and cartaway surplus excavated material |  |  |  | M3 | 34.69 | 598.13 | 2765.72 |  | 2765.72 | 20749.1297 | 95942.8268 | 0 | 95942.8268
3.2 CONCRETE WORK
3.2.1 | 50mm lean concrete quality c-5, with minimum cement
content of150kg/m3 of concrete
| a/Under bottom slab |  |  |  | M2 | 35.47 | 270.9 | 270.9 |  | 270.9 | 9608.823 | 9608.823 | 0 | 9608.823
[10 empty] | 0 | 0 | 0 | 0 | 0
3.2.2 | Water tight reinforced concrete quality c-30,400kg | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC 400mmthick bottom slab |  |  |  | M3 | 1434.18 | 58.08 | 64.37 |  | 64.37 | 83297.1744 | 92318.1666 | 0 | 92318.1666
| b/ In RC 150mmthick bottom slab |  |  |  | M2 | 215.13 | 208.8 | 220.53 |  | 220.53 | 44919.144 | 47442.6189 | 0 | 47442.6189
| c/ In RC 400mm wall |  |  |  | M3 | 1434.18 | 77.72 | 107.2 |  | 107.2 | 111464.4696 | 153744.096 | 0 | 153744.096
3.2.3 | Provide,cut and fix in position sawn structural wood | [8 empty] | 0 | 0 | 0 | 0 | 0
| or steel form work which ever is appropriate | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC bottom slab |  |  |  | M2 | 58.19 | 51.68 | 29.04 |  | 29.04 | 3007.2592 | 1689.8376 | 0 | 1689.8376
| b/ In RC 400mm wall |  |  |  | M2 | 58.19 | 388.6 | 495.8 |  | 495.8 | 22612.634 | 28850.602 | 0 | 28850.602
[10 empty] | 0 | 0 | 0 | 0 | 0
3.2.4 | Mild steel reinforcement according to structural | [8 empty] | 0 | 0 | 0 | 0 | 0
| drawings. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a)Dia 10mmdeformed bar |  |  |  | kg | 2.02 | 0 | 287.77 |  | 287.77 | 0 | 581.2954 | 0 | 581.2954
| b)Dia 12mmdeformed bar |  |  |  | kg | 2.02 | 26144.86 | 10453.54 |  | 10453.54 | 52812.6172 | 21116.1508 | 0 | 21116.1508
| c)Dia 14mmdeformed bar |  |  |  | kg | 2.02 | 0 | 4399.44 |  | 4399.44 | 0 | 8886.8688 | 0 | 8886.8688
| b)Dia 16mm deformed bar |  |  |  | kg | 2.02 | 26139.7 | 8030.97 |  | 8030.97 | 52802.194 | 16222.5594 | 0 | 16222.5594
3.2.6 | Install aproved quality PVC water stopper at | [8 empty] | 0 | 0 | 0 | 0 | 0
| construction joints |  |  |  | ML | 235 | 10.5 | 115.77 |  | 115.77 | 2467.5 | 27205.95 | 0 | 27205.95
| Total carried to summary | [8 empty] | 29765.9 | 433233.1338 | 596726.2503 | 0 | 596726.2503
4. SAND TRAP
4.1 EXCAVATION & EARTH WORK
4.1.1 | Trench excavation in ordinary soil for sandtrap to 1500 mm depth starting from reduced ground level. |  |  |  | M3 | 26.17 | 73.5273 | 89.52 |  | 89.52 | 1924.2107 | 2342.7384 | 0 | 2342.7384
[10 empty] | 0 | 0 | 0 | 0 | 0
4.1.2 | Back fill around sandtrap with borrowed selected material from quarry waste and well ram in layers not exceeding 200mm thickness. |  |  |  | M3 | 101.87 | 17.93 | 89.52 |  | 89.52 | 1826.5291 | 9119.4024 | 0 | 9119.4024
[10 empty] | 0 | 0 | 0 | 0 | 0
4.1.3 | Load and cart away surplus excavated material to an appropriate tip. |  |  |  | M3 | 34.11 | 91.91 | 89.52 |  | 89.52 | 3135.0501 | 3053.5272 | 0 | 3053.5272
[10 empty] | 0 | 0 | 0 | 0 | 0
| 4.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
4.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Under sandtrap |  |  |  | M2 | 35.47 | 35.764 | 47.668 |  | 47.668 | 1268.5491 | 1690.784 | 0 | 1690.784
4.2.2 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In sandtrap |  |  |  | M3 | 1434.18 | 25.39 | 25.05 |  | 25.05 | 36413.8302 | 35926.209 | 0 | 35926.209
4.2.3 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To sandtrap |  |  |  | M2 | 58.19 | 145.96 | 149.86 |  | 149.86 | 8493.4124 | 8720.3534 | 0 | 8720.3534
4.2.4 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Dia. 10mm deformed bar |  |  |  | kg | 2.02 | 1188.7529 |  |  | 0 | 2401.2809 | 0 | 0 | 0
| a) Dia. 12mm deformed bar |  |  |  | kg | 2.02 |  | 4700.07 | 0 | 4700.07 | 0 | 9494.1414 | 0 | 9494.1414
4.2.5 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 87.68 | 11.85 |  | 11.85 | 20604.8 | 2784.75 | 0 | 2784.75
[10 empty] | 0 | 0 | 0 | 0 | 0
| Total carried to summary | [7 empty] | 0 | 5203.058 | 76067.6625 | 73131.9058 | 0 | 73131.9058
6. IMHOFF TANK (PRIMARY SEDIMENTATION TANK)
CIVIL WORK
6.1 EXCAVATION & EARTH WORK
6.1.1 | Pit excavation in ordinary soil for Imhoff tank to a depth not exceeding 1500mm. |  |  |  | M3 | 26.11 | 117.4838 | 869.2896 |  | 869.2896 | 3067.5007 | 22697.1515 | 0 | 22697.1515
6.1.2 | Ditto but exceeding 1500mm but not exceeding 3000mm. |  |  |  | M3 | 48.12 | 117.4838 | 869.2896 |  | 869.2896 | 5653.318 | 41830.2156 | 0 | 41830.2156
6.1.3 | Ditto but exceeding 3000mm but not exceeding 4500mm. |  |  |  | M3 | 72.18 | 117.4838 | 392.3394 |  | 392.3394 | 8479.9771 | 28319.0559 | 0 | 28319.0559
6.1.4 | Ditto but exceeding 4500mm but not exceeding 6000mm. |  |  |  | M3 | 96.24 | 117.4838 |  |  | 0 | 11306.6361 | 0 | 0 | 0
6.1.5 | Ditto but exceeding 6000mm but not exceeding 7500mm. |  |  |  | M3 | 120.3 | 117.4838 |  |  | 0 | 14133.2951 | 0 | 0 | 0
6.1.6 | Ditto but exceeding 7500mm but not exceeding 9000mm. |  |  |  | M3 | 144.36 | 98.6863 |  |  | 0 | 14246.3615 | 0 | 0 | 0
6.1.7 | Fill around RC wall in non expansive excavated material from the site well rolled and compacted in layers not exceeding 200 mm thick. |  |  |  | M3 | 34.11 | 146.29 | 202.8342 |  | 202.8342 | 4989.9519 | 6918.6759 | 0 | 6918.6759
6.1.8 | Load and cart away surplus excavated material to an appropriate tip. |  |  |  | M3 | 34.69 | 857.63 | 2602.91 |  | 2602.91 | 29751.1847 | 90294.9479 | 0 | 90294.9479
| 6.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
6.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Under bottom slab |  |  |  | M2 | 35.47 | 61.6225 | 154.8 |  | 154.8 | 2185.7501 | 5490.756 | 0 | 5490.756
8.2.2 | Cyclopean concrete class C-15, packed with 40% stone boulders and 60% concrete with minimum cement content of 280kg/m3 cement cast into form work and vibrated. |  |  |  | M3 | 631.94 | 584.5 | 378.91 |  | 378.91 | 369368.93 | 239448.3854 | 0 | 239448.3854
6.2.3 | Water tight Reinforced concrete quality C-30, | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In 500mm thick bottom slab |  |  |  | M3 | 1494.18 | 74.8 | 74.8 |  | 74.8 | 111764.664 | 111764.664 | 0 | 111764.664
| b) In 500mm thick RC wall |  |  |  | M3 | 1494.18 | 332.32 | 347.8 |  | 347.8 | 496545.8976 | 519675.804 | 0 | 519675.804
| c) In 250mm thick RC wall |  |  |  | M3 | 1494.18 | 9.805 | 10.51 |  | 10.51 | 14650.4349 | 15703.8318 | 0 | 15703.8318
| d) In 250mm thick suspended slab |  |  |  | M3 | 1494.18 | 1.4 | 1.4 |  | 1.4 | 2091.852 | 2091.852 | 0 | 2091.852
| e) In 300mm thick suspended slab |  |  |  | M3 | 1494.18 | 24 | 24 |  | 24 | 35860.32 | 35860.32 | 0 | 35860.32
| f) In 250mm thick incline slab |  |  |  | M3 | 1494.18 | 48.775 | 58.2 |  | 58.2 | 72878.6295 | 86961.276 | 0 | 86961.276
6.2.4 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To 250mm thick bottom slab |  |  |  | M2 | 130 | 25.8 | 89.784 |  | 89.784 | 3354 | 11671.92 | 0 | 11671.92
| b) To RC wall |  |  |  | M2 | 130 | 1415.92 | 1610.32 |  | 1610.32 | 184069.6 | 209341.6 | 0 | 209341.6
| c) In 250mm thick RC wall |  |  |  | M2 | 130 |  | 103.1 |  | 103.1 |  | 13403 | 0 | 13403
| d) To Suspended slab |  |  |  | M2 | 130 | 93.6 | 85.6 |  | 85.6 | 12168 | 11128 | 0 | 11128
| f) To 250mm thick inclined slab |  |  |  | m2 | 130 |  | 226.1 |  | 226.1 |  | 29393 | 0 | 29393
6.2.5 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 | 0 |  | 0
| a) dia 10mm deformed bar |  |  |  | Kg | 2.61 | 2284.4487 | 3066.23 |  | 3066.23 | 5962.411 | 8002.8603 | 0 | 8002.8603
| b) dia 12mm deformed bar |  |  |  | Kg | 2.02 | 4233.0028 | 4147.45 | 0 | 4147.45 | 8550.6656 | 8377.849 | 0 | 8377.849
* Var | dia 14 mm deformed bar |  |  |  | Kg | 2.02 |  |  |  | 0 | 0 | 0 | 0 | 0
| c) dia 16mm deformed bar |  |  |  | Kg | 2.02 | 8907.4944 | 8368.25 |  | 8368.25 | 17993.1387 | 16903.865 | 0 | 16903.865
| d) dia 20mm deformed bar |  |  |  | Kg | 2.02 | 46745.539 | 56277.92 |  | 56277.92 | 94425.9888 | 113681.3984 | 0 | 113681.3984
6.2.6 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 289.2 | 557 |  | 557 | 67962 | 130895 | 0 | 130895
| Total carried to summary | [7 empty] | 0 | 80518.8368 | 1591460.5073 | 1759855.4287 | 0 | 1759855.4287
7. AERATION TANK
CIVIL WORK
7.1 EXCAVATION & EARTH WORK
7.1.1 | Pit excavation in ordinary soil for aeration tank to a depth not exceeding 1500mm. |  |  |  | M3 | 26.11 | 77.61 |  |  | 0 | 2026.3971 | 0 | 0 | 0
7.1.2 | Fill around RC wall in non expansive excavated material from the site well rolled and compacted in layers not exceeding 200 mm thick. |  |  |  | M3 | 134.37 | 11.88 |  | 0 | 0 | 1596.3156 | 0 | 0 | 0
| Fill under Aeration Tank (VO-3) |  |  |  | M4 | 134.37 | 2925 | 2016.27 |  | 2016.27 | 393032.25 | 270926.1999 | 0 | 270926.1999
7.1.3 | Load and cart away surplus excavated material to an appropriate tip. |  |  |  | M3 | 34.69 | 97.01 |  |  | 0 | 3365.2769 | 0 | 0 | 0 |  |  | 0
| 7.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
7.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Under bottom slab |  |  |  | M2 | 35.47 | 167.2 | 167.2 | 0 | 167.2 | 5930.584 | 5930.584 | 0 | 5930.584
7.2.2 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In 250mm thick bottom slab |  |  |  | M3 | 1434.18 | 65.728 | 65.73 |  | 65.73 | 94265.783 | 94268.6514 | 0 | 94268.6514
| b) In Beam |  |  |  | M3 | 1434.18 | 4.1715 | 3.82 |  | 3.82 | 5982.6819 | 5478.5676 | 0 | 5478.5676
| c) In 400mm thick RC wall |  |  |  | M3 | 1434.18 | 117.84 | 156.62 | 0 | 156.62 | 169003.7712 | 224621.2716 | 0 | 224621.2716
| d) In 300mm thick RC wall |  |  |  | M3 | 1434.18 | 3.8 | 3.8 |  | 3.8 | 5449.884 | 5449.884 | 0 | 5449.884 |  |  | 0
| e) In 250mm thick RC wall |  |  |  | M3 | 1434.18 | 15.16 | 31.56 |  | 31.56 | 21742.1688 | 45262.7208 | 0 | 45262.7208
| f) In 250mm thick suspended slab |  |  |  | m3 | 1434.18 | 5.02 | 8.26 |  | 8.26 | 7199.5836 | 11846.3268 | 0 | 11846.3268
| g) In 400mm thick suspended slab |  |  |  | M3 | 1434.18 |  | 1.8 |  | 1.8 | 0 | 2581.524 | 0 | 2581.524
7.2.3 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To 250mm thick bottom slab |  |  |  | M2 | 58.19 | 27.85 | 22.96 | 0 | 22.96 | 1620.5915 | 1336.0424 | 0 | 1336.0424
| b) To Beam |  |  |  | M2 | 58.19 | 34.865 | 25.46 |  | 25.46 | 2028.7944 | 1481.5174 | 0 | 1481.5174
| c) To RC wall |  |  |  | M2 | 58.19 | 1233.8 | 1185.92 |  | 1185.92 | 71794.822 | 69008.6848 | 0 | 69008.6848
| f) To 250mm thick Suspended salb |  |  |  | M2 | 58.19 | 19.66 | 37.56 |  | 37.56 | 1144.0154 | 2185.6164 | 0 | 2185.6164
7.2.4 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Dia 10 mm deformed bar |  |  |  | Kg | 2.61 | 220.3986 | 1726.5 |  | 1726.5 | 575.2403 | 4506.165 | 0 | 4506.165
| b) Dia 12 mm deformed bar |  |  |  | Kg | 2.02 | 7180.2073 | 6973.72 |  | 6973.72 | 14504.0187 | 14086.9144 | 0 | 14086.9144
| c) Dia 16 mm deformed bar |  |  |  | Kg | 2.02 | 18906.5545 | 14639.36 |  | 14639.36 | 38191.2401 | 29571.5072 | 0 | 29571.5072
| d) Dia 20 mm deformed bar |  |  |  | Kg | 2.02 | 6007.9018 | 25102.42 | 0 | 25102.42 | 12135.9616 | 50706.8884 | 0 | 50706.8884
7.2.6 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 192 | 245.5 |  | 245.5 | 45120 | 57692.5 | 0 | 57692.5
| Total carried to summary | [7 empty] | 0 | 52414.46 | 896709.38 | 896941.5661 |  | 896941.5661
8. DORTMUND TANK (FINAL SEDIMENTATION TANK)
CIVIL WORK
8.1 EXCAVATION & EARTH WORK
8.1.1 | Pit excavation in ordinary soil for retention tank to a depth not exceeding 1500mm. |  |  |  | M3 | 26.17 | 135.375 | 642.735 |  | 642.735 | 3542.7638 | 16820.3749 | 0 | 16820.3749 |  |  | 0
8.1.2 | Ditto as item 8.1.1 but to a depth exceeding 1500mm but not exceeding 3000mm. |  |  |  | M3 | 48.12 | 135.375 | 642.735 |  | 642.735 | 6514.245 | 30928.4082 | 0 | 30928.4082
8.1.3 | Ditto as item 8.1.1 but to a depth exceeding 3000mm but not exceeding 4500mm. |  |  |  | M3 | 72.18 | 135.375 | 64.2735 |  | 64.2735 | 9771.3675 | 4639.2612 | 0 | 4639.2612
8.1.4 | Ditto as item 8.1.1 but to a depth exceeding 4500mm but not exceeding 6000mm. |  |  |  | M3 | 96.24 | 74.4064 |  |  | 0 | 7160.8695 | 0 | 0 | 0
8.1.7 | Fill around RC wall in non expansive excavated material from the site well rolled and compacted in layers not exceeding 200 mm thick. |  |  |  | M3 | 34.11 | 122.89 |  |  | 0 | 4191.7779 | 0 | 0 | 0
8.1.8 | Load and cart away surplus excavated material to an appropriate tip. |  |  |  | M3 | 34.69 | 600.66 | 1822.15 |  | 1822.15 | 20836.8954 | 63210.3835 | 0 | 63210.3835
| 8.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
8.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Under mat slab |  |  |  | M2 | 35.47 | 73.96 | 75.69 |  | 75.69 | 2623.3612 | 2684.7243 | 0 | 2684.7243
8.2.2 | Cyclopean concrete class C-15, packed with 40% stone boulders and 60% concrete with minimum cement content of 280kg/m3 cement cast into form work and vibrated. |  |  |  | M3 | 631.94 | 347.98 | 320.73 |  | 320.73 | 219902.4812 | 202682.1162 | 0 | 202682.1162
8.2.3 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8 .Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In 500mm thick bottom slab |  |  |  | M3 | 1494.18 | 36.125 | 47.865 |  | 47.865 | 53977.2525 | 71518.9257 | 0 | 71518.9257
| b) In 500mm thick RC wall |  |  |  | M3 | 1494.18 | 168.48 | 175.16 |  | 175.16 | 251739.4464 | 261720.5688 | 0 | 261720.5688 |  |  | 0
| c) In 250mm thick RC wall |  |  |  | M3 | 1494.18 | 12.8925 | 12.89 |  | 12.89 | 19263.7157 | 19259.9802 | 0 | 19259.9802
| d) In 250mm thick suspended slab |  |  |  | M3 | 1494.18 | 3.3 | 3.66 |  | 3.66 | 4930.794 | 5468.6988 | 0 | 5468.6988
| e) In 250mm thick inclined |  |  |  | M3 | 1494.18 | 67.875 | 37.33 |  | 37.33 | 101417.4675 | 55777.7394 | 0 | 55777.7394
8.2.4 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To 500mm thick bottom slab |  |  |  | M2 | 130 | 17 | 58.416 |  | 58.416 | 2210 | 7594.08 | 0 | 7594.08
| b) To 500mm thick RC wall |  |  |  | M2 | 130 | 665.42 | 713.36 |  | 713.36 | 86504.6 | 92736.8 | 0 | 92736.8
| c) To 250mm thick RC wall |  |  |  | M2 | 130 | 93.84 | 218.52 |  | 218.52 | 12199.2 | 28407.6 | 0 | 28407.6
| d) To 250mm thick Suspended slab |  |  |  | M2 | 130 | 23.14 | 23.79 |  | 23.79 | 3008.2 | 3092.7 | 0 | 3092.7
| e) To 250mm inclinedslab | e) In 250mm thick inclined |  |  | M2 | 130 |  | 132.85 |  | 132.85 | 0 | 17270.5 | 0 | 17270.5
8.2.5 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) dia 10mm deformed bar |  |  |  | Kg | 2.61 | 1643.2456 | 1116.92 |  | 1116.92 | 4288.871 | 2915.1612 | 0 | 2915.1612
| b) dia 12mm deformed bar |  |  |  | Kg | 2.02 | 1817.6206 | 2836.6288 | 0 | 2836.6288 | 3671.5935 | 5729.9902 | 0 | 5729.9902
| c) dia 14mm deformed bar |  |  |  | Kg | 2.02 | 10837.4633 | 14366.81 |  | 14366.81 | 21891.6758 | 29020.9562 | 0 | 29020.9562
| c) dia 16mm deformed bar |  |  |  | Kg | 2.02 |  | 2033.75 |  | 2033.75 |  | 4108.175 | 0 | 4108.175
8.2.6 | Supply & Install approved quality PVC water stopper at construction joints |  |  |  | ml | 235 |  | 240.4 |  | 240.4 |  | 56494 | 0 | 56494
| Total carried to summary | [7 empty] | 0 | 23312.5133 | 839646.5779 | 982081.1439 | 0 | 982081.1439
|  | Pumping Stations | [14 empty] | 0
11.1 Inlet water pumping station
11.1.1 Excavation and earth work
11.1.1.1 | Pit excavation in ordinary soil to a depth not
| exceeding 1500mm |  |  |  | M3 | 26.17 | 20.03 | 73.13 |  | 73.13 | 524.1851 | 1913.8121 | 0 | 1913.8121
0
11.1.1.2 | Ditto but to a depth exceeding 1500mm but | [11 empty] | 0
| not exceeding 3000mm |  |  |  | M3 | 48.12 | 20.03 | 73.13 |  | 73.13 | 963.8436 | 3519.0156 | 0 | 3519.0156
0
11.1.1.3 | Ditto but to a depth exceeding 3000mm but | [11 empty] | 0
| not exceeding 4500mm |  |  |  | M3 | 70.07 | 6.01 | 73.13 |  | 73.13 | 421.1207 | 5124.2191 | 0 | 5124.2191
[12 empty] | 0 | 0
11.1.1.4 | Fill around RC wall in non expansive excavated | [10 empty] | 0 | 0
| material from the site |  |  |  | M3 | 25.01 | 34.11 | 13.5 |  | 13.5 | 853.0911 | 337.635 | 0 | 337.635
[12 empty] | 0 | 0
11.1.1.5 | Load and cartaway surplus excavated material | [10 empty] | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 57.57 | 219.38 |  | 219.38 | 1997.1033 | 7610.2922 | 0 | 7610.2922
| 11.1.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
11.1.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Under bottom slab |  |  |  | M2 | 35.47 | 9.875 | 10.53 |  | 10.53 | 350.2663 | 373.4991 | 0 | 373.4991
11.1.2.2 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In 250mm thick bottom slab |  |  |  | M3 | 1434.18 | 2.4688 | 2.47 |  | 2.47 | 3540.6319 | 3542.4246 | 0 | 3542.4246
| c) In 400mm thick RC wall |  |  |  | M3 | [5 empty] | 0 | 0 | 0 | 0
| d) In 300mm thick RC wall |  |  |  | M3 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| e) In 250mm thick RC wall |  |  |  | M3 | 1434.18 | 8.3637 | 8.36 |  | 8.36 | 11995.123 |  | 0 | 11989.7448
| f) In 250mm thick suspended slab |  |  |  | M3 | 1434.18 |  | 0.91 |  | 0.91 | 0 | 1305.1038 | 0 | 1305.1038
11.1.2.3 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To 250mm thick bottom slab |  |  |  | M2 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| b) To Beam |  |  |  | M2 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| c) To RC wall |  |  |  | M2 | 58.19 | 66.91 | 64.04 |  | 64.04 | 3893.4929 | 3726.4876 | 0 | 3726.4876
| f) To 250mm thick Suspended salb |  |  |  | M2 |  |  | 10.54 |  | 10.54 | 0 | 0 | 0 | 0
11.1.2.4 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Dia 10 mm deformed bar |  |  |  | Kg | 2.61 | 845.92 | 819.02 |  | 819.02 | 2207.8512 | 2137.6422 | 0 | 2137.6422
| b) Dia 12 mm deformed bar |  |  |  | Kg | 2.02 | 720.56 | 518.16 |  | 518.16 | 1455.5312 | 1046.6832 | 0 | 1046.6832
11.1.2.5 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 0 | 22 |  | 22 | 0 | 5170 | 0 | 5170
[10 empty] | 0 | 0 |  | 0 | 0
[10 empty] | 0 | 0 |  | 0 | 0
| 11.2 Excess and Return pumping station | [8 empty] | 0 | 0 |  | 0 | 0
| 1. Excavation and Earth Work | [8 empty] | 0 | 0 |  | 0 | 0
[10 empty] | 0 | 0 |  | 0 | 0
11.2.1.1 | Pit excavation in ordinary soil to a depth not | [8 empty] | 0 | 0 |  | 0 | 0
| exceeding 1500mm |  |  |  | M3 | 26.17 | 43.37 | 53.63 | 0 | 53.63 | 1134.9929 |  | 0 | 1403.4971
[10 empty] | 0 | 0 |  | 0 | 0
11.2.1.1 | Ditto but to a depth exceeding 1500mm but | [8 empty] | 0 | 0 |  | 0 | 0
| not exceeding 3000mm |  |  |  | M3 | 48.12 | 9 | 35.75 | 0 | 35.75 | 433.08 |  | 0 | 1720.29
[10 empty] | 0 | 0 |  | 0 | 0
11.1.1.3 | Ditto but to a depth exceeding 3000mm but | [8 empty] | 0 | 0 |  | 0 | 0
| not exceeding 4500mm |  |  |  | M3 | 70.07 | 0 |  |  | 0 | 0 |  | 0 | 0
[10 empty] | 0 | 0 |  | 0 | 0
11.1.1.4 | Fill UNDER RC Bottom Slab in non expansive excavated | [8 empty] | 0 | 0 |  | 0 | 0
| material from the site |  |  |  | M3 | 25.01 | 30.24 | 89.38 | 0 | 89.38 | 756.3024 |  | 0 | 2235.3938
[10 empty] | 0 | 0 |  | 0 | 0
11.1.1.5 | Load and cartaway surplus excavated material | [8 empty] | 0 | 0 |  | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 49.15 | 89.38 | 0 | 89.38 | 1705.0135 |  | 0 | 3100.5922
| 11.2.2 CONCRETE WORK | [8 empty] | 0 | 0 |  | 0 | 0
11.1.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 |  | 0 | 0
| a) Under bottom slab |  |  |  | M2 | 35.47 | 9.36 | 8.75 | 0 | 8.75 | 331.9992 |  | 0 | 310.3625
11.2.2.3 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 |  | 0 | 0
| a) In 250mm thick bottom slab |  |  |  | M3 | 1434.18 | 2.19 | 2.19 | 0 | 2.19 | 3140.8542 |  | 0 | 3140.8542
| b) In 250mm thick RC wall |  |  |  | M3 | 1434.18 | 6.3 | 15.35 | 0 | 15.35 | 9035.334 |  | 0 | 22014.663
11.2.2.4 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 |  | 0 | 0
| a) To 250mm thick bottom slab |  |  |  | M2 | 58.19 | 4.34 | 11.52 | 0 | 11.52 | 252.5446 |  | 0 | 670.3488
| b) To 250mm RC wall |  |  |  | M2 | 58.19 | 54.56 | 137.48 | 0 | 137.48 | 3174.8464 |  | 0 | 7999.9612
11.2.2.5 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 |  | 0 | 0
| a) Dia 10 mm deformed bar |  |  |  | Kg | 2.61 | 841.81 | 212.25 |  | 212.25 | 2197.1241 |  | 0 | 553.9725
| b) Dia 12 mm deformed bar |  |  |  | Kg | 2.02 | 383.78 | 3768.99 |  | 3768.99 | 775.2356 |  | 0 | 7613.3598
11.1.2.6 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 0 | 22 | 0 | 22 | 0 |  | 0 | 5170
[10 empty] | 0 | 0 |  | 0 | 0
11.4 | Raw Water Pumping Station | [8 empty] | 0 | 0 |  | 0 | 0
11.4.1 | 1. Excavation and Earth Work | [8 empty] | 0 | 0 |  | 0 | 0
[10 empty] | 0 | 0 |  | 0 | 0
11.4.1.1 | Pit excavation in ordinary soil to a depth not | [8 empty] | 0 | 0 |  | 0 | 0
| exceeding 1500mm |  |  |  | M3 | 26.17 | 20.3 |  | 188.2125 | 188.2125 | 531.251 |  | 4925.5211 | 4925.5211
[10 empty] | 0 | 0 |  | 0 | 0
11.2.1.1 | Ditto but to a depth exceeding 1500mm but | [8 empty] | 0 | 0 |  | 0 | 0
| not exceeding 3000mm |  |  |  | M3 | 48.12 | 20.3 |  | 188.2125 | 188.2125 | 976.836 |  | 9056.7855 | 9056.7855
[10 empty] | 0 | 0 |  | 0 | 0
11.1.1.3 | Ditto but to a depth exceeding 3000mm but | [8 empty] | 0 | 0 |  | 0 | 0
| not exceeding 4500mm |  |  |  | M3 | 48.12 | 6.01 |  | 376.425 | 376.425 | 289.2012 |  | 18113.571 | 18113.571
[10 empty] | 0 | 0 |  | 0 | 0
11.1.1.4 | Fill UNDER RC Bottom Slab in non expansive excavated | [8 empty] | 0 | 0 |  | 0 | 0
| material from the site |  |  |  | M3 | 25.01 | 34.11 |  | 0 | 0 | 853.0911 |  | 0 | 0
[10 empty] | 0 | 0 |  | 0 | 0
11.1.1.5 | Load and cartaway surplus excavated material | [8 empty] | 0 | 0 |  | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 57.57 |  | 752.85 | 752.85 | 1997.1033 |  | 26116.3665 | 26116.3665
| 11.2.2 CONCRETE WORK | [8 empty] | 0 | 0 |  | 0 | 0
11.1.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 |  | 0 | 0
| a) Under bottom slab |  |  |  | M2 | 35.47 | 9.88 |  | 10.53 | 10.53 | 350.4436 |  | 373.4991 | 373.4991
11.2.2.3 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 |  | 0 | 0
| a) In 250mm thick bottom slab |  |  |  | M3 | 1434.18 | 2.47 |  | 2.4688 | 2.4688 | 3542.4246 |  | 3540.6319 | 3540.6319
| b) In 250mm thick RC wall |  |  |  | M3 | 1434.18 | 8.36 |  | 13.5013 | 13.5013 | 11989.7448 |  | 19363.2227 | 19363.2227
11.2.2.4 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 |  | 0 | 0
| a) To 250mm thick bottom slab |  |  |  | M2 | 58.23 | 3.23 |  | 3.225 | 3.225 | 188.0829 |  | 187.7918 | 187.7918
| b) To 250mm RC wall |  |  |  | M2 | 58.23 | 66.91 |  | 108.01 | 108.01 | 3896.1693 |  | 6289.4223 | 6289.4223
11.2.2.5 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 |  | 0 | 0
| a) Dia 10 mm deformed bar |  |  |  | Kg | 2.61 | 540.22 |  | 819.02 | 819.02 | 1409.9742 |  | 2137.6422 | 2137.6422
| b) Dia 12 mm deformed bar |  |  |  | Kg | 2.02 | 562.92 |  | 698.383 | 698.383 | 1137.0984 |  | 1410.7337 | 1410.7337
11.1.2.6 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 0 |  | 15 | 15 | 0 |  | 3525 | 3525
[10 empty] | 0 | 0 |  | 0 | 0
0
| Total carried to summary | [9 empty] | 78300.9875 | 35806.8145 | 95040.1877 | 130847.0022
LOT-2
1.SITE PREPARATION
1.1.1 | Site clearing |  |  |  | Ha | 11363.68 | 0.97 | 0.93 |  | 0.93 | 11022.7696 | 10568.2224 | 0 | 10568.2224
1.1.2 | Trench excavation |  |  |  | m3 | 26.17 | 218.03 | 1077.3 |  | 1077.3 | 5705.8451 | 28192.941 | 0 | 28192.941
var. | Ditto but between 1.5m & 3.0m |  |  |  | m3 | 48.12 | 0 | 1077.3 |  | 1077.3 | 0 | 51839.676 | 0 | 51839.676
var. | Ditto but between 3m & 4.5m |  |  |  | m3 | 72.18 |  |  |  | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| VO-4 Rock Excavation | [8 empty] | 0 | 0 | 0 | 0 | 0
| Retaining Wall | [8 empty] | 0 | 0 | 0 | 0 | 0
1.01) | Trench excavaion in soft rock not exceeding 1500mm depth |  |  |  | m3 | 135.37 | 521.55 | 521.98 |  | 521.98 | 70602.2235 | 70660.4326 | 0 | 70660.4326
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
1.02) | Ditto but exceeding 1500mm but not exceeding 3000mmdepth |  |  |  | m3 | 168.62 | 521.55 | 521.98 |  | 521.98 | 87943.761 | 88016.2676 | 0 | 88016.2676
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
1.03) | Ditto but exceeding 3000mm but not exceeding 4500mmdepth |  |  |  | m3 | 198.38 | 86.93 | 87 |  | 87 | 17245.1734 | 17259.06 | 0 | 17259.06
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.3 | Bulk excavation all over the water threatment plant area |  |  |  | m3 | 26.11 | 30491.88 | 27437.55 | 0 | 27437.55 | 796142.9868 | 716394.4305 | 0 | 716394.4305
1.1.4 | Load and cart awy surplus excavated material |  |  |  | m3 | 34.69 | 27081.37 | 33286.7 | 0 | 33286.7 | 939452.7253 | 1154715.623 | 0 | 1154715.623
1.1.5 | Back fil around retaining |  |  |  | m3 | 101.87 |  | 4117.68 |  | 4117.68 |  | 419468.0616 | 0 | 419468.0616
1.2 CONCRETE WORK
1.2.1 | 50mm lean concrete quality c-5
| a) Under strip foundation |  |  |  | M2 | 26.11 | 102.78 | 393.3 |  | 393.3 | 2683.5858 | 10269.063 | 0 | 10269.063
1.2.2 | Reinforced concrete quality c-25
| a) In strip foundation |  |  |  | M3 | 1098.8 | 10.28 | 56.43 |  | 56.43 | 11295.664 | 62005.284 | 0 | 62005.284
1.2.3 | Provide,cut and fix in position of form work
| a) To strip foundation |  |  |  | M2 | 58.19 | 17.25 | 51.96 |  | 51.96 | 1003.7775 | 3023.5524 | 0 | 3023.5524
1.2.4 | Mild steel reinforcement
| a) Dia 8mm deformed bar |  |  |  | kg | 2.56 | 477.12 | 2433.04 |  | 2433.04 | 1221.4272 | 6228.5824 | 0 | 6228.5824
| b) Dia 14mm |  |  |  | kg | 2.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1.3 MASONRY WORK
1.3.1 | Average 1200mm thick hard trachytic
roughly dressed stone masonry retaining
| wall bedded in cement mortar 1:3 |  |  |  | M3 | 578.54 | 407.03 | 1062.5 | 0 | 1062.5 | 235483.1362 | 614698.75 | 0 | 614698.75
1.4.3 | Masonary Work | [8 empty] | 0 | 0 | 0 | 0 | 0
| Average 750mm thick hard trachytic roughly dressed stone | [8 empty] | 0 | 0 | 0 | 0 | 0
| masonary retaining wall below beded in cement mortar (1:3) |  |  |  | M3 | 578.54 | 545.96 |  |  | 0 | 315859.6984 | 0 | 0 | 0
|  |  | Total carried to summary | [7 empty] | 2495662.7738 | 3253339.9465 | 0 | 3253339.9465
9. SLUDGE DRYING BED - 1st UNIT
CIVIL WORK
9.1 EXCAVATION & EARTH WORK
9.1.1 | Bulk excavation in ordinary soil to a depth of 1.5m |  |  |  | M3 | 26.11 | 358.44 | 1122.36 | 0 | 1122.36 | 9358.8684 | 29304.8196 | 0 | 29304.8196
var. | Ditto but between 1.5m & 3.0m |  |  |  | m3 | 48.12 | 0 | 1110.36 |  | 1110.36 | 0 | 53430.5232 | 0 | 53430.5232
9.1.2 | Fill around RC wall in non expansive excavated | [10 empty] | 0 | 0 | 0
| material from the site |  |  |  | M3 | 34.11 | 54.72 | 0 |  | 0 | 1866.4992 | 0 | 0 | 0
var | Ditto,with selected material but under slab |  |  |  | M3 | 34.11 | 0 |  |  | 0 | 0 | 0 | 0 | 0
var | Fill in side sludge RC wall in non expansive excavated |  |  |  |  | 34.11 |  | 427.15 |  | 427.15 | 0 | 14570.0865 | 0 | 14570.0865
| material from out site | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
9.1.3 | Load and cartaway surplus excavated material | [10 empty] | 0 | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 477.92 | 3051.48 | 0 | 3051.48 | 16579.0448 | 105855.8412 | 0 | 105855.8412
9.2 CONCRETE WORK
9.2.1 | 50mm lean concrete quality c-5, with minimum
cement content of150kg/m3 of concrete
| a/Under bottom slab |  |  |  | M2 | 35.47 | 182.4 | 196.32 | 0 | 196.32 | 6469.728 | 6963.4704 | 0 | 6963.4704
9.2.2 | Water tight reinforced concrete quality c-30,400kg | [8 empty] | 0 | 0 | 0 | 0 | 0
| of cement/m3 and complast WP-400 or equivalent | [8 empty] | 0 | 0 | 0 | 0 | 0
| water tightadmixture 8 lit/m3 filled in to formwork | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC 400mmthick bottom slab |  |  |  | M3 | 1434.18 | 72.96 | 71.04 | 0 | 71.04 | 104637.7728 | 101884.1472 | 0 | 101884.1472
| b/ In RC 300mm wall |  |  |  | M3 | 1434.18 | 77.17 | 92.02 | 0 | 92.02 | 110675.6706 | 131973.2436 | 0 | 131973.2436
9.2.3 | Provide,cut and fix in position sawn structural wood | [8 empty] | 0 | 0 | 0 | 0 | 0
| or steel form work which ever is appropriate | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC bottom slab |  |  |  | M2 | 58.19 | 49.76 | 80.81 | 0 | 80.81 | 2895.5344 | 4702.3339 | 0 | 4702.3339
| b/ In RC 300mm wall |  |  |  | M2 | 58.19 | 514.48 | 576.23 | 0 | 576.23 | 29937.5912 | 33530.8237 | 0 | 33530.8237
9.2.4 | Mild steel reinforcement according to structural | [8 empty] | 0 | 0 | 0 | 0 | 0
| drawings. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a)Dia 12mmdeformed bar |  |  |  | kg | 2.02 | 7153.37 | 7868.75 | 0 | 7868.75 | 14449.8074 | 15894.875 | 0 | 15894.875
| b)Dia 14mm deformed bar |  |  |  | kg | 2.02 | 12401.91 | 13995.63 | 0 | 13995.63 | 25051.8582 | 28271.1726 | 0 | 28271.1726
| b)Dia 16mm deformed bar |  |  |  | kg | 2.02 | 29.82 | 50.53 |  | 50.53 | 60.2364 | 102.0706 | 0 | 102.0706
9.2.5 | 10mm thick 150mm deep water proof expansion joint | [8 empty] | 0 | 0 | 0 | 0 | 0
| filled with impervios joint filler material |  |  |  | ML | 35 | 46.2 | 204.8 |  | 204.8 | 1617 | 7168 | 0 | 7168
9.2.6 | Install aproved quality PVC water stopper at | [8 empty] | 0 | 0 | 0 | 0 | 0
| construction joints |  |  |  | ML | 235 | 32 | 800.78 | 0 | 800.78 | 7520 | 188183.3 | 0 | 188183.3
9.3 SANITARY WORK
9.3.4 | Filter Media
Supply and spread grannular filter media in the sudge drying beds for the infltretion of the water with in the sludge
| Dia 0-2mm, 20cm thick sand |  |  |  | M3 | 537.21 | 101 |  | 101 | 101 | 54258.21 | 0 | 54258.21 | 54258.21
| Dia 0-12mm, 6cm thick sand |  |  |  | M3 | 537.21 | 30.3 |  | 30.3 | 30.3 | 16277.463 | 0 | 16277.463 | 16277.463
|  |  |  | Sub-Total-1 | [6 empty] | 331119.6114 | 721834.7075 | 70535.673 | 721834.7075
9 SLUDGE DRYING BED - 2nd unit
9.1 EXCAVATION & EARTH WORK
9.1.1 | Bulk excavation in ordinary soil to a depth of 1.5m |  |  |  | M3 | 26.11 | 358.44 | 1122.36 | 0 | 1122.36 | 9358.8684 | 29304.8196 | 0 | 29304.8196
var. | Ditto but between 1.5m & 3.0m |  |  |  | m3 | 48.12 | 0 | 1110.36 |  | 1110.36 | 0 | 53430.5232 | 0 | 53430.5232
[10 empty] | 0 | 0 | 0 | 0 | 0
9.1.2 | Fill around RC wall in non expansive excavated | [8 empty] | 0 | 0 | 0 | 0 | 0
| material from the site |  |  |  | M3 | 34.11 | 54.72 |  |  | 0 | 1866.4992 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
var | Ditto,but under slab |  |  |  | M3 | 34.11 | 0 |  |  | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0
var | Fill in side sludge RC wall in non expansive excavated |  |  |  | M3 | [6 empty] | 0 | 0 | 0
| material from out site |  |  |  |  | 34.11 | 0 | 427.15 | 0 | 427.15 | 0 | 14570.0865 | 0 | 14570.0865
[10 empty] | 0 | 0 | 0 | 0 | 0
9.1.3 | Load and cartaway surplus excavated material | [8 empty] | 0 | 0 | 0 | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 477.92 | 3051.48 | 0 | 3051.48 | 16579.0448 | 105855.8412 | 0 | 105855.8412
[10 empty] | 0 | 0 | 0 | 0 | 0
| 9.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
9.2.1 | 50mm lean concrete quality c-5, with minimum cement | [8 empty] | 0 | 0 | 0 | 0 | 0
| content of150kg/m3 of concrete | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/Under bottom slab |  |  |  | M2 | 35.47 | 182.4 | 196.32 | 0 | 196.32 | 6469.728 | 6963.4704 | 0 | 6963.4704
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.2 | Water tight reinforced concrete quality c-30,400kg | [8 empty] | 0 | 0 | 0 | 0 | 0
| of cement/m3 and complast WP-400 or equivalent | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC 400mmthick bottom slab |  |  |  | M3 | 1434.18 | 72.96 | 71.04 | 0 | 71.04 | 104637.7728 | 101884.1472 | 0 | 101884.1472
| b/ In RC 300mm wall |  |  |  | M3 | 1434.18 | 77.17 | 90.87 | 0 | 90.87 | 110675.6706 | 130323.9366 | 0 | 130323.9366
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.3 | Provide,cut and fix in position sawn structural wood | [8 empty] | 0 | 0 | 0 | 0 | 0
| or steel form work which ever is appropriate | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC bottom slab |  |  |  | M2 | 58.19 | 49.76 | 80.81 | 0 | 80.81 | 2895.5344 | 4702.3339 | 0 | 4702.3339
| b/ In RC 300mm wall |  |  |  | M2 | 58.19 | 514.48 | 646.55 | 0 | 646.55 | 29937.5912 | 37622.7445 | 0 | 37622.7445 | 282142.692
[10 empty] | 0 | 0 | 0 | 0 | 0 | 70535.673
9.2.4 | Mild steel reinforcement according to structural | [8 empty] | 0 | 0 | 0 | 0 | 0
| drawings. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a)Dia 12mmdeformed bar |  |  |  | kg | 2.02 | 7153.37 | 7627.21 |  | 7627.21 | 14449.8074 | 15406.9642 | 0 | 15406.9642
| b)Dia 14mm deformed bar |  |  |  | kg | 2.02 | 12401.91 | 13491.5 |  | 13491.5 | 25051.8582 | 27252.83 | 0 | 27252.83
| b)Dia 16mm deformed bar |  |  |  | kg | 2.02 | 29.82 | 50.53 |  | 50.53 | 60.2364 | 102.0706 | 0 | 102.0706
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.5 | 10mm thick 150mm deep water proof expansion joint | [8 empty] | 0 | 0 | 0 | 0 | 0
| filled with impervios joint filler material |  |  |  | ML | 35 | 46.2 | 204.8 |  | 204.8 | 1617 | 7168 | 0 | 7168
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.6 | Install aproved quality PVC water stopper at | [8 empty] | 0 | 0 | 0 | 0 | 0
| construction joints |  |  |  | ML | 235 | 32 | 800.78 | 0 | 800.78 | 7520 | 188183.3 | 0 | 188183.3
9.3 SANITARY WORK
9.3.4 | Filter Media
Supply and spread grannular filter media in the sudge drying beds for the infltretion of the water with in the sludge
| Dia 0-2mm, 20cm thick sand |  |  |  | M3 | 537.21 | 101 |  | 101 | 101 | 54258.21 | 0 | 54258.21 | 54258.21
| Dia 0-12mm, 6cm thick sand |  |  |  | M3 | 537.21 | 30.3 |  | 30.3 | 30.3 | 16277.463 | 0 | 16277.463 | 16277.463
|  |  |  | Sub-Total-2 | [6 empty] | 331119.6114 | 722771.0679 | 70535.673 | 722771.0679
9 SLUDGE DRYING BED -3rd unit
9.1 EXCAVATION & EARTH WORK
9.1.1 | Bulk excavation in ordinary soil to a depth of 1.5m |  |  |  | M3 | 26.11 | 358.44 | 1196.22 | 0 | 1196.22 | 9358.8684 | 31233.3042 | 0 | 31233.3042
[10 empty] | 0 | 0 | 0 | 0 | 0
var. | Ditto but between 1.5m & 3.0m |  |  |  | m3 | 48.12 | 0 | 1035.75 |  | 1035.75 | 0 | 49840.29 | 0 | 49840.29
[10 empty] | 0 |  | 0 |  | 0
var. | Ditto but between 3.0m & 4.0m |  |  |  | m4 | 48.12 |  | 750.16 |  | 750.16 |  | 36097.6992 |  | 36097.6992
[10 empty] | 0 | 0 | 0 | 0 | 0
9.1.2 | Fill around RC wall in non expansive excavated | [8 empty] | 0 | 0 | 0 | 0 | 0
| material from the site |  |  |  | M3 | 34.11 | 54.72 | 106 |  | 106 | 1866.4992 | 3615.66 | 0 | 3615.66
[10 empty] | 0 | 0 | 0 | 0 | 0
var | Ditto,but under slab |  |  |  | M3 | 34.11 | 0 |  |  | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
var | Fill in side sludge RC wall in non expansive excavated | [8 empty] | 0 | 0 | 0 | 0 | 0
| material from out site |  |  |  | M3 | 101.87 |  | 427.15 | 0 | 427.15 | 0 | 43513.7705 | 0 | 43513.7705
Var-4 | Rock Excavation | [8 empty] | 0 | 0 | 0 | 0 | 0
| Bulk excavation in soft rock depth not exceeding 1500 |  |  |  | M3 | 121.6 | 148.5 | 148.47 |  | 148.47 | 18057.6 | 18053.952 | 0 | 18053.952
[10 empty] | 0 | 0 | 0 | 0 | 0
| Ditto but exceeding 1500mm but not exceeding 3000 |  |  |  | M3 | 143.06 | 39.6 | 39.33 |  | 39.33 | 5665.176 | 5626.5498 | 0 | 5626.5498
[10 empty] | 0 | 0 | 0 | 0 | 0
| Bulk excavation in hard rock depth not exceeding 1500 |  |  |  | M3 | 207.39 | 141.6 | 141.65 |  | 141.65 | 29366.424 | 29376.7935 | 0 | 29376.7935
[10 empty] | 0 | 0 | 0 | 0 | 0
| Ditto but exceeding 1500mm but not exceeding 3000 |  |  |  | M3 | 244.31 | 94.4 | 94.43 |  | 94.43 | 23062.864 | 23070.1933 | 0 | 23070.1933
9.1.3 | Load and cartaway surplus excavated material | [8 empty] | 0 | 0 | 0 | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 477.92 | 2676.5 | 0 | 2676.5 | 16579.0448 | 92847.785 | 0 | 92847.785
[10 empty] | 0 | 0 | 0 | 0 | 0
| 9.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
9.2.1 | 50mm lean concrete quality c-5, with minimum cement | [8 empty] | 0 | 0 | 0 | 0 | 0
| content of150kg/m3 of concrete | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/Under bottom slab |  |  |  | M2 | 35.47 | 182.4 | 196.32 | 0 | 196.32 | 6469.728 | 6963.4704 | 0 | 6963.4704
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.2 | Water tight reinforced concrete quality c-30,400kg | [8 empty] | 0 | 0 | 0 | 0 | 0
| of cement/m3 and complast WP-400 or equivalent | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC 400mmthick bottom slab |  |  |  | M3 | 1434.18 | 72.96 | 71.04 | 0 | 71.04 | 104637.7728 | 101884.1472 | 0 | 101884.1472
| b/ In RC 300mm wall |  |  |  | M3 | 1434.18 | 77.17 | 102.54 | 0 | 102.54 | 110675.6706 | 147060.8172 | 0 | 147060.8172
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.3 | Provide,cut and fix in position sawn structural wood | [8 empty] | 0 | 0 | 0 | 0 | 0
| or steel form work which ever is appropriate | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC bottom slab |  |  |  | M2 | 58.19 | 49.76 | 80.81 | 0 | 80.81 | 2895.5344 | 4702.3339 | 0 | 4702.3339
| b/ In RC 300mm wall |  |  |  | M2 | 58.19 | 514.48 | 640.79 | 0 | 640.79 | 29937.5912 | 37287.5701 | 0 | 37287.5701
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.4 | Mild steel reinforcement according to structural | [8 empty] | 0 | 0 | 0 | 0 | 0
| drawings. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a)Dia 12mmdeformed bar |  |  |  | kg | 2.02 | 7153.37 | 7868.75 | 0 | 7868.75 | 14449.8074 | 15894.875 | 0 | 15894.875
| b)Dia 14mm deformed bar |  |  |  | kg | 2.02 | 12401.91 | 14046.16 | 0 | 14046.16 | 25051.8582 | 28373.2432 | 0 | 28373.2432
| b)Dia 16mm deformed bar |  |  |  | kg | 2.02 | 29.82 |  |  | 0 | 60.2364 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.5 | 10mm thick 150mm deep water proof expansion joint | [8 empty] | 0 | 0 | 0 | 0 | 0
| filled with impervios joint filler material |  |  |  | ML | 35 | 46.2 | 204.8 |  | 204.8 | 1617 | 7168 | 0 | 7168
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.6 | Install aproved quality PVC water stopper at | [8 empty] | 0 | 0 | 0 | 0 | 0
| construction joints |  |  |  | ML | 235 | 32 | 800.78 | 0 | 800.78 | 7520 | 188183.3 | 0 | 188183.3
9.3 SANITARY WORK
9.3.4 | Filter Media
Supply and spread grannular filter media in the sudge drying beds for the infltretion of the water with in the sludge
| Dia 0-2mm, 20cm thick sand |  |  |  | M3 | 537.21 | 101 |  | 101 | 101 | 54258.21 | 0 | 54258.21 | 54258.21
| Dia 0-12mm, 6cm thick sand |  |  |  | M3 | 537.21 | 30.3 |  | 30.3 | 30.3 | 16277.463 | 0 | 16277.463 | 16277.463
|  |  |  | Sub-Total-3 | [6 empty] | 407271.6754 | 870793.7545 | 70535.673 | 870793.7545
9. SLUDGE DRYING BED -4th unit
9.1 EXCAVATION & EARTH WORK
9.1.1 | Bulk excavation in ordinary soil to a depth of 1.5m |  |  |  | M3 | 26.11 | 358.44 | 1196.22 | 0 | 1196.22 | 9358.8684 | 31233.3042 | 0 | 31233.3042
var. | Ditto but between 1.5m & 3.0m |  |  |  | m3 | 48.12 | 0 | 1184.22 |  | 1184.22 | 0 | 56984.6664 | 0 | 56984.6664
[10 empty] | 0 |  | 0 | 0 | 0
var. | Ditto but between 3.0m & 4.5m |  |  |  | m3 | 72.18 |  | 1026.32 |  | 1026.32 |  | 74079.7776 | 0 | 74079.7776
[10 empty] | 0 |  | 0 | 0 | 0
9.1.2 | Fill around RC wall in non expansive excavated | [8 empty] | 0 |  | 0 | 0 | 0
| material from the site |  |  |  | M3 | 34.11 | 54.72 |  |  | 0 | 1866.4992 | 0 | 0 | 0
[12 empty] | 0 |  | 0
var | Ditto,but under slab |  |  |  | M3 | 34.11 | 0 |  |  | 0 | 0 | 0 | 0 | 0
var | Fill in side sludge RC wall in non expansive excavated
| material from out site |  |  |  | M3 | 101.87 | 0 | 427.15 |  | 427.15 |  | 43513.7705 | 0 | 43513.7705
Var-4 | Rock Excavation | [8 empty] | 0 | 0 | 0 | 0 | 0
| Bulk excavation in soft rock depth not exceeding 1500 |  |  |  | M3 | 121.6 | 290.4 | 290.29 |  | 290.29 | 35312.64 | 35299.264 | 0 | 35299.264
[10 empty] | 0 | 0 | 0 | 0 | 0
| Ditto but exceeding 1500mm but not exceeding 3000 |  |  |  | M3 | 143.06 | 280.72 | 280.62 |  | 280.62 | 40159.8032 | 40145.4972 | 0 | 40145.4972
[10 empty] | 0 | 0 | 0 | 0 | 0
| Bulk excavation in hard rock depth not exceeding 1500 |  |  |  | M3 | 207.39 | 264 | 264.19 |  | 264.19 | 54750.96 | 54790.3641 | 0 | 54790.3641
[10 empty] | 0 | 0 | 0 | 0 | 0
| Ditto but exceeding 1500mm but not exceeding 3000 |  |  |  | M3 | 244.31 | 264 | 264.19 |  | 264.19 | 64497.84 | 64544.2589 | 0 | 64544.2589
[10 empty] | 0 | 0 | 0 | 0 | 0
| Ditto but exceeding 3000mm but not exceeding 4500 |  |  |  | M3 | 287.42 | 21.12 | 21.13 |  | 21.13 | 6070.3104 | 6073.1846 | 0 | 6073.1846
9.1.3 | Load and cartaway surplus excavated material | [8 empty] | 0 |  | 0 | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 477.92 | 4594.93 | 0 | 4594.93 | 16579.0448 | 159398.1217 | 0 | 159398.1217
| 9.2 CONCRETE WORK | [8 empty] | 0 |  | 0 |  | 0
9.2.1 | 50mm lean concrete quality c-5, with minimum cement | [8 empty] | 0 |  | 0 |  | 0
| content of150kg/m3 of concrete | [8 empty] | 0 |  | 0 |  | 0
| a/Under bottom slab |  |  |  | M2 | 35.47 | 182.4 | 196.32 | 0 | 196.32 | 6469.728 | 6963.4704 | 0 | 6963.4704
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.2 | Water tight reinforced concrete quality c-30,400kg | [8 empty] | 0 |  | 0 |  | 0
| of cement/m3 and complast WP-400 or equivalent | [8 empty] | 0 |  | 0 |  | 0
| a/In RC 400mmthick bottom slab |  |  |  | M3 | 1434.18 | 72.96 | 71.04 | 0 | 71.04 |  | 101884.1472 |  | 101884.1472
| b/ In RC 300mm wall |  |  |  | M3 | 1434.18 | 77.17 | 102.54 | 0 | 102.54 |  | 147060.8172 |  | 147060.8172
[10 empty] | 0 |  | 0 |  | 0
9.2.3 | Provide,cut and fix in position sawn structural wood | [8 empty] | 0 | 0 | 0 | 0 | 0
| or steel form work which ever is appropriate | [8 empty] | 0 | 0 | 0 | 0 | 0
| a/In RC bottom slab |  |  |  | M2 | 58.19 | 49.76 | 75.13 | 0 | 75.13 | 2895.5344 | 4371.8147 | 0 | 4371.8147
| b/ In RC 300mm wall |  |  |  | M2 | 58.19 | 514.48 | 640.79 | 0 | 640.79 | 29937.5912 | 37287.5701 | 0 | 37287.5701
[10 empty] | 0 | 0 | 0 | 0 | 0
9.2.4 | Mild steel reinforcement according to structural | [8 empty] | 0 | 0 | 0 | 0 | 0
| drawings. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a)Dia 12mmdeformed bar |  |  |  | kg | 2.02 | 7153.37 | 7894.324 | 0 | 7894.324 | 14449.8074 | 15946.5345 | 0 | 15946.5345
| b)Dia 14mm deformed bar |  |  |  | kg | 2.02 | 12401.91 | 13995.63 | 0 | 13995.63 | 25051.8582 | 28271.1726 | 0 | 28271.1726
| b)Dia 16mm deformed bar |  |  |  | kg | 2.02 | 29.82 | 50.528 |  | 50.528 | 60.2364 | 102.0666 | 0 | 102.0666
[10 empty] | 0 |  | 0 |  | 0
9.2.5 | 10mm thick 150mm deep water proof expansion joint | [8 empty] | 0 |  | 0 |  | 0
| filled with impervios joint filler material |  |  |  | ML | 35 | 46.2 | 204.8 |  | 204.8 |  | 7168 |  | 7168
[10 empty] | 0 |  | 0 |  | 0
9.2.6 | Install aproved quality PVC water stopper at | [8 empty] | 0 |  | 0 |  | 0
| construction joints |  |  |  | ML | 235 | 32 | 800.78 | 0 | 800.78 | 7520 | 188183.3 | 0 | 188183.3
9.3 SANITARY WORK
9.3.4 | Filter Media
Supply and spread grannular filter media in the sudge drying beds for the infltretion of the water with in the sludge
| Dia 0-2mm, 20cm thick sand |  |  |  | M3 | 537.21 | 101 |  | 101 | 101 | 54258.21 | 0 | 54258.21 | 54258.21
| Dia 0-12mm, 6cm thick sand |  |  |  | M3 | 537.21 | 30.3 |  | 30.3 | 30.3 | 16277.463 | 0 | 16277.463 | 16277.463
|  |  |  | Sub-Total-4 | [6 empty] | 314980.7216 | 1103301.1024 | 70535.673 | 1173836.7754
| Total carried to summary | [7 empty] | 0 | 0 | 1384491.6198 | 3418700.6323 | 282142.692 | 3700843.3243
10 | RETEINTION BASIN
10.1.1 | Pit excavation in ordinary soil to a depth not
| exceeding 1500mm |  |  |  | M3 | 26.17 | 201.96 | 188.16 | 0 | 188.16 | 5285.2932 | 4924.1472 | 0 | 4924.1472
[10 empty] | 0 | 0 | 0 | 0 | 0
10.1.2 | Ditto but to a depth exceeding 1500mm but | [8 empty] | 0 | 0 | 0 | 0 | 0
| not exceeding 3000mm |  |  |  | M3 | 48.12 | 188.5 | 188.16 | 0 | 188.16 | 9070.62 | 9054.2592 | 0 | 9054.2592
[10 empty] | 0 | 0 | 0 | 0 | 0
10.1.3 | Ditto but to a depth exceeding 3000mm but | [8 empty] | 0 | 0 | 0 | 0 | 0
| not exceeding 4500mm |  |  |  | M3 | 70.07 | 93.46 | 34.08 | 0 | 34.08 | 6548.7422 | 2387.9856 | 0 | 2387.9856
[10 empty] | 0 | 0 | 0 | 0 | 0
10.1.4 | Fill around RC wall in non expansive excavated | [8 empty] | 0 | 0 | 0 | 0 | 0
| material from the out site |  |  |  | M3 | 101.87 | 160.08 | 210 |  | 210 | 16307.3496 | 21392.7 | 0 | 21392.7
[10 empty] | 0 | 0 | 0 | 0 | 0
10.1.5 | Load and cartaway surplus excavated material | [8 empty] | 0 | 0 | 0 | 0 | 0
| to an appropriate tip |  |  |  | M3 | 34.69 | 685.07 | 470.4 | 0 | 470.4 | 23765.0783 | 16318.176 | 0 | 16318.176
| 10.2 CONCRETE WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
10.2.1 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete: | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Under bottom slab |  |  |  | M2 | 35.47 | 35.47 | 84.24 | 0 | 84.24 | 1258.1209 | 2987.9928 | 0 | 2987.9928
10.2.2 | Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately) | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In 400mm thick bottom slab |  |  |  | M3 | 1434.18 | 17.92 | 46.5 |  | 46.5 | 25700.5056 | 66689.37 | 0 | 66689.37
| c) In 200mm thick RC wall |  |  |  | M3 | 1434.18 | 12.87 | 6.05 | 0 | 6.05 | 18457.8966 | 8676.789 | 0 | 8676.789
| d) In 400mm thick RC wall |  |  |  | M3 | 1434.18 | 43.16 | 35 | 0 | 35 | 61899.2088 | 50196.3 | 0 | 50196.3
10.2.3 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To RC bottom slab |  |  |  | M2 | 58.19 | 19.95 | 35.5 | 0 | 35.5 | 1160.8905 | 2065.745 | 0 | 2065.745
| b) To RC 400mm wall |  |  |  | M2 | 58.19 | 217 | 252.05 | 0 | 252.05 | 12627.23 | 14666.7895 | 0 | 14666.7895
10.2.4 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Dia 10 mm deformed bar |  |  |  | Kg | 2.02 | 4083.54 | 5634 | 0 | 5634 | 8248.7508 | 11380.68 | 0 | 11380.68
| b) Dia 12 mm deformed bar |  |  |  | Kg | 2.02 | 4608.1 | 6573.3 |  | 6573.3 | 9308.362 | 13278.066 | 0 | 13278.066
10.2.5 | Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer. |  |  |  | Ml | 235 | 0 | 36.38 |  | 36.38 | 0 | 8549.3 | 0 | 8549.3
[10 empty] | 0 | 0 | 0 | 0 | 0
| Total carried to summary | [8 empty] | 0 | 199638.0485 | 232568.3003 | 0 | 232568.3003
13 | UV DISINFECTION SYSTEM | [8 empty] | 0 | 0 | 0 | 0 | 0
13.1 | Supply, Install, test and commision UV(Ultra Violet) disinfection unit complete with electrical control works associated with electrical control works associated with the installation all in accordance with the manufacturer`s instruction. | [8 empty] | 0 | 0 | 0 | 0 | 0
| Input power =3KW |  |  |  | No | 38477.76 | 1 | 0.67 | 0 | 0.67 | 38477.76 | 25780.0992 | 0 | 25780.0992
| Total carried to summary | [9 empty] | 38477.76 | 25780.0992 | 0 | 25780.0992
14 | STORM WATER DRAINAGE | [8 empty] | 0 | 0 | 0 | 0 | 0
| Construct Storm Water drainage cahnnel out of 400mm thick | [8 empty] | 0 | 0 | 0 | 0 | 0
| internally plastered stone masonaryas showen in the detail | [8 empty] | 0 | 0 | 0 | 0 | 0
| drawing | [8 empty] | 0 | 0 | 0 | 0 | 0
14.1 | Average depth of channel 400mm |  |  |  | Ml | 303.94 | 500 | 259 | 0 | 259 | 151970 | 78720.46 | 0 | 78720.46
14.2 | Ditto but covered with removable RC Cover according to | [8 empty] | 0 | 0 | 0 | 0 | 0
| where showen in the drawing |  |  |  | Ml | 631.79 | 250 |  |  | 0 | 157947.5 | 0 | 0 | 0
| Total carried to summary | [9 empty] | 309917.5 | 78720.46 | 0 | 78720.46
| 15. SERVICE BUILDING | [10 empty] | 0
| A.SUB STRUCTURE | [10 empty] | 0
0
| 15.1 EXCAVATION & EARTH WORK | [10 empty] | 0
15.1.1 | Pit excavation for footing to a depth not | [10 empty] | 0
| exceeding 1500mm in ordinary soil |  |  |  | M3 | 26.17 | 7.23 | 7.23 |  | 7.23 | 189.2091 | 189.2091 | 0 | 189.2091
15.1.2 | Fill around foundation and building |  |  |  | M3 | 47.66 | 2.22 | 63.7 |  | 63.7 | 105.8052 | 3035.942 | 0 | 3035.942
0
15.1.3 | Fill under hard core with non expansive material |  |  |  | M3 | 47.66 | 135.88 | 181.1 |  | 181.1 | 6476.0408 | 8631.226 | 0 | 8631.226
15.1.4 | Load and cartaway surplus excavated material |  |  |  | M3 | 34.69 | 109.68 | 71.1 |  | 71.1 | 3804.7992 | 2466.459 | 0 | 2466.459
15.1.5 | 250mm thick basaltic stone hardcore |  |  |  | M2 | 40.49 | 226.47 | 226.37 |  | 226.37 | 9169.7703 | 9165.7213 | 0 | 9165.7213
15.2 CONCRETE WORK
15.2.1 | 50mm lean concrete quality C-5
| a) Under footing |  |  |  | M2 | 35.47 | 14.46 | 21.25 |  | 21.25 | 512.8962 | 753.7375 | 0 | 753.7375
| b) Under floor slab & beam |  |  |  | M2 | 35.47 | 260.43 | 32.3 |  | 32.3 | 9237.4521 | 1145.681 | 0 | 1145.681
15.2.2 | Reinforced concrete quality C-25
| a) To footing |  |  |  | M3 | 1086.27 | 3.14 | 6.06 |  | 6.06 | 3410.8878 | 6582.7962 | 0 | 6582.7962
| b) To foundation column |  |  |  | M3 | 1086.27 | 1.87 | 1.27 |  | 1.27 | 2031.3249 | 1379.5629 | 0 | 1379.5629
| c) To Grade beam |  |  |  | M3 | 1086.27 | 16.98 | 16.64 |  | 16.64 | 18444.8646 | 18075.5328 | 0 | 18075.5328
| d) To 100mm thick ground floor slab |  |  |  | M2 | 108.63 | 226.47 | 226.37 |  | 226.37 | 24601.4361 | 24590.5731 | 0 | 24590.5731
15.2.3 | Provide cut and fix in position sawn structural
wood or steel formwork
| a) To footing |  |  |  | M2 | 58.19 | 15 | 23.34 |  | 23.34 | 872.85 | 1358.1546 | 0 | 1358.1546
| b) To foundation column |  |  |  | M2 | 58.19 | 15.04 | 23.01 |  | 23.01 | 875.1776 | 1338.9519 | 0 | 1338.9519
| c) To Grade beam |  |  |  | M2 | 58.19 | 169.8 | 169.55 |  | 169.55 | 9880.662 | 9866.1145 | 0 | 9866.1145
15.2.4 | Mild steel reinforcement summary
| a) Dia.8mm deformed bar |  |  |  | kg | 2.61 | 1064.22 | 961.54 |  | 961.54 | 2777.6142 | 2509.6194 | 0 | 2509.6194
[10 empty] | 0 | 0 | 0 | 0 | 0
| b) Dia.10mm deformed bar |  |  |  | kg | 2.61 | 107.06 | 1197.67 |  | 1197.67 | 279.4266 | 3125.9187 | 0 | 3125.9187
[10 empty] | 0 | 0 | 0 | 0 | 0
| c) Dia.14mm deformed bar |  |  |  | kg | 2.02 | 1108.14 | 290.69 |  | 290.69 | 2238.4428 | 587.1938 | 0 | 587.1938
[10 empty] | 0 | 0 | 0 | 0 | 0
| d) Dia.16mm deformed bar |  |  |  | kg | 2.61 | 19.64 | 0 |  | 0 | 51.2604 | 0 | 0 | 0
B SUPER STRUCTURE
15.3 CONCRETE WORK
15.3.1 | Reinforced concrete quality C-25
| a) To elevation columns |  |  |  | M3 | 1098.8 | 3.98 | 3.621 |  | 3.621 | 4373.224 | 3978.7548 | 0 | 3978.7548
| b) To floor beams |  |  |  | M3 | 1098.8 | 8.78 | 8.99 |  | 8.99 | 9647.464 | 9878.212 | 0 | 9878.212
| c) To top tie beam |  |  |  | M3 | 1098.8 | 3.56 | 3.69 |  | 3.69 | 3911.728 | 4054.572 | 0 | 4054.572
15.3.2 | Provide cut and fix in position sawn structural
wood or steel formwork
| a) To elevation columns |  |  |  | M2 | 66.68 | 70.69 | 64.71 |  | 64.71 | 4713.6092 | 4314.8628 | 0 | 4314.8628
| b) To floor beams |  |  |  | M2 | 66.68 | 117.06 | 108.64 |  | 108.64 | 7805.5608 | 7244.1152 | 0 | 7244.1152
| c) To top tie beam |  |  |  | M2 | 66.68 | 47.42 | 48.97 |  | 48.97 | 3161.9656 | 3265.3196 | 0 | 3265.3196
15.3.3 | Mild steel reinforcement summary
| a) Dia.8mm deformed bar |  |  |  | kg | 2.26 | 621.1 | 621.62 |  | 621.62 | 1403.686 | 1404.8612 | 0 | 1404.8612
| b) Dia.12mm deformed bar |  |  |  | kg | 2.02 | 114.47 | 114.73 |  | 114.73 | 231.2294 | 231.7546 | 0 | 231.7546
| c) Dia.14mm deformed bar |  |  |  | kg | 2.02 | 1250.52 | 2592.61 |  | 2592.61 | 2526.0504 | 5237.0722 | 0 | 5237.0722
| d) Dia.16mm deformed bar |  |  |  | kg | 2.02 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
15.4 BLOCK WORK
15.4.1 | Class C, 190mm thick wall with 1:3 mortar |  |  |  | M2 | 151.2 | 327.41 | 380.51 | 0 | 380.51 | 49504.392 | 57533.112 | 0 | 57533.112
15.4.2 | Class C, 90mm thick wall with 1:3 mortar |  |  |  | M2 | 123.59 | 11.04 | 27.42 | 0 | 27.42 | 1364.4336 | 3388.8378 | 0 | 3388.8378
15.5 ROOFING
15.5.1 | G-28 CIS roof cover |  |  |  | M2 | 120 | 295.41 | 263.99 |  | 263.99 | 35449.2 | 31678.8 | 0 | 31678.8
15.5.2 | G-28 Galvanized sheet metal gutter
| devt. Length=840mm |  |  |  | ML | 109.51 | 39.7 | 0 |  | 0 | 4347.547 | 0 | 0 | 0
15.5.3 | G-28 Galvanized sheet metal gutter
| devt. Length=310mm |  |  |  | ML | 40.42 | 39.7 | 0 |  | 0 | 1604.674 | 0 | 0 | 0
15.5.4 | G-28 Galvanized sheet metal gutter down pipe |  |  |  | ML | 109.51 | 31.57 | 0 |  | 0 | 3457.2307 | 0 | 0 | 0
15.5.5 | Ditto but copping with gutter flashing
| devt. Length=475mm |  |  |  | ML | 61.93 | 50.71 | 0 |  | 0 | 3140.4703 | 0 | 0 | 0
15.5.6 | Ditto but copping with capping
| devt. Length=265mm |  |  |  | ML | 34.55 | 50.71 | 0 |  | 0 | 1752.0305 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| 16.6 CARPENTARY AND JOINERY | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
16.6.4 | Supply and Fix 8mm thick chipwood ceiling. Price include | [8 empty] | 0 | 0 | 0 | 0 | 0
| 40mmx50mm zigba wooden battens with c/c 600.. |  |  |  | M2 | 114.42 | 137.29 | 315.43 | 0 | 315.43 | 15708.7218 | 36091.5006 | 0 | 36091.5006
15.6.2 | Supplay& fix Flush type Wooden Doors of 40cm thick both side covered with 4mm thick ply wood
| a)D3 size 990*2990 |  |  |  | M2 | 2696.65 | 2 | 2 | 0 | 2 | 5393.3 | 5393.3 | 0 | 5393.3
| b)D3 size 800*2990 |  |  |  | M2 | 2179.11 | 7 | 7 | 0 | 7 | 15253.77 | 15253.77 | 0 | 15253.77
15.6.4 | Supply,fabricate and mount wood truss according to | [8 empty] | 0 | 0 | 0 | 0 | 0
| the structural drawing | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| a) Eucalyptes wood upper & lower members Dia 100mm |  |  |  | ML | 14.37 | 47.5 | 504.05 |  | 504.05 | 682.575 | 7243.1985 | 0 | 7243.1985
[10 empty] | 0 | 0 | 0 | 0 | 0
| b) Eucalyptes wood vertical & diagonal members | [8 empty] | 0 | 0 | 0 | 0 | 0
| Dia 100mm |  |  |  | ML | 14.37 | 38.74 | 378 |  | 378 | 556.6938 | 5431.86 | 0 | 5431.86
[10 empty] | 0 | 0 | 0 | 0 | 0
| c)Sawn zigba wood roof purlins |  |  |  | ML | 25.36 | 381.05 | 364.25 |  | 364.25 | 9663.428 | 9237.38 | 0 | 9237.38
[10 empty] | 0 | 0 | 0 | 0 | 0
| 15.7 METAL WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
15.7.1 | Doors
| a) D1 size 700x2040mm covered with 1mm ribed sheeet |  |  |  | Pcs | 834.71 | 2 | 2 | 0 | 2 | 1669.42 | 1669.42 | 0 | 1669.42
| b) D2 size 1590x2990mm covered with 1mm ribed sheeet |  |  |  | Pcs | 2778.91 | 1 | 1 | 0 | 1 | 2778.91 | 2778.91 | 0 | 2778.91
| c) D5 size 700x2040mm covered with 1mm ribed sheeet |  |  |  | Pcs | 834.71 | 2 | 2 | 0 | 2 | 1669.42 | 1669.42 | 0 | 1669.42
| d) D6 size 1590x2990mm covered with 1mm ribed sheeet |  |  |  | Pcs | 2778.91 | 1 | 1 | 0 | 1 | 2778.91 | 2778.91 | 0 | 2778.91
| e) D7 size 5590x4390mm covered with 1mm ribed sheeet |  |  |  | Pcs | 14344.42 | 1 | 1 | 0 | 1 | 14344.42 | 14344.42 | 0 | 14344.42
[10 empty] | 0 | 0 | 0 | 0 | 0
15.7.2 | Window | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) W1 size 1590x1990mm |  |  |  | Pcs | 1668.46 | 4 | 6 |  | 6 | 6673.84 | 10010.76 | 0 | 10010.76
| b) W2 size 790x1990mm |  |  |  | Pcs | 828.98 | 3 | 5 |  | 5 | 2486.94 | 4144.9 | 0 | 4144.9
| c) W3 size 1190x2990mm |  |  |  | Pcs | 1876.22 | 1 | 2 | 0 | 2 | 1876.22 | 3752.44 | 0 | 3752.44
| d) W4 size 790x1990mm |  |  |  | Pcs | 828.98 | 3 | 6 | 0 | 6 | 2486.94 | 4973.88 | 0 | 4973.88
| e) W5 size 3790x1990mm |  |  |  | Pcs | 3977.02 | 3 | 3 | 0 | 3 | 11931.06 | 11931.06 | 0 | 11931.06
var | Accordig to letterMHE/UCBP/5074/13 |  |  |  | m2 | 527.3 |  | 15.6 | 0 | 15.6 |  |  | 0 | 8225.88
| 15.8)Finishing Work | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
15.8.2 | Apply Three Coats of Plastering In Cement Mortar | [6 empty] | 0 |  | 0
| (1:3).Price shall include exposed surface of beams & | [6 empty] | 0 |  | 0
| Column ,pre-cleaning &preparation of the surface |  |  |  | m2 | 55.76 | 394.58 | 658.95 | 0 | 658.95 | 22001.7808 | 36743.052 | 0 | 36743.052
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
15.8.6 | 50mm thick smooth finished cement screed (1:3) floor finish | [8 empty] | 0 | 0 | 0 | 0 | 0
| with glass crack protection. Price include all accessories |  |  |  | m2 | 60.06 | 181.85 | 217.87 | 0 | 217.87 | 10921.911 | 13085.2722 | 0 | 13085.2722
[10 empty] | 0 | 0 | 0 | 0 | 0
| Total carried to summary | [9 empty] | 362232.6758 | 413546.1213 | 0 | 421772.0013
16. SITE ROAD
carriage way
12 | Clearing and grubbing
21.01 | Clearing and grubbing |  |  |  | ha | 11363.68 | 1.82 | 1.34 |  | 1.34 | 20681.8976 | 15227.3312 | 0 | 15227.3312
[10 empty] | 0 | 0 | 0 | 0 | 0
42 | Road way and Borrow Excavation | [8 empty] | 0 | 0 | 0 | 0 | 0
42.01 | Cut and Borrow to fill | [8 empty] | 0 | 0 | 0 | 0 | 0
42.01(a)i | Cut to fill/embankment ,compaction to 95 % AASHTO T-180 |  |  |  | M³ |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
42.01(a) ii | Borrow to fill ,compaction to 95 % AASHTO T-181 |  |  |  | M³ | 134.5279 | 14445.32 | 27327.74 | 5271.802 | 32599.542 | 1943298.1045 | 3676342.6039 | 709204.2844 | 4385546.8883
42.03 | Cut to spoil obtained from | [8 empty] | 0 | 0 | 0 | 0 | 0
42.03(a) | common (normal) Excavation |  |  |  | M³ | 68.7075 | 5962.87 | 17601.55 |  | 17601.55 | 409694.146 | 1209359.2508 | 0 | 1209359.2508
42.03(b) | Hard Excavation |  |  |  | M³ |  |  |  |  | 0 | 0 | 0 | 0 | 0
44.05 | 45cm thick Selected material compaction to 95 % AASHTO T-180 |  |  |  | M³ | 214.74 | 5398.6832 | 1452 |  | 1452 | 1159313.2304 | 311802.48 | 0 | 311802.48
| Total carried to summary | [7 empty] | 5271.802 |  | 3532987.3785 | 5212731.6658 | 709204.2844 | 5921935.9503
SA5 | SANITORY WORK
1. ADDITONAL SANITARY WORKS
1.1 | Piping Work
1.1.1 | UPVC (PN6) gravity pipe work below ground inatallation
complet with fittings, adaptors, sealants all the necessay accories
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia. 90mm (outside diameter) |  |  |  | Ml | 253.63 | 50 |  | 0 | 0 | 12681.5 | 0 | 0 | 0
| Dia. 110mm (outside diameter) |  |  |  | Ml | 306.26 | 171 | 21.6 | 0 | 21.6 | 52370.46 | 6615.216 | 0 | 6615.216
| Dia. 160mm (outside diameter) |  |  |  | Ml | 846.34 | 118 | 152.32 |  | 152.32 | 99868.12 | 128914.5088 | 0 | 128914.5088
| Dia. 225mm (outside diameter) |  |  |  | Ml | 1806.29 | 1603 | 1610.56 |  | 1610.56 | 2895482.87 | 2909138.4224 | 0 | 2909138.4224
| Dia. 315mm (outside diameter) |  |  |  | Ml | 3562.15 | 98 | 118.96 | 0 | 118.96 | 349090.7 | 423753.364 | 0 | 423753.364
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.2 | Ditto as above but UPVC (PN10) pressur pipe with fittings | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia. 90mm (outside diameter) |  |  |  | Ml | 266.31 | 66 |  | 65 | 65 | 17576.46 | 0 | 17310.15 | 17310.15
| Dia. 110mm (outside diameter) |  |  |  | Ml | 321.57 | 16 | 7.2 | 0 | 7.2 | 5145.12 | 2315.304 | 0 | 2315.304
| Dia. 160mm (outside diameter) |  |  |  | Ml | 889.17 | 1098 | 391 |  | 391 | 976308.66 | 347665.47 | 0 | 347665.47
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.3 | Polyethylene (PN10) pipe work above and below ground | [8 empty] | 0 | 0 | 0 | 0 | 0
| installation for flushing complete with fittings, adaptor, pipe | [8 empty] | 0 | 0 | 0 | 0 | 0
| brackets all required accessoires | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia. 50mm (outside diameter) |  |  |  | Ml | 534.03 | 700 | 35.4 | 400 | 435.4 | 373821 | 18904.662 | 213612 | 232516.662
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.4 | Slotted UPVC Pipes | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| PN-6 purpose made soltted UPVC pipes for the drainage of | [8 empty] | 0 | 0 | 0 | 0 | 0
| seepage water from sludge drying bed complet with all the | [8 empty] | 0 | 0 | 0 | 0 | 0
| necessary connection fittings | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia. 160mm (outside diameter) |  |  |  | Ml | 941.25 | 352 | 180 | 132 | 312 | 331320 | 169425 | 124245 | 293670
1.2 | 1.2) Geo-Textile linning(400m/m2) work complet with all necessay accessories and fixing mechanisms in accordance with the technical specification and detailed drawing. |  |  |  | m2 | 263.18 | 5700 | 5800 |  | 5800 | 1500126 | 1526444 | 0 | 1526444
1.3 | 1.3) Geo-Membrane 2mm thick high density(HD)geo-membrane complet with all necessay accessories and fixing mechanisms in accordance with the technical specification and detailed drawing. |  |  |  | m2 | 333.35 | 2850 | 2900 |  | 2900 | 950047.5 | 966715 | 0 | 966715
1.4 | Construct Dia.1000mm and 100mm thick reinforced concrete perfotated pipe inside sludge drying beds completed with 3000mm thick mass concrete support as shown on the drawing. Depth 2300mm |  |  |  | No | 6025.74 | 36 | 34 |  | 34 | 216926.64 | 204875.16 | 0 | 204875.16
| Total carried to summary | [9 empty] | 7820272.59 | 6704766.1072 | 355167.15 | 7059933.2572
| Connection of Ifrastructure Utilities to WWTP | [12 empty] | 0
1 | Water Supply Installation | [12 empty] | 0
1.1 | HDPE Pipe | [12 empty] | 0
| Supply and install HDPE (PN 10) pipes below ground installation completed with all accessories |  |  |  | ml | 268.5 | 210 | 210 | 150 | 360 | 56385 | 56385 | 40275 | 96660
3 | Earth Work
3.1 | Trench Excavation
b) Soft Rock
| 1-2m Depth, Width = 0.8m |  |  |  | M3 | 214.38 | 0.96 | 360 | 60 | 420 | 205.8048 | 77176.8 | 12862.8 | 90039.6
3.2 | Back filling and Compaction | [8 empty] | 0 | 0 |  | 0 | 0
| Back filling and Compaction from excavated sellected material |  |  |  | M3 | 64 | 119 | 252 | 180 | 432 | 7616 | 16128 | 11520 | 27648
3.3 | Cart away
| Cart away excess excavated material at suitable trip |  |  |  | M3 | 61.3 | 30 |  |  | 0 | 1839 |  | 0 | 0
| Total carried to summary | [9 empty] | 98091.12 | 149689.8 | 64657.8 | 214347.6
Var. no.06
1) Fuel Tank Foundation
1.01 | 1.01) Lean concrete under footing |  |  |  | m2 | 102.82 | 9.5 |  | 9.5 | 9.5 | 976.79 |  | 976.79 | 976.79
1.02 | 1.02) Reinforced Concrete C -25 in footing |  |  |  | M3 | 2756.15 | 1.78 |  | 1.776 | 1.776 | 4905.947 | 0 | 4894.9224 | 4894.9224
1.03 | 1.03) Mild Steel Reinforcement
| a) Dia 10mm |  |  |  | kg | 7.59 | 113.34 |  | 137.83 | 137.83 | 860.2506 | 0 | 1046.1297 | 1046.1297
1.05 | 1.05) Steel Form Work | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) In footing |  |  |  | m2 | 195.62 | 2.44 |  | 2.44 | 2.44 | 477.3128 | 0 | 477.3128 | 477.3128
| Sub Total | [9 empty] | 7220.3004 |  | 7395.1549 | 7395.1549
14 | 1) Fuel Tank Foundation
1 | 1. Correction work | [8 empty] | 0 | 0 | 0 | 0 | 0
1.1 | 1.1) Removal of the existing construction and make ready for new floor slab casting | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) RC floor slab price including of concrete and steel re-bar |  |  |  | m2 | 106.38 | 11 |  | 11.4 | 11.4 | 1170.18 | 0 | 1212.732 | 1212.732
| b) 25 cm thick hard core and re-use again for new concrete casting |  |  |  | m2 | 26.62 | 11 |  | 11.4 | 11.4 | 292.82 | 0 | 303.468 | 303.468
| c) Excavate the exsting selected material to an appropriat depth |  |  |  | M3 | 181.72 | 2 |  | 2.04 |  | 363.44 |  | 370.7088 | 370.7088
1.2 | 1.2) Removal of vertical surfaces
| a) Door: Type Door-09: size :1410*3010 |  |  |  | no | 119.21 | 1 |  | 1 | 1 | 119.21 | 0 | 119.21 | 119.21
| b) Windows: Type w-05: size :870*800mm |  |  |  | no | 105.96 | 1 |  | 1 | 1 | 105.96 | 0 | 105.96 | 105.96
1.2.2 | 1.2.2) Removal of the existing HCB wall in two wing parts of block |  |  |  | m2 | 62.8 | 35 |  | 35 | 35 | 2198 | 0 | 2198 | 2198
2 | 2) Excavation and Earth Work | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.1 | 2.1) Trench excavation to lay cable trench to a depth not exceeding 1.5m in ordinary siol |  |  |  | M3 | 92.79 | 11.12 |  | 11.28 | 11.28 | 1031.8248 | 0 | 1046.6712 | 1046.6712
2.2 | 2.2) Cart away surplus excavated material to an aproprite trip |  |  |  | M3 | 61.3 | 13.4 |  | 13.8 | 13.8 | 821.42 | 0 | 845.94 | 845.94
2.3 | 2.3) Re-use 250mm thick basaltic stone hard core |  |  |  | m2 | 39.25 | 11 |  | 11.4 | 11.4 | 431.75 | 0 | 447.45 | 447.45
3 | 3) Concrete Work | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 3.1) Reinforced Concrete quality C-25 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| a) To Generater pad (floor slab ) |  |  |  | M3 | 2756.15 | 2.25 |  | 2.28 | 2.28 | 6201.3375 | 0 | 6284.022 | 6284.022
| b) To concrete cable Trench duct |  |  |  | M3 | 2756.15 | 6.88 |  | 7.94 | 7.94 | 18962.312 | 0 | 21883.831 | 21883.831
| c) To 50mm thick R.C cover for electric cable duct |  |  |  | m2 | 137.8075 | 5.38 |  | 5.225 | 5.225 | 741.4044 | 0 | 720.0442 | 720.0442
| d) To 100mm thick ground floor slab suround of genetator pad |  |  |  | m2 | 275.62 | 6.7 |  | 6.96 | 6.96 | 1846.654 | 0 | 1918.3152 | 1918.3152
3.2 | 3.2) Provide, cut and fix in position swam structural wood or steel form work which ever is approprite. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| a) To Generater pad (floor slab ) |  |  |  | m2 | 195.62 | 2.5 |  | 3.48 | 3.48 | 489.05 | 0 | 680.7576 | 680.7576
| a) To Generater pad (floor slab ) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| b) To concrete cable Trench duct and R.C Cover |  |  |  | m2 | 195.62 | 34.11 |  | 30.305 | 30.305 | 6672.5982 | 0 | 5928.2641 | 5928.2641
3.3 | 3.3) Mild steel reinforcement according to structural drawings | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| a) Dia 8 mm deformed bars |  |  |  | kg | 7.59 | 29 |  | 29 | 29 | 220.11 | 0 | 220.11 | 220.11
| b) Dia 10 mm deformed bars |  |  |  | kg | 7.59 | 307 |  | 307 | 307 | 2330.13 | 0 | 2330.13 | 2330.13
| b) Dia 14 mm deformed bars |  |  |  | kg | 5.72 | 167 |  | 167 | 167 | 955.24 | 0 | 955.24 | 955.24
4 | 4) Block Work | [8 empty] | 0 | 0 | 0 | 0 | 0
| 4.1) Class C. 190mm thick HCB which can satisfy the designed strength, bedded in cement mortar(1:3) including pointing on both side of wall surface |  |  |  | m2 | 324.79 | 16 |  | 16 | 16 | 5196.64 | 0 | 5196.64 | 5196.64
| 5) Manholes | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) Manholes in bricks and with concrete base internally of 1100x1100 with a depth 900 including reinforced concrete cover with lifting handle. |  |  |  | No | 7927.91 | 2 |  | 7927.91 | 7927.91 | 15855.82 | 0 | 15855.82 | 62851756.9681
| Sub Total | [9 empty] | 66005.9009 |  | 68623.3141 | 68623.3141
UV- Disinfection
1.1 | 1.1) Excavation and Earth Work
1.1.1 | 1.1.1) Bulk excavation in ordinary siol for UV Disinfection to not exceeding 3000 mm |  |  |  | M3 | 83.51 | 58.66 |  | 114.5598 | 114.5598 | 4898.6966 |  | 9566.8889 | 9566.8889
1.1.2 | 1.1.2) Fill around RC wall in non expansive excavated material to an approprite tirp |  |  |  | M3 | 68.48 | 36.99 |  | 78.3 | 78.3 | 2533.0752 | 0 | 5361.984 | 5361.984
1.1.3 | 1.1.3) Load Cart away surplus excavated material to an aproprite trip |  |  |  | M3 | 61.3 | 58.66 |  | 114.5598 | 114.5598 | 3595.858 | 0 | 7022.5157 | 7022.5157
1.2 | 1.2) Concrete Work | [8 empty] | 0 | 0 | 0 | 0 | 0
| 1.2.1) 50 mm lean Concrete Work quality C-5 | [10 empty] | 0
| a) Under bottom slab |  |  |  | m2 | 102.82 | 18.47 |  | 18.2144 | 18.2144 | 1899.0854 |  | 1872.8046 | 1872.8046
1.2.2 | 1.2.2) Water tight reinforced concrete quality C-30, 400kg of cement/m3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| a) In RC 800mm thick bottom slab |  |  |  | M3 | 3683.75 | 6.2 |  | 6.4375 | 6.4375 | 22839.25 | 0 | 23713.9933 | 23713.9933
| b) In RC 500mm thick bottom slab |  |  |  | M3 | 3683.75 | 1.97 |  | 1.7812 | 1.7812 | 7256.9875 | 0 | 6561.6797 | 6561.6797
| c) In RC 400mm thick bottom slab |  |  |  | M3 | 3683.75 | 1.89 |  | 1.8954 | 1.8954 | 6962.2875 | 0 | 6982.1798 | 6982.1798
| d) In RC 300mm thick bottom slab |  |  |  | M3 | 3683.75 | 0.42 |  | 0.4158 | 0.4158 | 1547.175 | 0 | 1531.7032 | 1531.7032
| e) In RC 250mm thick wall |  |  |  | M3 | 3683.75 | 3.66 |  | 3.7355 | 3.7355 | 13482.525 | 0 | 13760.6942 | 13760.6942
1.2.3 | 1.2.3) Provide, cut and fix in position swam structural wood or steel form work which ever is approprite. | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) To RC bottom slab |  |  |  | m2 | 195.62 | 29 |  | 11.715 | 11.715 | 5672.98 | 0 | 2291.6883 | 2291.6883
| b) To 250 mm thick wall |  |  |  | m2 | 195.62 | 307 |  | 29.8841 | 29.8841 | 60055.34 | 0 | 5845.9276 | 5845.9276
1.2.4 | 1.2.4) Mild steel reinforcement according to structural drawings | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| a) Dia 10 mm deformed bars |  |  |  | kg | 7.59 | 6.17 |  | 7.44 | 7.44 | 46.8303 | 0 | 56.4696 | 56.4696
| b) Dia 12 mm deformed bars |  |  |  | kg | 5.72 | 1823.31 |  | 1678.06 | 1678.06 | 10429.3332 | 0 | 9598.5032 | 9598.5032
| c) Dia 14 mm deformed bars |  |  |  | kg | 5.72 | 21.02 |  | 291.85 | 291.85 | 120.2344 | 0 | 1669.382 | 1669.382
| Sub Total | [9 empty] | 141339.6581 |  | 95836.4141 | 95836.4141
| Total carried to summary | [9 empty] | 214565.8594 |  | 171854.8831 | 171854.8831
VO-5 | VO-5 Reinstalltion of Electrical Cables and Water Supply | [8 empty] | 0 | 0 | 0 | 0 | 0
| Water Supply Work | [8 empty] | 0 | 0 | 0 | 0 | 0
| 1.01) | Dismantel and remove HDPE Pipes and accessories | [7 empty] | 0 | 0 | 0 | 0 | 0
|  | Diam 90mm |  |  | Ml | 44.76 | 363.5 | 363.5 |  | 363.5 | 16270.26 | 16270.26 | 0 | 16270.26
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.02) | Reinstall, test disinfect and commission the disma | [7 empty] | 0 | 0 | 0 | 0 | 0
|  | Diam 90mm |  |  | Ml | 70.62 | 362.5 | 363.5 |  | 363.5 | 25599.75 | 25670.37 | 0 | 25670.37
[10 empty] | 0 | 0 | 0 | 0 | 0
| Electric Work | [8 empty] | 0 | 0 | 0 | 0 | 0
| 1.01) | Dismantel and remove PVC instlated under ground cable | [7 empty] | 0 | 0 | 0 | 0 | 0
|  | 3x50/25 +1x25 |  |  | Ml | 44.25 | 95.04 | 95.04 |  | 95.04 | 4205.52 | 4205.52 | 0 | 4205.52
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.02) | Ditto but 3x35/16 +1x16 |  |  | Ml | 44.25 | 128.28 | 128.28 |  | 128.28 | 5676.39 | 5676.39 | 0 | 5676.39
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.03) | Ditto but 3x120/70 +1x70 |  |  | Ml | 44.25 | 32.88 | 32.88 |  | 32.88 | 1454.94 | 1454.94 | 0 | 1454.94
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.04) | Ditto but 5x16 |  |  | Ml | 44.25 | 76.69 | 76.69 |  | 76.69 | 3393.5325 | 3393.5325 | 0 | 3393.5325
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.05) | Ditto but 5x6 |  |  | Ml | 44.25 | 31.49 | 31.49 |  | 31.49 | 1393.4325 | 1393.4325 | 0 | 1393.4325
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.06) | Dismantel and remove Sub distribution pilar |  |  | pcs | 147.23 | 1 | 1 |  | 1 | 147.23 | 147.23 | 0 | 147.23
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.01) | Reinstall PVC instlated under ground cable | [7 empty] | 0 | 0 | 0 | 0 | 0
|  | 3x50/25 +1x25 |  |  | Ml | 123.32 | 95.04 | 95.04 |  | 95.04 | 11720.3328 | 11720.3328 | 0 | 11720.3328
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.02) | Ditto but 3x35/16 +1x16 |  |  | Ml | 123.32 | 128.28 | 128.28 |  | 128.28 | 15819.4896 | 15819.4896 | 0 | 15819.4896
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.03) | Ditto but 3x120/70 +1x70 |  |  | Ml | 123.32 | 32.88 | 32.88 |  | 32.88 | 4054.7616 | 4054.7616 | 0 | 4054.7616
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.04) | Ditto but 5x16 |  |  | Ml | 123.32 | 76.69 | 76.69 |  | 76.69 | 9457.4108 | 9457.4108 | 0 | 9457.4108
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.05) | Ditto but 5x6 |  |  | Ml | 123.32 | 31.49 | 31.49 |  | 31.49 | 3883.3468 | 3883.3468 | 0 | 3883.3468
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.06) | Reinstall Sub distribution pilar |  |  | pcs | 926.04 | 1 | 1 |  | 1 | 926.04 | 926.04 | 0 | 926.04
| Total carried to summary | [9 empty] | 104002.4366 | 104073.0566 | 0 | 104073.0566
SA 4 | Supplementary Agreement | [8 empty] | 0 | 0 | 0 | 0 | 0
Remaining Road Work (SA 4)
|  | Carriage Way | [7 empty] | 0 | 0 | 0 | 0 | 0
32.01) | Excavaion in soft rock |  |  |  | M³ | 53.18 | 480 | 331.2 |  | 331.2 | 25526.4 | 17613.216 | 0 | 17613.216
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
32.02) | Back filling using imported material |  |  |  | M³ | 161.86 | 180 | 124.8 |  | 124.8 | 29134.8 | 20200.128 | 0 | 20200.128
[10 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
32.07) | Concrete below head wall |  |  |  | M³ | 2214.01 | 21.84 | 24 |  | 24 | 48353.9784 | 53136.24 | 0 | 53136.24
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
33.16) | Reinforced drain cover 1.6x0.3x0.2m |  |  |  | Pcs | 750.33 | 27 | 24 |  | 24 | 20258.91 | 18007.92 | 0 | 18007.92
[10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0
34.01) | Stone Pitcing |  |  |  | m2 | 200.44 | 48 | 42 |  | 42 | 9621.12 | 8418.48 | 0 | 8418.48
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
34.03 b) | Cement mortared Stone Wall |  |  |  | M³ | 1034.66 | 24 | 19.2 |  | 19.2 | 24831.84 | 19865.472 | 0 | 19865.472
[10 empty] | 0 | 0 | 0 | 0 | 0
0
33.01) | Concrete Curbing class A |  |  |  | Ml | 204.41 | 400 | 390 |  | 390 | 81764 | 79719.9 | 0 | 79719.9
[10 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Total Carried | [6 empty] | 0 | 0 | 0 | 0 | 0
| Walk Way | [8 empty] | 0 | 0 | 0 | 0 | 0
21.00) | Clearing and grubbing (hactar) |  |  |  | ha | 18232.09 | 2.4 | 1.04 |  | 1.04 | 43757.016 | 18961.3736 | 0 | 18961.3736
[10 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0
32.01) | Excavaion in soft rock |  |  |  | M³ | 53.18 | 128 | 113.4 |  | 113.4 | 6807.04 | 6030.612 | 0 | 6030.612
[11 empty] | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0
32.01c) | Trapizoidal Open Ditch |  |  |  | Ml | 58.06 | 6000 | 380 |  | 380 | 348360 | 22062.8 | 0 | 22062.8
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
32.02) | Back filling using imported material |  |  |  | M³ | 161.86 | 40.5 | 39.6 |  | 39.6 | 6555.33 | 6409.656 | 0 | 6409.656
[10 empty] | 0 | 0 | 0 | 0 | 0
0
32.07) | Concrete below head wall |  |  |  | M³ | 2214.01 | 26.34 | 18 |  | 18 | 58317.0234 | 39852.18 | 0 | 39852.18
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
33.16a) | Reinforced drain cover 1.6x0.3x0.2m |  |  |  | Pcs | 750.33 | 28 | 0 |  | 0 | 21009.24 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
0
33.16b) | Reinforced drain cover 1.5x0.3x0.1m |  |  |  | Pcs | 615.26 | 100 | 202 | 0 | 202 | 61526 | 124282.52 | 0 | 124282.52
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
34.01) | Stone Pitcing |  |  |  | m2 | 200.44 | 180 | 144 |  | 144 | 36079.2 | 28863.36 | 0 | 28863.36
[10 empty] | 0 | 0 | 0 | 0 | 0
0
34.03 b) | Cement mortared Stone Wall |  |  |  | M³ | 1034.66 | 108 | 45 |  | 45 | 111743.28 | 46559.7 | 0 | 46559.7
[10 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Road way and borrow excavation | [8 empty] | 0 | 0 | 0 | 0 | 0
42.03 ) | Commen (Normal) Excavation | [8 empty] | 0 | 0 | 0 | 0 | 0
| for two and three meter walk wat |  |  |  | M³ | 72.04 | 15840 | 5581.6934 |  | 5581.6934 | 1141113.6 | 402105.1889 | 0 | 402105.1889
[10 empty] | 0 | 0 | 0 | 0 | 0
51.01 ) | Sub base layer | [9 empty] | 0 | 0 |  | 0
| for two and three meter walk way |  |  |  | M³ | 252.49 | 2700 | 4579.3933 |  | 4579.3933 | 681723 | 1156251.0143 | 0 | 1156251.0143
| Total carried to summary | [7 empty] | 0 | 12059.3266 | 2756481.7778 | 2068339.7609 | 0 | 2068339.7609
VO-3 | Waste Water Drainage Pipes at Culvert
1.1.2 | Lay test and commission PN6 uPVC wast water drain pipe
including excavation of the trench to a width of 70mm and
depth upto 3000mm. Price shall include spread of 100mm
thick sand bedding around the pipe and backfill
Excavation in odrinary soil
| Dia. 160 |  |  |  | Ml | 313.08 | 879 | 649 |  | 649 | 275197.32 | 203188.92 | 0 | 203188.92
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Dia.200 |  |  |  | Ml | 321.31 | 502 | 430 |  | 430 | 161297.62 | 138163.3 | 0 | 138163.3
[10 empty] | 0 | 0 | 0 | 0 | 0
2 | Construct reinforced concrete manhole including RC Bast | [8 empty] | 0 | 0 | 0 | 0 | 0
| slab and RC cover as per the detail drawing. Price include | [8 empty] | 0 | 0 | 0 | 0 | 0
| excavation of pit , cart away and backfilling | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia 1000mm upto 2-3m depth |  |  |  | No | 7470.12 | 97 | 67 |  | 67 | 724601.64 | 500498.04 | 0 | 500498.04
| Total carried to summary | [9 empty] | 1161096.58 | 841850.26 | 0 | 841850.26
1 | SITE SANITARY WORKS | [8 empty] | 0 | 0 | 0 | 0 | 0
1.1 | MAIN CAMPUS | [8 empty] | 0 | 0 | 0 | 0 | 0
1.3.1 | 50 M3capacity elevated water reservoir | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
1.3.1.1 | Provide dia. 150mm GSP inlet pipe from pump house |  |  |  | ml | 23.1 | 10 | 49.15 | 0 | 49.15 | 231 | 1135.365 | 0 | 1135.365
1.3.1.2 | Provide 8"(200mm) GSP over flow and drain pipe |  |  |  | ml | 23.1 | 8 | 19.3 | 0 | 19.3 | 184.8 | 445.83 | 0 | 445.83
1.3.1.3 | Provide dia. 250mm GSP outlet pipe from water tank |  |  |  | ml | 23.1 | 20 | 30.08 | 0 | 30.08 | 462 | 694.848 | 0 | 694.848
[10 empty] | 0 | 0 | 0 | 0 | 0
1.3.1.7 | Supply and Fix Brass Gate valves of approved quality | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) On pipe inlet point to tank dia. 150mm |  |  |  | no | 2079 | 1 | 1 | 0 | 1 | 2079 | 2079 | 0 | 2079
| b) On water tank drain pipe, dia. 100mm |  |  |  | no | 783.67 | 1 | 1 | 0 | 1 | 783.67 | 783.67 | 0 | 783.67
| c) On water distribution pipe after tank dia. 250mm |  |  |  | no | 3638.25 | 1 | 1 | 0 | 1 | 3638.25 | 3638.25 | 0 | 3638.25
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.3.2.1 EXCAVATION AND EARTH WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
1.3.2.1.1 | clear and remove top soil |  |  |  | M2 | 4.34 | 40.69 | 40.69 |  | 40.69 | 176.5946 | 176.5946 | 0 | 176.5946
1.3.2.1.2 | Pit excavation to 1500mm in ordinary soil |  |  |  | M3 | 28.92 | 61.04 | 8.82 |  | 8.82 | 1765.2768 | 255.0744 | 0 | 255.0744
1.3.2.1.3 | Fill around foundation |  |  |  | M3 | 117.1 | 29.21 | 43.24 |  | 43.24 | 3420.491 | 5063.404 | 0 | 5063.404
1.3.2.1.4 | Cart away excavated material |  |  |  | M3 | 32.71 | 69.18 | 45.81 |  | 45.81 | 2262.8778 | 1498.4451 | 0 | 1498.4451
1.3.2.2 CONCRETE WORK
1.3.2.2.1 | Lean concrete under
| a) Footing |  |  |  | M2 | 36.34 | 0 | 10.24 |  | 10.24 | 0 | 372.1216 | 0 | 372.1216
| b) Grade beam |  |  |  | M2 | 36.34 | 0 | 51.48 |  | 51.48 | 0 | 1870.7832 | 0 | 1870.7832
1.3.2.2.2 | C-25 reinforced concrete to
| a) Footing |  |  |  | M3 | 1281.48 |  | 3.58 |  | 3.58 | 0 | 4587.6984 | 0 | 4587.6984
| b) Foundation column |  |  |  | M3 | 1281.48 |  | 0.47 |  | 0.47 | 0 | 602.2956 | 0 | 602.2956
| c) Grade beam |  |  |  | M3 | 1281.48 |  | 2.01 |  | 2.01 | 0 | 2575.7748 | 0 | 2575.7748
| d)Elevation column |  |  |  | M3 | 1281.48 |  | 3.6 |  | 3.6 | 0 | 4613.328 | 0 | 4613.328
| e) Intermediate beam |  |  |  | M3 | 1281.48 |  | 2.07 |  | 2.07 | 0 | 2652.6636 | 0 | 2652.6636
| f) Top tie beam |  |  |  | M3 | 1281.48 |  | 3.68 |  | 3.68 | 0 | 4715.8464 | 0 | 4715.8464
| g) Bottom slab |  |  |  | M3 | 1281.48 | 5.31 | 9.8 |  | 9.8 | 6804.6588 | 12558.504 | 0 | 12558.504
| h) Reservoir wall |  |  |  | M3 | 1281.48 | 10.11 | 13.02 |  | 13.02 | 12955.7628 | 16684.8696 | 0 | 16684.8696
| i) top slab cover |  |  |  | M3 | 1281.48 | 3.06 | 4.04 |  | 4.04 | 3921.3288 | 5177.1792 | 0 | 5177.1792
1.3.2.2.3 | Form work to:-
| a) Footing |  |  |  | M2 | 59.08 |  | 8.96 |  | 8.96 | 0 | 529.3568 | 0 | 529.3568
| b) Foundation column |  |  |  | M2 | 59.08 |  | 11.29 |  | 11.29 | 0 | 667.0132 | 0 | 667.0132
| c) Grade beam |  |  |  | M2 | 59.08 |  | 16.56 |  | 16.56 | 0 | 978.3648 | 0 | 978.3648
| d)Elevation column |  |  |  | M2 | 59.08 |  | 48 |  | 48 | 0 | 2835.84 | 0 | 2835.84
| e) Intermediate beam |  |  |  | M2 | 59.08 |  | 36.72 |  | 36.72 | 0 | 2169.4176 | 0 | 2169.4176
| f) Top tie beam |  |  |  | M2 | 59.08 |  | 22.08 |  | 22.08 | 0 | 1304.4864 | 0 | 1304.4864
| g) Bottom slab |  |  |  | M2 | 59.08 | 4.9 | 49 |  | 49 | 289.492 | 2894.92 | 0 | 2894.92
| h) Reservoir wall |  |  |  | M2 | 59.08 | 101.11 | 130.24 |  | 130.24 | 5973.5788 | 7694.5792 | 0 | 7694.5792
| i) top slab cover |  |  |  | M2 | 59.08 | 22.68 | 23.04 |  | 23.04 | 1339.9344 | 1361.2032 | 0 | 1361.2032 |  | 32.6667
1.3.2.2.4 | Reinforcement bar
| a) Dia 8mm |  |  |  | kg | 2.01 | 1335.29 | 453.78 |  | 453.78 | 2683.9329 | 912.0978 | 0 | 912.0978
| b) Dia 10mm |  |  |  | kg | 2.01 | 2597.49 | 314.79 |  | 314.79 | 5220.9549 | 632.7279 | 0 | 632.7279
| c) Dia 12mm |  |  |  | kg | 1.59 | 10775.18 | 4128.03 |  | 4128.03 | 17132.5362 | 6563.5677 | 0 | 6563.5677
| d) Dia 14mm |  |  |  | kg | 1.59 | 875.2 | 398.49 |  | 398.49 | 1391.568 | 633.5991 | 0 | 633.5991
| e) Dia 16mm |  |  |  | kg | 1.59 | 1782.82 | 1588.35 |  | 1588.35 | 2834.6838 | 2525.4765 | 0 | 2525.4765
1.3.2.2.5 | PVC wsater stopper |  |  |  | ML | 168.19 | 33.46 | 59.2 |  | 59.2 | 5627.6374 | 9956.848 | 0 | 9956.848
1.3.2.3 finishing work
1.3.2.3.1 | Apply three coats of plastering to
| a) Internal RC sutface of reservoir |  |  |  | M2 | 66.45 | 123.8 | 92.92 |  | 92.92 | 8226.51 | 6174.534 | 0 | 6174.534
| b)External RC surface of reservoir |  |  |  | M3 | 68.86 | 123.8 | 92.92 |  | 92.92 | 8524.868 | 6398.4712 | 0 | 6398.4712
1.3.2.3.2 | 50mm thick cement sand screed in 1:3 mortar
| a) To receive Xypex Water proofig |  |  |  | M2 | 60.05 | 63.6 | 92.92 |  | 92.92 | 3819.18 | 5579.846 | 0 | 5579.846
1.3.2.3.3 | Supply and lay 4mm thick approved quality membrane type water proofing material to roof slab according to manufactureres instructions and Engineers approval
[5 empty] | M2 | 290 | 17.4 | 27.5625 |  | 27.5625 | 5046 | 7993.125 | 0 | 7993.125
1.3.2.3.4 | Apply Xypex Water proofing material to internal
| wall and bottom slab |  |  |  | M2 | 234 | 63.6 | 121.45 |  | 121.45 | 14882.4 | 28419.3 | 0 | 28419.3
| Total carried to summary | [7 empty] | 0 |  | 121678.987 | 168406.3199 | 0 | 168406.3199
1.3.3 | 500 M3capacity ground water reservoir
1.3.3.12 | Fix brass gate valve of approved quality including adaptors to
| HDPE pipes | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) On pipe inlet point to tank dia. 4" |  |  |  | no | 2079 | 1 | 1 | 0 | 1 | 2079 | 2079 | 0 | 2079
| b) On water tank drain pipe, dia. 6" |  |  |  | no | 783.67 | 1 | 1 | 0 | 1 | 783.67 | 783.67 | 0 | 783.67
| c) On water distribution pipe after tank dia. 6" |  |  |  | no | 3638.25 | 1 | 1 | 0 | 1 | 3638.25 | 3638.25 | 0 | 3638.25
[10 empty] | 0 | 0 | 0 | 0 | 0
1.3.3.14 | Construct valve boxes in ordinary soil with double brick wall |  |  |  | no | 8928 | 1 | 1 | 0 | 1 | 8928 | 8928 | 0 | 8928
| RC base slab size = 1.5 x 1.0 x 1.0 | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| 1.3.4.1 EXCAVATION AND EARTH WORK | [8 empty] | 0 | 0 | 0 | 0 | 0
1.3.4.1.1 | clear and remove top soil |  |  |  | M2 | 4.34 | 499.2 | 167.42 |  | 167.42 | 2166.528 | 726.6028 | 0 | 726.6028
1.3.4.1.2 | Bulk excavation |  |  |  | M3 | 28.92 | 299.52 | 652.92 |  | 652.92 | 8662.1184 | 18882.4464 | 0 | 18882.4464
1.3.4.1.3 | Fill around foundation |  |  |  | M3 | 117.1 | 36.71 | 58.11 |  | 58.11 | 4298.741 | 6804.681 | 0 | 6804.681
1.3.4.1.4 | Cart away excavated material |  |  |  | M3 | 32.71 | 399.36 | 686.4 |  | 686.4 | 13063.0656 | 22452.144 | 0 | 22452.144
1.3.4.2 CONCRETE WORK
1.3.4.2.1 | C-5 lean concrete
| a) Bottom slab |  |  |  | M2 | 36.34 | 145.33 | 145.27 |  | 145.27 | 5281.2922 | 5279.1118 | 0 | 5279.1118
1.3.4.2.2 | C-35 reinforced concrete
| a) Bottom slab |  |  |  | M3 | 1281.48 | 30.43 | 179.39 |  | 179.39 | 38995.4364 | 229884.6972 | 0 | 229884.6972
| b)Top slab |  |  |  | M3 | 1281.48 | 34.64 | 51.12 | 0 | 51.12 | 44390.4672 | 65509.2576 | 0 | 65509.2576
| c)To RC reservoir wall |  |  |  | M3 | 1281.48 | 55.16 | 46.383 |  | 46.383 | 70686.4368 | 59438.8868 | 0 | 59438.8868
1.3.4.2.3 | Form work to
| a) Bottom slab |  |  |  | M2 | 59.08 | 17.1 |  |  | 0 | 1010.268 | 0 | 0 | 0
| b) Roof slab |  |  |  | M2 | 59.08 | 137.59 | 2.82 | 0 | 2.82 | 8128.8172 | 166.6056 | 0 | 166.6056
| c)To RC reservoir wall |  |  |  | M2 | 59.08 | 368.25 |  |  | 0 | 21756.21 | 0 | 0 | 0
1.3.2.2.4 | Reinforcement bar
| a) Dia 8mm |  |  |  | kg | 2.01 | 1335.29 | 865.29 |  | 865.29 | 2683.9329 | 1739.2329 | 0 | 1739.2329
| b) Dia 10mm |  |  |  | kg | 2.01 | 2597.49 | 1011.72 |  | 1011.72 | 5220.9549 | 2033.5572 | 0 | 2033.5572
| c) Dia 12mm |  |  |  | kg | 1.59 | 10775.18 | 5664.72 |  | 5664.72 | 17132.5362 | 9006.9048 | 0 | 9006.9048
| d) Dia 14mm |  |  |  | kg | 1.59 | 875.2 | 7070.28 |  | 7070.28 | 1391.568 | 11241.7452 | 0 | 11241.7452
| e) Dia 16mm |  |  |  | kg | 1.59 | 1782.82 | 3387.28 |  | 3387.28 | 2834.6838 | 5385.7752 | 0 | 5385.7752
1.3.4.3 finishing work
1.3.4.3.1 | Apply three coats of plastering to
| a) Internal RC sutface of reservoir |  |  |  | M2 | 66.45 | 178.2 | 0 |  | 0 | 11841.39 | 0 | 0 | 0
| b)External RC surface of reservoir |  |  |  | M3 | 66.45 | 0 |  |  | 0 |  | 0 | 0 | 0
1.3.2.3.2 | 50cm thick cement sand screed smoothly finished flooring in mortar mix (1:3)
| a)To receive Xypex Water Proofing |  |  |  | M2 | 60.05 | 514.9 | 121.45 | 0 | 121.45 | 30919.745 | 7293.0725 | 0 | 7293.0725
1.3.2.3.3 | Supply and lay 4mm thick approved quality membrane type water proofing material to roof slab according to manufactureres instructions and Engineers approval
[5 empty] | M2 | 290 | 138.6 | 167.42 | 0 | 167.42 | 40194 |  | 0 | 48551.8
1.3.2.3.4 | Apply Xypex Water proofing material to internal
| wall and bottom slab in accordance with the manufacturer |  |  |  | M2 | 234 | 693.1 | 410.42 | 0 | 410.42 | 162185.4 |  | 0 | 96038.28
instruction and Engineers approval
| Total carried to summary | [7 empty] | 0 |  | 508272.5116 | 461273.641 | 0 | 605863.721
2.1.1 | DOMESTIC WATER SUPPLY SYSTEM
1/Excavation in black cotton soil
with compression connection
| Dia 20mm |  |  |  | ml | 53.55 | 290 | 0 |  | 0 | 15529.5 | 0 | 0 | 0
| Dia 25mm |  |  |  | ml | 53.55 | 135 | 289.95 | 0 | 289.95 | 7229.25 | 15526.8225 | 0 | 15526.8225
| Dia 32mm |  |  |  | ml | 54.6 | 630 | 628.05 |  | 628.05 | 34398 | 34291.53 | 0 | 34291.53
| Dia 40mm |  |  |  | ml | 55.65 | 1085 | 1168.9 |  | 1168.9 | 60380.25 | 65049.285 | 0 | 65049.285
| Dia 50mm |  |  |  | ml | 56.7 | 1112 | 1337.35 | 0 | 1337.35 | 63050.4 | 75827.745 | 0 | 75827.745
| Dia 75mm |  |  |  | ml | 58.8 | 1200 | 1546.7 | 0 | 1546.7 | 70560 | 90945.96 | 0 | 90945.96
| Dia 90mm |  |  |  | ml | 59.85 | 980 | 1126 | 0 | 1126 | 58653 | 67391.1 | 0 | 67391.1
| Dia 100mm |  |  |  | ml | 60.9 | 1330 | 1439 | 0 | 1439 | 80997 | 87635.1 | 0 | 87635.1
| with fussion connection | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia 90mm (OD 110mm) |  |  |  | ml | 59.85 | 1000 | 783.7 | 0 | 783.7 | 59850 | 46904.445 | 0 | 46904.445
| Dia 125mm |  |  |  | ml | 64.05 | 350 | 300 |  | 300 | 22417.5 | 19215 | 0 | 19215
| Dia 150mm |  |  |  | ml | 66.15 | 610 | 600 |  | 600 | 40351.5 | 39690 | 0 | 39690
| Dia 200mm (OD 250mm) |  |  |  | ml | 70.35 | 175 | 273 | 0 | 273 | 12311.25 | 19205.55 | 0 | 19205.55
| Dia 250mm |  |  |  | ml | 76.5 | 105 | 100 |  | 100 | 8032.5 | 7650 | 0 | 7650
[10 empty] | 0 | 0 | 0 | 0 | 0
| Ditto but with RC cover | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| Dia 50mm |  |  |  | ml | 147.28 | 7 | 24 |  | 24 | 1030.96 | 3534.72 | 0 | 3534.72
| Dia 75mm |  |  |  | ml | 149.38 | 12 | 12 |  | 12 | 1792.56 | 1792.56 | 0 | 1792.56
| Dia 90mm |  |  |  | ml | 150.43 | 22 | 27 |  | 27 | 3309.46 | 4061.61 | 0 | 4061.61
| Dia 100mm |  |  |  | ml | 151.48 | 8 | 18 |  | 18 | 1211.84 | 2726.64 | 0 | 2726.64
| Dia 125mm |  |  |  | ml | 153.58 | 18 | 18 |  | 18 | 2764.44 | 2764.44 | 0 | 2764.44
| Dia 150mm |  |  |  | ml | 156.73 | 22 | 27 |  | 27 | 3448.06 | 4231.71 | 0 | 4231.71
| Dia 200mm |  |  |  | ml | 161.98 | 12 | 15 |  | 15 | 1943.76 | 2429.7 | 0 | 2429.7
0
| 1/Excavation in weathered rock | [8 empty] | 0
0
| with compression connection | [8 empty] | 0
0
| Dia 20mm |  |  |  | ml | 95.55 | 15 |  |  | 0 | 1433.25 | 0 | 0 | 0
| Dia 25mm |  |  |  | ml | 96.6 | 7 | 214.97 |  | 214.97 | 676.2 | 20766.102 | 0 | 20766.102
| Dia 32mm |  |  |  | ml | 96.6 | 35 | 233.05 |  | 233.05 | 3381 | 22512.63 | 0 | 22512.63
| Dia 40mm |  |  |  | ml | 97.65 | 60 | 256.9 |  | 256.9 | 5859 | 25086.285 | 0 | 25086.285
| Dia 50mm |  |  |  | ml | 98.7 | 60 | 551.35 |  | 551.35 | 5922 | 54418.245 | 0 | 54418.245
| Dia 75mm |  |  |  | ml | 100.8 | 65 | 813.7 |  | 813.7 | 6552 | 82020.96 | 0 | 82020.96
| Dia 90mm |  |  |  | ml | 102.9 | 52 | 51 |  | 51 | 5350.8 | 5247.9 | 0 | 5247.9
| Dia 100mm |  |  |  | ml | 103.95 | 70 | 539 |  | 539 | 7276.5 | 56029.05 | 0 | 56029.05
0
| with fussion connection | [8 empty] | 0
0
| Dia 125mm |  |  |  | ml | 106.05 | 20 | 20 |  | 20 | 2121 | 2121 | 0 | 2121
| Dia 150mm |  |  |  | ml | 108.15 | 35 | 35 |  | 35 | 3785.25 | 3785.25 | 0 | 3785.25
| Dia 200mm |  |  |  | ml | 112.35 | 10 | 79 |  | 79 | 1123.5 | 8875.65 | 0 | 8875.65
| Dia 250mm |  |  |  | ml | 117.6 | 6 | 6 |  | 6 | 705.6 | 705.6 | 0 | 705.6
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.2 | Valve | [8 empty] | 0 | 0 | 0 | 0 | 0
| Bronz gate Valves 20mm |  |  |  | No | 33.08 | 8 | 8 | 0 | 8 | 264.64 | 264.64 | 0 | 264.64
| Bronz gate Valves 32mm |  |  |  | No | 37.8 | 2 | 2 | 0 | 2 | 75.6 | 75.6 | 0 | 75.6
| Bronz gate Valves 50mm |  |  |  | No | 59.85 | 6 | 6 | 0 | 6 | 359.1 | 359.1 | 0 | 359.1
| Bronz gate Valves 75mm |  |  |  | No | 162.75 | 12 | 12 | 0 | 12 | 1953 | 1953 | 0 | 1953
| Bronz gate Valves 90mm |  |  |  | No | 286.65 | 5 | 5 | 0 | 5 | 1433.25 | 1433.25 | 0 | 1433.25
| Bronz gate Valves 100mm |  |  |  | No | 711.38 | 9 | 9 | 0 | 9 | 6402.42 | 6402.42 | 0 | 6402.42
| Bronz gate Valves 125mm |  |  |  | No | 1388.63 | 1 | 1 | 0 | 1 | 1388.63 | 1388.63 | 0 | 1388.63
| Bronz gate Valves 150mm |  |  |  | No | 1890 | 4 | 4 | 0 | 4 | 7560 | 7560 | 0 | 7560
| Bronz gate Valves 200mm |  |  |  | No | 2362.5 | 2 | 2 | 0 | 2 | 4725 | 4725 | 0 | 4725
| Bronz gate Valves 250mm |  |  |  | No | 3307.5 | 1 | 1 | 0 | 1 | 3307.5 | 3307.5 | 0 | 3307.5
| Air releas valves 50mm |  |  |  | No | 378 | 2 | 2 | 0 | 2 | 756 | 756 | 0 | 756
| Wash out valves at end |  |  |  | No | 330.75 | 2 | 2 | 0 | 2 | 661.5 | 661.5 | 0 | 661.5
1.1.4 | Water Pumps, Accessories | [8 empty] | 0 | 0 | 0 | 0 | 0
| Centrifugal Water pumps |  |  |  | No | 5520 | 3 | 2 | 0 | 2 | 16560 | 11040 | 0 | 11040
| Brass gate valve 150mm (6") |  |  |  | No | 4025 | 3 | 2 | 0 | 2 | 12075 | 8050 | 0 | 8050
| Brass gate valve 200mm (8") |  |  |  | No | 4025 | 3 | 2 | 0 | 2 | 12075 | 8050 | 0 | 8050
| Brass one way adaptor |  |  |  | No | 4025 | 3 | 2 | 0 | 2 | 12075 | 8050 | 0 | 8050
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1.3 | Valve box | [8 empty] | 0 | 0 | 0 | 0 | 0
| i) Construct valve boxes in ordinary soil(black cotton) soil with double brick wall, R.C base slab & R.C cover.Price shall include excavation of pit,cartawy & backfilling. | [8 empty] | 0 | 0 | 0 | 0 | 0
| Size=1.5X1.0X1.0m |  |  |  | No | 7416 | 18 | 22 | 0 | 22 | 133488 | 163152 | 0 | 163152
| ii)Construct valve boxes inweatherd rock with double brick wall, R.C base slab & R.C cover.Price shall include excavation of pit,cartawy & backfilling. | [8 empty] | 0 | 0 | 0 | 0 | 0
| Size=1.5X1.0X1.0m |  |  |  | NO | 7848 | 2 |  |  | 0 | 15696 | 0 | 0 | 0
| iii)Construct valve boxes in hard rock with double brick wall, R.C base slab & R.C cover.Price shall include excavation of pit,cartawy & backfilling. | [8 empty] | 0 | 0 | 0 | 0 | 0
| Size=1.5X1.0X1.0m |  |  |  | No | 8280 | 2 |  |  | 0 | 16560 | 0 | 0 | 0
| Total carried to summary | [9 empty] | 840862.97 | 1099671.2295 | 0 | 1099671.2295
2.3 | PUMP HOUSE
A SUB STRUCTURE
1. EXCAVATION & EARTH WORK
| Clear and remove top soil |  |  |  | M2 | 4.34 | 59.84 | 48 |  | 48 | 259.7056 | 208.32 | 0 | 208.32
| Bulk excavation |  |  |  | M3 | 28.92 | 35.9 | 168 |  | 168 | 1038.228 | 4858.56 | 0 | 4858.56
| Fill under hard core with non expansive material |  |  |  | M3 | 35.37 | 7.88 | 9.6 |  | 9.6 | 278.7156 | 339.552 | 0 | 339.552
| Load and cartaway surplus excavated material |  |  |  | M3 | 32.71 | 47.87 | 177.6 |  | 177.6 | 1565.8277 | 5809.296 | 0 | 5809.296
| 250mm thick basaltic stone hardcore |  |  |  | M2 | 41.46 | 19.7 | 20.16 |  | 20.16 | 816.762 | 835.8336 | 0 | 835.8336
2.CONCRETE WORK
1678066.9973
50mm lean concrete quality C-5 under
| a) ground floor slab and beam |  |  |  | M2 | 36.34 | 24.5 | 24 |  | 24 | 890.33 | 872.16 | 0 | 872.16
8928
C-25 reiforced concrete
| a) Grade beam |  |  |  | M3 | 1089 | 2.4 | 1.43 |  | 1.43 | 2613.6 | 1557.27 | 0 | 1557.27
| b) 150mm thick ground floor slab |  |  |  | M2 | 163.35 | 19.7 | 19.25 |  | 19.25 | 3217.995 | 3144.4875 | 0 | 3144.4875
Provide cut and fix in position sawn structural
wood or steel formwork
| a) To Grade beam |  |  |  | M2 | 59.08 | 19.2 | 6 |  | 6 | 1134.336 | 354.48 | 0 | 354.48
Mild steel reinforcement bar
| a) Dia.8mm deformed bar |  |  |  | kg | 2.01 | 144.5 | 37.92 |  | 37.92 | 290.445 | 76.2192 | 0 | 76.2192
| b) Dia.10mm deformed bar |  |  |  | kg | 1.59 | 0 | 146.54 |  | 146.54 | 0 | 232.9986 | 0 | 232.9986
| c) Dia.12mm deformed bar |  |  |  | kg | 1.59 | 0 | 212.59 |  | 212.59 | 0 | 338.0181 | 0 | 338.0181
| d) Dia.14mm deformed bar |  |  |  | kg | 1.59 | 171.23 | 159.59 |  | 159.59 | 272.2557 | 253.7481 | 0 | 253.7481
B SUPER STRUCTURE
1. CONCRETE WORK
Reinforced concrete quality C-25
| a) To elevation columns |  |  |  | M3 | 1102.58 | 0.65 | 0.43 |  | 0.43 | 716.677 | 474.1094 | 0 | 474.1094
| b) To roof beams |  |  |  | M3 | 1102.58 | 1.34 | 1.21 |  | 1.21 | 1477.4572 | 1334.1218 | 0 | 1334.1218
| c) To lintel |  |  |  | M3 | 1102.58 | 0.16 | 0 |  | 0 | 176.4128 | 0 | 0 | 0
Provide cut and fix in position sawn structural
wood or steel formwork
| a) To elevation columns |  |  |  | M2 | 67.68 | 10.84 | 8.64 |  | 8.64 | 733.6512 | 584.7552 | 0 | 584.7552
| b) To roof beams |  |  |  | M2 | 67.68 | 17.84 | 15.52 |  | 15.52 | 1207.4112 | 1050.3936 | 0 | 1050.3936
| c) To lintel |  |  |  | M2 | 67.68 | 2.4 | 0 |  | 0 | 162.432 | 0 | 0 | 0
Mild steel reinforcement bar
| a) Dia.8mm deformed bar |  |  |  | kg | 2.01 | 43.96 | 54.51 |  | 54.51 | 88.3596 | 109.5651 | 0 | 109.5651
| b) Dia.12mm deformed bar |  |  |  | kg | 1.59 | 76.66 | 132.13 |  | 132.13 | 121.8894 | 210.0867 | 0 | 210.0867
0
| 2. BLOCK WORK | [8 empty] | 0
| 200mm thick class C HCB wall |  |  |  | M2 | 153.52 | 50.54 | 50.54 |  | 50.54 | 7758.9008 | 7758.9008 | 0 | 7758.9008
3.ROOFING
| Galvanized EGA 400, 4mm thick roof cover |  |  |  | M2 | 128.79 | 33 | 33 |  | 33 | 4250.07 | 4250.07 | 0 | 4250.07
6 STRUCTURAL STEEL WORK
6.01 | RHS lattice purlins
| a) 25x25x2.5mm |  |  |  | kg | 21.13 | 89.87 | 89.87 |  | 89.87 | 1898.9531 | 1898.9531 | 0 | 1898.9531
7. FINISHING
7.01 | Applying three coats of plastering
| a)To internal wall surface |  |  |  | M2 | 54.7 | 42.28 | 46.81 | 0 | 46.81 | 2312.716 | 2560.507 | 0 | 2560.507
7.02 | Applying two coats of plastering and one coat of
tyrolean rendering
| a)To external wall surface |  |  |  | M2 | 69.16 | 68.54 | 54.21 | 0 | 54.21 | 4740.2264 | 3749.1636 | 0 | 3749.1636
7.03 | 50mm thick cement screed floor finish |  |  |  | M2 | 60.05 | 19.7 | 20.12 | 0 | 20.12 | 1182.985 | 1208.206 | 0 | 1208.206
7.05 | 1000mm w ide and 80mm thick C-20 pre-cast concrete pavement
ement around the building bedded on100mm thick sand/
| red ash base and joint pointed inn cement & sand mortar |  |  |  | M2 | 121.36 | 29.76 | 24 | 0 | 24 | 3611.6736 | 2912.64 | 0 | 2912.64
[10 empty] | 0 | 0 | 0 | 0 | 0
VO-4 | PUMP HOUSE ELECTRICAL CONNECTION | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
1.1 | Under ground cable 3x150/70+1x70 sqmm from SDB 5/5 to | [8 empty] | 0 | 0 | 0 | 0 | 0
| Pump Station SDB-p |  |  |  | Ml | 16.15 | 90 | 325 | 0 | 325 | 1453.5 | 5248.75 | 0 | 5248.75
[10 empty] | 0 | 0 | 0 | 0 | 0
1.2 | Cable Trench |  |  |  | M3 | 175.79 | 43.2 | 15.6 | 0 | 15.6 | 7594.128 | 2742.324 | 0 | 2742.324
[10 empty] | 0 | 0 | 0 | 0 | 0
1.3 | Warnining Tapes 100mm wide plastic tape colourd yellow |  |  |  | Ml | 5 | 90 | 325 | 0 | 325 | 450 | 1625 | 0 | 1625
[10 empty] | 0 | 0 | 0 | 0 | 0
| Total carried to summary | [9 empty] | 52315.6439 | 56598.4894 | 0 | 56598.4894
3 | SITE ELECTRICAL WORK
CENTRAL MAIN DISTRIBUTION BOARD
| CMDB-1 |  |  |  | NO | 4000 | 1 | 1 |  | 1 | 4000 | 4000 | 0 | 4000
| CMDB-2 |  |  |  | NO | 3000 | 2 | 1 |  | 1 | 6000 | 3000 | 0 | 3000
| CMDB-3 |  |  |  | NO | 4500 | 1 | 2 |  | 2 | 4500 | 9000 | 0 | 9000
| CMDB-5 |  |  |  | NO | 4000 | 1 | 2 |  | 2 | 4000 | 8000 | 0 | 8000
SUB DISTRIBUTION PILLAR
[6 empty] | 120 | 295.41 | 1 |  | 1 | 35449.2 | 120 | 0 | 120
SDP-5/1
| SDP-1/1 |  |  |  | NO | 3000 | 1 | 1 |  | 1 | 3000 | 3000 | 0 | 3000
| SDP-1/2 |  |  |  | NO | 3000 | 1 | 1 |  | 1 | 3000 | 3000 | 0 | 3000
| SDP-3/1 |  |  |  | NO | 2000 | 1 | 1 |  | 1 | 2000 | 2000 |  | 2000
| SDP-3/4 |  |  |  | NO | 3500 | 1 | 0 |  | 0 | 3500 | 0
| SDP-2/3 |  |  |  | NO | 2700 | 1 | 0 |  | 0 | 2700 | 0
| SDP-2/4 |  |  |  | NO | 2700 | 1 | 0 |  | 0 | 2700 | 0
| SDP-4/1 |  |  |  | NO | 2300 | 1 | 1 |  | 1 | 2300 | 2300 | 0 | 2300
| SDP-4/4 |  |  |  | NO | 2500 | 1 | 1 |  | 1 | 2500 | 2500 | 0 | 2500
| SDP-5/2 |  |  |  | NO | 2500 | 1 | 1 |  | 1 | 2500 | 2500 | 0 | 2500
| SDP-1/3 |  |  |  | NO | 1700 | 1 | 1 |  | 1 | 1700 | 1700 | 0 | 1700
| SDP-1/4 |  |  |  | NO | 2000 | 1 | 1 |  | 1 | 2000 | 2000 | 0 | 2000
| SDP-2/2 |  |  |  | NO | 2500 | 1 |  |  | 0 | 2500 | 0 | 0 | 0
| SDP-4/3 |  |  |  | NO | 2600 | 1 |  |  |  | 2600 | 0
| SDP-5/3 |  |  |  | NO | 3000 | 1 | 1 |  | 1 | 3000 | 3000 | 0 | 3000
| SDP-3/3 |  |  |  | NO | 1600 | 1 | 1 |  | 1 | 1600 | 1600 | 0 | 1600
| SDP-2/1 |  |  |  | NO | 1300 | 1 | 0 |  | 0 | 1300 | 0 | 0 | 0
| SDP-4/2 |  |  |  | NO | 1200 | 1 | 1 |  | 1 | 1200 | 1200 | 0 | 1200
| SDP-3/2 |  |  |  | NO | 1100 | 1 | 1 |  | 1 | 1100 | 1100 | 0 | 1100
| SDP-4/5 |  |  |  | NO | 1200 | 1 | 1 |  | 1 | 1200 | 1200 | 0 | 1200
| SDP-5/5 |  |  |  | NO | 2500 | 1 | 1 |  | 1 | 2500 | 2500 | 0 | 2500
POWER DISTRIBUTION SYSTEM
under ground cable
a) PVC sheathed pvc insulated underground cable
| type NYY 0.6/1KV of (3x150/70+1x70) sq mm |  |  |  | ml | 50 | 107 | 50 |  | 50 | 5350 | 2500 | 0 | 2500
| from transformer to CMDBs | [8 empty] | 0 | 0 | 0 | 0 | 0
| b) (3x150/70+1x70)sq mm from CMDBs to SDPs |  |  |  | ml | 50 | 260 |  |  | 0 | 13000 | 0 | 0 | 0
| C) (3X120/70+1X70)sq mm from CMDBs to SDPs |  |  |  | ml | 50 | 763 | 937 |  | 937 | 38150 | 46850 | 0 | 46850
| d) (3x95/50+1x50)sq mm from CMDBs to SDPs |  |  |  | ml | 30 | 855 | 220 |  | 220 | 25650 | 6600 | 0 | 6600
| e) (3x70/35+1x35)sq mm from CMDBs to SDPs |  |  |  | ml | 30 | 590 | 310 |  | 310 | 17700 | 9300 | 0 | 9300
| f) (3x50/25+1x25)sq mm from CMDBs to SDPs |  |  |  | ml | 30 | 50 | 135 |  | 135 | 1500 | 4050 | 0 | 4050
| g) (3x35/16+1x16)sq mm from CMDBs to SDPs |  |  |  | ml | 10 | 300 | 708 |  | 708 | 3000 | 7080 | 0 | 7080
| h) (3x120/70+1x70)sq mm from SDPs to building |  |  |  | ml | 50 | 46 |  |  | 0 | 2300 | 0 | 0 | 0
| i)(3x95/50+1x50)sq mm from SDPs to building |  |  |  | ml | 30 | 6 | 0 |  | 0 | 180 | 0 | 0 | 0
| j) (3x70/35+1x35)sq mm from SDPs to building |  |  |  | ml | 30 | 70 | 69 |  | 69 | 2100 | 2070 | 0 | 2070
| k) (3x50/25+1x25)sqa mm from SDPs to building |  |  |  | ml | 30 | 33 | 30 |  | 30 | 990 | 900 | 0 | 900
| l) (3x35/16+1x16)sq mm from SDPs to building |  |  |  | ml | 10 | 696 | 690 |  | 690 | 6960 | 6900 | 0 | 6900
| m) (3x25/16+1x16)sq mm from SDPs to building |  |  |  | ml | 10 | 735 | 701 |  | 701 | 7350 | 7010 | 0 | 7010
| n) (5x16)sq mm from SDPs to building |  |  |  | ml | 4 | 2090 | 2118.4 |  | 2118.4 | 8360 | 8473.6 | 0 | 8473.6
| o) (5x10)sq mm from SDPs to building |  |  |  | ml | 3.5 | 3270 | 4002 |  | 4002 | 11445 | 14007 | 0 | 14007
| p) (5x6) sq mm from SDPs to building |  |  |  | ml | 3.5 | 613 | 1308.5 |  | 1308.5 | 2145.5 | 4579.75 | 0 | 4579.75
| q) (5x4)sq mm from SDPs to building |  |  |  | ml | 3.5 | 332 | 340 |  | 340 | 1162 | 1190 | 0 | 1190
| r) (5x6)sq mm from street and compound light |  |  |  | ml | 3.5 | 6616 | 800 |  | 800 | 23156 | 2800 | 0 | 2800
| s) (3x2.5)sq mm for street and compound lighting | [8 empty] | 0 | 0 | 0 | 0 | 0
| from fuse inside the pole connection window to |  |  |  | ml | 3.5 | 894 | 889 |  | 889 | 3129 | 3111.5 | 0 | 3111.5
| the fitting | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| UNDER GROUND DUCTS/PIPES | [8 empty] | 0 | 0 | 0 | 0 | 0
| a) pvc pipe of 110mm dia |  |  |  | ML | 6 | 87 | 83 |  | 83 | 522 | 498 | 0 | 498
[10 empty] | 0 | 0 | 0 | 0 | 0
| CABLE TRENCHES | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| a) trench excavation |  |  |  | M3 | 117 | 11486 | 10040.9 |  | 10040.9 | 1343862 | 1174785.3 | 0 | 1174785.3
[10 empty] | 0 | 0 | 0 | 0 | 0
| WARNING TAPS | [8 empty] | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0
| 100mm wide plastic tape |  |  |  | ML | 2 | 11486 | 10414 |  | 10414 | 22972 | 20828 |  | 20828
EXTERNAL LIGHTING
a) Street lighting pole of 8m height above
| ground level |  |  |  | NO | 487.66 | 60 | 56 |  | 56 | 29259.6 | 27308.96 |  | 27308.96
b)Galvanized street lighting pole of 3m high
| above ground level |  |  |  | NO | 487.66 | 99 | 32 |  | 32 | 48278.34 | 15605.12 |  | 15605.12
[10 empty] | 0 | 0 | 0 |  | 0
| Exterior light Fitting | [8 empty] | 0 | 0 | 0 |  | 0
| a) PHILIPS CEM Ms 21150B0 |  |  |  | NO | 42 | 60 |  |  | 0 | 2520 | 0 |  | 0
[10 empty] | 0 | 0 | 0 |  | 0
| b) PHILIPS HPP090 HPL-N 80W |  |  |  | NO | 42 | 99 |  |  | 0 | 4158 | 0 |  | 0
| Total carried to summary | [7 empty] | 0 | 33954.8 | 1724048.64 | 1420167.23 | 0 | 1420167.23

## Grand Summary
SUMMARY OF STATEMENT
PROJECT: DESSE UCBP INFRASTRUCTURE AND WWTP(LOT 1 & LOT 2)
CONTRACTOR: TRUST CONSTRUCTION
CONSULTANT: MH ENGINEERING PLC
CLIENT : GIZ IS
DETAILS OF WORKS EXCUTED AND/OR MATERIALS SUPPLIED
Item | Block/work |  |  |  | Contract |  |  |  | Executed
LOT-1
1 | SITE PREPARATION |  |  |  | 1388898.72 |  |  |  | 980558.423
2 | SCREENING UNIT |  |  |  |  | 7934.86 |  |  | 0
3 | EMERGENCY RETENTION TANK |  |  |  | 437745.45 |  |  |  | 596726.2503
4 | SAND TRAP |  |  |  | 80952.26 |  |  |  | 73131.9058
5 | PARSHALL FLUME |  |  |  |  | 25005.2 |  |  | 0
6 | IMHOFF TANK |  |  |  | 1621233.07 |  |  |  | 1759855.4287
7 | AERATION TANK |  |  |  |  | 579026.98 |  |  | 896941.5661
8 | SEDIMENTATION TANK |  |  |  | 874446.91 |  |  |  | 982081.1439
11 | PUMING STATIONS (Inlet, Excess Return Raw water) |  |  |  |  | 164205.35 |  |  | 130847.0022
12 | STAND BY GENERATOR |  |  |  |  | 102490.05 |  |  | 0
|  |  | TOTAL |  | 5281938.85 |  |  |  | 5420141.7199
LOT-2
1 | SITE PREPARATION |  |  |  | 1388898.76 |  |  |  | 3253339.9465
9 | SLUDGE DRYING BED |  |  |  | 1812160.27 |  |  |  | 3700843.3243
10 | RETENSION BASIN /over flow/ |  |  |  |  | 174027.43 |  |  | 232568.3003
13 | UV DISINFECTION SYSTEM |  |  |  |  | 38477.76 |  |  | 25780.0992
14 | STORM WATER DRAINAGE |  |  |  | 309917.5 |  |  |  | 78720.46
15 | SERVICE BUILDING |  |  |  | 421794.31 |  |  |  | 421772.0013
16 | SITE ROAD |  |  |  | 3248593.2 |  |  |  | 5921935.9503
17 | SITE SANITARY WORK |  |  |  |  | 429478.41 |  |  | 0
18 | SITE ELECTRICAL WORK |  |  |  |  | 113716.52 |  |  | 0
|  |  | TOTAL |  | 7937064.16 |  |  |  | 13634960.0819
SUPPLEMENTARY WORKS
1ST SUPPLEMNTARY
SN MAIN CAMPUS
| 50m3 ELEVATED WATER RESERVOIR |  |  |  | 119477.02 |  |  |  | 168406.3199
| 500m3 GROUND WATER RESERVOIR |  |  |  | 530947.59 |  |  |  | 605863.721
PUMP HOUSE
| PUMP HOUSE |  |  |  | 50037.35 |  |  |  | 56598.4894
2ND SUPPLEMNTARY
1 | SITE ELECTRICAL WORKS
| SITE ELECTRICAL WORK |  |  |  | 1768798.44 |  |  |  | 1420167.23
2 | SITE SANITARY WORK
| DOMESTIC WATER SUPPLY SYSTEM |  |  |  | 855434.07 |  |  |  | 1099671.2295
3 | 5th SUPPLEMNTARY Agreement
| SA-5 Additional Sanitory Works |  |  |  | 7820272.59 |  |  |  | 7059933.2572
| Connection of Infrasructure to WWTP | [5 empty] | 0 | 98091.12 | 214347.6
| Var. no.06 | [6 empty] | 214565.8594 | 171854.8831
|  |  | TOTAL |  | 11338147.0193 |  |  |  | 10796842.7301
| VARIATION WORK | [7 empty] | 340278.05
Vo-1 | BOULDER MATERIAL | [7 empty] | 110054.25
Vo-3 | Waste Water Drainage at Pipe Culvert |  |  |  | 1349895.73 |  |  |  | 841850.26
| PRICE ADJUSTMENT |  |  |  | 6265671.42 |  |  |  | 6265671.42
VO 5 | Reinstallation of Electric Cables and HDPE pipes |  |  |  | 104002.44 |  |  |  | 104073.0566
SA 4 | Remaining Road Work |  |  |  | 2756481.78 |  |  |  | 2068339.7609
|  |  | TOTAL |  | 10476051.37 |  |  |  | 9730266.7975
|  | GRAND TOTAL |  |  | 35033201.3993 |  |  |  | 39582211.3294
Contractor_________________ |  |  | Consultant_______________ |  |  |  | Client_________________

## Sewage uPVC Pipe and Manhole
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 18 |  |  | 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | Waste Water Drainage Pipe at Culvert (VO-3)
Item No: |  | Prepared by: | Gebru G/medhin |  | Date:
VO-3
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity | Unit
VO-3 | Waste Water Drainage Pipe
1.1.2) Lay test commission uPVC pipe
depth GREATER than 1500mm
|  | a) Dia 160 |  |  | 1 | 0 | 0
|  | a) Dia 200 |  |  | 1 | 0 | 0
2) Reinforced Concrete Manhole
| a) Dia.1000mm up to 2-3m depth |  |  |  | 1 | 8 | 8 | no
From UV Disinfection to Raw Water Pumping Station
|  | Date: |  | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 19 |  |  | 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | Waste Water Drainage Pipe at Culvert (VO-3)
Item No: |  | Prepared by: | Gebru G/medhin |  | Date:
VO-3
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity | Unit
VO-3 | Waste Water Drainage Pipe
1.1.2) Lay test commission uPVC pipe
depth GREATER than 1500mm
|  | a) Dia 160 |  |  | 1 | 0 | 0
|  | a) Dia 200 |  |  | 1 | 180 | 180
2) Reinforced Concrete Manhole
| a) Dia.1000mm up to 2-3m depth |  |  |  | 1 | 26 | 26 | no
From UV Disinfection to Raw Water Pumping Station
|  | Date: |  | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## SA5 Additional Sani Works
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 18 |  |  | 1 of 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | SA-5 Additional Sanitary Works
Item No: |  | Prepared by: | Gebru G/medhin |  | Date:
SA-5
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity | Unit
1.1) Pipe Works
1.1.1) uPVC (PN6) gravity pipe work below ground installation complet with fittings, adaptors, sealants and all necessay accessories
| a) Dia. 90mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| b) Dia. 110mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| c) Dia. 160mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| d) Dia. 225mm (Outside Diameter) |  |  |  | 1 | 750 | 750 | ml
from UV Disinfection to Raw water pumping station
| e) Dia. 315mm (Outside Diameter) |  |  |  | 1 | 0 | 0
1.1.2) Ditto as above but uPVC (PN10) Pressure Pipes with fittings
| a) Dia. 90mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| b) Dia. 110mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| c) Dia. 160mm (Outside Diameter) |  |  |  | 1 | 0 | 0
from Emergency Septic Tank to Sand Trap
1.2) Geo-Textile linning(400m/m2) work complet with all necessay accessories and fixing mechanisms in accordance with the technical specification and detailed drawing.
In 2 sludge drying bed |  |  |  |  | 4 | 29
Area=29*25=725m2 | [5 empty] | 25 | 2900
2900
| Total for this Payment |  |  |  | 0.6 |  | 1740
1.3) Geo-Membrane 2mm thick high density(HD)geo-membrane complet with all necessay accessories and fixing mechanisms in accordance with the technical specification and detailed drawing.
In 2 sludge drying bed |  |  |  |  | 2 | 29
| Area=29*25=725m2 |  |  |  |  | 25 | 1450
| Total for This Payment | [5 empty] | 1450
1.4 Construct Perforated Pipe in SDBs |  |  |  |  | 0.64 | 36 | 23.04 | no
|  | Date: | Name: |  | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 20 |  |  | 1 of 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | SA-5 Additional Sanitary Works
Item No: |  | Prepared by: | Gebru G/medhin |  | Date:
SA-5
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity | Unit
1.1) Pipe Works
1.1.1) uPVC (PN6) gravity pipe work below ground installation complet with fittings, adaptors, sealants and all necessay accessories
| a) Dia. 90mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| b) Dia. 110mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| c) Dia. 160mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| d) Dia. 225mm (Outside Diameter) |  |  |  | 1 | 0 | 0 | ml
from UV Disinfection to Raw water pumping station
| e) Dia. 315mm (Outside Diameter) |  |  |  | 1 | 0 | 0
1.1.2) Ditto as above but UPVC (PN10) Pressure Pipes with fittings
| a) Dia. 90mm (Outside Diameter) |  |  |  | 1 | 65 | 65
| b) Dia. 110mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| c) Dia. 160mm (Outside Diameter) |  |  |  | 1 | 0 | 0
from Emergency Septic Tank to Sand Trap
1.1.4 Slotted Upvc Pipe |  |  |  |  | 4 | 45 | 312 | ml
Previous |  |  |  |  | 1 | 18 | 180 | ml
Total For this Payment |  |  |  |  | 1 | 132 | 132 | ml
1.4 Construct Perforated Pipe in SDBs |  |  |  |  | 1 | 0 | 0 | no
Connection of Infrastructure Utilities |  |  |  | to WWTP
1. Water Supply Installation
1. Water Supply Installation
1.1 HDPE Pipe |  | Dia.63mm (out Side diameter |  |  | 1 | 150 | 150 | ml
3. Earth Work
3.1 . Trench Execavation
b) . Soft Rock |  |  |  |  | 1 | 50
1-2m Depth, Width = 0.8m | [5 empty] | 1.5
[6 empty] | 0.8 | 60 | m3
3.1. Back filling and Compaction
Back filling and Compaction with Sellected material |  |  |  |  | 1 | 150
1.5
[6 empty] | 0.8 | 180 | m3
1.1.3) Polyethylene (PN10) pipe works above and below ground installation for flushing connection |  |  |  |  | 1 | 400 | 400 | ml
|  | Date: | Name: |  | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 19 |  |  | 1 of 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | SA-5 Additional Sanitary Works
Item No: |  | Prepared by: | Gebru G/medhin |  | Date:
SA-5
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity | Unit
1.1) Pipe Works
1.1.1) uPVC (PN6) gravity pipe work below ground installation complet with fittings, adaptors, sealants and all necessay accessories
| a) Dia. 90mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| b) Dia. 110mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| c) Dia. 160mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| d) Dia. 225mm (Outside Diameter) |  |  |  | 1 | 558 | 558 | ml
from UV Disinfection to Raw water pumping station
| e) Dia. 315mm (Outside Diameter) |  |  |  | 1 | 0 | 0
1.1.2) Ditto as above but uPVC (PN10) Pressure Pipes with fittings
| a) Dia. 90mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| b) Dia. 110mm (Outside Diameter) |  |  |  | 1 | 0 | 0
| c) Dia. 160mm (Outside Diameter) |  |  |  | 1 | 0 | 0
from Emergency Septic Tank to Sand Trap
1.1.4 Slotted Upvc Pipe |  |  |  |  | 4 | 45 | 180 | ml
Previous |  |  |  |  | 1 | 18 | 18 | ml
Total For this Payment |  |  |  |  | 1 | 162 | 162 | ml
1.4 Construct Perforated Pipe in SDBs |  |  |  |  | 1 | 12.96 | 12.96 | no
Connection of Infrastructure Utilities |  |  |  | to WWTP
1. Water Supply Installation
1. Water Supply Installation
1.1 HDPE Pipe |  | Dia.63mm (out Side diameter |  |  | 1 | 210 | 210 | ml
3. Earth Work
3.1 . Trench Execavation
b) . Soft Rock |  |  |  |  | 1 | 300
1-2m Depth, Width = 0.8m | [5 empty] | 1.5
[6 empty] | 0.8 | 360 | m3
3.1. Back filling and Compaction
Back filling and Compaction with Sellected material |  |  |  |  | 1 | 210
1.5
[6 empty] | 0.8 | 252 | m3
|  | Date: | Name: |  | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Imhoff
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 18 |  |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 1 | Imhoff Tank
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity | Unit
6.2 CONCRETE WORK
6.2.3) Water tight RCC C-30 concrete class
b) In 500mm thick RC wall |  |  |  | 1 | 49.6
0.5
[5 empty] | 4 | 99.2 | m3
6.2.4)Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate.
b) In 500mm thick RC wall |  |  |  | 2 | 49.6
[5 empty] | 4 | 396.8 | m2
F) 250mm inclined slab |  |  |  | 8 | 6.65
[5 empty] | 4.25 | 226.1 | m2
6.2.5)Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire and concrete spacers.
a) dia. 10mm deformed bars | [5 empty] | 3066.2309 | kg
d) dia 20mm deformed bar
[6 empty] | 9954.641 | kg
6.2.6)Supply and install approved quality PVC water stopper at construction joints and as directed by the Engineer.
| Horzontal=51.8+0.3*4+0.6=53.6 |  |  | 2 | 53.6 | 107.2
| Vertical=2+0.3=2.3 |  |  | 8 | 2.3 | 18.4
| Total for this payment |  |  |  |  | 125.6
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM: | [7 empty] | 914817051
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 19 |  |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 1 | Imhoff Tank
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity | Unit
6.2 CONCRETE WORK
6.2.3) Water tight RCC C-30 concrete class
c) In 250mm thick RC wall |  |  |  | 1 | 1.5
2.8
[5 empty] | 0.25 | 1.05 | m3
|  |  |  | 1 | 1.15
2.8
[5 empty] | 0.25 | 0.805 | m3
|  |  |  | 2 | 16
0.95
[5 empty] | 0.25 | 7.6 | m3
|  |  |  | 2 | 0.75
2.8
[5 empty] | 0.25 | 1.05 | m3
[6 empty] | 10.505 | m3 Total in c
d) In 250mm thick suspended slab |  |  |  | 1 | 1.25
2.8
[5 empty] | 0.25 | 0.875 | m3
|  |  |  | 1 | 0.75
2.8
[5 empty] | 0.25 | 0.525 | m3
[6 empty] | 1.4 | m3 Total in d
e) In 300mm thick suspended slab |  |  |  | 2 | 16
2.5
[5 empty] | 0.3 | 24 | m3
6.2.4)Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate.
steel form work
c) To 250mm thick RC wall |  |  |  | 2 | 1.63
[5 empty] | 2.8 | 9.128 | m2
|  |  |  | 2 | 1.28
[5 empty] | 2.8 | 7.168 | m2
|  |  |  | 4 | 16
[5 empty] | 1.1 | 70.4 | m2
|  |  |  | 2 | 16
[5 empty] | 0.25 | 8 | m2
|  |  |  | 4 | 0.75
[5 empty] | 2.8 | 8.4 | m2
[6 empty] | 103.096 | m2 Total in c
d) To suspended slab |  |  |  | 1 | 1.25
[5 empty] | 2.8 | 3.5 | m2
|  |  |  | 1 | 0.75
[5 empty] | 2.8 | 2.1 | m2
|  |  |  | 2 | 2.5
[5 empty] | 16 | 80 | m2
[6 empty] | 85.6 | m2 Total in d
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Dortmund
Contractor |  | Payment: | Sheet No: | page No:
Trust Construction |  | 18 |  |  | 1
Project / site: |  | Building ID / Infra Component:
UCBP/Dessie | 1 | Dortmund Tank
Item No: | Gebru G/medhin | Date:
8
Description / Drawing / Sketch: |  | Number | Dimension | Quantity | Unit
8.2 CONCRETE WORK
b) In 500mm thick RC wall
|  | 1 | 36
2.94
|  |  | 0.5 | 52.92 | m3
c) In 250mm thick RC wall |  | 4 | 9.55
|  |  | 1.35 |  |  | 75.8475
|  |  | 0.25 | 12.8925 | m3
d) In 250mm thick suspended slab |  | 4 | 9.15
0.4
|  |  | 0.25 | 3.66 | m3
e) 250mm thick inclined slab |  | 4 | 7.5
0.85
|  |  | 0.25 | 6.375 | m3
8.2.4) Form Work
b) In 500mm thick RC wall |  | 2 | 36
|  |  | 2.95 | 212.4 | m2
c) To 250mm thick RC wall |  | 4 | 9.8
|  |  | 1.35 | 52.92 | m2
|  | 4 | 9.5
|  |  | 1.1 | 41.8 | m2
Total for this payment |  |  |  | 94.72 | m2
e) In 250mm thick inclined |  | 4 | 4.125
|  |  | 8.74 | 144.21 | m2
d) In 250mm thick suspended slab |  | 4 | 9.15
|  |  | 0.65 | 23.79 | m2
8.2.2) Mild Steel Re-bar
a) dia 10mm deformed bar |  | 1 |  | 1116.9243 | kg
c) dia 14mm deformed bar |  | 1 |  | 203.112 | kg
8.2.6) PVC Water Stoper |  | 1 |  | 30.4 | ml
Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Payment: | Sheet No: | page No:
Trust Construction |  | 19 |  |  | 1
Project / site: |  | Building ID / Infra Component:
UCBP/Dessie | 1 | Dortmund Tank , SDBs and Inlet pumping Station
Item No: | Gebru G/medhin | Date:
8
Description / Drawing / Sketch: |  | Number | Dimension | Quantity | Unit
8.Dortmund Tank
8.2.5 Mild steel reinforcement bars |  | 1 | 14366.81 | 14366.81 | kg
C) Dia 14mm Previous |  |  | 605.47 | 605.47 | kg
Total For this Payment |  |  |  | 13761.34 | kg
11. Inlet water Pumping Station
11.2.4. Mild steel reinforcemet bars
a) Dia.10mm |  | 1 | 819.02 | 819.02 | kg
b) Dia 12mm |  | 1 | 518.16 | 518.16 | kg
11.2.5. PVC Water Stopper |  | 1 | 22 | 22 | ml
9) Sludge Drying Beds
9.2.4. Mild Steel reinforcement bars
a) Dia.12mm |  | 1 | 7627.21 | 7627.21 | kg
Previous |  | 1 | 4405.02 | 4405.02 | kg
Total For this payment |  |  | 3222.19 | 3222.19 | kg
B) Dia 14mm |  | 1 | 13491.5 | 13491.5 | kg
Previous |  | 1 | 8980.7 | 8980.7 | kg
Total For this payment |  |  | 4510.8 | 4510.8 | kg
1.Site preparation
1.2.1. Stone Masonry Retaining Wall | A=(1+0.5)/2 *18 | 1 | 13.5 | 13.5 | m2
| V= |  | 1 | 13.5 | m3
Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Raw water pumping station
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: |  | page No:
Trust Construction |  |  |  | 20 |  |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 5B | Raw Water Pumping Station
Item No: |  | Prepared by: | Gebru G/medhin | Date:
11.4
Description / Drawing / Sketch:
Civil Work |  |  |  | Number | Dimension | Quantity | Unit
11.4.1. Excavation and Earth Work
11.4.1.1 Pit excavation in ordinary siol to a depth not exceeding 1500 mm |  |  |  | 1 | 11.95
10.5
[5 empty] | 1.5 | 188.2125 | m3
11.4.1.2 Ditto but to a depth exceeding 1500 mm but not exeeding 3000mm
|  |  |  | 1 | 11.95
10.5
[5 empty] | 1.5 | 188.2125 | m3
11.4.1.3 Ditto but to a depth exceeding 3000mm mm but not exeeding 6000mm
|  |  |  | 1 | 11.95
10.5
[5 empty] | 3 | 376.425 | m3
11.4.5 Load and cart away surplus excavated material to approprite trip
|  |  |  | 1 | 11.95
10.5
[5 empty] | 6 | 752.85 | m3
11.4.2. Concrete Work
11.4.2.1 50 mm C- 5 lean Concrete, minimum cement content 150 kg/m3
a) Under bottom slab |  |  |  | 1 | 4.05
[5 empty] | 2.6 | 10.53 | m2
11.4.2.2 Water tight Reinforced Concrete, quality C-30 400 kg/m3 and complast WP - 400 filled to form work
a) In 250mm thick bottom slab |  |  |  | 1 | 3.95
2.5
[5 empty] | 0.25 | 2.4688 | m3
b) In 250mm thick RC wall |  |  |  | 4 | 4.65
2.5
[5 empty] | 0.25 | 11.625 | m3
In Suspende slab wall |  |  |  | 2 | 3.95
0.95
[5 empty] | 0.25 | 1.8762 | m3
Total in b | [5 empty] | 13.5013 | m3
11.4.2.3 Provide, cut and fix in position sawn structural wood or steel form work
a) In 250mm thick bottom slab |  |  |  | 2 | 6.45
[5 empty] | 0.25 | 3.225 | m2
b) In 250mm thick RC wall |  |  |  | 8 | 4.65
[5 empty] | 2.5 | 93 | m2
In Suspende slab wall |  |  |  | 4 | 3.95
[5 empty] | 0.95 | 15.01 | m2
Total in b | [5 empty] | 108.01 | m2
11.4.2.4 Mild steel Re-bar according to structural drawings. |  |  |  | 1 | 819.02 | 819.02 | kg
a) Dia 10mm deformed bar |  |  |  | 1 | 698.383 | 698.383 | kg
b) Dia 12mm deformed bar
PVC Water Stoper |  |  |  | 2 | 7.5 | 15 | ml
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## EMERGENCY
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 18 |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 5B | Emergency Tank
Item No: |  | Prepared by: | Gebru G/medhin | Date:
10.1
Description / Drawing / Sketch:
|  |  |  | Number | Dimension | Quantity
3.1) Excavation and Earth Work
3.1.4) Fill around RC Wall
Volume of Excavation |  |  |  | 1 | 31.8
16.5
[5 empty] | 3.95 | 2072.565
2072.565
Volume of Structure diduct |  |  |  | 1 | 24.8
9.5
[5 empty] | 3.95 | 930.62
| Fill Volume |  |  |  |  | 0
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## service building
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 17 |  | 0 | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Survice Building
Item No: |  | Prepared by: |  | Date:
15.8
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
13.6) Carpentry and Joinery
Chipwood Ceiling
|  |  |  | 1 | 14.45
[5 empty] | 9.65 | 139.4425
|  |  |  | 1 | 4.1
[5 empty] | 3.72 | 15.252
|  |  |  | 1 | 1.35
[5 empty] | 4.17 | 5.6295
|  |  |  | 1 | 1.35
[5 empty] | 1.35 | 1.8225
|  |  |  | 1 | 4.1
[5 empty] | 3.77 | 15.457
|  |  |  | 1 | 2.45
[5 empty] | 0.75 | 1.8375
|  |  |  | 1 | 1.5
[5 empty] | 2.16 | 3.24
|  |  |  | 1 | 2.85
[5 empty] | 1.16 | 3.306
| Total for this payment |  |  |  |  | 185.987
15.6.2)Supplay& fix Flush type Wooden Doors of 40cm thick both side covered with 4mm thick ply wood
| a)D3 size 990*2990 |  |  | 1 | 2 | 2
| b)D3 size 800*2990 |  |  | 1 | 7 | 7
15.7 METAL WORK
e) W5 size 3790x1990mm ABOVE TOP TIE BEAM
| size=3.8*0.75=2.85m2 |  |  | 4 | 2.85 | 11.4
| size=2.8*0.75=2.1m2 |  |  | 2 | 2.1 | 4.2
15.6
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## AEARATION
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 19 |  |  | 1 of 2
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 1 | Aeration tank
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Description / Drawing / Sketch:
|  |  |  | Number | Dimension | Quantity | Unit
7.2 CONCRETE WORK
7.2.2)Water tight Reinforced concrete quality C-30, 400 kg of cement/m3 and Conplast WP-400 or equivalent water tight admixture 8Lit/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately)
b) In Beam |  |  |  | 4 | 3.35
0.95
[5 empty] | 0.3 | 3.819 | m3
d) In 300mm thick RC wall |  |  |  | 2 | 5.5
1.15
[5 empty] | 0.3 | 3.795 | m3
e)In 250mm thick RC wall |  |  |  | 2 | 5.9
7.2
[5 empty] | 0.25 | 21.24 | m3
|  |  |  | 1 | 11.83
1.4
[5 empty] | 0.25 | 4.1405 | m3
[6 empty] | 25.3805 | m3 Total in e
f)In 250mm thick suspended slab |  |  |  | 1 | 13.85
0.75
[5 empty] | 0.25 | 2.5969 | m3
|  |  |  | 2 | 2.2
5.15
[5 empty] | 0.25 | 5.665 | m3
[6 empty] | 8.2619 | m3 Total in f
g)In 400mm thick suspended slab |  |  |  | 1 | 4.1
1.1
[5 empty] | 0.4 | 1.804 | m3
7.2.3 Provide, cut & fix in position sawn structural wood formwork
b) In Beam |  |  |  | 8 | 3.35
[5 empty] | 0.95 | 25.46 | m2
d) In 300mm thick RC wall |  |  |  | 4 | 5.5
[5 empty] | 1.35 | 29.7 | m2
e)In 250mm thick RC wall |  |  |  | 4 | 5.9
[5 empty] | 7.2 | 169.92 | m2
|  |  |  | 2 | 11.83
[5 empty] | 1.525 | 36.0815 | m2
[6 empty] | 206.0015 | m2
[6 empty] | 235.7015 | m2 Total in RC wall
f)In 250mm thick suspended slab |  |  |  | 1 | 13.85
[5 empty] | 0.75 | 10.3875 | m2
|  |  |  | 2 | 2.2
[5 empty] | 5.15 | 22.66 | m2
[6 empty] | 33.0475 | m2
g)In 400mm thick suspended slab
|  |  |  | 1 | 4.1
[5 empty] | 1.1 | 4.51 | m2
[6 empty] | 37.5575 | m2 Total
7.2.4 Mild steel reinforcement according to structural drawing.
a) Dia 8 mm deformed bar |  |  |  | 1 | 1 | 188.37 | kg
b) Dia 10 mm deformed bar |  |  |  | 1 | 1 | 1538.13 | kg
[6 empty] | 1726.5 | kg
c) Dia 12 mm deformed bar |  |  |  | 1 | 1 | 1861.3 | kg
d) Dia 16 mm deformed bar |  |  |  | 1 | 1 | 1693.13 | kg
7.2.6)Supply & Install approved quality PVC water stopper at construction joints
|  |  |  | 2 | 5.8 | 11.6
|  |  |  | 2 | 1.75 | 3.5
[6 empty] | 15.1 | ml
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## bar schedule (2)
Contractor |  | Trust Construction
Project / site: |  | UCBP/Dessie
Consultant |  | MHE
Client |  | GIZ
| Bar No | Location | Shape | Ø | L | No of | No.of bar | Re-bars
[6 empty] | Member | per mem | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
Imhoff Tank
| 1 |  |  | 20 | 12 | 1 | 129 | " | " | " | " | " | " | 1548 | "
| 1' | Wall |  | 20 | 3.7 | 1 | 258 | " | " | " | " | " | " | 954.6 | "
| 2 | and |  | 20 | 2.38 | 1 | 129 | " | " | " | " | " | " | 307.02 | "
| 3 | Top Slab |  | 20 | 9.5 | 1 | 129 | " | " | " | " | " | " | 1225.5 | "
| 6 |  |  | 10 | 2.6 | 1 | 19 | " | " | 49.4 | " | " | " | " | "
| 7 |  |  | 10 | 5.52 | 1 | 19 | " | " | 104.88 | " | " | " | " | "
| 8 |  |  | 10 | 2.03 | 1 | 286 | " | " | 580.58 | " | " | " | " | "
| 9 |  |  | 10 | 1.68 | 1 | 19 | " | " | 31.92 | " | " | " | " | "
| 10 |  |  | 10 | 2.1 | 1 | 19 | " | " | 39.9 | " | " | " | " | "
| 11 |  |  | 10 | 4.05 | 1 | 56 | " | " | 226.8 | " | " | " | " | "
| 17 |  |  | 10 | 3.3 | 1 | 214 | " | " | 706.2 | " | " | " | " | "
| 18 |  |  | 10 | 6.15 | 1 | 214 | " | " | 1316.1 | " | " | " | " | "
| 19 |  |  | 10 | 1.6 | 1 | 214 | " | " | 342.4 | " | " | " | " | "
| 20 |  |  | 10 | 3.7 | 1 | 162 | " | " | 599.4 | " | " | " | " | "
| 21 |  |  | 10 | 12 | 1 | 81 | " | " | 972 | " | " | " | " | "
[5 empty] | Total Length |  |  | 0 | 0 | 4969.58 | 0 | 0 | 0 | 4035.12 | 0
[5 empty] | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
[5 empty] | Total Weight |  |  | 0 | 0 | 3066.2309 | 0 | 0 | 0 | 9954.641 | 0
| Bar No | Location | Shape | Ø | L | No of | No.of bar | Re-bars
[6 empty] | Member | per mem | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
AERATION TANK
| Bottom slab | [6 empty] | " | " | " | " | " | " | " | "
| 9 |  |  | 16 | 6.25 | 6 | 3 | " | " | " | " | " | 112.5 | " | "
| 10 |  |  | 16 | 6.25 | 6 | 2 | " | " | " | " | " | 75 | " | "
|  |  |  | 16 | 6.25 | 6 | 3 | " | " | " | " | " | 112.5 | " | "
| 3 |  |  | 12 | 1.45 | 32 | 2 | " | " | " | 92.8 | " | " | " | "
| 4 |  |  | 12 | 0.8 | 32 | 2 | " | " | " | 51.2 | " | " | " | "
| 1 |  |  | 12 | 2.4 | 32 | 2 | " | " | " | 153.6 | " | " | " | "
|  |  |  | 12 | 1.2 | 14 | 28 | " | " | " | 470.4 | " | " | " | "
|  |  |  | 12 | 3.83 | 58 | 1 | " | " | " | 222.14 | " | " | " | "
|  |  |  | 12 | 7.8 | 6 | 2 | " | " | " | 93.6 | " | " | " | "
|  |  |  | 12 | 7.8 | 10 | 2 | " | " | " | 156 | " | " | " | "
|  |  |  | 12 | 2.1 | 53 | 1 | " | " | " | 111.3 | " | " | " | "
|  |  |  | 12 | 1.3 | 58 | 1 | " | " | " | 75.4 | " | " | " | "
|  |  |  | 12 | 3.83 | 48 | 1 | " | " | " | 183.84 | " | " | " | "
|  |  |  | 12 | 6.45 | 6 | 2 | " | " | " | 77.4 | " | " | " | "
|  |  |  | 12 | 6.45 | 10 | 2 | " | " | " | 129 | " | " | " | "
|  |  |  | 12 | 2.1 | 42 | 1 | " | " | " | 88.2 | " | " | " | "
|  |  |  | 12 | 1.3 | 48 | 1 | " | " | " | 62.4 | " | " | " | "
|  |  |  | 12 | 10.2 | 9 | 2 | " | " | " | 183.6 | " | " | " | "
|  |  |  | 12 | 4.6 | 9 | 2 | " | " | " | 82.8 | " | " | " | "
|  |  |  | 12 | 4.7 | 32 | 2 | " | " | " | 300.8 | " | " | " | "
|  |  |  | 12 | 1.3 | 32 | 2 | " | " | " | 83.2 | " | " | " | "
|  |  |  | 12 | 1.3 | 7 | 4 | " | " | " | 36.4 | " | " | " | "
|  |  |  | 16 | 4.4 | 8 | 4 | " | " | " | " | " | 140.8 | " | "
|  |  |  | 16 | 1.8 | 10 | 8 | " | " | " | " | " | 144 | " | "
|  |  |  | 16 | 1.9 | 32 | 2 | " | " | " | " | " | 121.6 | " | "
[5 empty] | Total Length |  |  | 0 | 0 | 0 | 2654.08 | 0 | 706.4 | 0 | 0
[5 empty] | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
[5 empty] | Total Weight |  |  | 0 | 0 | 0 | 2356.823 | 0 | 1115.4056 | 0 | 0
| Bar No | Location | Shape | Ø | L | No of | No.of bar | Re-bars
[6 empty] | Member | per mem | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
DORTMUND TANK
| 3 |  |  | 10 | 2 | 265 | 1 | " | " | 530 | " | " | " | " | "
| 4 | Wall |  | 10 | 3.85 | 265 | 1 | " | " | 1020.25 | " | " | " | " | "
| 8 | and |  | 10 | 2.4 | 80 | 1 | " | " | 192 | " | " | " | " | "
| 9 | Suspended |  | 14 | 2.4 | 70 | 1 | " | " | " | " | 168 | " | " | "
| 10 | Slab |  | 10 | 1.7 | 40 | 1 | " | " | 68 | " | " | " | " | "
[5 empty] | Total Length |  |  | 0 | 0 | 1810.25 | 0 | 168 | 0 | 0 | 0
[5 empty] | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
[5 empty] | Total Weight |  |  | 0 | 0 | 1116.9243 | 0 | 203.112 | 0 | 0 | 0
| Bar No | Location | Shape | Ø | L | No of | No.of bar | Re-bars
[6 empty] | Member | per mem | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
Rain Water Pumping Station
| 4 | Correction |  | 12 | 8.75 | 38 | 1 | " | " | " | 332.5 | " | " | " | "
| 4' | Work in |  | 12 | 8.65 | 38 | 1 | " | " | " | 328.7 | " | " | " | "
| 4" | Bottom Slab |  | 12 | 6.4 | 130 | 1 | " | " | " | 832 | " | " | " | "
| 5 |  |  | 12 | 1 | 38 | 1 | " | " | " | 38 | " | " | " | "
[5 empty] | Total Length |  |  | 0 | 0 | 0 | 1531.2 | 0 | 0 | 0 | 0
[5 empty] | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
[5 empty] | Total Weight |  |  | 0 | 0 | 0 | 1359.7056 | 0 | 0 | 0 | 0
| Bar No | Location | Shape | Ø | L | No of | No.of bar | Re-bars
[6 empty] | Member | per mem | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
DORTMUND TANK
|  | Inclianed Beam |  | 12 | 5.35 | 5 | 1 | " | " | " | 26.75 | " | " | " | "
|  |  |  | 12 | 6.2 | 6 | 1 | " | " | " | 37.2 | " | " | " | "
|  |  |  | 12 | 6.35 | 4 | 1 | " | " | " | 25.4 | " | " | " | "
|  |  |  | 12 | 6.1 | 2 | 1 | " | " | " | 12.2 | " | " | " | "
|  |  |  | 12 | 6.3 | 1 | 1 | " | " | " | 6.3 | " | " | " | "
|  |  |  | 12 | 5.05 | 3 | 1 | " | " | " | 15.15 | " | " | " | "
|  |  |  | 12 | 6.9 | 4 | 1 | " | " | " | 27.6 | " | " | " | "
|  |  |  | 12 | 4.65 | 4 | 1 | " | " | " | 18.6 | " | " | " | "
|  |  |  | 12 | 5.3 | 1 | 1 | " | " | " | 5.3 | " | " | " | "
|  |  |  | 12 | 7.3 | 1 | 1 | " | " | " | 7.3 | " | " | " | "
|  |  |  | 12 | 4.6 | 7 | 1 | " | " | " | 32.2 | " | " | " | "
|  |  |  | 12 | 2.5 | 4 | 1 | " | " | " | 10 | " | " | " | "
|  |  |  | 12 | 3.5 | 7 | 1 | " | " | " | 24.5 | " | " | " | "
|  |  |  | 12 | 3.2 | 7 | 1 | " | " | " | 22.4 | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[8 empty] | " | " | " |  | " | " | " | "
[5 empty] | Total Length |  |  | 0 | 0 | 0 | 270.9 | 0 | 0 | 0 | 0
[5 empty] | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
[5 empty] | Total Weight |  |  | 0 | 0 | 0 | 240.5592 | 0 | 0 | 0 | 0

## Storm Water Drainage
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 17 |  | 0 | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Storm Water Drainage
Item No: |  | Prepared by: | Yohannes T/M | Date:
14
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
14.10) Construct Storm Water Drainage channel Average Depth of channel 400mm |  |  |  | 1 | 88 | 88
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## DS Retaining Wall
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 17 |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Retaining Wall Construction
Item No: |  | Prepared by: | Yohannes T/M | Date:
1.4.3
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
1.3 | Masonary Work
1.4.3 | Masonary Work
| Roughly dressed Retaining wall |  |  | 1 | 72
0.75
|  | Average Width = 1.0 + 0.5/2 = 0.75 |  |  | 1.05 | 56.7
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Walk way & crossing
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 17 |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Site Preparation Lot 2
Item No: |  | Prepared by: | Yohannes T/M | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
Walk Way
33.16b)Reinforced drain cover 1.5x0.3x0.1m |  |  |  | 1 | 46 | 46
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Water Supply
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 17 |  |  | 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | Domestic Water Supply System
Item No: |  | Prepared by: | Yohannes T/M |  | Date:
Supple Aggr
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity
SA) 1.1) | Domestic Water Sup System
1.1.1) HDPE PN 16 depth 800/width600mm
excavation in ordinary soil
|  | a)) Dia 40 |  |  | 1 | 10 | 10
|  | b) Dia 50 |  |  | 1 | 107 | 107
|  | c) Dia 90 |  |  | 1 | 24 | 24
|  | Date: |  | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Site Road
vbkl] |  | Take-off Sheet |  |  | Payment:
20
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | Site Road
Item No: |  | Prepared by: |  |  | Date:
16 |  |  | Gebru G/medhin
Description / Drawing / Sketch:
Number
42.00 Road Way and Borrow Excavation
42.01 Cut and Borrow to fill
42.01(a) ii Borrow to fill and Compaction
Road 02
with Slope 1:2
Station 0+000 | Bottom width = 8.4 m |  |  |  | 1
Top width = 6 m
Averege width = | 8.4+6/2 = 7 m | 7.2
| Fill = 0.61 | m
Station 0+020 | Bottom width = 12.4 m |  |  |  | 1
Top width = 6 m
12.4+6/2 = 9.2 m
Fill = 1.6 m
Station 0+040 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+060 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+080 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+100 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+120 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+140 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+160 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+180 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+200 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Station 0+220 | Bottom width = 8 m |  |  |  | 1
Top width = 6 m
8+6/2 = 7 m
Total Fill Volume
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
vbkl] |  | Take-off Sheet |  |  | Payment:
20
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | Site Road 02
Item No: |  | Prepared by: |  |  | Date:
16 |  |  | Gebru G/medhin
Description / Drawing / Sketch:
42.00 Road Way and Borrow Excavation
42.01 Cut and Borrow to fill
42.01(a) ii Borrow to fill and Compaction
Station | Top fill width in(m) | Fill Depth in (m) | Bottom Fill Width in (m) | Fill Area (m^2) | Fill Volume (m^3)
0 | 9 | 0.61 | 11.44 | 6.2342 | 0
20 | 9 | 1.6 | 15.4 | 19.52 | 257.542
40 | 9 | 1.86 | 16.44 | 23.6592 | 431.792
60 | 9 | 1.49 | 14.96 | 17.8502 | 415.094
80 | 9 | 1.45 | 14.8 | 17.255 | 351.052
100 | 9 | 1.55 | 15.2 | 18.755 | 360.1
120 | 9 | 1.76 | 16.04 | 22.0352 | 407.902
140 | 9 | 1.28 | 14.12 | 14.7968 | 368.32
160 | 9 | 2.7 | 19.8 | 38.88 | 536.768
180 | 9 | 3.12 | 21.48 | 47.5488 | 864.288
200 | 9 | 2.58 | 19.32 | 36.5328 | 840.816
220 | 9 | 0.7 | 11.8 | 7.28 | 438.128
0+000 to 000+220 |  |  |  |  | 5271.802
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## SDB Gates 1 2 3 and 4
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 17 |  | 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Sludge Drying Bed 1 2 3 & 4 Gates
Item No: |  | Prepared by: |  | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
VO-
Sludge Draying Bed 1 |  |  |  | 1 | 4
1.01) | Bulk Excavaion in ordinary soil to 1500mm depth |  |  |  | 2
[5 empty] | 1.5 | 12 | 12
1.02) | Load and Car away excavated material |  |  | 1 | 4
2
[5 empty] | 1.5 | 12 | 9
Concrete Work | [7 empty] | 423.87
1.03) | Lean Concrete |  |  | 1 | 4
2
[6 empty] | 8 | 0
1.04) | Water Tight C-30 Concrete Bottom Slab |  |  | 1 | 4
2
[5 empty] | 0.4 | 3.2 | 3.2
24.2
1.05) | Water Tight C-30 Concrete Wall |  |  | 2 | 1.66 |  | -24.2
1.7
[5 empty] | 0.4 | 2.2576
| Middle of the Gate Wall |  |  | 1 | 0.8
0.95
[5 empty] | 1.7 | 1.292
| Grand Total |  |  |  |  | 3.5496
1.06) | Water Stopper |  |  | 1 |  | 5.9
1.07) | Provide,cut and fix in position of form work
| Bottom Slab |  |  | 1 | 16.2
| (2*2=4) + | (2*4.1)=16.2 |  |  | 0.45 | 7.29
| RC Wall |  |  | 4 | 1.71
| 3.6*2=7.2 |  |  |  | 1.75
11.97
2.6*2 = 5.2
|  |  |  | 2 | 0.85
1
1.7
| Grand Total |  |  |  |  | 13.67
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 15 |  | 2
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Sludge Drying Bed 1 2 3 & 4 Gates
Item No: |  | Prepared by: |  | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
Sludge Draying Bed 2 |  |  |  | 1 | 4
1.01) | Bulk Excavaion in ordinary soil to 1500mm depth |  |  |  | 2
[5 empty] | 1.5 | 12
1.02) | Load and Car away excavated material |  |  | 1 | 4
2
[5 empty] | 1.5 | 12
Concrete Work
1.03) | Lean Concrete |  |  | 1 | 4
2
8
1.04) | Water Tight C-30 Concrete Bottom Slab |  |  | 1 | 4
2
[5 empty] | 0.4 | 3.2
1.05) | Water Tight C-30 Concrete Wall |  |  | 2 | 1.66
1.7
[5 empty] | 0.4 | 2.2576
| Middle of the Gate Wall |  |  | 1 | 0.8
0.95
[5 empty] | 1.7 | 1.292
| Grand Total |  |  |  |  | 3.5496
1.06) | Water Stopper |  |  | 1 |  | 5.9
1.07) | Provide,cut and fix in position of form work
| Bottom Slab |  |  | 1 | 16.2
| (2*2=4) + | (2*4.1)=16.2 |  |  | 0.45 | 7.29
| RC Wall |  |  | 4 | 1.71
| 3.6*2=7.2 |  |  |  | 1.75
11.97
2.6*2 = 5.2
|  |  |  | 2 | 0.85
1
1.7
| Grand Total |  |  |  |  | 13.67
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 15 |  | 2
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Sludge Drying Bed 1 2 3 & 4 Gates
Item No: |  | Prepared by: |  | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
Sludge Draying Bed 3 |  |  |  | 1 | 4
1.01) | Bulk Excavaion in ordinary soil to 1500mm depth |  |  |  | 2
[5 empty] | 1.5 | 12
1.02) | Load and Car away excavated material |  |  | 1 | 4
2
[5 empty] | 1.5 | 12
Concrete Work
1.03) | Lean Concrete |  |  | 1 | 4
2
8
1.04) | Water Tight C-30 Concrete Bottom Slab |  |  | 1 | 4
2
[5 empty] | 0.4 | 3.2
1.05) | Water Tight C-30 Concrete Wall |  |  | 2 | 1.66
1.7
[5 empty] | 0.4 | 2.2576
| Middle of the Gate Wall |  |  | 1 | 0.8
0.95
[5 empty] | 1.7 | 1.292
| Grand Total |  |  |  |  | 3.5496
1.06) | Water Stopper |  |  | 1 |  | 5.9
1.07) | Provide,cut and fix in position of form work
| Bottom Slab |  |  | 1 | 16.2
| (2*2=4) + | (2*4.1)=16.2 |  |  | 0.45 | 7.29
| RC Wall |  |  | 4 | 1.71
| 3.6*2=7.2 |  |  |  | 1.75
11.97
2.6*2 = 5.2
|  |  |  | 2 | 0.85
1
1.7
| Grand Total |  |  |  |  | 13.67
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 15 |  | 2
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Sludge Drying Bed 1 2 3 & 4 Gates
Item No: |  | Prepared by: |  | Date:
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity
Sludge Draying Bed 4 |  |  |  | 1 | 4
1.01) | Bulk Excavaion in ordinary soil to 1500mm depth |  |  |  | 2
[5 empty] | 1.5 | 12
1.02) | Load and Car away excavated material |  |  | 1 | 4
2
[5 empty] | 1.5 | 12
Concrete Work
1.03) | Lean Concrete |  |  | 1 | 4
2
8
1.04) | Water Tight C-30 Concrete Bottom Slab |  |  | 1 | 4
2
[5 empty] | 0.4 | 3.2
1.05) | Water Tight C-30 Concrete Wall |  |  | 2 | 1.66
1.7
[5 empty] | 0.4 | 2.2576
| Middle of the Gate Wall |  |  | 1 | 0.8
0.95
[5 empty] | 1.7 | 1.292
| Grand Total |  |  |  |  | 3.5496
1.06) | Water Stopper |  |  | 1 |  | 5.9
1.07) | Provide,cut and fix in position of form work
| Bottom Slab |  |  | 1 | 16.2
| (2*2=4) + | (2*4.1)=16.2 |  |  | 0.45 | 7.29
| RC Wall |  |  | 4 | 1.71
| 3.6*2=7.2 |  |  |  | 1.75
11.97
2.6*2 = 5.2
|  |  |  | 2 | 0.85
1
1.7
| Grand Total |  |  |  |  | 13.67
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## 500 m3 Ground Reservior
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 17 |  |  | 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | 500m3 Capacity RC Ground Water Reservior
Item No: |  | Prepared by: |  |  | Date:
1.3.3
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity
500m3 Ground Reservior
Brass Gate Valve
| a) On Pipe Inlet point from tank dia. 4'' |  |  |  | 1 | 1 | 1
| a) On Water Tank Drain Pipe dia. 6'' |  |  |  | 1 | 1 | 1
| a) On Water distribution pipe after |  |  |  | 1 | 1 | 1
tank dia.6''
| Brick Valve Box |  |  |  | 1 | 1 | 1
|  | Date: |  | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Pump House
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 17 |  |  | 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | Pump House
Item No: |  | Prepared by: |  |  | Date:
2
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity
Super Structure
7) Finishing Work
| Internal Three Coats of Plastering |  |  |  | 2 | 5.59
[6 empty] | 3 | 33.54
Avg depth = 2.87 |  |  |  |  | 2 | 3.6
[6 empty] | 2.87 | 20.664
|  | ddt D-01 |  |  | -1 | 3.04
[6 empty] | 2.1 | -6.384
|  | ddt W-01 |  |  | -1 | 2.02
[6 empty] | 0.5 | -1.01
46.81
| External Two Coats of Plastering |  |  |  | 2 | 6
| and one coats of Rendering |  |  |  |  | 3.2 | 38.4
Avg depth = 2.9 |  |  |  |  | 2 | 4
[6 empty] | 2.9 | 23.2
|  | ddt D-01 |  |  | -1 | 3.04
[6 empty] | 2.1 | -6.384
|  | ddt W-01 |  |  | -1 | 2.02
[6 empty] | 0.5 | -1.01
54.206
| Cement Screed 50mm thick |  |  |  | 1 | 5.59
[6 empty] | 3.6 | 20.124
VO-4 Pump House Electrical Connection
| 1.1) Under Ground Cable 3x150/70+1x70 sqmm |  |  |  | 1 | 325 | 325
from SDB 5/5 to Pump Station SDB-p
| 1.2) Cable Trench |  |  |  | 1 | 325
0.8
[6 empty] | 0.06 | 15.6
| 1.2) Warning Tape 100mm wide |  |  |  | 1 | 325 | 325
|  | Date: |  | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## 50 m3 Elevated Tank
Contractor |  | Take-off Sheet |  |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  |  | 17 |  |  | 1
Project / site: |  | Lot: |  |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 |  | 50m3 Capacity RC Water Reservior
Item No: |  | Prepared by: |  |  | Date:
1.3.1
Description / Drawing / Sketch: |  |  |  |  | Number | Dimension | Quantity
50m3 Capacity RC Water Res
dia 150mm GSP Inlet pipe from Pump House |  |  |  |  | 1 | 49.15 | 49.15
dia 200mm GSP Drain Pipe |  |  |  |  | 1 | 19.3 | 19.3
dia 250mm GSP Outlet pipe from the Tank |  |  |  |  | 1 | 30.08 | 30.08
Brass Gate Valve
| a) On Pipe Inlet point from tank dia. 150mm |  |  |  | 1 | 1 | 1
| a) On Water Tank Drain Pipe dia. 100mm |  |  |  | 1 | 1 | 1
| a) On Water distribution pipe after |  |  |  | 1 | 1 | 1
tank dia. 250mm
|  | Date: |  | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## Variation order No.06
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 20 |  |  | 1 of 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | 1) Fuel Tank Foundation
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Var. no.06
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity | Unit
1) Fuel Tank Foundation
1.01) Lean concrete under footing
|  |  |  | 1 | 2.5
[5 empty] | 3.8 | 9.5 | m2
1.02) Reinforced Concrete C -25 in footing |  |  |  | 1 | 2.4
3.7
[5 empty] | 0.2 | 1.776 | m3
1.03) Mild Steel Reinforcement
a) Dia 10mm |  |  |  | 1 | 137.83 | 137.83 | kg
1.05) Steel Form Work
a) In footing |  |  |  | 2 | 6.1
[5 empty] | 0.2 | 2.44 | m2
14. Service Boulding
Modification work for Generater Location
1. Correction work
1.1) Removal of the existing construction and make ready for new floor slab casting
a) RC floor slab price including of concrete and steel re-bar |  |  |  | 1 | 3.8
[5 empty] | 3 | 11.4 | m2
b) 25 cm thick hard core and re-use again for new concrete casting |  |  |  | 1 | 3.8
[5 empty] | 3 | 11.4 | m2
c) Excavate the exsting selected material to an appropriat depth |  |  |  | 1 | 3.4
2
[5 empty] | 0.3 | 2.04 | m3
1.2) Removal of vertical surfaces
a) Door: Type Door-09: size :1410*3010 |  |  |  | 1 | 1 | 1 | no
b) Windows: Type w-05: size :870*800mm |  |  |  | 1 | 1 | 1 | no
1.2.2) Removal of the existing HCB wall in two wing parts of block |  |  |  | 1 | 4
[5 empty] | 3.1 | 12.4 | m2
|  |  |  | 1 | 4
[5 empty] | 4.1 | 16.4 | m2
|  |  |  | 1 | 2
[5 empty] | 3.1 | 6.2 | m2
|  |  | Total |  |  | 35 | m2
|  | Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 20 |  |  | 1 of 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Service Building Modification work
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Var. no.06
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity | Unit
2) Excavation and Earth Work
2.1) Trench excavation to lay cable trench to a depth not exceeding 1.5m in ordinary siol |  |  |  | 1 | 9.4
1.5
[5 empty] | 0.8 | 11.28 | m3
2.2) Cart away surplus excavated material to an aproprite trip |  |  |  | 1 | 11.5
1.5
[5 empty] | 0.8 | 13.8 | m3
2.3) Re-use 250mm thick basaltic stone hard core |  |  |  | 1 | 3.8
[5 empty] | 3 | 11.4 | m2
3) Concrete Work
3.1) Reinforced Concrete quality C-25
a) To Generater pad (floor slab ) |  |  |  | 1 | 3.8
2
[5 empty] | 0.3 | 2.28 | m3
b) To concrete cable Trench duct |  |  |  | 2 | 10.45
0.9
[5 empty] | 0.2 | 3.762 | m3
|  |  |  | 1 | 10.45
0.8
[5 empty] | 0.5 | 4.18 | m3
| Total |  |  |  |  | 7.942 | m3
c) To 50mm thick R.C cover for electric cable duct |  |  |  | 1 | 10.45
[5 empty] | 0.5 | 5.225 | m2
d) To 100mm thick ground floor slab suround of genetator pad |  |  |  | 2 | 5.8
[5 empty] | 0.6 | 6.96 | m2
3.2) Provide, cut and fix in position swam structural wood or steel form work which ever is approprite.
a) To Generater pad (floor slab ) |  |  |  | 2 | 5.8
[5 empty] | 0.3 | 3.48 | m2
b) To concrete cable Trench duct and R.C Cover |  |  |  | 2 | 10.45
[5 empty] | 0.9 | 18.81 | m2
|  |  |  | 1 | 10.45
[5 empty] | 0.5 | 5.225 | m2
|  |  |  | 4 | 10.45
[5 empty] | 0.15 | 6.27 | m2
|  | Total |  |  |  | 30.305 | m2
3.3) Mild steel reinforcement according to structural drawings
a) Dia 8 mm deformed bars |  |  |  | 1 | 29 | 29 | kg
b) Dia 10 mm deformed bars |  |  |  | 1 | 307 | 307 | kg
b) Dia 14 mm deformed bars |  |  |  | 1 | 167 | 167 | kg
4) Block Work
4.1) Class C. 190mm thick HCB which can satisfy the designed strength, bedded in cement mortar(1:3) including pointing on both side of wall surface |  |  |  | 1 | 4
[5 empty] | 4 | 16 | m2
5) Manholes
a) Manholes in bricks and with concrete base internally of 1100x1100 with a depth 900 including reinforced concrete cover with lifting handle. |  |  |  | 1 | 2 | 2 | m2
|  | Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 20 |  |  | 1 of 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | UV- Disinfection
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Var. no.06
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity | Unit
1.1) Excavation and Earth Work
1.1.1) Bulk excavation in ordinary siol for UV Disinfection to not exceeding 3000 mm |  |  |  | 1 | 8.62
4.43
[5 empty] | 3 | 114.5598 | m3
1.1.2) Fill around RC wall in non expansive excavated material to an approprite tirp |  |  |  | 2 | 13.05
3
[5 empty] | 1 | 78.3 | m3
1.1.3) Load Cart away surplus excavated material to an aproprite trip |  |  |  | 1 | 8.62
4.43
[5 empty] | 3 | 114.5598 | m3
1.2) Concrete Work
1.2.1) 50 mm lean Concrete Work quality C-5
a) Under bottom slab |  |  |  | 1 | 6.72
[5 empty] | 2.52 | 16.9344 | m2
In pedstals |  |  |  | 2 | 0.8
[5 empty] | 0.8 | 1.28 | m2
| Total in a |  |  |  |  | 18.2144 | m2
1.2.2) Water tight reinforced concrete quality C-30, 400kg of cement/m3
a) In RC 800mm thick bottom slab |  |  |  | 1 | 3.215
2.43
[5 empty] | 0.8 | 6.25 | m3
In RC 750mm thick Pedstal PD - 2 |  |  |  | 1 | 0.5
0.5
[5 empty] | 0.75 | 0.1875 | m3
|  | Total |  |  |  | 6.4375 | m3
b) In RC 500mm thick bottom slab |  |  |  | 1 | 1.5
2.375
[5 empty] | 0.5 | 1.7812 | m3
c) In RC 400mm thick bottom slab |  |  |  | 1 | 1.95
2.43
[5 empty] | 0.4 | 1.8954 | m3
d) In RC 300mm thick bottom slab |  |  |  | 1 | 1.4
0.99
[5 empty] | 0.3 | 0.4158 | m3
e) In RC 250mm thick wall |  |  |  | 1 | 2.88
1.23
[5 empty] | 0.25 | 0.8856 | m3
|  |  |  | 2 | 3.215
0.93
[5 empty] | 0.25 | 1.495 | m3
|  |  |  | 1 | 4.075
1.33
[5 empty] | 0.25 | 1.3549 | m3
|  | Total in e |  |  |  | 3.7355 | m3
|  | Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 20 |  |  | 1 of 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | UV- Disinfection
Item No: |  | Prepared by: | Gebru G/medhin | Date:
Var. no.06
Description / Drawing / Sketch: |  |  |  | Number | Dimension | Quantity | Unit
1.2.3) Provide, cut and fix in position swam structural wood or steel form work which ever is approprite.
a) To RC bottom slab |  |  |  | 1 | 5.38
[5 empty] | 0.5 | 2.69 | m2
|  |  |  | 2 | 3.215
[5 empty] | 0.8 | 5.144 | m2
|  |  |  | 1 | 1.93
[5 empty] | 0.3 | 0.579 | m2
|  |  |  | 1 | 8.255
[5 empty] | 0.4 | 3.302 | m2
Total in a | [5 empty] | 11.715 | m2
b) To 250 mm thick wall |  |  |  | 2 | 2.88
[5 empty] | 1.23 | 7.0848 | m2
|  |  |  | 4 | 3.215
[5 empty] | 0.93 | 11.9598 | m2
|  |  |  | 2 | 4.075
[5 empty] | 1.33 | 10.8395 | m2
Total in b | [5 empty] | 29.8841 | m2
1.2.4) Mild steel reinforcement according to structural drawings
a) Dia 10 mm deformed bars |  |  |  | 1 | 7.44 | 7.44 | kg
b) Dia 12 mm deformed bars |  |  |  | 1 | 1678.06 | 1678.06 | kg
c) Dia 14 mm deformed bars |  |  |  | 1 | 291.85 | 291.85 | kg
|  | Date: | Name: | Signature and Stamp:
Contractor:
MH E RE:
GIZ-IS SM:

## DS Bar Sche RB SDB g ERP
TRUST CONSTRUCTION DESSIE PROJECT
Project:-Waste Water treatment plant construction
Location:- Dessie wollo university
Contractor:- Trust con.
RETENTION BASIN BAR SCHEDULE
s/n | Location | Bar | Dia. | No of | No of | Total | Length | Total | ᴓ 6 | ᴓ 8 | ᴓ 10 | ᴓ 12 | ᴓ 14 | ᴓ 16 | ᴓ 20
|  | Shape | (mm) | Bars | Mem. | No of | of | Length
[5 empty] | Bar | Bar | Bar
RETENTION
BASIN
| Bottom |  | 12 | 62 | 2 | 124 | 10.3 | 1277.2 |  |  |  | 1277.2
| slab |  | 12 | 168 | 2 | 336 | 7.3 | 2452.8 |  |  |  | 2452.8
|  |  | 12 | 24 | 4 | 96 | 2.1 | 201.6 |  |  |  | 201.6
|  |  | 12 | 84 | 2 | 168 | 11.3 | 1898.4 |  |  |  | 1898.4
|  |  | 12 | 31 | 2 | 62 | 8.3 | 514.6 |  |  |  | 514.6
| vertical |  | 14 | 46 | 4 | 184 | 1.6 | 294.4 |  |  |  |  | 294.4
| wall |  | 14 | 46 | 4 | 184 | 3.2 | 588.8 |  |  |  |  | 588.8
|  |  | 14 | 65 | 4 | 260 | 1.6 | 416 |  |  |  |  | 416
|  |  | 14 | 65 | 4 | 260 | 3.2 | 832 |  |  |  |  | 832
|  |  | 14 | 46 | 2 | 92 | 2.81 | 258.52 |  |  |  |  | 258.52
|  |  | 14 | 46 | 2 | 92 | 3.5 | 322 |  |  |  |  | 322
|  |  | 14 | 46 | 2 | 92 | 3.7 | 340.4 |  |  |  |  | 340.4
|  |  | 14 | 65 | 2 | 130 | 2.81 | 365.3 |  |  |  |  | 365.3
|  |  | 14 | 65 | 2 | 92 | 3.5 | 322 |  |  |  |  | 322
|  |  | 14 | 65 | 2 | 92 | 3.7 | 340.4 |  |  |  |  | 340.4
|  |  | 14 | 65 | 1 | 65 | 2.1 | 136.5 |  |  |  |  | 136.5
|  |  | 14 | 46 | 1 | 46 | 2.1 | 96.6 |  |  |  |  | 96
[6 empty] | length(m) | [5 empty] | 6344.6 | 4312.32
[6 empty] | Weigth(kg/m) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.469
[6 empty] | Total weigth(kg) |  |  | 0 | 0 | 0 | 5634.0048 | 5213.5949 | 0 | 0
TRUST CONSTRUCTION DESSIE PROJECT
Bar Schedule
Project:-Water treatment plant construction
Location:- Dessie wollo university
Contractor:- Trust con.
SLUDGE DRYING BED GATE BAR SCHEDULE
s/n | Location | Bar SHAPE | Dia.(MM) | No of BAR | No of MEMBERS | Total NO. OF BAR | LENGTH OF BAR | Total LENGTH | ᴓ 6 | ᴓ 8 | ᴓ 10 | ᴓ 12 | ᴓ 14 | ᴓ 16 | ᴓ 20
|  |  | 14 | 28 | 4 | 112 | 4.5 | 504 |  |  |  |  | 504
|  |  | 14 | 66 | 4 | 264 | 2.5 | 660 |  |  |  |  | 660
|  |  | 14 | 66 | 4 | 264 | 2.2 | 580.8 |  |  |  |  | 580.8
|  |  | 12 | 40 | 4 | 160 | 2.25 | 360 |  |  |  | 360
|  |  | 12 | 40 | 4 | 160 | 1.3 | 208 |  |  |  | 208
[6 empty] | length(m) | [5 empty] | 568 | 1744.8
[6 empty] | Weigth(kg/m) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.469
[6 empty] | Total weigth(kg) |  |  | 0 | 0 | 0 | 504.384 | 2109.4632 | 0 | 0
TRUST CONSTRUCTION DESSIE PROJECT
Bar Schedule
Project:-Water treatment plant construction
Location:- Dessie wollo university
Contractor:- Trust con.
EXCESS AND RETURN PUMPING STATION
s/n | Location | Bar SHAPE | Dia.(MM) | No of BAR | No of MEMBERS | Total NO. OF BAR | LENGTH OF BAR | Total LENGTH | ᴓ 6 | ᴓ 8 | ᴓ 10 | ᴓ 12 | ᴓ 14 | ᴓ 16 | ᴓ 20
| BOTTOM |  | 10 | 24 | 2 | 48 | 2.6 | 124.8 |  |  | 124.8
| BOTTOM |  | 10 | 18 | 2 | 36 | 3.6 | 129.6 |  |  | 129.6
| VERTICAL BAR |  | 12 | 206 | 2 | 412 | 8.03 | 3308.36 |  |  |  | 3308.36
| HOR.BAR |  | 12 | 78 | 2 | 156 | 2.3 | 358.8 |  |  |  | 358.8
| HOR.BAR |  | 12 | 78 | 2 | 156 | 3.7 | 577.2 |  |  |  | 577.2
| Diagonal bar |  | 10 | 14 | 4 | 56 | 1.6 | 89.6 |  |  | 89.6
[6 empty] | length(m) |  |  |  |  | 344 | 4244.36 | 0
[6 empty] | Weigth(kg/m) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.469
[6 empty] | Total weigth(kg) |  |  | 0 | 0 | 212.248 | 3768.9917 | 0 | 0 | 0

## SDBs
Contractor |  | Take-off Sheet |  | Payment: | Sheet No: | page No:
Trust Construction |  |  |  | 20 |  |  | 1 of 1
Project / site: |  | Lot: |  | Building ID / Infra Component:
UCBP/Dessie |  |  | 2 | Sludge Drying Beds
Item No: |  | Prepared by: |  | Date:
9 |  |  | Gebru G/medhin
Description / Drawing / Sketch: | [6 empty] | Unit
|  |  |  | Number | Dimension | Quantity
9.3.4 Filter Media
Supply and spread grannular filter media in the SDB -1
Dia 0 - 2mm,20cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.2 | 101 | m3
Dia 0 - 12mm, 6cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.06 | 30.3 | m3
Supply and spread grannular filter media in the SDB -2
Dia 0 - 2mm,20cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.2 | 101 | m3
Dia 0 - 12mm, 6cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.06 | 30.3 | m3
Supply and spread grannular filter media in the SDB -3
Dia 0 - 2mm,20cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.2 | 101 | m3
Dia 0 - 12mm, 6cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.06 | 30.3 | m3
Supply and spread grannular filter media in the SDB -4
Dia 0 - 2mm,20cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.2 | 101 | m3
Dia 0 - 12mm, 6cm thick sand |  |  |  | 1 | 25
20.2
[5 empty] | 0.06 | 30.3 | m3
| Date: | Name: | Signature and Stamp:
Contractor:
MH E RE: