## certificate
OROMIA HEALTH BUREAU
Contract NO _____________ |  |  |  | Date of Signature __________ |  |  | Tele - 011 - 3 - 69 - 01- 40
Certeficate of Payment NO - 15 | [7 empty] | AMOUNT (ETB)
[6 empty] | Main Contract |  | 30078993.96
For Measurement Certeficate NO 14
Variation NO. 1
Project - Dedessa Primary Hospital
Variation NO. 2
Location - I/A/Bora Zone
Variation NO. 3
Client - Oromia Health Bureau
Supplentary Agr. 1
Contractor -Trust Construction
[6 empty] | Total (ETB) |  | 30078993.96
According to the supervisor of the works __________________ certeficate measurement
The value of work executed to date is ETB () ETB
[8 empty] | Exe. | 20894560.27
Previous Payment |  |  |  | Deductions |  | Amount |  | VAT | 3134184.04
No | VAT | Amount (Birr) | [5 empty] | Sum | 24028744.31
Advan. | 784669.41 | 5231129.38 | 1 | Previous Payment |  | 18092916.91
1 | 245728.12 | 1556278.1
2 | 56596.41 | 358443.94 | 2 | Rebate %
3 | 506782.2 | 3142195.05
4 | 109432.05 | 683950.29 | 3 | Retention, 5 % |  | 1044728.01
5 | 128180.99 | 801131.23
6 | 157383.85 | 983649.03 | 4 | Penality
7 | 196162.09 | 1226013.06
8 | 199656.26 | 1247851.6 | 5 | Advance Repaid, 20% |  | 4805748.86
9 | 90215.26 | 563845.37
10 | 32827.97 | 205174.82 |  | Total Deductions |  | 23943393.78
11 | 46366.87 | 289792.95
12 | 88196.87 | 551229.13 |  |  |  | Total with VAT |  | 85350.53
13 | 190195.21 | 1188720.05
14 | 447850.78 | 2799067.36
Sub total | 2495574.93 | 15597341.98
Total + vat | 18092916.91
Work Exceuted |  |  |  |  | Advance Payments |  | VAT Payment
Previous Total work Executed (A) |  | Up to date work executed (B) | Difference C = B-A |  | Advance Payment = (0.2 *B) |  | VAT Payment
15479406.09 |  | 20894560.27 | 5415154.18 |  | Total | 6015798.79 | Total to date | 3134184.04
[5 empty] | Repaid | 4805748.86 | Previous + Advace VAT | 3122411.74
[5 empty] | Out standing | 1210049.93 | Current | 11772.3
I certify that the Contractor is entitled to the sum of Birr |  |  |  |  | 85350.53
birr only.
Certified by__________________ |  |  | Date______________ |  |  | Approved by _____________________

## Grand Summary
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
GRAND SUMMARY NO-15
Item No | Block Name | Contract Amount | To date Executed Amount
1 | OPD | 2418142.4 | 2001642.77
2 | Waiting and Registration | 753474.44 | 717430.51
3 | IPD | 3703336 | 2860477.06
4 | OR and Delivery | 3670461.86 | 3036340
5 | Emergency | 1976399.06 | 1368395.97
6 | Diagnostic Service | 1775447.21 | 1522419.61
7 | Administration | 1727693.75 | 1530204.9
7 | staff house | 796213 | 725479.68
9 | Service Quarter | 357112 | 346794.73
10 | Generator House | 202846 | 119806.46
11 | Transformer House | 300559.26 | 197930.96
12 | Kitchen | 1766605.28 | 1503695.46
13 | Store | 752342.56 | 420935.68
14 | Morgue | 183834 | 145202.88
15 | Guard House | 271216 | 161303.97
16 | Dry Latrine | 265488 | 171152.92
18 | Civil Site work | 3396424.1 | 3452318.32
19 | Site Sanitary Installation | 1611965 | 785395.14
20 | Site Electrical Installation | 1602700 | 0
Total |  | 27532259.92 | 21066927.02
Rebate 5% |  | 1376613 | 1053346.35
Amount after rebate |  | 26155646.92 | 20013580.67
variation work (cobble stone) |  |  | 880979.6
Grand Sum |  | 26155646.92 | 20894560.27

## cobble stone
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for Variation Work No - 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount (birr)
|  |  |  | previous | current | To date |  |  | Previous | Current | To Date
Road & parking
1.1 | cobble stone | M2 |  | 2138.3 |  | 2138.3 | 412 | 0 | 880979.6 | 0 | 880979.6
TOTAL CARRIED TO SUMMARY | [7 empty] | 0 | 880979.6 | 0 | 880979.6

## Material on Site
Certeficate of Payment NO - 15
Project: - Dhedhesa Primary Hospital
Contractor: - Trust Construction
Consultant: - Oromia Health Bureau
Client: - Oromia Regional State Health Bureau
Location: - I/A/Bora Zone
MATERIAL ON SITE
It. | Material Description | Unit | Quantity | Unit Price | Amount
1 | Ceramic Wall 20x30x6cm | m2 | 1220.05 | 130 | 158606.5 | 964.4 m2 todate delivered
2 | Ceramic Floor 30x30x8cm | m2 | 73 | 195.65 | 14282.45 | 300m2 to date delivered
3 | Ceramic Skerting 10x60x8cm | ml | 1372.63 | 33 | 45296.79 | 1980 ml todate delivered
4 | Rotto 4000lit | pcs | 2 | 7565.22 | 15130.44 | 2 Pcs todate Delivered
5 | RHS 80x80x5mm | pcs | 4 | 1391.3 | 5565.2 | 4 Pcs todate Delivered
6 | RHS 80x80x4mm | pcs | 11 | 982.61 | 10808.71 | 11 Pcs todate Delivered
7 | RHS 20x20x2mm | pcs | 38 | 165.22 | 6278.36 | 132 Pcs todate Delivered
8 | RHS 40x20x2m | pcs | 109 | 247.83 | 27013.47 | 358 Pcs todate Delivered
9 | RHS 20x10x1mm | pcs | 30 | 60.87 | 1826.1 | 30 Pcs todate Delivered
10 | RHS 15x15x1.5mm | pcs | 27 | 130.43 | 3521.61 | 27 Pcs todate Delivered
11 | RHS 30x30x3mm | pcs | 50 | 234.78 | 11739 | 28 Pcs todate Delivered
13 | RHS 30x30x2mm | pcs | 93 | 234.78 | 21834.54 | 30 Pcs todate Delivered
16 | Angle Iron 60x60x5 | pcs | 21 | 782.61 | 16434.81
17 | Wooden Door | m2 | 280.26 | 1700 | 476442 | 123 pcs Delivered with diferent Sizes
18 | Figured Glass | m2 | 99.04 | 226.09 | 22391.95 | 99.04 m2 todate delivered
19 | Clear Glass | m2 | 221.77 | 179.91 | 39898.64 | 221.77 m2 todate delivered
20 | Copper Conductor 1x10 | ml | 50 | 32 | 1600 | 50m todate delivered
24 | Power Cable 4x16 | ml | 425 | 212 | 90100 | 425m todate delivered
25 | PHILPS TMS 012/236 IMK with 2xTLD 36W | Pcs | 37 | 521.74 | 19304.38
26 | PHILPS TMS 012/136 IMK with 1xTLD 36W | Pcs | 33 | 347.83 | 11478.39
Total Amount |  |  |  |  | 999553.34
80% of material |  |  |  |  | 799642.67

## OPD Sum
Project: - Dhedhesa Primary Hospital
Contractor : - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau
Client: - Oromia Regional State Health Bureau
Location: - I/A/Bora Zone
Summary of Statement for OPD - 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 150795 | 125779.4 | 0 | 125779.4
2 | CONCRETE WORKS | 440255 | 385180.56 | 0 | 385180.56
3 | MASONRY WORKS | 329400 | 146016 | 0 | 146016
TOTAL A |  | 920450 | 656975.96 | 0 | 656975.96
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 176402 | 165517.14 | 3403.76 | 168920.9
2 | BLOCK WORK | 207900 | 163623.6 | 0 | 163623.6
3 | ROOFING | 151027.4 | 149128.2 | 0 | 149128.2
4 | CARPENTRY & JOINERY | 158882 | 162824.16 | 7182 | 170006.16
5 | METAL WORK | 81346 | 77883 | 4914 | 82797
6 | FINISHING | 531470 | 472320.5 | 10901 | 483221.5
7 | PAINTING | 31720 | 15736.5 | 0 | 15736.5
8 | GLAZING WORK | 25320 | 9891.2 | 0 | 9891.2
9 | SANITARY INSTALLATION | 40630 | 12309.75 | 29818 | 42127.75
10 | ELECTRICAL INSTALLATION | 92995 | 19280 | 39934 | 59214
TOTAL B |  | 1497692.4 | 1248514.05 | 96152.76 | 1344666.81
TOTAL A+ B |  | 2418142.4 | 1905490.01 | 96152.76 | 2001642.77

## OPD Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for OPD No - 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount (birr)
|  |  |  | previous | current | To date |  |  | Previous | Current | To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear off site | M2 | 485 | 585 |  | 585 | 6 | 2910 | 3510 | 0 | 3510
1.2 | Bulk Excavation | M3 | 720 | 365.6 |  | 365.6 | 50 | 36000 | 18280 | 0 | 18280
1.4 | Trench Excavation | M3 | 120 | 245.1 |  | 245.1 | 40 | 4800 | 9804 | 0 | 9804
1.5 | Selected backfill | M3 | 288 | 55.22 |  | 55.22 | 100 | 28800 | 5522 | 0 | 5522
1.6 | Cart away | M3 | 433.5 | 786.2 |  | 786.2 | 70 | 30345 | 55034 | 0 | 55034
1.7 | 25cm thick hard core | M2 | 480 | 395.64 |  | 395.64 | 85 | 40800 | 33629.4 | 0 | 33629.4
TOTAL CARRIED TO SUMMARY | [7 empty] | 143655 | 125779.4 | 0 | 125779.4
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete
| a) massonary foundation | M2 | 182 | 130.55 |  | 130.55 | 100 | 18200 | 13055 | 0 | 13055
2.2 | 10cm thick reinforced concrete floor slab | M2 | 480 | 395.64 |  | 395.64 | 350 | 168000 | 138474 | 0 | 138474
2.3 | Reinforced concrete class C-25,
| a) In grade beam & step | M3 | 24 | 27.11 |  | 27.11 | 2900 | 69600 | 78619 | 0 | 78619
2.4 | form work or metal panel. To:-
| a) In grade beam & step | M2 | 204 | 221.04 |  | 221.04 | 120 | 24480 | 26524.8 | 0 | 26524.8
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 1552 | 2003.56 |  | 2003.56 | 38 | 58976 | 76135.28 | 0 | 76135.28
| b) Dia. 12mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 2528 | 1244.51 |  | 1244.51 | 38 | 96064 | 47291.38 | 0 | 47291.38
2.6 | 12/2 cm chip wood expansion joint | m | 329 | 338.74 |  | 338.74 | 15 | 4935 | 5081.1 | 0 | 5081.1
TOTAL CARRIED TO SUMMARY | [7 empty] | 440255 | 385180.56 | 0 | 385180.56
3. Masonry Work
3.1 | 50cm high trychitic stone masonreyBNGL | M3 | 160 | 130.55 |  | 130.55 | 1000 | 160000 | 130550 | 0 | 130550
3.2 | Ditto but ANGL | M3 | 154 | 14.06 |  | 14.06 | 1100 | 169400 | 15466 | 0 | 15466
TOTAL CARRIED TO SUMMARY | [7 empty] | 329400 | 146016 | 0 | 146016
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25
| a) In elevation column | M3 | 4.5 | 3.46 |  | 3.46 | 2900 | 13050 | 10034 | 0 | 10034
| b) In beams | M3 | 14 | 13.03 |  | 13.03 | 2900 | 40600 | 37787 | 0 | 37787
| c) Lintel | M3 | 1.1 | 0 | 0.42 | 0.42 | 2900 | 3190 | 0 | 1218 | 1218
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 77 | 69.12 |  | 69.12 | 120 | 9240 | 8294.4 | 0 | 8294.4
| b) In beams | M2 | 192 | 175.2 |  | 175.2 | 120 | 23040 | 21024 | 0 | 21024
| c) Lintel | M2 | 10.1 | 0 | 6.98 | 6.98 | 120 | 1212 | 0 | 837.6 | 837.6
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 1727 | 1755.04 | 18.8 | 1773.84 | 38 | 65626 | 66691.52 | 714.4 | 67405.92
| c) Dia. 8 mm deformed bar | Kg | 538 | 570.69 | 38.72 | 609.41 | 38 | 20444 | 21686.22 | 1471.36 | 23157.58
| d) Dia. 6 mm deformed bar | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 176402 | 165517.14 | 3403.76 | 169758.5
2. BLOCK WORK
| a) 20 cm thick | M2 | 498 | 190.33 |  | 190.33 | 320 | 159360 | 60905.6 | 0 | 60905.6
| b) 15 cm thick | M2 | 156 | 366.85 |  | 366.85 | 280 | 43680 | 102718 | 0 | 102718
TOTAL CARRIED TO SUMMARY | [7 empty] | 203040 | 163623.6 | 0 | 163623.6
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 585.4 | 523.08 |  | 523.08 | 230 | 134642 | 120308.4 | 0 | 120308.4
3.2 | G-30 ribbed sheet ceiling under eave | M2 | 59 | 143.06 |  | 143.06 | 130 | 7670 | 18597.8 | 0 | 18597.8
3.3 | G-30 Flashing | m | 29 | 0 |  | 0 | 80 | 2320 | 0 | 0 | 0
3.4 | G-30 flat metal sheet gutter | m | 64 | 102.22 |  | 102.22 | 100 | 6400 | 10222 | 0 | 10222
TOTAL CARRIED TO SUMMARY | [7 empty] | 151032 | 149128.2 | 0 | 149128.2
4.CARPENTRY & JOINERY
4.1 | All structural member shall be free of harm full
| a)diameter 10 -12cm | m | 817 | 740.43 |  | 740.43 | 22 | 17974 | 16289.46 | 0 | 16289.46
| b) diameter 8 - 10cm | m | 583 | 632.26 |  | 632.26 | 15 | 8745 | 9483.9 | 0 | 9483.9
| c) Purlin zigba size 5/7cm | m | 563 | 580.8 |  | 580.8 | 32 | 18016 | 18585.6 | 0 | 18585.6
4.2 | 25*2.5cm Zigba wooden fascia board . | m | 99 | 102.06 |  | 102.06 | 70 | 6930 | 7144.2 | 0 | 7144.2
4.3 | Supply and fix 40mm thick wood framed door
| a) Type D2 size -80/270cm | No | 4 | 5 |  | 5 | 4104 | 16416 | 20520 | 0 | 20520
| b) Type D3 size -70/270cm | No | 4 | 4 |  | 4 | 3591 | 14364 | 14364 | 0 | 14364
| c) Type D1 size -90/270cm | No | 15 | 15 |  | 15 | 4617 | 69255 | 69255 | 0 | 69255
| d) Type D6 size -140/270cm | No | 1 | 1 | 1 | 2 | 7182 | 7182 | 7182 | 7182 | 14364
TOTAL CARRIED TO SUMMARY | [7 empty] | 158882 | 162824.16 | 7182 | 170006.16
5.METAL WORKS
5.1 | Windows
| a) Type W1: size-100/160cm | no | 1 | 1 |  | 1 | 2080 | 2080 | 2080 | 0 | 2080
| b) Type w3: size:-150/160cm | no | 15 | 14 |  | 14 | 3120 | 46800 | 43680 | 0 | 43680
| c) Type w9: size:-125/60cm | no | 1 | 2 |  | 2 | 975 | 975 | 1950 | 0 | 1950
| d) Type w10: size:-130/160cm | no | 5 | 5 |  | 5 | 2704 | 13520 | 13520 | 0 | 13520
| e) Type w25: size:-290/60cm | no | 1 | 1 |  | 1 | 2262 | 2262 | 2262 | 0 | 2262
5.2 | Doors
| a) Type D10: size-140/270cm | no | 2 | 2 | 1 | 3 | 4914 | 9828 | 9828 | 4914 | 14742
| b) Type D11: size:-130/270cm | no | 1 | 1 |  | 1 | 4563 | 4563 | 4563 | 0 | 4563
TOTAL CARRIED TO SUMMARY | [7 empty] | 80028 | 77883 | 4914 | 82797
6. FINISHING
6.1 | Apply two coats of plastering and rendering | m2 | 430 | 161.87 |  | 161.87 | 90 | 38700 | 14568.3 | 0 | 14568.3
6.2 | Apply three coats of plastering | m2 | 789 | 1119.98 |  | 1119.98 | 100 | 78900 | 111998 | 0 | 111998
6.3 | Plastic ceiling nailed on battens | m2 | 480 | 436.75 |  | 436.75 | 270 | 129600 | 117922.5 | 0 | 117922.5
6.4 | 200x300x6mm glazed ceramic wall | m2 | 65 | 75.3 |  | 75.3 | 290 | 18850 | 21837 | 0 | 21837
6.5 | 8mm thick non slippery ceramic 60x60x8cm | m2 | 480 | 421.39 | 21.38 | 442.77 | 300 | 144000 | 126417 | 6414 | 132831
6.6 | Ceramic tile skiring 10/0.8cm | ml | 450 | 256.59 | 44.87 | 301.46 | 100 | 45000 | 25659 | 4487 | 30146
6.7 | Terrazo window cill bedded on | ml | 43 | 31.25 |  | 31.25 | 150 | 6450 | 4687.5 | 0 | 4687.5
6.8 | 30/30/3mm angle iron corner protection | m2 | 67 | 0 |  | 0 | 70 | 4690 | 0 | 0 | 0
6.9 | 10cm thick c-20 RC 1.2m wide pavement | m2 | 122 | 122.16 |  | 122.16 | 320 | 39040 | 39091.2 | 0 | 39091.2
6.1 | Concret pipes of half diameter 30cm | ml | 128 | 101.4 |  | 101.4 | 100 | 12800 | 10140 | 0 | 10140
6.11 | 10x40cm curb stone around the building | ml | 128 | 0 |  | 0 | 105 | 13440 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 531470 | 472320.5 | 10901 | 483221.5
7. PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | m2 | 395 | 559.99 |  | 559.99 | 26 | 10270 | 14559.74 | 0 | 14559.74
7.2 | ditto but oil paint to a height of 150 cm | m2 | 395 | 0 |  | 0 | 26 | 10270 | 0 | 0 | 0
7.3 | external rendered surface | m2 | 430 | 45.26 |  | 45.26 | 26 | 11180 | 1176.76 | 0 | 1176.76
TOTAL CARRIED TO SUMMARY | [7 empty] | 31720 | 15736.5 | 0 | 15736.5
8.GLAZING
8.1 | 4mm thick clear glass | M2 | 12 | 44.96 |  | 44.96 | 220 | 2640 | 9891.2 | 0 | 9891.2
8.2 | 4mm thick frosted glass | M2 | 63 |  |  | 0 | 360 | 22680 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 25320 | 9891.2 | 0 | 9891.2
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 15mm diameter;internal | lm | 20 | 14.85 |  | 14.85 | 65 | 1300 | 965.25 | 0 | 965.25
| 20mm diameter;internal | lm | 14 | 48.74 |  | 48.74 | 75 | 1050 | 3655.5 | 0 | 3655.5
9.5 | Supply and install waste water pipes made of rigid plastic pipe (upvc) of approved standard including
| 50mm diameter | lm | 5 | 82.85 |  | 82.85 | 60 | 300 | 4971 | 0 | 4971
| 75mm diameterthickness=3mm | lm | 8 | 12.6 |  | 12.6 | 90 | 720 | 1134 | 0 | 1134
| 100mm diameter | lm | 20 | 13.2 |  | 13.2 | 120 | 2400 | 1584 | 0 | 1584
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 12 |  | 17 | 17 | 600 | 7200 | 0 | 10200 | 10200
9.7 | Supply and fix low flush white vitreous china water closet | No | 5 |  | 5 | 5 | 900 | 4500 | 0 | 4500 | 4500
9.9 | Supply and fix toilet paper holder | No | 12 |  | 5 | 5 | 90 | 1080 | 0 | 450 | 450
9.1 | Supply and fix crystal glass mirror size 500x400mm | No | 7 |  | 17 | 17 | 200 | 1400 | 0 | 3400 | 3400
9.16 | Supply and fix 50mm diameter floor drain | No | 3 |  | 3 | 3 | 120 | 360 | 0 | 360 | 360
9.18 | Supply and fix 100mm 3.2mm thickness down pipes | lm | 48 |  | 51.2 | 51.2 | 90 | 4320 | 0 | 4608 | 4608
9.2 | Supply and fix stainless steel sink chemial resisit with single bowl Size 1200*600mm | No | 7 |  | 7 | 7 | 900 | 6300 | 0 | 6300 | 6300
TOTAL CARRIED TO SUMMARY | [7 empty] | 30930 | 12309.75 | 29818 | 42127.75
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | Light points in rigid therimoplastic conduit of 16mm fed by pvc conductor of 3x2.5mm(wire to be of ethioplastic or approved equivalent) | Pcs | 62 | 62 |  | 62 | 200 | 12400 | 12400 | 0 | 12400
3 | Switches
3.02 | Double(774005+774042) | Pcs | 16 | 3 |  | 3 | 120 | 1920 | 360 | 0 | 360
3.03 | Two -Way(774006+774041) | Pcs | 4 | 4 |  | 4 | 80 | 320 | 320 | 0 | 320
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduitof diameter 16mm fed by pvc conductor of 3x2.5mm2(Wire to be of ethiolastic or approved equivalent) | Pcs | 30 | 30 |  | 30 | 100 | 3000 | 3000 | 0 | 3000
5 | Socket outlet
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | Pcs | 30 | 32 |  | 32 | 100 | 3000 | 3200 | 0 | 3200
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable from | Pcs | 14 |  | 14 | 14 | 130 | 1820 | 0 | 1820 | 1820
7 | Type of light Fitting with lamp
7.01 | PHILPS TMS 012/236 IMK with 2xTLD 36W | Pcs | 22 |  | 22 | 22 | 700 | 15400 | 0 | 15400 | 15400
7.02 | PHILPS TMS 012/136 IMK with 1xTLD 36W | Pcs | 30 |  | 30 | 30 | 450 | 13500 | 0 | 13500 | 13500
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp | Pcs | 5 |  | 5 | 5 | 250 | 1250 | 0 | 1250 | 1250
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp | Pcs | 5 |  | 5 | 5 | 250 | 1250 | 0 | 1250 | 1250
8 | TV Points
8.01 | TV Points fed through RG6 Coaxial 75 ohm TV | pc | 1 |  | 1 | 1 | 130 | 130 | 0 | 130 | 130
11 | Low Voltage Earthing system
11.01 | Copper Earthing rod of 16x2400mm to be driven on earth with Earthing pit of 500x500x50mm | Pc | 1 |  | 1 | 1 | 2000 | 2000 | 0 | 2000 | 2000
11.02 | Copper conductor of 1x10mm2 for Earthing | ml | 35 |  | 38.2 | 38.2 | 120 | 4200 | 0 | 4584 | 4584
TOTAL CARRIED TO SUMMARY | [7 empty] | 60190 | 19280 | 39934 | 59214

## TOF OPD (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | OPD
CONTRACTOR :- Trust Construction | [5 empty] | Page No | 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6. Finishing Works |  |  | 15.8
|  |  | 6.3 4 mm Thick plastic ceiling | 1 | 0.9
1 | 2.5 |  | Corrider |  | 0.25
| 2.35 |  |  |  |  | 0.23
|  | 5.88 |  | 1 | 1.3
4 | 4.7 |  |  |  | 0.25
| 2.35 |  |  |  |  | 0.33
|  | 44.18 |  |  |  | 16.36 | M2 Sub Total
1 | 4.8 |  |  | 1 | 2.95 |  | Injection
| 2.35 |  |  |  | 3.95
|  | 11.28 |  |  |  | 11.65
1 | 5.75 |  |  | 1 | 0.9
| 2.35 |  |  |  | 0.25
|  | 13.51 |  |  |  | 0.23
|  | 74.85 | M2 Sub Total |  |  | 11.88 | M2 Sub Total
|  |  |  | 3 | 2.8 |  | Exam Room 1-2-3
1 | 3.95 |  | Wating area |  | 3.95
| 2.5 |  |  |  |  | 33.18
|  | 9.88 |  | 3 | 0.9
1 | 3.95 |  |  |  | 0.25
| 1.25 |  |  |  |  | 0.68
|  | 4.94 |  |  |  | 33.86 | M2 Sub Total
|  | 14.82 | M2 Sub Total | 1 | 2.05 |  | Store
1 | 4 |  | Dispensary |  | 3.95
| 2.5 |  |  |  |  | 8.1
|  | 10 | M2 Sub Total | 1 | 0.8
|  | 99.67 | M2 Total of item No 6.3 |  | 0.25
0.2
|  |  | 6.5 8mm Thick Ceramic tile flooring. |  |  | 8.3 | M2 Sub Total
|  |  | ANC/PNC/PMTCT | 1 | 2.5 |  | Consultation Room
1 | 4.6 |  |  |  | 1.8
| 3.95 |  |  |  |  | 4.5
|  | 18.17 |  | 1 | 0.9
1 | 0.9 |  |  |  | 0.25
| 0.25 |  |  |  |  | 0.23
|  | 0.23 |  | 1 | 0.9
|  | 18.4 | M2 Sub Total |  | 0.2
1 | 2.95 |  | Familly Planning |  |  | 0.18
| 3.95 |  |  |  |  | 4.91 | M2 Sub Total
|  | 11.65 |  | 1 | 2.65 |  | Casher
1 | 0.9 |  |  |  | 1.7
| 0.25 |  |  |  |  | 4.51 | M2 Sub Total
|  | 0.23 |  | 1 | 3.8 |  | Dispensary
|  | 11.88 | M2 Sub Total |  | 4
1 | 2.95 |  | under 5 Clinc |  |  | 15.2
| 3.95 |  |  | 1 | 1.3
|  | 11.65 |  |  | 0.25
1 | 0.9 |  |  |  |  | 0.33
| 0.25 |  |  |  |  | 15.53 | M2 Sub Total
|  | 0.23 |  | 1 | 5.35 |  | Medicine Store
|  | 11.88 | M2 Sub Total |  | 4
1 | 4 |  | Wating area(OPD) |  |  | 21.4
3.95
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | OPD
CONTRACTOR :- Trust Construction | [5 empty] | Page No:- | 2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 0.9
0.25
0.23
|  | 21.63 | M2 Total
1 | 3.55 |  | EPI/ Growth
4
14.2
1 | 0.9
0.25
0.23
|  | 14.43 | M2 Sub Total
1 | 4.7 |  | Procedure Room-2
4
18.8
1 | 0.9
0.25
0.23
|  | 19.03 | M2 Sub Total
1 | 3.5 |  | Procedure Room-2
4
14
1 | 0.9
0.25
0.23
|  | 14.23 | M2 Sub Total
1 | 5 |  | Phthalmology
4
20
1 | 0.9
0.25
0.23
|  | 20.23 | M2 Sub Total
1 | 4.65 |  | Dental
4
18.6
1 | 0.9
0.25
0.23
|  | 18.83 | M2 Sub Total
1 | 35.1 |  | Corridor
2.4
|  | 84.24 | M2 Sub Total
|  | 330.13 | M2 Total of item No 6.5
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | OPD
CONTRACTOR :- Trust Construction | [5 empty] | Page No:- | 3
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. SUB - STRUCTURE
1) Excavation & Earth Work
1.6 cart away
site clerance
1 | 38.1 |  | 35.1+3=38.1
| 16.2 |  | 13.2+3=16.2
| 0.3 | 185.17
1 | 38.1 |  | bulk
16.2
| 0.93 | 574.01
5 | 35.6 |  | trench
1
| 1 | 178
8 | 8.7
1
| 1 | 69.6
|  | 1006.78 | m3 Total 1.6
|  | 786.2 | Previous payment
|  | 220.58 | m3 Total 1.6 Remaining

## OPD TOS
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [6 empty] | Block: - OPD
Client: - Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | 6.5. Ceramic floor 30x30x8cm
|  |  | 1. CONCRETE WORKS | 2 | 4 |  | Toilet male & female corridor
|  |  | 1.1. Reinforced concrete class C-25 |  | 1.3 | 10.4
c) Lintel
1 | 1.3 |  | D1 | 4 | 1.45 |  | Internal toilet room for male & female
| 0.15 |  |  |  | 1 | 5.8
| 0.3 | 0.06
|  |  |  | 1 | 1.75 |  | Handi. Cap
3 | 1.2 |  | D2 |  | 2.96 | 5.18
0.15
| 0.3 | 0.16 |  |  |  | 21.38 | m2 net area item 6.5.b
4 | 1.1 |  | D3 |  |  |  | 6.6)Approved ceramic skirting 10/0.9cm
| 0.15 |  |  | 1 | 7.62 |  | Casher Room
| 0.3 | 0.2 |  |  |  | 7.62
|  | 0.42 | m3 net area item 1.1.c | 1 | 8.56 |  | Consultation Room
8.56
1.2. form work or metal panel. To:-
|  |  | c) Lintel | 1 | 12.1 |  | Dispensary Room
1 | 1.3 |  | D1 |  |  | 12.1
| 0.75 | 0.98
|  |  |  | 1 | 17.04 |  | Medicine Store
3 | 1.2 |  | D2 |  |  | 17.04
| 0.75 | 2.7
|  |  |  | 1 | 14.3 |  | Wating area
4 | 1.1 |  | D2 |  |  | 14.3
| 0.75 | 3.3
|  |  |  | 2 | 14.2 |  | Procedure Room
|  | 6.98 | m2 net area item 1.2.c |  |  | 28.4
|  |  | 1.3. Reinforcement steel bars | 2 | 16.7 |  | Ophtalmology & Dental Room
|  |  | b. ф12 mm deformed bars |  |  | 33.4
1 | 18.8
|  | 18.8 | kg net wight item 1.3.b | 1 | 54.6 |  | Main Corridor
54.6
1 | 38.72 |  | c. ф8 mm deformed bars
|  | 38.72 | kg net wight item 1.3.c | 1 | 16.44 |  | ANC Room
16.44
4.CARPENTRY & JOINERY
|  |  | 4.3. Wood framed door | 2 | 13.1 |  | Family Planning & Under 5 Clinic
|  |  | d) Doors Type D6 size -140/270cm |  |  | 26.2
1 | 1
|  | 1 | Pcs net number item 4.3.d | 1 | 15.1 |  | EPI Room
15.1
5.METAL WORKS
|  |  | 5.2. Doors | 1 | 11.6 |  | Injection Room
|  |  | a) Type D10: size-140/270cm |  |  | 11.6
1 | 1
|  | 1 | Pcs net number item 5.2.a | 1 | 12.8 |  | Examination Room
12.8
|  |  |  | 1 | 13.2 |  | Examination Room
13.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 12.4 |  | Examination Room |  |  |  | 7.00. Type of light Fitting with lamp
|  | 12.4 |  |  |  |  | 7.01. PHILPS TMS 012/236 IMK with 2xTLD 36W
|  |  |  | 1 | 22
1 | 11.26 |  | Store Room |  |  | 22 | Pcs net number item 7.01
11.26
7.02. PHILPS TMS 012/136 IMK with 1xTLD 36W
2 | 3.22 |  | Toilet Entrance | 1 | 30
|  | 6.44 |  |  |  | 30 | Pcs net number item 7.02
|  | 301.46 | m2 Total area |  |  |  | 7.03. RZB 59251.002 with RZB 05-56150Q50W lamp
|  |  |  | 1 | 5
|  | 256.59 | Previous Payment |  |  | 5 | Pcs net number item 7.03
|  | 44.87 | m net length item 6.6 |  |  |  | 7.04. RZB 59222.002 with RZB 05-56150Q50W lamp
|  |  |  | 1 | 5
|  |  | 9. SANITARY INSTALLATION |  |  | 5 | Pcs net number item 7.04
9.6. Hand wash basin
1 | 17 | [5 empty] | 8.00. TV Points
|  | 17 | Pcs net number item 9.6 |  |  |  | 8.01. TV Points fed through RG6 Coaxial 75 ohm TV
|  |  |  | 1 | 1
|  |  | 9.7. Water closet |  |  | 1 | Pcs net number item 8.01
1 | 5
|  | 5 | Pcs net number item 9.7 |  |  |  | 11.00. Low Voltage Earthing system
11.01. Copper Earthing rod of 16x2400mm
|  |  | 9.9. Toilet paper holder | 1 | 1
1 | 5 |  |  |  |  | 1 | Pcs net number item 11.01
|  | 5 | Pcs net number item 9.9
11.02. Copper conductor of 1x10mm2
|  |  | 9.10. Crystal glass mirror | 1 | 38.2
1 | 17 |  |  |  |  | 38.2 | m net length item 11.02
|  | 17 | Pcs net number item 9.10
9.16. 50mm diameter floor drain
1 | 3
|  | 3 | Pcs net number item 9.10
9.18. 100mm Down pipes
1 | 51.2
|  | 51.2 | m net length item 9.18
9.20. Stainless steel sink Size 1200*600mm
1 | 7
|  | 7 | Pcs net number item 9.10
10. ELECTRICAL INSTALLATION
6.00. Telephone/Data points
6.01. Tel. pt fed through cat 5E UTP cable
1 | 14
|  | 14 | Pcs net number item 6.01

## OPD Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - OPD
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D1 |  | 12 | 1.75 | 1 | 2 | 2 |  |  |  | 3.5
|  |  | 12 | 1.25 | 1 | 2 | 2 | - | - | - | 2.5 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
| D2 |  | 12 | 1.65 | 3 | 2 | 6 |  |  |  | 9.9
|  |  | 12 | 1.15 | 3 | 2 | 6 | - | - | - | 6.9 | -
| Stirrups |  | 8 | 0.85 | 3 | 7 | 21 | - | 17.85 | - | - | -
| D3 |  | 12 | 1.55 | 4 | 2 | 8 | - | - | - | 12.4 | -
|  |  | 12 | 1.05 | 4 | 2 | 8 | - | - | - | 8.4 | -
| Stirrups |  | 8 | 0.85 | 4 | 7 | 28 | - | 23.8 | - | - | -
-
TOTAL LENGTH | [8 empty] | 47.6 | 0 | 43.6 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 18.8 | 0 | 38.72 | 0

## Wait Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Statement for Wating & Registration No 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 60744.9 | 53944.35 | 0 | 53944.35
2 | CONCRETE WORKS | 154058.18 | 158710.4 | 0 | 158710.4
3 | MASONRY WORKS | 132600 | 84258 | 0 | 84258
TOTAL A |  | 347403.08 | 296912.75 | 0 | 296912.75
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 79739.86 | 72023.78 | 0 | 72023.78
2 | BLOCK WORK | 48099.6 | 50637.2 | 0 | 50637.2
3 | ROOFING | 58226 | 54440.9 | 0 | 54440.9
4 | CARPENTRY & JOINERY | 25422 | 34227.4 | 0 | 34227.4
5 | METAL WORK | 21255 | 18135 | 0 | 18135
6 | FINISHING | 157855.4 | 134708.6 | 6360 | 141068.6
7 | PAINTING | 10965.5 | 7328.88 | 0 | 7328.88
8 | GLAZING WORK | 4508 | 1936 | 0 | 1936
9 | ELECTRICAL INSTALLATION | 0 | 0 | 40720 | 40720
TOTAL B |  | 406071.36 | 373437.76 | 47080 | 420517.76
TOTAL A+ B |  | 753474.44 | 670350.51 | 47080 | 717430.51

## Wait Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for Waiting & Registration NO - 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount (birr)
|  |  |  | previous | current | To date |  |  | Previous | Current | To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear off site | M2 | 245.7 | 226.8 |  | 226.8 | 6 | 1474.2 | 1360.8 | 0 | 1360.8
1.2 | Bulk Excavation | M3 | 107 | 144.14 |  | 144.14 | 50 | 5350 | 7207 | 0 | 7207
1.4 | Trench Excavation | M3 | 53 | 88.4 |  | 88.4 | 40 | 2120 | 3536 | 0 | 3536
1.5 | Selected backfill | M3 | 109 | 90.64 |  | 90.64 | 100 | 10900 | 9064 | 0 | 9064
1.6 | Car away | M3 | 390 | 300.58 |  | 300.58 | 70 | 27300 | 21040.6 | 0 | 21040.6
1.7 | 25cm thick stone hard core | M2 | 135 | 138.07 |  | 138.07 | 85 | 11475 | 11735.95 | 0 | 11735.95
TOTAL CARRIED TO SUMMARY | [7 empty] | 58619.2 | 53944.35 | 0 | 53944.35
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete
| a) massonary foundation | M2 | 74 | 48.2 |  | 48.2 | 100 | 7400 | 4820 | 0 | 4820
2.2 | 10cm thick RC C-20 | M2 | 135 | 138.07 |  | 138.07 | 350 | 47250 | 48324.5 | 0 | 48324.5
2.3 | RC C-25
| a) In grade beam & step | M3 | 10.04 | 10.04 |  | 10.04 | 2900 | 29116 | 29116 | 0 | 29116
2.4 | form work or
| a) In grade beam & step | M2 | 83.52 | 80.16 |  | 80.16 | 120 | 10022.4 | 9619.2 | 0 | 9619.2
| d) Steps | M2 | 1 | 0 |  | 0 | 130 | 130 | 0 | 0 | 0
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 827.31 | 1022.52 |  | 1022.52 | 38 | 31437.78 | 38855.76 | 0 | 38855.76
| b) Dia. 12mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 693.5 | 678.18 |  | 678.18 | 38 | 26353 | 25770.84 | 0 | 25770.84
2.6 | 10/2 cm chip wood expansion joint | m | 156.6 | 146.94 |  | 146.94 | 15 | 2349 | 2204.1 | 0 | 2204.1
TOTAL CARRIED TO SUMMARY | [7 empty] | 154058.18 | 158710.4 | 0 | 158710.4
3. Masonry Work
3.1 | stone masonrey BNGL | M3 | 51.2 | 48.2 |  | 48.2 | 1000 | 51200 | 48200 | 0 | 48200
3.2 | Ditto but ANGL | M3 | 74 | 32.78 |  | 32.78 | 1100 | 81400 | 36058 | 0 | 36058
TOTAL CARRIED TO SUMMARY | [7 empty] | 132600 | 84258 | 0 | 84258
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | RC C-25
| a) In elevation column | M3 | 1.73 | 1.73 |  | 1.73 | 2900 | 5017 | 5017 | 0 | 5017
| b) In beams | M3 | 6.26 | 6.07 |  | 6.07 | 2900 | 18154 | 17603 | 0 | 17603
1.2 | form work
| a) In elevation column | M2 | 34.56 | 34.56 |  | 34.56 | 100 | 3456 | 3456 | 0 | 3456
| b) In beams | M2 | 62.64 | 79.36 |  | 79.36 | 100 | 6264 | 7936 | 0 | 7936
1.3 | Reinforcement steel bars
| b) Dia. 12mm deformed bar | Kg | 790.03 | 706.67 |  | 706.67 | 38 | 30021.14 | 26853.46 | 0 | 26853.46
| c) Dia. 8 mm deformed bar | Kg | 349.34 | 293.64 |  | 293.64 | 38 | 13274.92 | 11158.32 | 0 | 11158.32
TOTAL CARRIED TO SUMMARY | [7 empty] | 76187.06 | 72023.78 | 0 | 72023.78
2. BLOCK WORK
Concrete block wall class "B"
| a) 20 cm thick | M2 | 137.79 | 146.56 |  | 146.56 | 320 | 44092.8 | 46899.2 | 0 | 46899.2
| b) 15 cm thick | M2 | 14.31 | 13.35 |  | 13.35 | 280 | 4006.8 | 3738 | 0 | 3738
TOTAL CARRIED TO SUMMARY | [7 empty] | 48099.6 | 50637.2 | 0 | 50637.2
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 198 | 191.16 |  | 191.16 | 230 | 45540 | 43966.8 | 0 | 43966.8
3.2 | G-30 ribbed sheet ceiling under eave | M2 | 34.2 | 38.57 |  | 38.57 | 130 | 4446 | 5014.1 | 0 | 5014.1
3.3 | G-30 Flashing | m | 58 | 0 |  | 0 | 80 | 4640 | 0 | 0 | 0
3.4 | G-30 flat metal sheet gutter | m | 36 | 54.6 |  | 54.6 | 100 | 3600 | 5460 | 0 | 5460
TOTAL CARRIED TO SUMMARY | [7 empty] | 58226 | 54440.9 | 0 | 54440.9
4.CARPENTRY & JOINERY
4.1 | carpentry swan eucalyptus truss
| a)diameter 10 -12cm | m | 503.8 | 503.8 |  | 503.8 | 22 | 11083.6 | 11083.6 | 0 | 11083.6
| b) diameter 8 - 10cm | m | 288.4 | 288.4 |  | 288.4 | 15 | 4326 | 4326 | 0 | 4326
| c) Purlin zigba size 5/7cm | m | 461.4 | 461.4 |  | 461.4 | 32 | 14764.8 | 14764.8 | 0 | 14764.8
4.2 | 25*2.5cm Zigba wooden fascia board . | m | 57.9 | 57.9 |  | 57.9 | 70 | 4053 | 4053 | 0 | 4053
TOTAL CARRIED TO SUMMARY | [7 empty] | 34227.4 | 34227.4 | 0 | 34227.4
5.METAL WORKS
5.1 | Windows
| a) Type w3: size-150/160cm | no | 1 | 1 |  | 1 | 3120 | 3120 | 3120 | 0 | 3120
| b) type w7: size:-100/160cm | no | 3 | 3 |  | 3 | 2080 | 6240 | 6240 | 0 | 6240
5.2 | Doors
| a) Type D2: size-80/270cm | no | 2 | 2 |  | 2 | 2808 | 5616 | 5616 | 0 | 5616
| b) type D1: size:-90/270cm | no | 1 | 1 |  | 1 | 3159 | 3159 | 3159 | 0 | 3159
TOTAL CARRIED TO SUMMARY | [7 empty] | 18135 | 18135 | 0 | 18135
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendering | M2 | 74.26 | 44.79 |  | 44.79 | 90 | 6683.4 | 4031.1 | 0 | 4031.1
6.2 | Apply three coats of plastering | M2 | 217.18 | 237.09 |  | 237.09 | 100 | 21718 | 23709 | 0 | 23709
6.3 | 4mm thick best type plastic ceiling | M2 | 135 | 135.63 |  | 135.63 | 270 | 36450 | 36620.1 | 0 | 36620.1
6.4 | 8mm thick non slippery ceramic | M2 | 135 | 144.3 |  | 144.3 | 290 | 39150 | 41847 | 0 | 41847
6.5 | Ceramic tile skiring 10/0.8cm | M2 | 93.3 | 77.85 | 21.2 | 99.05 | 300 | 27990 | 23355 | 6360 | 29715
6.6 | Terrazo window cill | m | 8.5 | 3.5 |  | 3.5 | 100 | 850 | 350 | 0 | 350
6.8 | 10cm thick c-20 RC 1.2m wide pavement | M2 | 68.4 | 68.52 |  | 68.52 | 70 | 4788 | 4796.4 | 0 | 4796.4
6.9 | Concret pipes of half diameter 30cm | ml | 61.8 | 0 |  | 0 | 100 | 6180 | 0 | 0 | 0
6.1 | 10X40cm curb stone around the building | ml |  | 0 |  | 0 | 105 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 143809.4 | 134708.6 | 6360 | 141068.6
7. PAINTING
7.1 | Internal plastered surfaceand external beams & Coloumns | M2 | 217.18 | 237.09 |  | 237.09 | 26 | 5646.68 | 6164.34 | 0 | 6164.34
7.2 | Ditto but oil paint to a height of 150 cm | M2 | 130.31 | 0 |  | 0 | 26 | 3388.06 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 74.26 | 44.79 |  | 44.79 | 26 | 1930.76 | 1164.54 | 0 | 1164.54
TOTAL CARRIED TO SUMMARY | [7 empty] | 10965.5 | 7328.88 | 0 | 7328.88
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 12.98 | 8.8 |  | 8.8 | 220 | 2855.6 | 1936 | 0 | 1936
8.2 | 4mm thick frosted glass | M2 | 4.59 |  |  | 0 | 360 | 1652.4 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 4508 | 1936 | 0 | 1936
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | Light points in rigid therimoplastic conduit of 16mm | Pcs |  |  | 20 | 20 | 200 | 0 | 0 | 4000 | 4000
3 | Switches
3.02 | Double(774005+774042) | Pcs |  |  | 6 | 6 | 120 | 0 | 0 | 720 | 720
3.03 | Two -Way(774006+774041) | Pcs |  |  | 5 | 5 | 80 | 0 | 0 | 400 | 400
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduitof diameter 16mm | Pcs |  |  | 15 | 15 | 100 | 0 | 0 | 1500 | 1500
5 | Socket outlet
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | Pcs |  |  | 15 | 15 | 100 | 0 | 0 | 1500 | 1500
7 | Type of light Fitting with lamp
7.01 | PHILPS TMS 012/236 IMK with 2xTLD 36W | Pcs |  |  | 35 | 35 | 700 | 0 | 0 | 24500 | 24500
7.02 | PHILPS TMS 012/136 IMK with 1xTLD 36W | Pcs |  |  | 8 | 8 | 450 | 0 | 0 | 3600 | 3600
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp | Pcs |  |  | 11 | 11 | 250 | 0 | 0 | 2750 | 2750
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp | Pcs |  |  | 7 | 7 | 250 | 0 | 0 | 1750 | 1750
7.05 | Massive 70107/11 | Pcs |  |  | 1 | 1 |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 0 | 0 | 40720 | 40720

## Wait Rebar (hidden)
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau | [10 empty] | Block Type :- |  | Waiting
CONSULTANT :-Engineers of Oromia Health Bureau | [10 empty] | Block :-
CONTRACTOR :-Trust Construction | [10 empty] | Page No. :- |  | 1 of 2
LOCATION :- Dhedesa
Rebar Bar Detail
Item No. | Location | Shape | Ø | L | No. of mebers | No. | Re-bars | [6 empty] | Remark
[7 empty] | Ø6 | Ø8 | Ø10 | Ø12 | Ø14 | Ø16 | Ø20
A. SUB STRUCTURE
Grade Beam
|  |  | 14 | 10.25 | 4 | 3 | " | " | " | " | 123 | " | "
|  |  | 14 | 9.55 | 4 | 3 | " | " | " | " | 114.6 | " | "
|  |  | 8 | 1.2 | 4 | 44 | " | 211.2 | " | " | " | " | "
|  |  | 14 | 10.25 | 4 | 3 | " | " | " | " | 123 | " | "
|  |  | 14 | 5.71 | 4 | 3 | " | " | " | " | 68.52 | " | "
|  |  | 14 | 11.65 | 4 | 3 | " | " | " | " | 139.8 | " | "
|  |  | 14 | 5.71 | 4 | 3 | " | " | " | " | 68.52 | " | "
|  |  | 14 | 12 | 4 | 3 | " | " | " | " | 144 | " | "
|  |  | 14 | 5.36 | 4 | 3 | " | " | " | " | 64.32 | " | "
|  |  | 8 | 1.2 | 4 | 79 | " | 379.2 | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[8 empty] | " |  |  | " | " | "
[8 empty] | " |  |  | " | " | "
|  |  |  | Total Length |  |  | 0 | 590.4 | 0 | 0 | 845.76 | 0 | 0
|  |  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467
|  |  |  | Total Weight(For 1 Block) |  |  | 0 | 233.21 | 0 | 0 | 1022.52 | 0 | 0
Prepared by …………………………… | [6 empty] | Re-bars Ø14: Checked by ……………………………
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau | [6 empty] | Re-bars Ø14: Block Type :-; Re-bars Ø20: Waiting
CONSULTANT :-Engineers of Oromia Health Bureau | [6 empty] | Re-bars Ø14: Block :-
CONTRACTOR :-Trust Construction | [6 empty] | Re-bars Ø14: Page No. :-; Re-bars Ø20: 2 of 2
LOCATION :- Dhedesa
Rebar Bar Detail
Item No. | Location | Shape | Ø | L | No. of mebers | No. | Re-bars Ø6: Re-bars | Remark
[7 empty] | Ø6 | Ø8 | Ø10 | Ø12 | Ø14 | Ø16 | Ø20
A. SUPER STRUCTURE
Elevation Column
| C1 |  | 12 | 3.8 | 16 | 4 | " | " | " | 243.2 | " | " | "
|  |  | 8 | 1.2 | 16 | 15 | " | 288 | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[8 empty] | " |  |  | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[8 empty] | " |  |  | " | " | "
[8 empty] | " |  |  | " | " | "
[8 empty] | " |  |  | " | " | "
[8 empty] | " |  |  | " | " | "
|  |  |  | Total Length |  |  | 0 | 288 | 0 | 243.2 | 0 | 0 | 0
|  |  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467
|  |  |  | Total Weight(For 1 Block) |  |  | 0 | 113.76 | 0 | 215.96 | 0 | 0 | 0
Prepared by …………………………… | [6 empty] | Re-bars Ø14: Checked by ……………………………
PROJECT :- Staff Residence & Facility Project Lot-III
CLIENT :- Derba Midroc Cement Factory | [6 empty] | Re-bars Ø14: Block Type :-; Re-bars Ø20: Residence Type C
CONSULTANT :- Construction Design Share Company | [6 empty] | Re-bars Ø14: Block :- | 24
CONTRACTOR :- SA Construction PLC. | [6 empty] | Re-bars Ø14: Page No. :- | 12
LOCATION :- Derba
Rebar Cutting, Bending and Fixing
Item No. | Location | Shape | Ø | L | Qty | No. | Re-bars Ø6: Re-bars | Remark
[7 empty] | Ø6 | Ø8 | Ø10 | Ø12 | Ø14 | Ø16 | Ø20
1st &2nd Floor slab
Axis 1-2&5-6(A-D)
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
Axis 2-3&4-5(A-D) | bar: Re-bars Ø6 to Re-bars Ø20
"
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
Axis 3-4(A-B') | bar: Re-bars Ø6 to Re-bars Ø20
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | "
|  |  |  | Total Length |  |  | 0 | 0 | 0 | 0 | 2716.458 | 0 | 0
|  |  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467
|  |  |  | Total Weight(For 1 Block) |  |  | 0 | 0 | 0 | 0 | 3284.2 | 0 | 0 |  | 3284.2
Signature
|  | Contractor |  |  |  |  | Re-bars Ø16: Supervisor/consultant
PROJECT :- DMC Staff Residence And Facility
CLIENT :- DMC
CONSULTANT:- CD S.Co.
CONTRACTOR:-SA Construction | [6 empty] | Re-bars Ø6: Rebar Cutting, Bending and Fixing
LOCATION:-Derba
Block Type | Residence Type-C |  |  | Block | 24&25
Item No. | Location | Shape | Ø | L | Qty | No. | Re-bars Ø6: Re-bars
[7 empty] | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
B. SUPER STRUCTURE
Stair Case 1ST&2ND FLOOR
SECTION 3-3 | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
SECTON 2-2 | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
|  |  |  | Total Length |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
|  |  |  | Total Weight |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT :- DMC Staff Residence And Facility
CLIENT :- DMC
CONSULTANT:- CD S.Co.
CONTRACTOR:-SA Construction | [6 empty] | Re-bars 6: Rebar Cutting, Bending and Fixing
LOCATION:-Derba
Block Type | Residence Type-C |  |  | Block | 25
Item No. | Location | Shape | Ø | L | Qty | No. | Re-bars 6: Re-bars
[7 empty] | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24
B. SUPER STRUCTURE
1st and 2nd
intermidate and floor beams
Axis -A
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
Axis A' | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
Axis B' | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
Axis B'' | bar: Re-bars 6 to Re-bars 20
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
AXIS D | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
AXIS 1&6
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
AXIS 2&5 | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
AXIS 3&4 | bar: Re-bars 6 to Re-bars 24
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
[7 empty] | " | " | " | " | " | " | " | "
|  |  |  | Total Length |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209 | 1.579 | 2.467 | 3.552
|  |  |  | Total Weight |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 346.97 | 0 | 215.96 | 4306.72 | 0 | 0 |  | 4869.65 | 8960.156

## TOF WAITING (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Waiting and Registration
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6. Finishing works |  | 16.55
|  |  | 6.3 4 mm thick plastic celing |  | 2.45
| 3.9 |  | Central triagle |  |  | 40.5475
| 3.35 |  |  |  | 12
|  | 13.07 | M2 Sub total |  | 2.85
| 2.9 |  | Casher Area |  |  | 34.2
| 1.75 |  |  |  | 4.15
|  | 5.08 | M2 Sub total |  | 0.25
| 2.9 |  | REG Area |  |  | 1.0375
| 1.95 |  |  |  | 2.25
|  | 5.66 | M2 Sub total |  | 0.25
| 3.85 |  | Main waiting area |  |  | 0.5625
| 2.45 |  |  |  | 1.2
|  | 9.43 |  |  | 0.25
| 5.95 |  |  |  |  | 0.3
| 2.45 |  |  |  |  | 120.7275 | M2 Sub total
|  | 14.58 |  |  |  |  | Deduction
| 5.75 |  |  | -1 | 0.9 |  | door edge
| 2.45 |  |  |  | 0.25 |  | central rtiangle of casher
|  | 14.09 |  |  |  | -0.23
| 5.75 |  |  | -1 | 0.8 |  | Rec/Reg
| 2.9 |  |  |  | 0.25
|  | 16.68 |  |  |  | -0.2
| 5.95 |  |  |  |  | -0.43 | M2 Sub total
| 2.9 |  |  |  |  | 144.3 | m2 Total ofitem 6.4
17.26
5.75
3.4
19.55
5.95
3.4
20.23
|  | 111.82 | M2 Sub total
|  | 135.63 | m2 Total of item 6.3
6.4 8 mm Thick ceramic flooring
| 3.9 |  | Central triagle
3.4
|  | 13.26 | M2 Sub total
| 2.85 |  | Casher Area
1.75
|  | 4.99 | M2 Sub total
| 2.95 |  | REG Area
1.95
|  | 5.75 | M2 Sub total
| 11.9 |  | Main waiting area
3.4
40.46
2.2
0.25
0.55
11.05
0.25
2.76
1.25
0.25
0.31
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Waiting and Registration
CONTRACTOR :- Trust Construction | [5 empty] | Page No:- | 2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. SUB - STRUCTURE
1) Excavation & Earth Work
1.6 Cart Away
Site Clearing
1 | 19.5
12.6
| 0.3 | 73.71
Bulk Excavation
1 | 19.5
12.6
| 0.91 | 223.59
4 | 17 |  | Trench Excavation
1
| 1 | 68
4 | 10.1
1
| 1 | 40.4
|  | 405.7 | Total m3 to 1.6
|  | 300.58 | Previous payment
|  | 105.12 | m3 Total 1.6 Remaining

## Wait TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Waiting & Registration
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.6)Approved ceramic skirting 10/0.9cm |  |  |  | 7.00. Type of light Fitting with lamp
2 | 8.7 |  | Cashier & REC./REG. |  |  |  | 7.01. PHILPS TMS 012/236 IMK with 2xTLD 36W
|  | 17.4 |  | 1 | 35
[6 empty] | 35 | Pcs net number item 7.01
1 | 13.7 |  | Central Triage
|  | 13.7 |  |  |  |  | 7.02. PHILPS TMS 012/136 IMK with 1xTLD 36W
|  |  |  | 1 | 8
1 | 7.7 |  | Corridor |  |  | 8 | Pcs net number item 7.02
7.7
7.03. RZB 59251.002 with RZB 05-56150Q50W lamp
1 | 60.253 |  | Main Waiting area | 1 | 11
|  | 60.25 |  |  |  | 11 | Pcs net number item 7.03
|  | 99.05 | m2 Total area |  |  |  | 7.04. RZB 59222.002 with RZB 05-56150Q50W lamp
|  |  |  | 1 | 7
|  | 77.85 | Previous Payment |  |  | 7 | Pcs net number item 7.04
|  | 21.2 | m2 net area item 6.5 |  |  |  | 7.05. Massive 70107/11
|  |  |  | 1 | 1
|  |  | 10. ELECTRICAL INSTALLATION |  |  | 1 | Pcs net number item 7.05
2.1. Light points
1 | 20
|  | 20 | Pcs net number
3. Switches
3.02. Double(774005+774042)
1 | 6
|  | 6 | Pcs net number
3.03. Two -Way(774006+774041)
1 | 5
|  | 5 | Pcs net number
4. Socket outlet points
4.01. Socket outlet points
1 | 15
|  | 15 | Pcs net number
5. Socket outlet
5.01. Socket outlet LEGRAND SUNO 774023 16 1ph
1 | 15
|  | 15 | Pcs net number

## IPD Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
SUMMARY OF STATEMENT for IPD - NO 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 447385 | 249160.58 | 0 | 249160.58
2 | CONCRETE WORKS | 704325 | 561665.92 | 0 | 561665.92
3 | MASONRY WORKS | 299000 | 88850 | 0 | 88850
TOTAL A |  | 1450710 | 899676.5 | 0 | 899676.5
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 262922 | 229067.54 | 14821.94 | 243889.48
2 | BLOCK WORK | 341660 | 281340.4 | 0 | 281340.4
3 | ROOFING | 207680 | 204586.8 | 0 | 204586.8
4 | CARPENTRY & JOINERY | 202786 | 205428.42 | 24624 | 230052.42
5 | METAL WORK | 191783 | 136097 | 0 | 136097
6 | FINISHING | 703080 | 635484.9 | 16605.4 | 652090.3
7 | PAINTING | 44590 | 22585.16 | 0 | 22585.16
8 | GLAZING WORK | 35700 |  | 0 | 0
9 | SANITARY INSTALLATION | 140200 | 46013 | 64302 | 110315
10 | ELECTRICAL INSTALLATION | 122225 | 20880 | 58964 | 79844
TOTAL B |  | 2252626 | 1781483.22 | 179317.34 | 1960800.56
TOTAL A+ B |  | 3703336 | 2681159.72 | 179317.34 | 2860477.06

## IPD Mea
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for IPD - NO 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount (birr)
|  |  |  | previous | current | To date |  |  | Previous | Current | To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear off site | M2 | 895 | 894.33 |  | 894.33 | 6 | 5370 | 5365.98 | 0 | 5365.98
1.2 | Bulk Excavation | M3 | 950 | 1108.96 |  | 1108.96 | 50 | 47500 | 55448 | 0 | 55448
1.4 | Trench Excavation | M3 | 380 | 165.7 |  | 165.7 | 40 | 15200 | 6628 | 0 | 6628
1.5 | Selected backfill | M3 | 2000 | 194.27 |  | 194.27 | 100 | 200000 | 19427 | 0 | 19427
1.6 | Car away | M3 | 1700 | 1542.96 |  | 1542.96 | 70 | 119000 | 108007.2 | 0 | 108007.2
1.7 | 25cm thick stone hard core | M2 | 685 | 638.64 |  | 638.64 | 85 | 58225 | 54284.4 | 0 | 54284.4
| TOTAL CARRIED TO SUMMARY | [6 empty] | 445295 | 249160.58 | 0 | 249160.58
2. CONCRETE WORKS
2.1 | Lean Concrete 5cm thick lean concrete
| a) massonary foundation | M2 | 180 | 177.7 |  | 177.7 | 100 | 18000 | 17770 | 0 | 17770
2.2 | 10cm thick RC C-20 | M2 |  | 631.45 |  | 631.45 | 350 | 0 | 221007.5 | 0 | 221007.5
2.3 | RC C-25
| a) In grade beam & step | M3 | 35 | 32.4 |  | 32.4 | 2900 | 101500 | 93960 | 0 | 93960
2.4 | form work or
| a) In grade beam & step | M2 | 265 | 249.76 |  | 249.76 | 120 | 31800 | 29971.2 | 0 | 29971.2
| d) Steps | M2 |  | 0 |  | 0 | 130 | 0 | 0 | 0 | 0
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 2850 | 2613.33 |  | 2613.33 | 38 | 108300 | 99306.54 | 0 | 99306.54
| b) Dia. 12mm deformed bar | Kg | 610 | 0 |  | 0 | 38 | 23180 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 3410 | 2450.96 |  | 2450.96 | 38 | 129580 | 93136.48 | 0 | 93136.48
2.6 | 10/2 cm chip wood expansion joint | m |  | 434.28 |  | 434.28 | 15 | 0 | 6514.2 | 0 | 6514.2
| TOTAL CARRIED TO SUMMARY | [6 empty] | 412360 | 561665.92 | 0 | 561665.92
3. Masonry Work
3.1 | Stone masonry BNGL | M3 | 145 | 88.85 |  | 88.85 | 1000 | 145000 | 88850 | 0 | 88850
3.2 | Ditto but ANGL | M3 | 140 | 0 |  | 0 | 1000 | 140000 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 285000 | 88850 | 0 | 88850
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 5.5 | 5.18 |  | 5.18 | 2900 | 15950 | 15022 | 0 | 15022
| b) In beams | M3 | 23 | 19.44 |  | 19.44 | 2900 | 66700 | 56376 | 0 | 56376
| c) Lintel | M3 | 1.3 | 0 | 1.55 | 1.55 | 2900 | 3770 | 0 | 4495 | 4495
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 108 | 103.68 |  | 103.68 | 100 | 10800 | 10368 | 0 | 10368
| b) In beams | M2 | 285 | 216.42 |  | 216.42 | 100 | 28500 | 21642 | 0 | 21642
| c) Lintel | M2 | 107 | 0 | 25.89 | 25.89 | 100 | 10700 | 0 | 2589 | 2589
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg | 50 | 0 |  | 0 | 38 | 1900 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 2500 | 2526.86 | 137.82 | 2664.68 | 38 | 95000 | 96020.68 | 5237.16 | 101257.84
| c) Dia. 8 mm deformed bar | Kg | 779 | 779.97 | 65.81 | 845.78 | 38 | 29602 | 29638.86 | 2500.78 | 32139.64
| d) Dia. 6 mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 262922 | 229067.54 | 14821.94 | 243889.48
2. BLOCK WORK
| a) 20 cm thick | M2 | 965 | 566.49 |  | 566.49 | 320 | 308800 | 181276.8 | 0 | 181276.8
| b) 15 cm thick | M2 | 100 | 357.37 |  | 357.37 | 280 | 28000 | 100063.6 | 0 | 100063.6
| TOTAL CARRIED TO SUMMARY | [6 empty] | 336800 | 281340.4 | 0 | 281340.4
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 805 | 792.96 |  | 792.96 | 230 | 185150 | 182380.8 | 0 | 182380.8
3.2 | G-30 Ribbed Sheet | M2 | 75 | 81.2 |  | 81.2 | 130 | 9750 | 10556 | 0 | 10556
3.3 | G-30 Flashing | m | 56 | 0 |  | 0 | 80 | 4480 | 0 | 0 | 0
3.4 | G-30 flat metal sheet gutter | m | 83 | 116.5 |  | 116.5 | 100 | 8300 | 11650 | 0 | 11650
| TOTAL CARRIED TO SUMMARY | [6 empty] | 207680 | 204586.8 | 0 | 204586.8
4.CARPENTRY & JOINERY
4.1 | carpentry swan eucalyptus truss
| a)-diameter 10 -12cm | M2 | 1195 | 1234.11 |  | 1234.11 | 22 | 26290 | 27150.42 | 0 | 27150.42
| b) diameter 8 - 10cm | M2 | 675 | 822.12 |  | 822.12 | 15 | 10125 | 12331.8 | 0 | 12331.8
| c) Purlin zigba size 5/7cm | m | 955 | 963.6 |  | 963.6 | 32 | 30560 | 30835.2 | 0 | 30835.2
4.2 | 25*2.5 cm Zigba wooden fascia board | m | 130 | 120 |  | 120 | 70 | 9100 | 8400 | 0 | 8400
4.3 | Supply 40mm thick wood framed door
| a) Type D5 size-100/270cm | No | 4 | 4 |  | 4 | 5130 | 20520 | 20520 | 0 | 20520
| b) Type D2 size -80/270cm | No | 9 | 9 |  | 9 | 4104 | 36936 | 36936 | 0 | 36936
| c) Type D3 size -70/270cm | No | 6 | 6 |  | 6 | 3591 | 21546 | 21546 | 0 | 21546
| d) Type D1 size -90/270cm | No | 9 | 9 |  | 9 | 4617 | 41553 | 41553 | 0 | 41553
| e) Type D7 size -120/270cm | No | 1 | 1 | 4 | 5 | 6156 | 6156 | 6156 | 24624 | 30780
| TOTAL CARRIED TO SUMMARY | [6 empty] | 202786 | 205428.42 | 24624 | 230052.42
5.METAL WORKS
5.1 | Windows
| a) W3- 150/160cm | no | 12 | 11 |  | 11 | 3120 | 37440 | 34320 | 0 | 34320
| b) W10- 130/160cm | no | 3 | 5 |  | 5 | 2704 | 8112 | 13520 | 0 | 13520
| c) W5- 75/160cm | no | 1 | 1 |  | 1 | 585 | 585 | 585 | 0 | 585
| d) W7- 90/60cm | no | 5 | 1 |  | 1 | 702 | 3510 | 702 | 0 | 702
| e) W10 - 130/60cm | no | 7 | 5 |  | 5 | 1014 | 7098 | 5070 | 0 | 5070
| f) W20 - 600/60cm | no | 1 | 1 |  | 1 | 4680 | 4680 | 4680 | 0 | 4680
5.2 | Window-Doors
| a) WD2 - 120/270cm | no | 3 | 3 |  | 3 | 8775 | 26325 | 26325 | 0 | 26325
| b)WD7 - 250/270cm | no | 5 | 2 |  | 2 | 4212 | 21060 | 8424 | 0 | 8424
5.4 | Doors
| a) D6 - 90/270cm | no | 5 | 5 |  | 5 | 3159 | 15795 | 15795 | 0 | 15795
| b) D10 - 80/270cm | no | 5 | 5 |  | 5 | 2808 | 14040 | 14040 | 0 | 14040
| c) D5 - 180/270Cm | no | 2 | 2 |  | 2 | 6318 | 12636 | 12636 | 0 | 12636
| TOTAL CARRIED TO SUMMARY |  |  | 0 |  | 0 |  | 151281 | 136097 | 0 | 136097
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendering | M2 | 255 | 240.92 |  | 240.92 | 90 | 22950 | 21682.8 | 0 | 21682.8
6.2 | Apply three coats of plastering | M2 | 1375 | 1328.64 |  | 1328.64 | 100 | 137500 | 132864 | 0 | 132864
6.3 | 4mm thick plastic ceiling nailed on batens | M2 | 685 | 543.27 |  | 543.27 | 270 | 184950 | 146682.9 | 0 | 146682.9
6.4 | 200*300*6mm glazed ceramic wall till | M2 | 192 | 182.26 | 57.26 | 239.52 | 290 | 55680 | 52855.4 | 16605.4 | 69460.8
6.5 | 8mm thick non slipery ceramic 60x60x8cm | M2 | 557 | 605.57 |  | 605.57 | 300 | 167100 | 181671 | 0 | 181671
6.6 | Ceramic tile skiring 10/0.8cm | ml | 485 | 373.16 |  | 373.16 | 100 | 48500 | 37316 | 0 | 37316
6.7 | Terrazo window cill bedded on | ml | 75 | 31.6 |  | 31.6 | 150 | 11250 | 4740 | 0 | 4740
6.8 | 30/30/3mm angle iron corner protection | M2 | 45 | 0 |  | 0 | 70 | 3150 | 0 | 0 | 0
6.9 | 10cm thick C-20 RC 1-2m wide pavement | M2 | 143 | 143.04 |  | 143.04 | 320 | 45760 | 45772.8 | 0 | 45772.8
6.1 | concret pipes of half diameter 30cm | ml | 128 | 119 |  | 119 | 100 | 12800 | 11900 | 0 | 11900
6.11 | 10X40cm curb stone around the building | ml | 128 | 0 |  | 0 | 105 | 13440 |  | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 703080 | 635484.9 | 16605.4 | 652090.3
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 710 | 664.32 |  | 664.32 | 26 | 18460 | 17272.32 | 0 | 17272.32
7.2 | Ditto but oil paint to a height of 1.5m | M2 | 750 | 0 |  | 0 | 26 | 19500 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 255 | 204.34 |  | 204.34 | 26 | 6630 | 5312.84 | 0 | 5312.84
TOTAL CARRIED TO SUMMARY | [7 empty] | 44590 | 22585.16 | 0 | 22585.16
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 15 |  | 46.04 | 46.04 | 220 | 3300 | 0 | 10128.8 | 10128.8
8.2 | 4mm thick frosted glass | M2 | 90 |  |  | 0 | 360 | 32400 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 35700 | 0 | 10128.8 | 10128.8
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 15mm diameter;internal | lm | 15 | 26 |  | 26 | 65 | 975 | 1690 | 0 | 1690
| 20mm diameter;internal | lm | 25 | 27 |  | 27 | 75 | 1875 | 2025 | 0 | 2025
| 25mm diameter;internal | lm | 100 | 90.3 |  | 90.3 | 90 | 9000 | 8127 | 0 | 8127
9.4 | Ditto item 3, but chrome plated 15mm water tap | No | 20 | 20 |  | 20 | 180 | 3600 | 3600 | 0 | 3600
9.5 | Supply and install waste water pipes made of rigid plastic pipe (upvc)
| 50mm diameter | lm | 15 | 58.45 |  | 58.45 | 60 | 900 | 3507 | 0 | 3507
| 75mm diameterthickness | lm | 21 | 14 |  | 14 | 90 | 1890 | 1260 | 0 | 1260
| 100mm diameter | lm | 110 | 59.2 |  | 59.2 | 120 | 13200 | 7104 | 0 | 7104
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 15 |  | 15 | 15 | 600 | 9000 | 0 | 9000 | 9000
9.7 | Supply and fix low flush white vitreous china water closet | No | 11 |  | 11 | 11 | 900 | 9900 | 0 | 9900 | 9900
9.9 | Supply and fix toilet paper holder | No | 11 |  | 5 | 5 | 90 | 990 | 0 | 450 | 450
9.1 | Supply and fix crystal glass mirror of size 500x400mm | No | 11 |  | 17 | 17 | 200 | 2200 | 0 | 3400 | 3400
9.11 | Supply and install shower units made of chrome-plated shower | No | 11 | 11 |  | 11 | 1700 | 18700 | 18700 | 0 | 18700
9.12 | Supply and fix 600mm long towel hanger for showers | No | 11 |  | 13 | 13 | 120 | 1320 | 0 | 1560 | 1560
9.13 | Supply and fix 1800x900mm bath white vitrous china complete | No | 2 |  | 2 | 2 | 2880 | 5760 | 0 | 5760 | 5760
9.14 | Supply and install electric water heater | No | 16 |  | 13 | 13 | 2000 | 32000 | 0 | 26000 | 26000
9.16 | Supply and fix 50mm diameter floor drain | No | 11 |  | 11 | 11 | 120 | 1320 | 0 | 1320 | 1320
9.18 | Supply and fix 100mm 3.2mm thickness down pipes made up of upvc | lm | 52 |  | 76.8 | 76.8 | 90 | 4680 | 0 | 6912 | 6912
TOTAL CARRIED TO SUMMARY | [7 empty] | 117310 | 46013 | 64302 | 110315
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | Light points in rigid therimoplastic conduit of 16mmfed by pvc conductor of 3x2.5mm2(wire to be of ethioplastic or approved equivalent) | Pcs | 92 | 92 |  | 92 | 200 | 18400 | 18400 | 0 | 18400
3 | Switches
3.03 | Two -Way(774006+774041) | Pcs | 38 | 31 |  | 31 | 80 | 320 | 2480 | 0 | 2480
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit | Pcs | 54 |  | 54 | 54 | 200 | 320 | 0 | 10800 | 10800
4.2 | Ditto as 4.01 but for water heater points | Pcs | 12 |  | 12 | 12 | 200 | 320 | 0 | 2400 | 2400
5 | Socket outlet
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | Pcs | 54 |  | 54 | 54 | 100 | 320 | 0 | 5400 | 5400
5.02 | Weather proof socket Legrand Suno 774022+774041 | Pcs | 12 |  | 12 | 12 | 250 | 320 | 0 | 3000 | 3000
6 | Telephone/Data points
6.01 | Telephone pt fed through cat 5E UTP cable | Pcs | 13 |  | 13 | 13 | 130 | 320 | 0 | 1690 | 1690
7 | Type of light Fitting with lamp
7.01 | PHILPS TMS 012/236 IMK with 2xTLD 36W | Pcs | 20 |  | 8 | 8 | 700 | 320 | 0 | 5600 | 5600
7.02 | PHILPS TMS 012/136 IMK with 1xTLD 36W | Pcs | 8 |  | 16 | 16 | 450 | 320 | 0 | 7200 | 7200
7.03 | RZB 59251.002 with RZB 05-56150Q50W | Pcs | 28 |  | 28 | 28 | 250 | 320 | 0 | 7000 | 7000
7.04 | RZB 59222.002 with RZB 05-56150Q50W | Pcs | 12 |  | 12 | 12 | 250 | 320 | 0 | 3000 | 3000
7.05 | MASSIVE 3202/02/67/1XE27/75W | Pcs | 24 |  | 24 | 24 | 270 | 320 | 0 | 6480 | 6480
8 | TV Points
8.01 | TV Points fed through RG6 Coaxial 75 ohm TV cable | Pcs | 5 |  | 5 | 5 | 130 | 320 | 0 | 650 | 650
11 | Low Voltage Earthing system
11.01 | Copper Earthing rod of 16x2400mm to be driven on earth with Earthing pit of 500x500x500mm | Pcs | 1 |  | 1 | 1 | 2000 | 320 | 0 | 2000 | 2000
11.02 | Copper conductor of 1x16mm2 for Earthing | ml | 25 |  | 31.2 | 31.2 | 120 | 320 | 0 | 3744 | 3744
TOTAL CARRIED TO SUMMARY | [7 empty] | 22880 | 20880 | 58964 | 79844

## TOS IPD (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- IPD
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4. Carpentry And joinery |  |  | 10.73 | M2 Sub total
|  |  | 4.2 25x 2.5, fascial Board | 1 | 38.1
2 | 40 |  |  |  | 2.45
|  | 80 |  |  |  | 93.35
2 | 20 |  |  | 2 | 1.8
|  | 40 |  |  | 0.25
|  | 120 | Ml Total of item 4.2 |  |  | 0.9
|  |  | 6. Finishing work |  |  | 94.25 | M2 Sub total
|  |  | 6.3 4mm plastic celling | 1 | 2.25 |  | Corridor
6 | 6 |  | General Ward |  | 2.25
| 3.45 |  |  |  |  | 5.06
|  | 124.2 | M2 Sub total | 1 | 0.9
4 | 6 |  | Maternity ward |  | 0.25
| 3.45 |  |  |  |  | 0.23
|  | 82.8 | M2 Sub total |  |  | 5.29 | M2 Sub total
1 | 3.5 |  | Assisted bath | 1 | 2.25 |  | Line/ Pajama Store
| 2.95 |  |  |  | 3.3
|  | 10.325 | M2 Sub total |  |  | 7.43
|  | 217.33 | M2 Total of item 6.3 | 1 | 0.9
2 | 6 |  | 6.5 8mm Thick Ceramic Tile Flooring |  | 0.25
| 7.15 |  | Maternity ward |  |  | 0.23
|  | 85.8 |  |  |  | 7.66 | M2 Sub total
2 | 1.25 |  |  | 2 | 2.8 |  | Changing Room
| 0.25 |  |  |  | 1.8
|  | 0.625 |  |  |  | 10.08
|  | 86.43 | M2 Sub total | 2 | 0.9
1 | 3.75 |  | Nurse station |  | 0.2
| 2.4 |  |  |  |  | 0.36
|  | 9 |  |  |  | 10.44 | M2 Sub total
1 | 0.9 |  |  | 1 | 6.1 |  | Corridor
| 0.25 |  |  |  | 1.4
|  | 0.225 |  |  |  | 8.54 | M2 Sub total
|  | 9.23 | M2 Sub total | 1 | 2.4 |  | Pharmascy
1 | 2.4 |  | Store |  | 5.8
| 3.2 |  |  |  |  | 13.92
|  | 7.68 |  | 1 | 0.9
1 | 0.9 |  |  |  | 0.25
| 0.2 |  |  |  |  | 0.23
|  | 0.18 |  |  |  | 14.15 | M2 Sub total
|  | 7.86 | M2 Sub total | 1 | 4.3 |  | Procedure Room
3 | 6 |  | General Ward |  | 5.8
| 7.15 |  |  |  |  | 24.94
|  | 128.7 |  | 1 | 1.3
3 | 1.25 |  |  |  | 0.25
| 0.25 |  |  |  |  | 0.33
|  | 0.9375 |  |  |  | 25.27 | M2 Sub total
|  | 129.64 | M2 Sub total | 1 | 4 |  | Doctors Room
2 | 3.5 |  | Assisted Bath |  | 5.8
| 2.95 |  |  |  |  | 23.2
|  | 20.65 |  | 1 | 0.9
2 | 1 |  |  |  | 0.25
| 0.2 |  |  |  |  | 0.23
|  | 0.4 |  |  |  | 23.43 | M2 Sub total
|  | 21.05 | M2 Sub total | 1 | 2.3 |  | Clean utility
1 | 1.45 |  | Corridor |  | 1.2
| 7.4 |  |  |  |  | 2.76
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- IPD
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 0.8
0.25
0.2
|  | 2.96 | M2 Sub total
1 | 2.3 |  | Duty room 1
4.5
10.35
1 | 0.8
0.2
0.16
|  | 10.51 | M2 Sub total
1 | 1.35 |  | Corridor
3.2
4.32
1 | 0.8
0.25
0.2
|  | 4.52 | M2 Sub total
1 | 2.1 |  | Duty room 2
4.45
9.35
1 | 0.8
0.2
0.16
|  | 9.51 | M2 Sub total
1 | 2 |  | Nurse station & store
2
4
1 | 2
3.9
7.8
1 | 0.8
0.2
0.16
|  | 11.96 | M2 Sub total
2 | 2.8 |  | Isolation room
4.65
26.04
2 | 0.9
0.2
0.36
|  | 26.4 | M2 Sub total
1 | 1.8 |  | Corridor
4.15
|  | 7.47 | M2 Sub total
|  | 527.3 | M2 Total of item 6.5
2 | 41 |  | 6.9 1.20m Pavment
1.2
98.4
2 | 18.6
1.2
44.64
|  | 143.04 | M2 Total of item 6.9
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- IPD
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 3
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. SUB - STRUCTURE
1) Excavation & Earth Work
1.6 cart away
1 | 894.325 |  | Site clerance
| 0.3 | 268.3
|  | 1108.96 | Bulk Excavation
|  | 301.79 | Trench Excavation
|  | 1679.05 | m3 total 1.6
|  | 1542.96 | Previous payment
|  | 136.09 | m3 Total 1.6 Remaining

## IPD TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - IPD
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | 1.3. Reinforcement steel bars
|  |  | 1. CONCRETE WORKS |  |  |  | b. ф12 mm deformed bars
|  |  | 1.1. Reinforced concrete class C-25 | 1 | 137.82
|  |  | c) Lintel |  |  | 137.82 | kg net wight item 1.3.b
5 | 1.3 |  | D1
| 0.15 |  |  | 1 | 65.81 |  | c. ф8 mm deformed bars
| 0.3 | 0.29 |  |  |  | 65.81 | kg net wight item 1.3.c
4 | 1.2 |  | D2 |  |  |  | 4.CARPENTRY & JOINERY
| 0.15 | [5 empty] | 4.3. Wood framed door
| 0.3 | 0.22 |  |  |  |  | e) Doors Type D7 size -120/270cm
|  |  |  | 1 | 4
13 | 1.1 |  | D3 |  |  | 4 | Pcs net number item 4.3.d
0.15
| 0.3 | 0.64 |  |  |  |  | 6. FINISHING
6.4. 200x300x6mm Glazed Ceramic Wall
1 | 1.3 |  | D5 | 4 | 3 |  | Bath Room
| 0.15 |  |  |  | 1.8 | 21.6
| 0.3 | 0.06
|  |  |  | 2 | 2.03 |  | "
5 | 1.2 |  | D10 |  | 1.8 | 7.31
0.15
| 0.3 | 0.27 |  | 2 | 1.5 |  | "
[5 empty] | 1.5 | 4.5
1 | 1.6 |  | W1
| 0.15 |  |  | 2 | 2.53 |  | "
| 0.3 | 0.07 |  |  | 1.8 | 9.11
|  | 1.55 | m3 net area item 1.1.c | 2 | 2.25 |  | Toilet Around Dutty room
[5 empty] | 1.8 | 8.1
1.2. form work or metal panel. To:-
|  |  | c) Lintel | 1 | 0.7 |  | "
5 | 1.3 |  | D1 |  | 1.8 | 1.26
| 0.75 | 4.88
|  |  |  | 1 | 1.33 |  | "
4 | 1.2 |  | D2 |  | 1.8 | 2.39
| 0.75 | 3.6
|  |  |  | 4 | 1.2 |  | Janitors Room
13 | 1.1 |  | D3 |  | 1.5 | 7.2
| 0.75 | 10.73
|  |  |  | 2 | 1.05 |  | "
1 | 1.3 |  | D5 |  | 1.05 | 2.21
| 0.75 | 0.98
|  |  |  | 2 | 0.7 |  | "
5 | 1.2 |  | D10 |  | 1.5 | 2.1
| 0.75 | 4.5
|  |  |  | 2 | 1.35 |  | Male & Female Shower Room
1 | 1.6 |  | W1 |  | 1.8 | 4.86
| 0.75 | 1.2
|  |  |  | 8 | 1.2 |  | "
|  | 25.89 | m2 net area item 1.2.c |  | 1.8 | 17.28
|  |  |  | 2 | 0.7 |  | "
[5 empty] | 1.8 | 2.52
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 1.05 |  | " | 1 | 0.75 |  | c) W5- 75/160cm
| 1.8 | 3.78 |  |  | 1.6 | 1.2
2 | 0.4 |  | " | 1 | 0.9 |  | d) W7- 90/60cm
| 1.8 | 1.44 |  |  | 0.6 | 0.54
8 | 1.2 |  |  | 5 | 1.3 |  | e) W10 - 130/60cm
| 1.5 | 14.4 | At WC Room |  | 0.6 | 3.9
4 | 1.05 |  | " | 1 | 6 |  | f) W20 - 600/60cm
| 1.5 | 6.3 |  |  | 0.6 | 3.6
4 | 0.4 |  | " |  |  | 46.04 | m2 net area to item no 8.1
| 1.5 | 2.4
9. SANITARY INSTALLATION
2 | 5.85 |  | Cooridor Male & Female Toilet |  |  |  | 9.6. Hand wash basin
| 1.5 | 17.55 |  | 1 | 15
[6 empty] | 15 | Pcs net number item 9.6
4 | 2.25 |  | Toilet Around Dutty room
| 1.8 | 16.2 |  |  |  |  | 9.7. Water closet
|  |  |  | 1 | 11
2 | 1.42 |  | " |  |  | 11 | Pcs net number item 9.7
| 1.8 | 5.11
9.9. Toilet paper holder
2 | 1.7 |  | Toilet Around Isolation room | 1 | 5
| 1.8 | 6.12 |  |  |  | 5 | Pcs net number item 9.9
1 | 1.9 |  | " |  |  |  | 9.10. Crystal glass mirror
| 1.8 | 3.42 |  | 1 | 17
[6 empty] | 17 | Pcs net number item 9.10
1 | 1.2 |  | "
| 1.8 | 2.16 |  |  |  |  | 9.12. Towel hanger
|  |  |  | 1 | 13
10 | 2.3 |  | Verenad Toilet |  |  | 13 | Pcs net number item 9.12
| 1.8 | 41.4
9.13. 1800x900mm bath
5 | 2 |  | " | 1 | 2
| 1.8 | 18 |  |  |  | 2 | Pcs net number item 9.13
5 | 1.2 |  | " |  |  |  | 9.14. Electric water heater
| 1.8 | 10.8 |  | 1 | 13
[6 empty] | 13 | Pcs net number item 9.14
|  | 239.52 | m2 Total area
9.16. 50mm diameter floor drain
|  | 182.26 | Previous Payment | 1 | 11
[6 empty] | 11 | Pcs net number item 9.10
|  | 57.26 | m2 net area item 6.4
9.18. 100mm Down pipes
|  |  | 8.GLAZING | 1 | 76.8
|  |  | 8.1. 4mm thick clear glass |  |  | 76.8 | m net length item 9.18
11 | 1.5 |  | a) W3- 150/160cm
| 1.6 | 26.4
5 | 1.3 |  | b) W10- 130/160cm
| 1.6 | 10.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 10. ELECTRICAL INSTALLATION |  |  |  | 11.00. Low Voltage Earthing system
|  |  | 4.00. Socket outlet points |  |  |  | 11.01. Copper Earthing rod of 16x2400mm
|  |  | 4.01. Socket outlet points | 1 | 1
1 | 54 |  |  |  |  | 1 | Pcs net number item 11.01
|  | 54 | Pcs net number item 4.01
11.02. Copper conductor of 1x16mm2 for Earthing
|  |  | 4.02. Ditto as 4.01 but for water heater | 1 | 31.2
1 | 12 |  |  |  |  | 31.2 | m net length item 11.02
|  | 12 | Pcs net number item 4.02
5.00. Socket outlet
5.01. Socket outlet LEGRAND SUNO 774023 16 1ph
1 | 54
|  | 54 | Pcs net number item 5.01
5.02. Weather proof socket Legrand Suno 774022+774041
1 | 12
|  | 12 | Pcs net number item 5.02
6.00. Telephone/Data points
6.01. Telephone pt fed through cat 5E UTP cable
1 | 13
|  | 13 | Pcs net number item 6.01
7.00. Type of light Fitting with lamp
7.01. PHILPS TMS 012/236 IMK with 2xTLD 36W
1 | 8
|  | 8 | Pcs net number item 7.01
7.02. PHILPS TMS 012/136 IMK with 1xTLD 36W
1 | 16
|  | 16 | Pcs net number item 7.02
7.03. RZB 59251.002 with RZB 05-56150Q50W
1 | 28
|  | 28 | Pcs net number item 7.03
7.04. RZB 59222.002 with RZB 05-56150Q50W
1 | 12
|  | 12 | Pcs net number item 7.04
7.05. MASSIVE 3202/02/67/1XE27/75W
1 | 24
|  | 24 | Pcs net number item 7.05
8.00. TV Points
8.01. TV Points fed through RG6 Coaxial 75 ohm TV cable
1 | 5
|  | 5 | Pcs net number item 8.01

## IPD Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - IPD
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D1 |  | 12 | 1.75 | 5 | 2 | 10 |  |  |  | 17.5
|  |  | 12 | 1.25 | 5 | 2 | 10 | - | - | - | 12.5 | -
| Stirrups |  | 8 | 0.85 | 5 | 7 | 35 | - | 29.75 | - | - | -
| D2 & D9 |  | 12 | 1.65 | 9 | 2 | 18 |  |  |  | 29.7
|  |  | 12 | 1.15 | 9 | 2 | 18 | - | - | - | 20.7 | -
| Stirrups |  | 8 | 0.85 | 9 | 7 | 63 | - | 53.55 | - | - | -
| D3 |  | 12 | 1.55 | 13 | 2 | 26 | - | - | - | 40.3 | -
|  |  | 12 | 1.05 | 13 | 2 | 26 | - | - | - | 27.3 | -
| Stirrups |  | 8 | 0.85 | 13 | 7 | 91 | - | 77.35 | - | - | -
| W1 |  | 12 | 2.05 | 1 | 2 | 2 | - | - | - | 4.1 | -
|  |  | 12 | 1.55 | 1 | 2 | 2 | - | - | - | 3.1 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
-
TOTAL LENGTH | [8 empty] | 166.6 | 0 | 155.2 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 65.81 | 0 | 137.82 | 0

## OR Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
SUMMARY OF STATEMENT for OR & DELIVERY - NO 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 243255 | 294000.52 | 0 | 294000.52
2 | CONCRETE WORKS | 347000 | 529990.08 | 0 | 529990.08
3 | MASONARY WORKS | 582504 | 182930 | 0 | 182930
TOTAL A |  | 1172759 | 1006920.6 | 0 | 1006920.6
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 251620 | 233757.66 | 14682.38 | 248440.04
2 | Block WORKS | 383880 | 248013.2 | 0 | 248013.2
3 | ROOFING WORKS | 206590 | 204651.9 | 0 | 204651.9
4 | CARPENTERY & JOINERY | 304685.86 | 120150.18 | 183654 | 303804.18
5 | METAL WORKS | 114738 | 113217 | 0 | 113217
6 | FINISHING | 871832 | 615057.6 | 37160.2 | 652217.8
7 | PAINTING | 65078 | 19386.38 | 0 | 19386.38
8 | GLAZING WORK | 27980 | 10278.4 | 0 | 10278.4
9 | SANITARY INSTALLATION | 106240 | 31802 | 50128 | 81930
10 | ELECTRICAL INSTALLATION | 165059 | 61250 | 86230.5 | 147480.5
TOTAL B |  | 2497702.86 | 1657564.32 | 371855.08 | 2029419.4
TOTAL A+ B |  | 3670461.86 | 2664484.92 | 371855.08 | 3036340

## OR Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for OR & Delivery - NO 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 825 | 888.17 |  | 888.17 | 6 | 4950 | 5329.02 | 0 | 5329.02
1.2 | Bulk Excavation | M3 | 412 | 870.4 |  | 870.4 | 50 | 20600 | 43520 | 0 | 43520
1.4 | Trench Excavation | M3 | 160 | 240.4 |  | 240.4 | 40 | 6400 | 9616 | 0 | 9616
1.5 | Selected backfill | M3 | 485 | 870.4 |  | 870.4 | 100 | 48500 | 87040 | 0 | 87040
1.6 | Car away | M3 | 1537 | 1377.25 |  | 1377.25 | 70 | 107590 | 96407.5 | 0 | 96407.5
1.7 | Stone hard core | M2 | 625 | 612.8 |  | 612.8 | 85 | 53125 | 52088 | 0 | 52088
TOTAL CARRIED TO SUMMARY | [7 empty] | 241165 | 294000.52 | 0 | 294000.52
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class
| a) massonary foundation | M2 | 83 | 182.93 |  | 182.93 | 100 | 8300 | 18293 | 0 | 18293
2.2 | 10cm thick reinforced concrete floor slab | M2 | 625 | 612.86 |  | 612.86 | 350 | 218750 | 214501 | 0 | 214501
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 39 | 35.27 |  | 35.27 | 2900 | 113100 | 102283 | 0 | 102283
2.4 | form work or metal panel To:-
| a) In grade beam & step | M2 | 253 | 282.12 |  | 282.12 | 120 | 30360 | 33854.4 | 0 | 33854.4
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 1856 | 1112.47 |  | 1112.47 | 38 | 70528 | 42273.86 | 0 | 42273.86
| b) Dia. 12mm deformed bar | Kg | 3482 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 0 | 2880.39 |  | 2880.39 | 38 | 0 | 109454.82 | 0 | 109454.82
2.6 | 12/2 cm chip wood expansion joint | m | 610 | 622 |  | 622 | 15 | 9150 | 9330 | 0 | 9330
TOTAL CARRIED TO SUMMARY | [7 empty] | 450188 | 529990.08 | 0 | 529990.08
3. Masonry Work
3.1 | stone masonreyBNGL | M3 | 160 | 182.93 |  | 182.93 | 1000 | 160000 | 182930 | 0 | 182930
3.2 | Ditto but ANGL | M3 | 170 | 0 |  | 0 | 1100 | 187000 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 347000 | 182930 | 0 | 182930
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 5 | 4.86 |  | 4.86 | 2900 | 14500 | 14094 | 0 | 14094
| b) In beams | M3 | 23 | 21.16 |  | 21.16 | 2900 | 66700 | 61364 | 0 | 61364
| c) Lintel | M3 | 1.2 | 0 | 1.56 | 1.56 | 2900 | 3480 | 0 | 4524 | 4524
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 101 | 97.2 |  | 97.2 | 100 | 10100 | 9720 | 0 | 9720
| b) In beams | M2 | 255 | 282.12 |  | 282.12 | 100 | 25500 | 28212 | 0 | 28212
| c) Lintel | M2 | 10 | 0 | 25.96 | 25.96 | 100 | 1000 | 0 | 2596 | 2596
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 2644 | 2419.52 | 65.81 | 2485.33 | 38 | 100472 | 91941.76 | 2500.78 | 94442.54
| c) Dia. 8 mm deformed bar | Kg | 786 | 748.05 | 133.2 | 881.25 | 38 | 29868 | 28425.9 | 5061.6 | 33487.5
| d) Dia. 6 mm deformed bar | Kg | 0 |  |  |  | 38 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 251620 | 233757.66 | 14682.38 | 248440.04
2. BLOCK WORK
| a) 20 cm thick | M2 | 833 | 533.97 |  | 533.97 | 320 | 266560 | 170870.4 | 0 | 170870.4
| b) 15 cm thick | M2 | 419 | 275.51 |  | 275.51 | 280 | 117320 | 77142.8 | 0 | 77142.8
TOTAL CARRIED TO SUMMARY | [7 empty] | 383880 | 248013.2 | 0 | 248013.2
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 800 | 786.33 |  | 786.33 | 230 | 184000 | 180855.9 | 0 | 180855.9
3.2 | G-30 Ribbed Sheet | M2 | 85 | 88.2 |  | 88.2 | 130 | 11050 | 11466 | 0 | 11466
3.4 | G-30 flat metal sheet gutter | m | 89 | 123.3 |  | 123.3 | 100 | 8900 | 12330 | 0 | 12330
TOTAL CARRIED TO SUMMARY | [7 empty] | 203950 | 204651.9 | 0 | 204651.9
4.CARPENTRY & JOINERY
4.1 | a)Upper & lower chord size-diameter 10 -12cm | m | 1305.31 | 1297.44 |  | 1297.44 | 22 | 28716.82 | 28543.68 | 0 | 28543.68
| b) Diagonal & vertical Members size dia 8 -10cm | m | 926 | 1360.34 |  | 1360.34 | 15 | 13890 | 20405.1 | 0 | 20405.1
| c) Purlin zigba size 5/7cm | m | 1013.22 | 1949.2 |  | 1949.2 | 32 | 32423.04 | 62374.4 | 0 | 62374.4
4.2 | 25*2.5 cm Zigba wooden fascia board price includes | m | 123 | 126.1 |  | 126.1 | 70 | 8610 | 8827 | 0 | 8827
4.3 | Supply 40mm thick wood framed door
| a) Type D2 size-140/270cm | No | 2 | 0 |  | 0 | 7182 | 14364 | 0 | 0 | 0
| b) Type D3 size -70/210cm | No | 15 | 0 | 8 | 8 | 2793 | 41895 | 0 | 22344 | 22344
| d) Type D2s size -80/270cm | No | 1 | 0 | 1 | 1 | 4104 | 4104 | 0 | 4104 | 4104
| e) Type D9s size -160/270cm | No | 2 | 0 |  | 0 | 8208 | 16416 | 0 | 0 | 0
| f) Type D6s size -140/270cm | No | 5 | 0 | 7 | 7 | 7182 | 35910 | 0 | 50274 | 50274
| g) Type D7 size-80/210cm | No | 9 | 0 | 10 | 10 | 3192 | 28728 | 0 | 31920 | 31920
| h) Type D1 size 90*270cm | No | 15 | 0 | 14 | 14 | 4617 | 69255 | 0 | 64638 | 64638
| i) Type D6 size 130/210 | No | 2 | 0 | 2 | 2 | 5187 | 10374 | 0 | 10374 | 10374
| j) Type D5 size 100/210 | No | 0 |  | 2 | 2 |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 304685.86 | 120150.18 | 183654 | 303804.18
5.METAL WORKS
5.1 | Windows
| a) W1-120/160cm | no | 4 | 3 |  | 3 | 2496 | 9984 | 7488 | 0 | 7488
| b)W3 - 150/160cm | no | 20 | 22 |  | 22 | 3120 | 62400 | 68640 | 0 | 68640
| c)W12 - 110/160cm | no | 1 | 2 |  | 2 | 858 | 858 | 1716 | 0 | 1716
| d)W13 - 150/60cm | no | 7 | 7 |  | 7 | 1170 | 8190 | 8190 | 0 | 8190
| e)W7 - 100/60cm | no | 4 | 2 |  | 2 | 780 | 3120 | 1560 | 0 | 1560
5.2 | Doors
| a) D1 - 90/270CM | no | 3 | 3 |  | 3 | 3159 | 9477 | 9477 | 0 | 9477
| b) D7 - 140/270CM | no | 1 | 1 |  | 1 | 4914 | 4914 | 4914 | 0 | 4914
| C) D10 - 80/270CM | no | 2 | 2 |  | 2 | 2808 | 5616 | 5616 | 0 | 5616
| d) D9 - 160/270CM | no | 1 | 1 |  | 1 | 5616 | 5616 | 5616 | 0 | 5616
TOTAL CARRIED TO SUMMARY | [7 empty] | 110175 | 113217 | 0 | 113217
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendering to external walls. | M2 | 833 | 272.28 |  | 272.28 | 90 | 74970 | 24505.2 | 0 | 24505.2
6.2 | Apply three coats of plastering to internal walls & external coloumns and beams. | M2 | 1671 | 946.7 |  | 946.7 | 100 | 167100 | 94670 | 0 | 94670
6.3 | 4mm thick best type plastic ceiling nailed on batens & | M2 | 625 | 600.44 |  | 600.44 | 270 | 168750 | 162118.8 | 0 | 162118.8
6.4 | 200*300*6mm glazed ceramic wall till | M2 | 422 | 250 | 57.88 | 307.88 | 290 | 122380 | 72500 | 16785.2 | 89285.2
6.5 | 8mm thick non slippery ceramic | M2 | 625 | 625.4 |  | 625.4 | 300 | 187500 | 187620 | 0 | 187620
6.6 | Ceramic tile skiring 10/0.8cm | ml | 610 | 215.34 | 203.75 | 419.09 | 100 | 61000 | 21534 | 20375 | 41909
6.7 | Terrazo window cill bedded on | ml | 73 | 38.8 |  | 38.8 | 150 | 10950 | 5820 | 0 | 5820
6.8 | 30/30/3mm angle iron corner protection | M2 | 3.6 | 0 |  | 0 | 70 | 252 | 0 | 0 | 0
6.9 | 10cm thick C-20 RC 1-2m wide pavement (including | M2 | 148 | 120.28 |  | 120.28 | 320 | 47360 | 38489.6 | 0 | 38489.6
6.1 | Concret pipes of half diameter 30cm | ml | 154 | 78 |  | 78 | 100 | 15400 | 7800 | 0 | 7800
6.11 | 10X40cm curb stone around the building | ml | 154 | 0 |  | 0 | 105 | 16170 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 871832 | 615057.6 | 37160.2 | 652217.8
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 835 | 473.35 |  | 473.35 | 26 | 21710 | 12307.1 | 0 | 12307.1
7.2 | Ditto but oil paint to a height of 1.5m | M2 | 835 | 0 |  | 0 | 26 | 21710 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 835 | 272.28 |  | 272.28 | 26 | 21710 | 7079.28 | 0 | 7079.28
TOTAL CARRIED TO SUMMARY | [7 empty] | 65130 | 19386.38 | 0 | 19386.38
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 11 | 46.72 |  | 46.72 | 220 | 2420 | 10278.4 | 0 | 10278.4
8.2 | 4mm thick frosted glass | M2 | 71 |  |  | 0 | 360 | 25560 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 27980 | 10278.4 | 0 | 10278.4
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 15mm diameter;internal | lm | 156 | 19.8 |  | 19.8 | 65 | 10140 | 1287 | 0 | 1287
| 20mm diameter;internal | lm | 16 | 112.2 |  | 112.2 | 75 | 1200 | 8415 | 0 | 8415
9.5 | Supply and install waste water pipes made of rigid plastic pipe (upvc) of approved standard including
| 50mm diameter | lm | 10 | 51.75 |  | 51.75 | 60 | 600 | 3105 | 0 | 3105
| 75mm diameterthickness=3mm | lm | 25 | 27.1 |  | 27.1 | 90 | 2250 | 2439 | 0 | 2439
| 100mm diameter | lm | 120 | 38.8 |  | 38.8 | 120 | 14400 | 4656 | 0 | 4656
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 19 |  | 19 | 19 | 600 | 11400 | 0 | 11400 | 11400
9.7 | Supply and fix low flush white vitreous china water closet | No | 8 |  | 10 | 10 | 900 | 7200 | 0 | 9000 | 9000
9.9 | Supply and fix toilet paper holder | No | 9 |  | 10 | 10 | 90 | 810 | 0 | 900 | 900
9.1 | Supply and fix crystal glass mirror of size 500x400mm | No | 8 |  | 19 | 19 | 200 | 1600 | 0 | 3800 | 3800
9.11 | Supply and install shower units made of chrome-plated shower | No | 11 | 7 |  | 7 | 1700 | 18700 | 11900 | 0 | 11900
9.12 | Supply and fix 600mm long towel hanger for showers | No | 7 |  | 7 | 7 | 120 | 840 | 0 | 840 | 840
9.14 | Supply and install electric water heater | No | 7 |  | 7 | 7 | 2000 | 14000 | 0 | 14000 | 14000
9.16 | Supply and fix 50mm diameter floor drain | No | 8 |  | 12 | 12 | 120 | 960 | 0 | 1440 | 1440
9.18 | Supply and fix 100mm 3.2mm thickness down pipes made up of upvc | lm | 60 |  | 67.2 | 67.2 | 90 | 5400 | 0 | 6048 | 6048
9.2 | Supply and fix stainless steel sink chemial resisit with single bowl | No | 2 |  | 3 | 3 | 900 | 1800 | 0 | 2700 | 2700
TOTAL CARRIED TO SUMMARY | [7 empty] | 91300 | 31802 | 50128 | 81930
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | Light points in rigid therimoplastic conduit of 16mmfed by pvc conductor of 3x2.5mm2 | Pcs | 138 | 138 |  | 138 | 200 | 27600 | 27600 | 0 | 27600
3 | Switches LEGRAND, SUNO,
3.01 | Single(774001+774041) | Pcs | 45 |  | 45 | 45 | 75 | 3375 | 0 | 3375 | 3375
3.02 | Double(774005+774042) | Pcs | 20 |  | 20 | 20 | 120 | 2400 | 0 | 2400 | 2400
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit | Pcs | 78 | 78 |  | 78 | 200 | 15600 | 15600 | 0 | 15600
4.2 | Ditto as 4.01 but for water heater points | Pcs | 13 | 13 |  | 13 | 200 | 2600 | 2600 | 0 | 2600
5 | Socket outlet
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | Pcs | 78 | 19 | 59 | 78 | 100 | 7800 | 1900 | 5900 | 7800
5.02 | Weather proof socket Legrand Suno 774022+774041 | Pcs | 13 |  | 13 | 13 | 150 | 1950 | 0 | 1950 | 1950
5.3 | Ditto as above 4.06 but for 25 A/1phf outlet | Pcs | 8 |  | 18 | 18 | 250 | 2000 | 0 | 4500 | 4500
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable from | Pcs | 13 |  | 13 | 13 | 130 | 1690 | 0 | 1690 | 1690
7 | Type of light Fitting with lamp
7.01 | PHILPS TMS 012/136 IMK with 1xTLD 36W | Pcs | 24 | 24 |  | 24 | 450 | 10800 | 10800 | 0 | 10800
7.02 | PHILPS TCS 097/236 IMK with 2xTLD 36W | Pcs | 70 |  | 70 | 70 | 700 | 49000 | 0 | 49000 | 49000
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | Pcs | 19 | 11 | 8 | 19 | 250 | 4750 | 2750 | 2000 | 4750
7.04 | RZB 59222.002 with /rzb 05-56150Q50W lamp or | Pcs | 11 |  | 11
7.5 | MASSIVE 3202/02/67/1XE27/75W | Pcs | 14 |  | 14 | 14 | 275 | 3850 | 0 | 3850 | 3850
8 | TV Points
8.01 | TV Points fed through RG6 Coaxial 75 ohm TV | Pc | 1 |  | 1 | 1 | 130 | 130 | 0 | 130 | 130
11 | Low Voltage Earthing system
11.01 | Copper Earthing rod of 16x2400mm | Pcs | 2 |  | 2 | 2 | 2000 | 4000 | 0 | 4000 | 4000
11.02 | Copper conductor of 1x16mm2 for Earthing | ml | 35 |  | 37.2 | 37.2 | 120 | 4200 | 0 | 4464 | 4464
11.03 | Cooper conductor of 1x6mm2 for Earthing | ml | 25 |  | 28.3 | 28.3 | 105 | 2625 | 0 | 2971.5 | 2971.5
TOTAL CARRIED TO SUMMARY | [7 empty] | 144370 | 61250 | 86230.5 | 147480.5

## TOS OR (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :-OR and delivery
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4. Carpentry And joinery |  |  |  | 6.5 8mm Thick ceramic tile floor
2 | 45.15 | 90.3 | 4.2 25x 2.5, fascial Board | 1 | 4.5 |  | Doctors Office
5.85
2 | 17.9 | 35.8 |  |  |  | 26.33
|  | 126.1 | Ml Total of item no 4.2 | 1 | 0.9
|  |  | 6. Finishing works |  | 0.2
|  |  | 6.3 4 mm Thick Plastic celing |  |  | 0.18
1 | 4.45 |  | corrider |  |  | 26.51 | M2 Sub Total
| 2.4 |  |  | 1 | 5.7 |  | Wating Area
|  | 10.68 |  |  | 5.85
1 | 2 |  |  |  |  | 33.35
| 2.4 |  |  | 1 | 2.25
|  | 4.8 |  |  | 0.2
1 | 3.45 |  |  |  |  | 0.45
| 2.4 |  |  | 1 | 1.4
|  | 8.28 |  |  | 0.25
2 | 5.7 |  |  |  |  | 0.35
| 2.4 |  |  |  |  | 34.15 | M2 Sub Total
|  | 27.36 |  | 1 | 2.9 |  | Changining Room
1 | 2.1 |  |  |  | 5.85
| 2.4 |  |  |  |  | 16.97
|  | 5.04 |  | 2 | 0.9
1 | 2.45 |  |  |  | 0.25
| 2.4 |  |  |  |  | 0.45
|  | 5.88 |  |  |  | 17.42 | M2 Sub Total
1 | 4.92 |  |  | 1 | 2.6 |  | Nurese Station | 218.38
| 4.85 |  |  |  | 5.85
|  | 23.86 |  |  |  | 15.21
1 | 4.05 |  |  | 1 | 0.9
| 2.4 |  |  |  | 0.25
|  | 9.72 |  |  |  | 0.23
|  | 95.62 | M2 Sub Total |  |  | 15.44 | M2 Sub Total
1 | 5.85 |  | Doctors office | 1 | 5.8 |  | Postnatal Room
| 4.45 |  |  |  | 5.85
|  | 26.03 | M2 Sub Total |  |  | 33.93
1 | 5.85 |  | Wating Area | 1 | 1.4
| 5.75 |  |  |  | 0.25
|  | 33.64 | M2 Sub Total |  |  | 0.35
1 | 5.85 |  | Changing Room |  |  | 34.28 | M2 Sub Total
| 2.9 |  |  | 1 | 2.1 |  | Clean Supply
|  | 16.97 | M2 Sub Total |  | 5.85
1 | 5.85 |  | Nurse Station |  |  | 12.29
| 2.65 |  |  | 1 | 0.9
|  | 15.5 | M2 Sub Total |  | 0.2
1 | 5.85 |  | Postnatal Room |  |  | 0.18
| 5.8 |  |  |  |  | 12.47 | M2 Sub Total
|  | 33.93 | M2 Sub Total | 1 | 3.45 |  | Anesthesian room
1 | 5.85 |  | Clean Supply |  | 5.85
| 2.1 |  |  |  |  | 20.18
|  | 12.29 | M2 Sub Total | 1 | 0.9
1 | 5.85 |  | Anstahesian Room |  | 0.2
| 3.45 |  |  |  |  | 0.18
|  | 20.18 | M2 Sub Total |  |  | 20.36 | M2 Sub Total
1 | 4.45 |  | Auto crave room | 1 | 2.45 |  | Preparation/Admission
| 3.55 |  |  |  | 2.3
|  | 15.8 | M2 Sub Total |  |  | 5.64
|  | 269.96 | Ml Total of item no 6.3
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :-OR and delivery
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 0.9 |  |  | 1 | 3.5
| 0.2 |  |  |  | 3.5
|  | 0.18 |  |  |  | 12.25
|  | 5.82 | M2 Sub Total | 1 | 0.9
1 | 4.45 |  | Instroment Room |  | 0.2
| 2.4 |  |  |  |  | 0.18
|  | 10.68 |  |  |  | 28.24 | M2 Sub Total
1 | 0.8 |  |  | 1 | 7.25 |  | Laboring Room
| 0.2 |  |  |  | 4.85
|  | 0.16 |  |  |  | 35.16
1 | 0.9 |  |  | 1 | 0.9
| 0.25 |  |  |  | 0.25
|  | 0.23 |  |  |  | 0.23
|  | 11.07 | M2 Sub Total | 1 | 1.4
1 | 4.45 |  | Store |  | 0.25
| 3.25 |  |  |  |  | 0.35
|  | 14.46 |  |  |  | 35.74 | M2 Sub Total
1 | 0.9 |  |  | 1 | 2.3 |  | Corridor
| 0.25 |  |  |  | 4.15
|  | 0.23 |  |  |  | 9.55 | M2 Sub Total
|  | 14.69 | M2 Sub Total | 1 | 7.25 |  | Utility Room
4 | 1.4 |  | Corridor |  | 3.35
| 0.25 |  |  |  |  | 24.29
|  | 1.4 |  | 1 | 1.4
1 | 17 |  |  |  | 0.25
| 2.45 |  |  |  |  | 0.35
|  | 41.65 |  |  |  | 24.64 | M2 Sub Total
1 | 17.85 |  |  | 1 | 7.25 |  | OR-Room
| 2.45 |  |  |  | 5
|  | 43.73 |  |  |  | 36.25
1 | 6.75 |  |  | 1 | 1.4
| 2.45 |  |  |  | 0.25
|  | 16.54 |  |  |  | 0.35
|  | 103.32 | M2 Sub Total |  |  | 36.6 | M2 Sub Total
1 | 4.45 |  | Disinfection /Washing | 1 | 4.85 |  | Recovery
| 3.5 |  |  |  | 4.9
|  | 15.58 |  |  |  | 23.77
1 | 1.3 |  |  | 1 | 1.4
| 0.2 |  |  |  | 0.25
|  | 0.26 |  |  |  | 0.35
1 | 0.9 |  |  | 1 | 2.15
| 0.25 |  |  |  | 2.3
|  | 0.23 |  |  |  | 4.95
|  | 16.07 | M2 Sub Total |  |  | 29.07 | M2 Sub Total
1 | 3.45 |  | Storing/Receving |  |  | 487.75 | Ml Total of item no 6.5
| 3.5 |  |  | 2 | 46.15 |  | 6.9 Pavement 1.2m
|  | 12.08 |  |  | 1.2
1 | 0.9 |  |  |  |  | 110.76
| 0.25 |  |  | 2 | 16.5
|  | 0.23 |  | . | 1.2
|  | 12.31 | M2 Sub Total |  |  | 39.6
1 | 3.5 |  | Auto clave room |  |  | 150.36 | M2 Total of item no6.9
4.45
15.58
1 | 0.9
0.25
0.23
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :-OR and delivery
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 3
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. Sub-structure
1) Excavation & Earth Work
1.6 Cart away
1.6 Cart away
1 | 888.17 |  | Site clerance
| 0.3 | 266.45 | 0
|  | 870.4 | Bulk excavation
|  | 240.4 | Trench excavation
|  | 1377.25 | m3 Total 1.6
|  | 1377.25 | Previous payment
|  | 0 | m3 Total 1.6 Remaining

## OR TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION | [6 empty] | Block: - OR & Delivery
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE | 1 | 1.5 |  | W12
|  |  | 1. CONCRETE WORKS |  | 0.75 | 1.13
1.1. Reinforced concrete class C-25
|  |  | c) Lintel |  |  | 25.96 | m2 net area item 1.2.c
1 | 1.3 |  | D1
| 0.15 | [5 empty] | 1.3. Reinforcement steel bars
| 0.3 | 0.06 |  |  |  |  | b. ф12 mm deformed bars
|  |  |  | 1 | 65.81
3 | 1.2 |  | D2 |  |  | 65.81 | kg net wight item 1.3.b
0.15
| 0.3 | 0.16 |  | 1 | 133.2 |  | c. ф8 mm deformed bars
[6 empty] | 133.2 | kg net wight item 1.3.c
14 | 1.1 |  | D3
| 0.15 | [5 empty] | 4.CARPENTRY & JOINERY
| 0.3 | 0.69 |  |  |  |  | 4.3. Wood framed door
b) Doors Type D3 size -70/270cm
2 | 1.3 |  | D5 | 1 | 8
| 0.15 |  |  |  |  | 8 | Pcs net number item 4.2.b
| 0.3 | 0.12
d) Doors Type D2 size -80/270cm
4 | 1.2 |  | D17 | 1 | 1
| 0.15 |  |  |  |  | 1 | Pcs net number item 4.2.b
| 0.3 | 0.22
f) Type D6s size -140/270cm
3 | 1.8 |  | D6s | 1 | 7
| 0.15 |  |  |  |  | 7 | Pcs net number item 4.2.f
| 0.3 | 0.24
g) Type D7 size-80/210cm
1 | 1.5 |  | W12 | 1 | 10
| 0.15 |  |  |  |  | 10 | Pcs net number item 4.2.g
| 0.3 | 0.07
h) Type D1 size 90*270cm
|  | 1.56 | m3 net area item 1.1.c | 1 | 14
[6 empty] | 14 | Pcs net number item 4.2.g
1.2. form work or metal panel. To:-
|  |  | c) Lintel |  |  |  | i) Type D6 size 130/210
1 | 1.3 |  | D1 | 1 | 2
| 0.75 | 0.98 |  |  |  | 2 | Pcs net number item 4.2.i
3 | 1.2 |  | D2 |  |  |  | j) Type D5 size 100/210
| 0.75 | 2.7 |  | 1 | 2
[6 empty] | 2 | Pcs net number item 4.2.j
14 | 1.1 |  | D3
| 0.75 | 11.55 |  |  |  |  | 6. FINISHING
6.4.a. 200x300x6mm Glazed Ceramic Wall
2 | 1.3 |  | D5 | 2 | 2.55 |  | Toilet Haddi Cap
| 0.75 | 1.95 |  |  | 1.5 | 7.65
4 | 1.2 |  | D17 | 1 | 2 |  | "
| 0.75 | 3.6 |  |  | 1.5 | 3
3 | 1.8 |  | D6s | 1 | 1 |  | "
| 0.75 | 4.05 |  |  | 1.5 | 1.5
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 1.8 |  | Toilet Male | 8 | 1.3 |  | "
| 1.5 | 2.7 |  |  | 1.5 | 15.6
2 | 1.3 |  | " | 2 | 1 |  | "
| 1.5 | 3.9 |  |  | 1.5 | 3
1 | 0.6 |  | " | 2 | 1.15 |  | "
| 1.8 | 1.08 |  |  | 1.5 | 3.45
1 | 1.26 |  | " | 1 | 1.4 |  | Nurse Station
| 1.8 | 2.27 |  |  | 1.2 | 1.68
2 | 1.2 |  | " | 1 | 3.5 |  | Disinfection Room
| 1.8 | 4.32 |  |  | 1.5 | 5.25
2 | 1.2 |  | " | 1 | 5.3 |  | Toilet B/n axis Y/03-Y/05
| 1.5 | 3.6 |  |  | 1.5 | 7.95
1 | 1.3 |  | " | 4 | 1.4 |  | "
| 1.5 | 1.95 |  |  | 1.8 | 10.08
1 | 0.6 |  | " | 1 | 1.4 |  | "
| 1.5 | 0.9 |  |  | 1.8 | 2.52
1 | 1.2 |  | " | 1 | 1.25 |  | "
| 1.5 | 1.8 |  |  | 1.8 | 2.25
2 | 1.3 |  | Toilet Female | 4 | 0.7 |  | "
| 1.5 | 3.9 |  |  | 0.8 | 2.24
1 | 1.8 |  | " | 4 | 1.5 |  | "
| 1.5 | 2.7 |  |  | 1.4 | 8.4
2 | 1.5 |  | " | 1 | 1.2 |  | "
| 1.2 | 3.6 |  |  | 1.5 | 1.8
1 | 1.19 |  | " | 1 | 1.15 |  | "
| 1.5 | 1.79 |  |  | 1.5 | 1.73
1 | 0.5 |  | " | 2 | 0.5 |  | "
| 1.5 | 0.75 |  |  | 1.5 | 1.5
"
3 | 1.2 |  | Ditto Above Shower Room | 1 | 1.05
| 1.8 | 6.48 |  |  | 1.5 | 1.58
1 | 0.5 |  | " | 1 | 2.95 |  | Hadi Cap Toilet
| 1.8 | 0.9 |  |  | 1.5 | 4.43
4 | 1.3 |  | Toilet Staff & Gentes | 1 | 1.95 |  | "
| 1.8 | 9.36 |  |  | 1.5 | 2.93
2 | 1.2 |  | " | 2 | 2.05 |  | "
| 1.8 | 4.32 |  |  | 1.5 | 6.15
2 | 0.5 |  | " | 2 | 3.55 |  | "
| 1.8 | 1.8 |  |  | 1.8 | 12.78
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 2.35 |  | " | 1 | 6.35 |  | "
| 1.8 | 4.23 |  |  | 2.7 | 17.15
1 | 1.35 |  | " |  |  | 307.88 | m2 Total area
| 1.8 | 2.43
[6 empty] | 250 | Previous Payment
1 | 3.1 |  | Utility Room
| 1.5 | 4.65 |  |  |  | 57.88 | m2 net area item 6.4
4 | 1.55 |  | Scurb Up |  |  |  | 6.6)Approved type 10/0.9mm skirting
| 1.5 | 9.3 |  |  | 15.2 |  | Disinfection washing
[6 empty] | 15.2 | L=3.5*2+5*2-1.3-0.9=14.80mt
2 | 1.8 |  | " |  | 15.4 |  | Auto clave
| 1.5 | 5.4 |  |  |  | 15.4 | L=3.6*2+5*2-1.3-0.9=15.00mt
[5 empty] | 11.4 |  | Sorting
1 | 2.5 |  | Sterile Room |  |  | 11.4 | L=3.5*2+3.1*2-0.9*2=11.4mt
| 1.5 | 3.75 |  |  | 11.6 |  | Clean supply
[6 empty] | 11.6 | L=3.6*2+3.1*2-0.9*2=11.60mt
1 | 7.25 |  | OR Room |  | 8.2 |  | "
| 2.7 | 19.58 |  |  |  | 8.2 | L=3.6*2+1.8*2-0.8-0.9X2=8.20mt
[5 empty] | 22.7 |  | Labouring
1 | 5 |  | " |  |  | 22.7 | L=7.25*2+5.25*2-0.9-1.4=22.70mt
| 2.7 | 13.5 |  |  | 9.5 |  | Utility room
[6 empty] | 9.5 | L=3.10*2+2.5*2-0.80-0.90=9.5mt
1 | 2.05 |  | " |  | 8.2 |  | Slice room
| 2.7 | 5.54 |  |  |  | 8.2 | L=2.5*2+2.85*2-0.8*2-0.90=8.20mt
[5 empty] | 9.6 |  | Sterile
1 | 1.17 |  | " |  |  | 9.6 | L=2.5*2+2.70*2-0.80=9.60mt
| 2.7 | 3.16 |  |  | 18.4 |  | Recovery room
[6 empty] | 18.4 | L=4.95*4-1.4=18.40mt
1 | 1.2 |  | " |  | 4.9 |  | Enterance
| 1 | 1.2 |  |  |  | 4.9 | L=2.15*2+2-1.4=4.90mt
[5 empty] | 7.1 |  | Nurse station
1 | 2.03 |  | " |  |  | 7.1 | L=2.15*2+2.80=7.10mt
| 2.7 | 5.48 |  |  | 13.8 |  | Corridor
[6 empty] | 13.8 | L=7.45*2+1.4-0.8*2-0.9=13.80mt
1 | 2.15 |  | " |  | 15.84 |  | Corridor Office
| 2.7 | 5.81 |  |  |  | 15.84 | L=7.02*2+2,5*2-1.4-.9*2=15.84mt
[5 empty] | 19.9 |  | Doctor's office
1 | 1.4 |  | " |  |  | 19.9 | L=5.9*2+4.5*2-0.90=19.90mt
| 2.7 | 3.78 |  |  | 20.37 |  | Wating area
[6 empty] | 20.37 | L=5.90+6.05+5.85+2.57=20.37mt
1 | 4.9 |  | Delivery Room |  | 9.2 |  | Changing room
| 2.7 | 13.23 |  |  |  | 9.2 | L=3.05*2+2.45*2-0.9*2=9.20mt
[5 empty] | 10.9 |  | Preparation room
1 | 1.05 |  | " |  |  | 10.9 | L=3.05*2+3.3*2-0.9*2=10.90mt
| 2.7 | 2.84 |  |  | 16.3 |  | Nurse station
[6 empty] | 16.3 | L=2.7*2+5.9*2-0.90=16.30mt
2 | 1.5 |  | " |  | 22 |  | Postnatal room
| 1.1 | 3.3 |  |  |  | 22 | L=5.90*2+5.80*2-1.40=22.00mt
[5 empty] | 15.3 |  | Clean supply
2 | 0.4 |  | " |  |  | 15.3 | L=2.25*2+585*2-0.90=15.30mt
| 2.7 | 2.16 |  |  | 14.4
[6 empty] | 14.4 | L=5.85*2+2.3*2+.6*2-.7*2-.9-.8=14.40mt
1 | 5.85 |  | "
| 2.7 | 15.8
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 17.7 |  | Ansthesian room |  |  |  | 9.20. Stainless steel sink Size 1200*600mm
|  | 17.7 | L=3.45*2+5.85*2-0.90=17.70mt | 1 | 3
| 4.4 |  |  |  |  | 3 | Pcs net number item 9.10
|  | 4.4 | L=1.25*2+2.2*2-0.8*2-0.9=4.40mt
| 12.9 |  | Changing room |  |  |  | 10. ELECTRICAL INSTALLATION
|  | 12.9 | L=3.65*2+3.25*2-0.90=12.90mt |  |  |  | 3.00. Switches LEGRAND, SUNO,
| 10.8 |  | Preparation/ admission room |  |  |  | 3.01. Single(774001+774041)
|  | 10.8 | L=3.65*2+2.40*2-1.20=10.90mt | 1 | 45
| 11.4 |  | Instrument room |  |  | 45 | Pcs net number item 3.01
|  | 11.4 | L=3.35*2+3.25*2-0.90*2=11.40mt
| 10.6 |  | Store |  |  |  | 3.02. Double(774005+774042)
|  | 10.6 | L=3.35*2+2.4*2-0.90=10.60mt | 1 | 20
| 23.08 |  | Corridor |  |  | 20 | Pcs net number item 3.02
|  | 23.08 | L=12+2.5*2+12.28-2.5-.90-1.4*2=23.08ml
| 28 |  | " |  |  |  | 5.00. Socket outlet
|  | 28 | L=19.7*2+2.5*2+0.5*2-2.5-2-2.8- |  |  |  | 5.01. Socket outlet LEGRAND SUNO 774023 16 1ph
|  |  | 1.4-1.4*3-0.90*5=28.00mt | 1 | 59
[6 empty] | 59 | Pcs net number item 5.01
|  | 419.09 | m Total length
5.02. Weather proof socket Legrand Suno 774022+774041
|  | 215.34 | Previous Payment | 1 | 13
[6 empty] | 13 | Pcs net number item 5.02
|  | 203.75 | m net length item 6.6
5.03. Ditto as above 4.06 but for 25 A/1phf outlet
|  |  | 9. SANITARY INSTALLATION | 1 | 18
|  |  | 9.6. Hand wash basin |  |  | 18 | Pcs net number item 5.03
1 | 19
|  | 19 | Pcs net number item 9.6 |  |  |  | 6.00. Telephone/Data points
6.01. Telephone points fed through cat 5E UTP cable
|  |  | 9.7. Water closet | 1 | 13
1 | 10 |  |  |  |  | 13 | Pcs net number item 6.01
|  | 10 | Pcs net number item 9.7
7.00. Type of light Fitting with lamp
|  |  | 9.9. Toilet paper holder |  |  |  | 7.02. PHILPS TMS 012/236 IMK with 2xTLD 36W
1 | 10 |  |  | 1 | 70
|  | 10 | Pcs net number item 9.9 |  |  | 70 | Pcs net number item 7.02
|  |  | 9.10. Crystal glass mirror |  |  |  | 7.03. RZB 59251.002 with RZB 05-56150Q50W
1 | 19 |  |  | 1 | 8
|  | 19 | Pcs net number item 9.10 |  |  | 8 | Pcs net number item 7.03
|  |  | 9.12. Towel hanger |  |  |  | 7.04. RZB 59222.002 with RZB 05-56150Q50W
1 | 7 |  |  | 1 | 11
|  | 7 | Pcs net number item 9.12 |  |  | 11 | Pcs net number item 7.04
|  |  | 9.14. Electric water heater |  |  |  | 7.05. MASSIVE 3202/02/67/1XE27/75W
1 | 7 |  |  | 1 | 14
|  | 7 | Pcs net number item 9.14 |  |  | 14 | Pcs net number item 7.05
|  |  | 9.16. 50mm diameter floor drain |  |  |  | 8.00. TV Points
1 | 12 | [5 empty] | 8.01. TV Points fed through RG6 Coaxial 75 ohm TV cable
|  | 12 | Pcs net number item 9.10 | 1 | 1
[6 empty] | 1 | Pcs net number item 8.01
9.18. 100mm Down pipes
1 | 67.2
|  | 67.2 | m net length item 9.18
T | D | S | Item No. and Description | T | D | S | Item No. and Description
11.00. Low Voltage Earthing system
11.01. Copper Earthing rod of 16x2400mm
1 | 2
|  | 2 | Pcs net number item 11.01
11.02. Copper conductor of 1x16mm2 for Earthing
1 | 37.2
|  | 37.2 | m net length item 11.02
11.03. Copper conductor of 1x6mm2 for Earthing
1 | 28.3
|  | 28.3 | m net length item 11.03

## OR Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - OR & Delivery
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D1 |  | 12 | 1.75 | 1 | 2 | 2 |  |  |  | 3.5
|  |  | 12 | 1.25 | 1 | 2 | 2 | - | - | - | 2.5 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
| D2 |  | 12 | 1.65 | 3 | 2 | 6 | - | - | - | 9.9 | -
|  |  | 12 | 1.15 | 3 | 2 | 6 | - | - | - | 6.9 | -
| Stirrups |  | 8 | 0.85 | 3 | 7 | 21 | - | 17.85 | - | - | -
| D3 |  | 12 | 1.55 | 14 | 2 | 28 | - | - | - | 43.4 | -
|  |  | 12 | 1.05 | 14 | 2 | 28 | - | - | - | 29.4 | -
| Stirrups |  | 8 | 0.85 | 14 | 7 | 98 | - | 83.3 | - | - | -
| D5 |  | 12 | 1.4 | 2 | 2 | 4 | - | - | - | 5.6 | -
|  |  | 12 | 0.95 | 2 | 2 | 4 | - | - | - | 3.8 | -
| Stirrups |  | 8 | 0.85 | 2 | 7 | 14 | - | 11.9 | - | - | -
| D17 |  | 12 | 1.6 | 4 | 2 | 8 | - | - | - | 12.8 | -
|  |  | 12 | 0.95 | 4 | 2 | 8 | - | - | - | 7.6 | -
| Stirrups |  | 8 | 0.85 | 4 | 7 | 28 | - | 23.8 | - | - | -
| D6s |  | 12 | 2.2 | 3 | 2 | 6 | - | - | - | 13.2 | -
|  |  | 12 | 0.95 | 3 | 2 | 6 | - | - | - | 5.7 | -
| Stirrups |  | 8 | 0.85 | 3 | 7 | 21 | - | 17.85 | - | - | -
| W12 |  | 12 | 1.9 | 1 | 2 | 2 | - | - | - | 3.8 | -
|  |  | 12 | 0.95 | 1 | 2 | 2 | - | - | - | 1.9 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
TOTAL LENGTH | [8 empty] | 166.6 | 0 | 150 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 65.81 | 0 | 133.2 | 0

## Emer Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
SUMMARY OF STATEMENT for EMERGENCY - NO 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 111999 | 109695.66 | 0 | 109695.66
2 | CONCRETE WORKS | 224700 | 250577.28 | 0 | 250577.28
3 | MASONARY WORKS | 396562 | 77150 | 0 | 77150
TOTAL A |  | 733261 | 437422.94 | 0 | 437422.94
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 184749 | 121285.64 | 3188.35 | 124473.99
2 | BLOCK WORK | 163800 | 104451.2 | 0 | 104451.2
3 | ROOFING | 117830 | 94373.7 | 0 | 94373.7
4 | CARPENTRY & JOINERY | 105832.7 | 101499.96 | 17955 | 119454.96
5 | METAL WORKS | 57941 | 60632 | 0 | 60632
6 | FINISHING | 395298.7 | 294861 | 18295 | 313156
7 | PAINTING | 43521.66 | 14207.18 | 0 | 14207.18
8 | GLAZING WORK | 21390 | 4752 | 0 | 4752
9 | SANITARY INSTALLATION | 67255 | 9345 | 20646 | 29991
10 | ELECTRICAL INSTALLATION | 85420 | 21800 | 43681 | 65481
TOTAL B |  | 1243038.06 | 827207.68 | 103765.35 | 930973.03
TOTAL A+ B |  | 1976299.06 | 1264630.62 | 103765.35 | 1368395.97

## Emer Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for Emergency - No - 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 501.2 | 377.41 |  | 377.41 | 6 | 3007.2 | 2264.46 | 0 | 2264.46
1.2 | Bulk Excavation | M3 | 136.68 | 539.69 |  | 539.69 | 50 | 6834 | 26984.5 | 0 | 26984.5
1.4 | Trench Excavation | M3 | 108 | 72.41 |  | 72.41 | 40 | 4320 | 2896.4 | 0 | 2896.4
1.5 | Selected backfill material | M3 | 318 | 38.67 |  | 38.67 | 100 | 31800 | 3867 | 0 | 3867
1.6 | Cart away surplus excavated material | M3 | 395 | 725.32 |  | 725.32 | 70 | 27650 | 50772.4 | 0 | 50772.4
1.7 | 25cm thick stone hard core | M2 | 278.68 | 269.54 |  | 269.54 | 85 | 23687.8 | 22910.9 | 0 | 22910.9
TOTAL CARRIED TO SUMMARY | [7 empty] | 97299 | 109695.66 | 0 | 109695.66
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class C-7
| a) massonary foundation | M2 | 83 | 77.15 |  | 77.15 | 100 | 8300 | 7715 | 0 | 7715
2.2 | 10cm thick reinforced concrete floor slab | M2 | 278.68 | 269.54 |  | 269.54 | 350 | 97538 | 94339 | 0 | 94339
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 28 | 16.08 |  | 16.08 | 2900 | 81200 | 46632 | 0 | 46632
2.4 | form work or metal panel To:-
| a) In grade beam & step | M2 | 168.8 | 126.12 |  | 126.12 | 120 | 20256 | 15134.4 | 0 | 15134.4
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 2234 | 1290.41 |  | 1290.41 | 38 | 84892 | 49035.58 | 0 | 49035.58
| c) Dia. 8 mm deformed bar | Kg | 2542 | 888.85 |  | 888.85 | 38 | 96596 | 33776.3 | 0 | 33776.3
2.6 | 10/2 cm chip wood expansion joint | m | 380 | 263 |  | 263 | 15 | 5700 | 3945 | 0 | 3945
TOTAL CARRIED TO SUMMARY | [7 empty] | 394482 | 250577.28 | 0 | 250577.28
3. Masonry Work
3.1 | Stone masonry BNGL | M3 | 107 | 77.15 |  | 77.15 | 1000 | 107000 | 77150 | 0 | 77150
3.2 | Ditto but ANGL | M3 | 107 | 0 |  | 0 | 1100 | 117700 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 224700 | 77150 | 0 | 77150
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 4.32 | 3.02 |  | 3.02 | 2900 | 12528 | 8758 | 0 | 8758
| b) In beams | M3 | 12 | 9.73 |  | 9.73 | 2900 | 34800 | 28217 | 0 | 28217
| c) In lintel | M3 | 1.29 | 0 | 0.33 | 0.33 | 2901 | 3742.29 | 0 | 957.33 | 957.33
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 96 | 60.48 |  | 60.48 | 100 | 9600 | 6048 | 0 | 6048
| b) In beams | M2 | 194 | 127.4 |  | 127.4 | 100 | 19400 | 12740 | 0 | 12740
| c) Lintel | M2 | 18 | 0 | 5.48 | 5.48 | 100 | 1800 | 0 | 548 | 548
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 1420 | 1313.8 | 14.1 | 1327.9 | 38 | 53960 | 49924.4 | 535.8 | 50460.2
| c) Dia. 8 mm deformed bar | Kg | 1290 | 410.48 | 30.19 | 440.67 | 38 | 49020 | 15598.24 | 1147.22 | 16745.46
| d) Dia. 6 mm deformed bar | Kg | 38 |  |  |  |  | 0 |  | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 184850.29 | 121285.64 | 3188.35 | 124473.99
2. BLOCK WORK
Concrete block wall class "B"
| a) 20 cm thick | M2 | 420 | 156.59 |  | 156.59 | 320 | 134400 | 50108.8 | 0 | 50108.8
| b) 15 cm thick | M2 | 105 | 194.08 |  | 194.08 | 280 | 29400 | 54342.4 | 0 | 54342.4
TOTAL CARRIED TO SUMMARY | [7 empty] | 163800 | 104451.2 | 0 | 104451.2
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 198 | 350.62 |  | 350.62 | 230 | 45540 | 80642.6 | 0 | 80642.6
3.2 | G-30 ribbed sheet ceiling under eave | M2 | 77 | 50.47 |  | 50.47 | 130 | 10010 | 6561.1 | 0 | 6561.1
3.4 | G-30 flat metal sheet gutter | m | 134 | 71.7 |  | 71.7 | 100 | 13400 | 7170 | 0 | 7170
TOTAL CARRIED TO SUMMARY | [7 empty] | 68950 | 94373.7 | 0 | 94373.7
4.CARPENTRY & JOINERY
4.1 | carpentry swan eucalyptus truss
| a) diameter 10 -12cm | m | 366 | 544.64 |  | 544.64 | 22 | 8052 | 11982.08 | 0 | 11982.08
| b) diameter 8 - 10cm | m | 77 | 408.48 |  | 408.48 | 15 | 1155 | 6127.2 | 0 | 6127.2
| c) Purlin zigba size 5/7cm | m | 128 | 454.24 |  | 454.24 | 32 | 4096 | 14535.68 | 0 | 14535.68
4.2 | wooden fascia board price includes | m | 134 | 74.9 |  | 74.9 | 70 | 9380 | 5243 | 0 | 5243
4.3 | Supply 40mm thick wood framed door
| a) Type D1 size-90/270cm | No | 8 | 8 |  | 8 | 4617 | 36936 | 36936 | 0 | 36936
| b) Type D2 size -80/270cm | No | 2 | 2 |  | 2 | 4104 | 8208 | 8208 | 0 | 8208
| c) Type D3s size -70/270cm | No | 0 | 0 | 5 | 5 | 3591 | 0 | 0 | 17955 | 17955
| d) Type D7s size -120/270cm | No | 2 | 3 |  | 3 | 6156 | 12312 | 18468 | 0 | 18468
TOTAL CARRIED TO SUMMARY | [7 empty] | 80139 | 101499.96 | 17955 | 119454.96
5.METAL WORKS
5.1 | Windows
| a) W1- 1.20/1.60cm | no | 3 | 2 |  | 2 | 2496 | 7488 | 4992 | 0 | 4992
| b) W3- 1.50/1.60cm | no | 9 | 9 |  | 9 | 3120 | 28080 | 28080 | 0 | 28080
| c) W1T - 1.25/0.60cm | no | 1 | 2 |  | 2 | 975 | 975 | 1950 | 0 | 1950
| d) W3T - 1.50/60cm | no | 1 | 1 |  | 1 | 1170 | 1170 | 1170 | 0 | 1170
| e) W7- 1.00/1.60cm | no | 2 | 2 |  | 2 | 2080 | 4160 | 4160 | 0 | 4160
| f) W9T - 4.25/60cm | no | 1 | 1 |  | 1 | 1326 | 1326 | 1326 | 0 | 1326
5.2 | Doors
| a) D4 - 1.50/2.70cm | no | 2 | 2 |  | 2 | 5265 | 10530 | 10530 | 0 | 10530
| b) D7 - 1.20/2.70cm | no | 1 | 2 |  | 2 | 4212 | 4212 | 8424 | 0 | 8424
TOTAL CARRIED TO SUMMARY | [7 empty] | 57941 | 60632 | 0 | 60632
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | M2 | 241 | 156.43 |  | 156.43 | 90 | 21690 | 14078.7 | 0 | 14078.7
6.2 | Apply three coats of plastering | M2 | 852 | 779.99 |  | 779.99 | 100 | 85200 | 77999 | 0 | 77999
6.3 | 4mm thick best type plastic ceiling | M2 | 292.31 | 224.46 |  | 224.46 | 270 | 78923.7 | 60604.2 | 0 | 60604.2
6.4 | 200*300*6mm glazed ceramic wall tile | M2 | 71 | 81.53 |  | 81.53 | 290 | 20590 | 23643.7 | 0 | 23643.7
6.5 | 8mm thick non slippery ceramic | M2 | 347 | 241.95 |  | 241.95 | 300 | 104100 | 72585 | 0 | 72585
6.6 | Ceramic tile Skiring 10/0.8cm | ml | 378 | 0 | 182.95 | 182.95 | 100 | 37800 | 0 | 18295 | 18295
6.7 | Terrazo Window cill bedded on | ml | 31.2 | 24.55 |  | 24.55 | 150 | 10950 | 3682.5 | 0 | 3682.5
6.8 | 30/30/3mm angle iron corner protection | M2 | 4.5 | 107.55 |  | 107.55 | 70 | 252 | 7528.5 | 0 | 7528.5
6.8 | 10cm thick c-20 RC 1.2m wide pavement | M2 | 68.4 | 88.92 |  | 88.92 | 320 | 21888 | 28454.4 | 0 | 28454.4
6.1 | Concret pipes of half diameter 30cm | ml | 80 | 62.85 |  | 62.85 | 100 | 8000 | 6285 | 0 | 6285
6.11 | 10X40cm curb stone around the building | ml | 80 |  |  | 0 |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 389393.7 | 294861 | 18295 | 313156
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 895.85 | 390 |  | 390 | 26 | 23292.1 | 10140 | 0 | 10140
7.2 | Ditto but oil paint to a height of 1.5m | M2 | 537.51 | 0 |  | 0 | 26 | 13975.26 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 240.55 | 156.43 |  | 156.43 | 26 | 6254.3 | 4067.18 | 0 | 4067.18
| TOTAL CARRIED TO SUMMARY | [6 empty] | 43521.66 | 14207.18 | 0 | 14207.18
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 10.5 | 21.6 |  | 21.6 | 220 | 2310 | 4752 | 0 | 4752
8.2 | 4mm thick frosted glass | M2 | 53 |  |  | 0 | 360 | 19080 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 21390 | 4752 | 0 | 4752
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 20mm diameter;internal | lm | 10 | 56.2 |  | 56.2 | 75 | 750 | 4215 | 0 | 4215
9.4 | Ditto item above, but chrome plated 15mm water tap | No | 1 | 1 |  | 1 | 180 | 180 | 180 | 0 | 180
9.5 | Supply and install waste water pipes made of rigid plastic pipe (upvc)
| 50mm diameter | lm | 22 | 31.7 |  | 31.7 | 60 | 1320 | 1902 | 0 | 1902
| 100mm diameter | lm | 8 | 25.4 |  | 25.4 | 120 | 960 | 3048 | 0 | 3048
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 12 |  | 8 | 8 | 600 | 7200 | 0 | 4800 | 4800
9.7 | Supply and fix Stainless steel sink chemial resisit with Double bowl | No | 5 |  | 1 | 1 | 550 | 2750 | 0 | 550 | 550
9.8 | Supply and fix low flush white vitreous china water closet | No | 6 |  | 6 | 6 | 900 | 5400 | 0 | 5400 | 5400
9.9 | Supply and fix toilet paper holder made of metal | No | 6 |  | 6 | 6 | 90 | 540 | 0 | 540 | 540
9.1 | Supply and fix crystal glass mirror | No | 12 |  | 8 | 8 | 200 | 2400 | 0 | 1600 | 1600
9.11 | Supply and install shower units | No | 1 |  | 1 | 1 | 1700 | 1700 | 0 | 1700 | 1700
9.12 | Supply and fix 600mm long towel hanger | No | 4 |  | 1 | 1 | 120 | 480 | 0 | 120 | 120
9.14 | Install electric water heater 50 liter capacity | No | 4 |  | 1 | 1 | 2000 | 8000 | 0 | 2000 | 2000
9.16 | Supply and fix 50mm diameter floor drain | No | 15 |  | 4 | 4 | 120 | 1800 | 0 | 480 | 480
9.18 | Supply and fix 100mm 3.2mm thickness down pipes | lm | 102 |  | 38.4 | 38.4 | 90 | 9180 | 0 | 3456 | 3456
TOTAL CARRIED TO SUMMARY | [7 empty] | 42660 | 9345 | 20646 | 29991
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | Light points in rigid therimoplastic conduit of 16mm | Pcs | 68 | 68 |  | 68 | 200 | 13600 | 13600 | 0 | 13600
3 | Switches
3.02 | Double(774005+774042) | Pcs | 14 | 5 |  | 5 | 120 | 1680 | 600 | 0 | 600
3.03 | Two -Way(774006+774041) | Pcs | 4 | 2 |  | 2 | 80 | 320 | 0 | 0 | 0
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit of diameter 16mm | Pcs | 38 | 38 |  | 38 | 200 | 7600 | 7600 | 0 | 7600
5 | Socket outlet
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | Pcs | 38 |  | 38 | 38 | 100 | 3800 | 0 | 3800 | 3800
5.02 | Weather proof socket Legrand Suno 774022+774041 | Pcs | 1 |  | 1 | 1 | 150 | 150 | 0 | 150 | 150
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable from | Pcs | 13 |  | 13 | 13 | 130 | 1690 | 0 | 1690 | 1690
7 | Type of light Fitting with lamp
7.01 | PHILPS TMS 012/136 IMK with 1xTLD 36W | Pcs | 35 |  | 8 | 8 | 450 | 15750 | 0 | 3600 | 3600
7.02 | PHILPS TCS 097/236 IMK with 2xTLD 36W | Pcs | 8 |  | 35 | 35 | 700 | 5600 | 0 | 24500 | 24500
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp | Pcs | 11 |  | 11 | 11 | 250 | 2750 | 0 | 2750 | 2750
7.04 | RZB 59222.002 with /rzb 05-56150Q50W lamp | Pcs | 7 |  | 7 |  | 250 | 1750 | 0 | 1750 | 1750
7.5 | MASSIVE 3202/02/67/1XE27/75W | Pcs | 5 |  | 1 | 1 | 275 | 1375 | 0 | 275 | 275
8 | TV Points
8.01 | TV Points fed through RG6 Coaxial 75 ohm TV | Pcs | 1 |  | 1 | 1 | 130 | 130 | 0 | 130 | 130
11 | Low Voltage Earthing system
11.01 | Copper Earthing rod of 16x2400mm | Pcs | 1 |  | 1 | 1 | 2000 | 2000 | 0 | 2000 | 2000
11.02 | Copper conductor of 1x16mm2 for Earthing | ml | 20 |  | 25.3 | 25.3 | 120 | 2400 | 0 | 3036 | 3036
TOTAL CARRIED TO SUMMARY | [7 empty] | 60595 | 21800 | 43681 | 65481

## TOS EMER (hidden)
TAKE OFF SHEET No8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :-Emergency
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. SUB - STRUCTURE
1.6 cart away
1.6 Cart away surplus excavated material
1 | 377.405 |  | Item 1.1 site clerance
| 0.3 | 113.22
|  | 539.69 | Item 1.2. from Bulk Excavation
|  | 137.2 | Item 1.5. from Trench Excavation
|  | 790.11 | m3 Total 1.6
|  | 725.32 | Previous payment
|  | 64.79 | m3 Total 1.6 Remaining

## Emer TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION | [6 empty] | Block: - Emergency
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | 6. FINISHING
|  |  | 1. CONCRETE WORKS |  |  |  | 6.6)Approved type 10/0.9mm skirting
|  |  | 1.1. Reinforced concrete class C-25 | 1 | 12.1 |  | Emerg. Waiting
|  |  | c) Lintel |  |  | 12.1 | L=4.40*2+1.55+1.75=12.10
1 | 1.6 |  | W9 | 1 | 13 |  | Archive
| 0.15 |  |  |  |  | 13 | L=4X2+2.95X2-0.9=13.00mt
| 0.3 | 0.07 |  | 1 | 12.1 |  | Hmis
[6 empty] | 12.1 | L=4X2+2.95X2-0.9X2=12.10mt
2 | 1.2 |  | D2 | 1 | 12.1 |  | Medical recording
| 0.15 |  |  |  |  | 12.1 | L=4X2+2.95X2-0.9X2=12.10mt
| 0.3 | 0.11 |  | 1 | 16.3 |  | Procedure room
[6 empty] | 16.3 | L=4X2+5.05X2-0.9X2=16.10mt
3 | 1.1 |  | D3 | 1 | 16.5 |  | Staff room
| 0.15 |  |  |  |  | 16.5 | L=4x2+5.05x2-0.9X2=16.30mt
| 0.3 | 0.15 |  | 1 | 36.65 |  | Corridor
[6 empty] | 36.65 | L=22.9*2+2.4*2-2.95-1.4*2-
|  | 0.33 | m3 net area item 1.1.c |  |  |  | 1.2*2-1*4-0.9*2=36.65mt
|  |  |  | 1 | 18.8 |  | Emergence triage examination
|  |  | 1.2. form work or metal panel. To:- |  |  | 18.8 | L=4.20x2+5.80x2-1.2=18.80mt
|  |  | c) Lintel | 1 | 21.7 |  | Observation room
1 | 1.6 |  | W9 |  |  | 21.7 | L=4.20x2+7.25x2-1.2=21.70mt
| 0.75 | 1.2 |  | 2 | 3.4 |  | Toilet
[6 empty] | 6.8 | L=1.4x2+1.2x2-1-0.8=3.40mt
2 | 1.2 |  | D2 | 1 | 3.7 |  | Toilet
| 0.75 | 1.8 |  |  |  | 3.7 | L=1.45x2+1.20x2-1-0.7-0.8=2.804mt
|  |  |  | 1 | 12 |  | Duty room
3 | 1.1 |  | D3 |  |  | 12 | L=2.2x2+4.2x2-0.80=12mt
| 0.75 | 2.48 |  | 4 | 0.15 |  | D1
0.6
|  | 5.48 | m2 net area item 1.2.c | 4 | 0.15 |  | 233.51
0.6
1.3. Reinforcement steel bars
|  |  | b. ф12 mm deformed bars |  |  | 182.95 | ml net area item 6.6
1 | 14.1
|  | 14.1 | kg net wight item 1.3.b |  |  |  | 9. SANITARY INSTALLATION
9.6. Hand wash basin
1 | 30.19 |  | c. ф8 mm deformed bars | 1 | 8
|  | 30.19 | kg net wight item 1.3.c |  |  | 8 | Pcs net number item 9.6
|  |  | 4.CARPENTRY & JOINERY |  |  |  | 9.7. Stainless steel sink chemial resisit with Double bowl
|  |  | 4.3. Wood framed door | 1 | 1
|  |  | C) Doors Type D3 size -70/270cm |  |  | 1 | Pcs net number item 9.7
1 | 5
|  | 5 | Pcs net number item 4.2.c |  |  |  | 9.8. Water closet
|  |  |  | 1 | 6
[6 empty] | 6 | Pcs net number item 9.8
9.9. Toilet paper holder
|  |  |  | 1 | 6
[6 empty] | 6 | Pcs net number item 9.9
9.10. Crystal glass mirror
|  |  |  | 1 | 8
[6 empty] | 8 | Pcs net number item 9.10
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 9.11. Shower Unit |  |  |  | 10. ELECTRICAL INSTALLATION
1 | 1 | [5 empty] | 5.00. Socket outlet
|  | 1 | Pcs net number item 9.11 |  |  |  | 5.01. Socket outlet LEGRAND SUNO 774023 16 1ph
|  |  |  | 1 | 38
|  |  | 9.12. Towel hanger |  |  | 38 | Pcs net number item 5.01
1 | 1
|  | 1 | Pcs net number item 9.12 |  |  |  | 5.02. Weather proof socket Legrand Suno 774022+774041
|  |  |  | 1 | 1
|  |  | 9.14. Electric water heater |  |  | 1 | Pcs net number item 5.02
1 | 1
|  | 1 | Pcs net number item 9.14 |  |  |  | 6.00. Telephone/Data points
6.01. Telephone points fed through cat 5E UTP cable
|  |  | 9.16. 50mm diameter floor drain | 1 | 13
1 | 4 |  |  |  |  | 13 | Pcs net number item 6.01
|  | 4 | Pcs net number item 9.10
7.00. Type of light Fitting with lamp
|  |  | 9.18. 100mm Down pipes |  |  |  | 7.01. PHILPS TMS 012/136 IMK with 1xTLD 36W
1 | 38.4 |  |  | 1 | 8
|  | 38.4 | m net length item 9.18 |  |  | 8 | Pcs net number item 7.01
7.02. PHILPS TMS 012/236 IMK with 2xTLD 36W
|  |  |  | 1 | 35
[6 empty] | 35 | Pcs net number item 7.02
7.03. RZB 59251.002 with RZB 05-56150Q50W
|  |  |  | 1 | 11
[6 empty] | 11 | Pcs net number item 7.03
7.04. RZB 59222.002 with RZB 05-56150Q50W
|  |  |  | 1 | 7
[6 empty] | 7 | Pcs net number item 7.04
7.05. MASSIVE 3202/02/67/1XE27/75W
|  |  |  | 1 | 1
[6 empty] | 1 | Pcs net number item 7.05
8.00. TV Points
8.01. TV Points fed through RG6 Coaxial 75 ohm TV cable
|  |  |  | 1 | 1
[6 empty] | 1 | Pcs net number item 8.01
11.00. Low Voltage Earthing system
11.01. Copper Earthing rod of 16x2400mm
|  |  |  | 1 | 1
[6 empty] | 1 | Pcs net number item 11.01
11.02. Copper conductor of 1x16mm2 for Earthing
|  |  |  | 1 | 25.3
[6 empty] | 25.3 | m net length item 11.02

## Eme Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - Emergency
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| W9 |  | 12 | 2.05 | 1 | 2 | 2 |  |  |  | 4.1
|  |  | 12 | 1.55 | 1 | 2 | 2 | - | - | - | 3.1 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
| D2 |  | 12 | 1.65 | 2 | 2 | 4 | - | - | - | 6.6 | -
|  |  | 12 | 1.15 | 2 | 2 | 4 | - | - | - | 4.6 | -
| Stirrups |  | 8 | 0.85 | 2 | 7 | 14 | - | 11.9 | - | - | -
| D3 |  | 12 | 1.55 | 3 | 2 | 6 | - | - | - | 9.3 | -
|  |  | 12 | 1.05 | 3 | 2 | 6 | - | - | - | 6.3 | -
| Stirrups |  | 8 | 0.85 | 3 | 7 | 21 | - | 17.85 | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
TOTAL LENGTH | [8 empty] | 35.7 | 0 | 34 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 14.1 | 0 | 30.19 | 0

## Dia Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Diagnostic service (X-Ray)- NO 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 157670.19 | 108159.79 | 0 | 108159.79
2 | CONCRETE WORKS | 259070.7 | 211341.86 | 0 | 211341.86
3 | MASONARY WORKS | 210000 | 73100 | 0 | 73100
TOTAL A |  | 626740.89 | 392601.65 | 0 | 392601.65
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 127020 | 113389.06 | 7903.54 | 121292.6
2 | BLOCK WORK | 223188.4 | 163174.8 | 0 | 163174.8
3 | ROOFING | 91981 | 85118.1 | 0 | 85118.1
4 | CARPENTRY & JOINERY | 121076 | 125393.04 | 104139 | 229532.04
5 | METAL WORKS | 84188 | 46098 | 41704 | 87802
6 | FINISHING | 319843.8 | 313602.2 | 6561 | 320163.2
7 | PAINTING | 33556.12 | 14780.22 | 0 | 14780.22
8 | GLAZING WORK | 17193 | 5280 | 0 | 5280
9 | SANITARY INSTALLATION | 50200 | 13601 | 35248 | 48849
10 | ELECTRICAL INSTALLATION | 75600 | 18700 | 35126 | 53826
TOTAL B |  | 1143846.32 | 899136.42 | 230681.54 | 1129817.96
TOTAL A+ B |  | 1770587.21 | 1291738.07 | 230681.54 | 1522419.61

## Dia Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Location - I/A/Bora Zone
Summary of Measurement for Diagnostics Service (X-Ray) - NO 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 434.09 | 392.34 |  | 392.34 | 6 | 2604.54 | 2354.04 | 0 | 2354.04
1.2 | Bulk Excavation | M3 | 558.18 | 470.81 |  | 470.81 | 50 | 27909 | 23540.5 | 0 | 23540.5
1.4 | Trench Excavation | M3 | 150 | 69.35 |  | 69.35 | 40 | 6000 | 2774 | 0 | 2774
1.5 | Selected backfill | M3 | 420 | 134.38 |  | 134.38 | 100 | 42000 | 13438 | 0 | 13438
1.6 | Cart away | M3 | 827.95 | 657.86 |  | 657.86 | 70 | 57956.5 | 46050.2 | 0 | 46050.2
1.7 | 25cm thick stone hard core | M2 | 220.59 | 235.33 |  | 235.33 | 85 | 18750.15 | 20003.05 | 0 | 20003.05
TOTAL CARRIED TO SUMMARY | [7 empty] | 155220.19 | 108159.79 | 0 | 108159.79
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class C-7
| a) massonary foundation | M2 | 100 | 73.1 |  | 73.1 | 100 | 10000 | 7310 | 0 | 7310
2.2 | 10cm thick reinforced concrete floor slab | M2 | 220.59 | 235.33 |  | 235.33 | 350 | 77206.5 | 82365.5 | 0 | 82365.5
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 16.67 | 15.17 |  | 15.17 | 2900 | 48343 | 43993 | 0 | 43993
| b) In footing pad | M3 |  | 0 |  | 0 | 2900 | 0 | 0 | 0 | 0
| c) In footing column | M3 |  | 0 |  | 0 | 2900 | 0 | 0 | 0 | 0
2.4 | Provide, cut and fix in position
| a) In grade beam & step | M2 | 128.76 | 119.16 |  | 119.16 | 120 | 15451.2 | 14299.2 | 0 | 14299.2
| d) Steps | M2 | 4 | 0 |  | 0 | 130 | 520 | 0 | 0 | 0
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 1145 | 1208.42 |  | 1208.42 | 38 | 43510 | 45919.96 | 0 | 45919.96
| b) Dia. 12mm deformed bar | Kg | 1455 | 0 |  | 0 | 38 | 55290 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg |  | 366.4 |  | 366.4 | 38 | 0 | 13923.2 | 0 | 13923.2
2.6 | 10/2 cm chip wood expansion joint | m | 259 | 235.4 |  | 235.4 | 15 | 3885 | 3531 | 0 | 3531
TOTAL CARRIED TO SUMMARY | [7 empty] | 254205.7 | 211341.86 | 0 | 211341.86
3. Masonry Work
3.1 | 50cm high BNGL | M3 | 100 | 73.1 |  | 73.1 | 1000 | 100000 | 73100 | 0 | 73100
3.2 | Ditto but ANGL | M3 | 100 | 0 |  | 0 | 1100 | 110000 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 210000 | 73100 | 0 | 73100
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 2.88 | 1.08 |  | 1.08 | 2900 | 8352 | 3132 | 0 | 3132
| b) In beams | M3 | 10.04 | 11.25 |  | 11.25 | 2900 | 29116 | 32625 | 0 | 32625
| c) Lintel | M3 | 0.84 | 0 | 0.83 | 0.83 | 2900 | 2436 | 0 | 2407 | 2407
1.2 | wood form work or metal panel. To:-
| a) In elevation column | M2 | 63.36 | 24.3 |  | 24.3 | 100 | 6336 | 2430 | 0 | 2430
| b) In beams | M2 | 193.92 | 119.96 |  | 119.96 | 100 | 19392 | 11996 | 0 | 11996
| c) Lintel | M2 | 11.2 | 4.87 | 13.8 | 18.67 | 100 | 1120 | 487 | 1380 | 1867
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg | 1123 | 0 |  | 0 | 38 | 42674 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 289 | 1225.62 | 73.08 | 1298.7 | 38 | 10982 | 46573.56 | 2777.04 | 49350.6
| c) Dia. 8 mm deformed bar | Kg | 174 | 373.75 | 35.25 | 409 | 38 | 6612 | 14202.5 | 1339.5 | 15542
| d) Dia. 6 mm deformed bar | Kg | 38 |  |  |  |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 127020 | 111446.06 | 7903.54 | 113389.06
2. BLOCK WORK
| a) 20 cm thick | M2 | 223.3 | 131.32 |  | 131.32 | 320 | 71456 | 42022.4 | 0 | 42022.4
| b) 15 cm thick | M2 | 276.33 | 212.53 |  | 212.53 | 280 | 77372.4 | 59508.4 | 0 | 59508.4
2.2 | 50cm thick well dressed stone masonary wall bedded in | M2 | 67.6 | 56.04 |  | 56.04 | 1100 | 74360 | 61644 | 0 | 61644
TOTAL CARRIED TO SUMMARY | [7 empty] | 223188.4 | 163174.8 | 0 | 163174.8
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 329.7 | 309.05 |  | 309.05 | 230 | 75831 | 71081.5 | 0 | 71081.5
3.2 | G-30 ribbed sheet ceiling under eave | M2 | 43 | 50.82 |  | 50.82 | 130 | 5590 | 6606.6 | 0 | 6606.6
3.2 | G-30 Ribbed Sheet | M2 | 43 |  |  | 0 | 130 | 5590 | 0 | 0 | 0
3.4 | G-30 flat metal sheet gutter | m | 48 | 74.3 |  | 74.3 | 100 | 4800 | 7430 | 0 | 7430
TOTAL CARRIED TO SUMMARY | [7 empty] | 91811 | 85118.1 | 0 | 85118.1
4.CARPENTRY & JOINERY
| a)-diameter 10 -12cm | m | 456 | 492.62 |  | 492.62 | 22 | 10032 | 10837.64 | 0 | 10837.64
| b) diameter 8 - 10cm | m | 299 | 582.2 |  | 582.2 | 15 | 4485 | 8733 | 0 | 8733
| c) Purlin zigba size 5/7cm | m | 471 | 416.7 |  | 416.7 | 32 | 15072 | 13334.4 | 0 | 13334.4
4.2 | 25*2.5 cm Zigba wooden fascia board | m | 134 | 75.4 |  | 75.4 | 70 | 9380 | 5278 | 0 | 5278
4.3 | Supply and fix 40mm thick wood framed door
| a) Type D1 size-90/270cm | No | 7 | 0 | 8 | 8 | 4617 | 32319 | 0 | 36936 | 36936
| b) Type D2 size -80/210cm | No | 7 | 0 | 8 | 8 | 4104 | 28728 | 0 | 32832 | 32832
| c) Type D3s size -70/270cm | No | 1 | 0 | 5 | 5 | 3591 | 3591 | 0 | 17955 | 17955
| d) Type D7s size -120/270cm | No | 2 | 0 | 1 | 1 | 6156 | 12312 | 0 | 6156 | 6156
| e) Type D8 size -100/270cm | No | 2 | 0 | 2 | 2 | 5130 | 10260 | 0 | 10260 | 10260
TOTAL CARRIED TO SUMMARY | [7 empty] | 126179 | 38183.04 | 104139 | 142322.04
5.METAL WORKS
5.1 | Windows
| a) WL1- 120/80cm (lead window) | no | 1 | 0 |  | 0 | 1248 | 1248 | 0 | 0 | 0
| b) WL2- 50/50cm (lead window) | no | 1 | 0 |  | 0 | 325 | 325 | 0 | 0 | 0
| c) WT1 - 70/60cm | no | 2 | 2 |  | 10 | 546 | 1092 | 1092 | 4368 | 5460
| d )W1T - 120/60cm | no | 2 | 2 |  | 10 | 936 | 1872 | 1872 | 7488 | 9360
| h) W3 - 150/160 | no | 10 | 10 |  | 15 | 3120 | 31200 | 31200 | 15600 | 46800
| i) Type W7 size-100/160cm | no | 2 |  |  |  | 2080 | 4160 | 0 | 2080 | 2080
| e) W3T - 150/60cm | no | 2 | 3 |  | 5 | 1170 | 2340 | 3510 | 2340 | 5850
Doors
| b) Type D2 size -80/270cm | no | 1 | 3 |  | 3 | 2808 | 2808 | 8424 | 0 | 8424
| c) Type D6 size-140/270cm | No | 2 |  | 2 | 2 | 4914 | 9828 | 0 | 9828 | 9828
TOTAL CARRIED TO SUMMARY | [7 empty] | 54873 | 46098 | 41704 | 87802
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendring | M2 | 190.04 | 120.25 |  | 120.25 | 90 | 17103.6 | 10822.5 | 0 | 10822.5
6.2 | Apply three coats of plastering to internal walls | M2 | 687.86 | 896.43 |  | 896.43 | 100 | 68786 | 89643 | 0 | 89643
6.3 | 4mm thick best type plastic ceiling | M2 | 254.46 | 262.29 |  | 262.29 | 270 | 68704.2 | 70818.3 | 0 | 70818.3
6.4 | 200*300*6mm glazed ceramic wall till | M2 | 93 | 83.9 |  | 83.9 | 290 | 26970 | 24331 | 0 | 24331
6.5.a | 8mm thick non slippery ceramic | M2 | 213 | 212.7 |  | 212.7 | 300 | 63900 | 63810 | 0 | 63810
6.6 | Ceramic tile skiring 10/0.8cm | ml | 273.6 | 147.16 | 65.61 | 212.77 | 100 | 27360 | 14716 | 6561 | 21277
6.7 | Terrazo window cill bedded on | ml | 31.2 | 22.3 |  | 22.3 | 150 | 4680 | 3345 | 0 | 3345
6.8 | 30/30/3mm angle iron corner protection | M2 | 31.2 | 0 |  | 0 | 70 | 2184 | 0 | 0 | 0
6.9 | 10cm thick C-20 RC 1-2m wide pavement | M2 | 82 | 89.52 |  | 89.52 | 320 | 26240 | 28646.4 | 0 | 28646.4
6.1 | concret pipes of half diameter 30cm | ml | 77 | 74.7 |  | 74.7 | 100 | 7700 | 7470 | 0 | 7470
6.11 | 10X40cm curb stone around the building | ml | 77 | 0 |  | 0 | 105 | 8085 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 321712.8 | 313602.2 | 6561 | 320163.2
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 687.86 | 448.22 |  | 448.22 | 26 | 17884.36 | 11653.72 | 0 | 11653.72 | 83.9
7.2 | Ditto but oil paint to a height of 1.5m | M2 | 412.72 | 0 |  | 0 | 26 | 10730.72 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 190.04 | 120.25 |  | 120.25 | 26 | 4941.04 | 3126.5 | 0 | 3126.5
| TOTAL CARRIED TO SUMMARY | [6 empty] | 33556.12 | 14780.22 | 0 | 14780.22
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 5.25 | 24 |  | 24 | 220 | 1155 | 5280 | 0 | 5280
8.2 | 4mm thick frosted glass | M2 | 44.55 |  |  | 0 | 360 | 16038 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 17193 | 5280 | 0 | 5280
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 20mm diameter;internal | lm | 20 | 70.8 |  | 70.8 | 75 | 1500 | 5310 | 0 | 5310
9.5 | Supply and install waste water pipes made of rigid plastic pipe (upvc)
| 50mm diameter | lm | 10 | 39.45 |  | 39.45 | 60 | 600 | 2367 | 0 | 2367
| 100mm diameter | lm | 48 | 35.2 |  | 35.2 | 120 | 5760 | 4224 | 0 | 4224
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 9 |  | 11 | 11 | 600 | 5400 | 0 | 6600 | 6600
9.7 | Supply and fix low flush white vitreous china water closet | No | 7 |  | 6 | 6 | 900 | 6300 | 0 | 5400 | 5400
9.9 | Supply and fix toilet paper holder made of metal | No | 7 |  | 6 | 6 | 90 | 630 | 0 | 540 | 540
9.1 | Supply and fix crystal glass mirror | No | 7 |  | 11 | 11 | 200 | 1400 | 0 | 2200 | 2200
9.11 | Supply and install shower units made of chrome-plated shower | No | 1 | 1 | 1 | 2 | 1700 | 1700 | 1700 | 1700 | 3400
9.12 | Supply and fix 600mm long towel hanger | No | 1 |  | 2 | 2 | 120 | 120 | 0 | 240 | 240
9.14 | Install electric water heater 50 liter capacity | No | 1 |  | 5 | 5 | 2000 | 2000 | 0 | 10000 | 10000
9.16 | Supply and fix 50mm diameter floor drain made of | No | 5 |  | 3 | 3 | 120 | 600 | 0 | 360 | 360
9.18 | Supply and fix 100mm down pipes made | lm | 36 |  | 51.2 | 51.2 | 90 | 3240 | 0 | 4608 | 4608
9.2 | Supply & fix Stainless steel sink chemical resistant with Double bowl | No | 7 |  | 4 | 4 | 900 | 6300 | 0 | 3600 | 3600
TOTAL CARRIED TO SUMMARY | [7 empty] | 35550 | 13601 | 35248 | 48849
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | Light points in rigid therimoplastic conduit of 16mm | Pcs | 54 | 54 |  | 54 | 200 | 10800 | 10800 | 0 | 10800
3 | Switches LEGRAND, SUNO,
3.01 | Single(774001+774041) | Pcs | 19 |  | 19 | 19 | 75 | 1425 | 0 | 1425 | 1425
3.02 | Double(774005+774042) | Pcs | 10 |  | 10 | 10 | 120 | 1200 | 0 | 1200 | 1200
3.03 | Two -Way(774006+774041) | Pcs | 4 |  | 4 | 4 | 80 | 320 | 0 | 320 | 320
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit of diameter 16mm | Pcs | 30 | 30 |  | 30 | 200 | 6000 | 6000 | 0 | 6000
5 | Socket outlet
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | Pcs | 30 | 19 | 11 | 30 | 100 | 3000 | 1900 | 1100 | 3000
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable | Pcs | 8 |  | 8 | 8 | 130 | 1040 | 0 | 1040 | 1040
7 | Type of light Fitting with lamp
7.01 | PHILPS TCS 098/236 IMK with 2xTLD 36W | Pcs | 19 |  | 19 | 19 | 700 | 13300 | 0 | 13300 | 13300
7.02 | PHILPS TCS 012/136 IMK with 1xTLD 36W | Pcs | 14 |  | 14 | 14 | 450 | 6300 | 0 | 6300 | 6300
7.03 | RZB 59251.002 with RZB 05-56150Q50W | Pcs | 14 |  | 14 | 14 | 250 | 3500 | 0 | 3500 | 3500
7.04 | RZB 59222.002 with /rzb 05-56150Q50W lamp or | Pcs | 6 |  | 6 |  | 250 | 1500 | 0 | 1500 | 1500
7.5 | MASSIVE 70107/02/11/1XE27/60W | Pc | 1 |  | 1 |  | 275 | 275 | 0 | 275 | 275
8 | TV Points
8.01 | TV Points fed through RG6 Coaxial 75 ohm TV | Pcs | 1 |  | 1 | 1 | 130 | 130 | 0 | 130 | 130
11 | Low Voltage Earthing system
11.01 | Copper Earthing rod of 16x2400mm | Pcs | 1 |  | 1 | 1 | 2000 | 2000 | 0 | 2000 | 2000
11.02 | Copper conductor of 1x16mm2 for Earthing | ml | 22 |  | 25.3 | 25.3 | 120 | 2640 | 0 | 3036 | 3036
TOTAL CARRIED TO SUMMARY | [7 empty] | 53430 | 18700 | 35126 | 53826

## tOS Dia (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Diagnostics Service (X-Ray)
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2. Block works | -1 | 0.8 |  | Deduction
1 | 6.1 |  | 2.21 50 cm stone Masonery ( BricK wall work) |  | 0.6
| 2.75 |  |  |  |  | -0.48
|  | 16.775 |  | -1 | 0.5
-1 | 0.2 |  |  |  | 0.6
| 2.75 |  |  |  |  | -0.3
|  | -0.55 |  | -2 | 1
-2 | 1 |  |  |  | 0.6
| 0.6 |  |  |  |  | -1.2
|  | -1.2 |  |  |  | -1.98 | M2 sub Total
1 | 4.6 |  |  |  |  | 117.1 | m2 Total of item 6.2
| 2.75 | [5 empty] | 6.5 :- 8mm Thick Ceramic Tile Flooring
|  | 12.65 |  | 1 | 3 |  | Bacteriology/AFB Room
1 | 0.5 |  |  |  | 4.2
| 2.75 |  |  |  |  | 12.6
|  | 1.375 |  | 1 | 1.3
1 | 1.1 |  |  |  | 0.2
| 2.75 |  |  |  |  | 0.26
|  | 3.025 |  |  |  | 12.86 | M2 sub Total
1 | 3.5 |  |  | 1 | 2.9 |  | Mematology
| 2.75 |  |  |  | 4.2
|  | 9.625 |  |  |  | 12.18
-1 | 0.2 |  |  | 1 | 1.3
| 2.75 |  |  |  | 0.2
|  | -0.55 |  |  |  | 0.26
1 | 5.85 |  |  |  |  | 12.44 | M2 sub Total
| 2.75 |  |  | 1 | 3 |  | Parasitology
|  | 16.0875 |  |  | 4.2
-1 | 1.2 |  |  |  |  | 12.6
| 0.6 |  |  | 1 | 1.2
|  | -0.72 |  |  | 0.2
-1 | 0.8 |  |  |  |  | 0.24
| 0.6 |  |  |  |  | 12.84 | M2 sub Total
|  | -0.48 |  | 1 | 2 |  | Specimen/Collection
|  | 56.0375 | m2 Total of item 2.2 |  | 3.45
6.9
|  |  | 6. Finishing works | 2 | 0.8
2 | 6.1 |  | 6.2 Three coats of Plastering |  | 0.2
| 2.75 |  |  |  |  | 0.32
|  | 33.55 |  |  |  | 7.22 | M2 sub Total
2 | 4.6 |  |  | 1 | 3.25 |  | Wating Area
| 2.75 |  |  |  | 2.2
|  | 25.3 |  |  |  | 7.15
2 | 0.5 |  |  | 1 | 4.4
| 2.75 |  |  |  | 5.9
|  | 2.75 |  |  |  | 25.96
2 | 1.1 |  |  | 1 | 1.8
| 2.75 |  |  |  | 0.8
|  | 6.05 |  |  |  | 1.44
2 | 3.5 |  |  |  |  | 34.55 | M2 sub Total
| 2.75 |  |  | 1 | 6.2 |  | Corridor
|  | 19.25 |  |  | 2.4
2 | 5.85 |  |  |  |  | 14.88
| 2.75 |  |  | 2 | 1.4
|  | 32.18 |  |  | 0.25
|  | 119.08 | M2 sub Total |  |  | 0.7
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Diagnostics Service (X-Ray)
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  | 15.58 | M2 sub Total
1 | 2.3 |  | Store
4
9.2
2 | 0.8
0.2
0.32
|  | 9.52 | M2 sub Total
1 | 3.1 |  | Archive
2.45
7.595
1 | 0.8
0.2
0.16
|  | 7.755 | M2 sub Total
1 | 2.7 |  | Corridor
1.65
|  | 4.455 | M2 sub Total
1 | 3.5 |  | Duty Room
2.45
8.575
1 | 0.8
0.2
0.16
|  | 8.735 | M2 sub Total
1 | 3.5 |  | Ultrasound Room
2.45
8.575
1 | 0.8
0.2
0.16
|  | 8.735 | M2 sub Total
|  | 134.69 | m2 Totalof itemNo 6.5
6.9 1.20 m Pavment
2 | 24.65
1.2
59.16
2 | 12.65
1.2
30.36
|  | 89.52 | m2 Totalof itemNo 6.9
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Diagnostics Service (X-Ray)
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 3
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. SUB - STRUCTURE
1.6 cart away
1 | 392.34 |  | site clearing
| 0.3 | 117.702
|  | 471.74 | bulk
|  | 140.2 | trench
|  | 729.65 | m3 total of item 1.6
|  | 657.86 | Previous payment
|  | 71.79 | m3 Total 1.6 Remaining

## Dia TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION | [6 empty] | Block: - Diagnostics Service (X-Ray)
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | 4.CARPENTRY & JOINERY
|  |  | 1. CONCRETE WORKS |  |  |  | 4.3. Wood framed door
|  |  | 1.1. Reinforced concrete class C-25 |  |  |  | a) Doors Type D1 size -90/270cm
|  |  | c) Lintel | 1 | 8
7 | 1.2 |  | D2 |  |  | 8 | Pcs net number item 4.3.a
0.15
| 0.3 | 0.38 |  |  |  |  | b) Doors Type D2 size -80/270cm
|  |  |  | 1 | 8
4 | 1.1 |  | D3 |  |  | 8 | Pcs net number item 4.3.b
0.15
| 0.3 | 0.2 |  |  |  |  | c) Doors Type D3 size -70/270cm
|  |  |  | 1 | 5
2 | 1.4 |  | D5 |  |  | 5 | Pcs net number item 4.3.c
0.15
| 0.3 | 0.13 |  |  |  |  | d) Doors Type D7 size -120/270cm
|  |  |  | 1 | 1
1 | 1.6 |  | D7 |  |  | 1 | Pcs net number item 4.3.d
0.15
| 0.3 | 0.07 |  |  |  |  | e) Doors Type D7 size -100/270cm
|  |  |  | 1 | 2
1 | 1.2 |  | D2L |  |  | 2 | Pcs net number item 4.3.e
0.15
| 0.3 | 0.05 |  |  |  |  | 5.METAL WORKS
5.2. Doors
|  | 0.83 | m3 net area item 1.1.c |  |  |  | c) Type D6: size-140/270cm
|  |  |  | 1 | 2
|  |  | 1.2. form work or metal panel. To:- |  |  | 2 | Pcs net number item 5.2.c
c) Lintel
7 | 1.2 |  | D2
| 0.75 | 6.3 |  |  |  |  | 6.6)Approved type cearmic skirting 10/0.9cm
Bacteriology/Hematology AFB room
4 | 1.1 |  | D3 | 3 | 13.6 |  | Parasitology
| 0.75 | 3.3 |  |  |  | 40.8 | L=4.2X2+3X2-0.8=13.60mt
2 | 1.4 |  | D5 | 1 | 11.8 |  | Specimen
| 0.75 | 2.1 |  |  |  | 11.8 | L=4.2X2+2.50X2-0.8x2=11.80mt
1 | 1.6 |  | D7 | 1 | 26.07 |  | Corridor
| 0.75 | 1.2 |  |  |  | 26.07 | L=4.35+6.85+4.15+1.50+3+2.95+0.15
2.80+3.00-0.8-0.7x3=26.07mt
1 | 1.2 |  | D2L | 1 | 16.1 |  | Corridor
| 0.75 | 0.9 |  |  |  | 16.1 | L=6.95+12.35-0.8x2-1.6=16.10mt
|  | 13.8 | m2 net area item 1.2.c | 1 | 10.6 |  | Duty room
[6 empty] | 10.6 | L=3.50X2+2.55X2-0.7-0.8=10.60mt
1.3. Reinforcement steel bars
|  |  | b. ф12 mm deformed bars | 1 | 10.9 |  | Store
1 | 73.08 |  |  |  |  | 10.9 | L=3.30X2+2.55X2-0.8=10.90mt
|  | 73.08 | kg net wight item 1.3.b
|  |  |  | 1 | 10.5 |  | Archive
1 | 35.25 |  | c. ф8 mm deformed bars |  |  | 10.5 | L=3.10X2+2.55X2-0.8=10.50mt
|  | 35.25 | kg net wight item 1.3.c
|  |  |  | 1 | 22.8 |  | Corridor
[6 empty] | 22.8 | L=9.7x2+1.5+4.35+2.85-1.6-1.6-.7-1.4=22.8mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 11.6 |  | Control room |  |  |  | 9.16. 50mm diameter floor drain
|  | 11.6 | L=3.35X2+3.25X2-0.8=11.60mt | 1 | 3
[6 empty] | 3 | Pcs net number item 9.10
1 | 10.4 |  | Dark room
|  | 10.4 | L=2.35X2+3.25X2-0.8=10.40mt |  |  |  | 9.18. 100mm Down pipes
|  |  |  | 1 | 51.2
1 | 18.9 |  | X - RAY room |  |  | 51.2 | Pcs net number item 9.18
|  | 18.9 | L=5.20X2+5.40X2-1.4-0.9=18.90mt
9.20. Double Bowl Stainless Steel
1 | 7.1 |  | corridor | 1 | 4
|  | 7.1 | L=1.10X2+4.6X2-0.7x5-0.8=7.10mt |  |  | 4 | Pcs net number item 9.20
2 | 4.9 |  | Change room |  |  |  | 10. ELECTRICAL INSTALLATION
|  | 9.8 | L=1.35X2+1.45X2-0.70=4.90mt |  |  |  | 3.00. Switches LEGRAND, SUNO,
3.01. Single(774001+774041)
1 | 5.4 |  | Barium kitchen | 1 | 19
|  | 5.4 | L=1.60X2+1.45X2-0.7=5.40mt |  |  | 19 | Pcs net number item 3.01
|  | 212.77 | m2 Total area |  |  |  | 3.02. Double(774005+774042)
|  |  |  | 1 | 10
|  | 147.16 | Previous Payment |  |  | 10 | Pcs net number item 3.02
|  | 65.61 | m2 net area item 6.4 |  |  |  | 3.03. Twoway(774005+774042)
|  |  |  | 1 | 4
|  |  | 9. SANITARY INSTALLATION |  |  | 4 | Pcs net number item 3.02
9.6. Hand wash basin
1 | 11 | [5 empty] | 5.00. Socket outlet
|  | 11 | Pcs net number item 9.6 |  |  |  | 5.01. Socket outlet LEGRAND SUNO 774023 16 1ph
|  |  |  | 1 | 11
|  |  | 9.7. Water closet |  |  | 11 | Pcs net number item 5.01
1 | 6
|  | 6 | Pcs net number item 9.7 |  |  |  | 6.00. Telephone/Data points
6.01. Telephone points fed through cat 5E UTP cable
|  |  | 9.9. Toilet paper holder | 1 | 8
1 | 6 |  |  |  |  | 8 | Pcs net number item 6.01
|  | 6 | Pcs net number item 9.9
7.00. Type of light Fitting with lamp
|  |  | 9.10. Crystal glass mirror |  |  |  | 7.01. PHILPS TMS 012/136 IMK with 1xTLD 36W
1 | 11 |  |  | 1 | 19
|  | 11 | Pcs net number item 9.10 |  |  | 19 | Pcs net number item 7.01
|  |  | 9.11. Shower Tray |  |  |  | 7.02. PHILPS TMS 012/236 IMK with 2xTLD 36W
1 | 1 |  |  | 1 | 14
|  | 1 | Pcs net number item 9.11 |  |  | 14 | Pcs net number item 7.02
|  |  | 9.12. Towel hanger |  |  |  | 7.03. RZB 59251.002 with RZB 05-56150Q50W
1 | 2 |  |  | 1 | 14
|  | 2 | Pcs net number item 9.12 |  |  | 14 | Pcs net number item 7.03
|  |  | 9.14. Electric water heater |  |  |  | 7.04. RZB 59222.002 with RZB 05-56150Q50W
1 | 5 |  |  | 1 | 6
|  | 5 | Pcs net number item 9.14 |  |  | 6 | Pcs net number item 7.04
7.05. MASSIVE 3202/02/67/1XE27/75W
|  |  |  | 1 | 1
[6 empty] | 1 | Pcs net number item 7.05
T | D | S | Item No. and Description | T | D | S | Item No. and Description
8.00. TV Points
8.01. TV Points fed through RG6 Coaxial 75 ohm TV cable
1 | 1
|  | 1 | Pcs net number item 8.01
11.00. Low Voltage Earthing system
11.01. Copper Earthing rod of 16x2400mm
1 | 1
|  | 1 | Pcs net number item 11.01
11.02. Copper conductor of 1x16mm2 for Earthing
1 | 25.3
|  | 25.3 | m net length item 11.02

## Dia Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - Diagnostics Service (X-Ray)
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D2 |  | 12 | 1.65 | 7 | 2 | 14 |  |  |  | 23.1
|  |  | 12 | 1.15 | 7 | 2 | 14 | - | - | - | 16.1 | -
| Stirrups |  | 8 | 0.85 | 7 | 7 | 49 | - | 41.65 | - | - | -
| D3 |  | 12 | 1.55 | 4 | 2 | 8 | - | - | - | 12.4 | -
|  |  | 12 | 1.05 | 4 | 2 | 8 | - | - | - | 8.4 | -
| Stirrups |  | 8 | 0.85 | 4 | 7 | 28 | - | 23.8 | - | - | -
| D5 |  | 12 | 1.4 | 2 | 2 | 4 | - | - | - | 5.6 | -
|  |  | 12 | 0.95 | 2 | 2 | 4 | - | - | - | 3.8 | -
| Stirrups |  | 8 | 0.85 | 2 | 7 | 14 | - | 11.9 | - | - | -
| D7 |  | 12 | 2.1 | 1 | 2 | 2 | - | - | - | 4.2 | -
|  |  | 12 | 1.55 | 1 | 2 | 2 | - | - | - | 3.1 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
| D2L |  | 12 | 1.65 | 1 | 2 | 2 | - | - | - | 3.3 | -
|  |  | 12 | 1.15 | 1 | 2 | 2 | - | - | - | 2.3 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
TOTAL LENGTH | [8 empty] | 89.25 | 0 | 82.3 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 35.25 | 0 | 73.08 | 0

## Adm Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for ADMINSTRATION - No 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | Excavation and Earth works | 97292 | 122198.85 | 0 | 122198.85
2 | CONCRETE WORKS | 287103 | 332709.32 | 0 | 332709.32
3 | MASONARY WORKS | 282600 | 99280 | 0 | 99280
TOTAL A |  | 666995 | 554188.17 | 0 | 554188.17
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 109781 | 126896.86 | 2693.35 | 129590.21
2 | BLOCK WORK | 136560 | 132466 | 0 | 132466
3 | ROOFING | 104830 | 106386.4 | 0 | 106386.4
4 | CARPENTRY & JOINERY | 99208 | 83247.51 | 18468 | 101715.51
5 | METAL WORKS | 63031 | 64279 | 0 | 64279
6 | FINISHING | 358130 | 348787 | 8754 | 357541
7 | PAINTING | 24024 | 15124.46 | 0 | 15124.46
8 | GLAZING WORK | 18660 | 6054.4 | 0 | 6054.4
9 | SANITARY INSTALLATION | 21710 | 19917.75 | 2736 | 22653.75
10 | ELECTRICAL INSTALLATION | 124764.75 | 30656 | 9550 | 40206
TOTAL B |  | 1060698.75 | 933815.38 | 42201.35 | 976016.73
TOTAL A+ B |  | 1727693.75 | 1488003.55 | 42201.35 | 1530204.9

## Adm Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Adminstration - NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 427 | 471.2 |  | 471.2 | 6 | 2562 | 2827.2 | 0 | 2827.2
1.2 | Bulk Excavation | M3 | 214 | 541.88 |  | 541.88 | 50 | 10700 | 27094 | 0 | 27094
1.4 | Trench Excavation | M3 | 112 | 98.9 |  | 98.9 | 40 | 4480 | 3956 | 0 | 3956
1.5 | Selected backfill | M3 | 204 | 87 |  | 87 | 100 | 20400 | 8700 | 0 | 8700
1.6 | Car away | M3 | 452 | 782.14 |  | 782.14 | 70 | 31640 | 54749.8 | 0 | 54749.8
1.7 | 25cm thick stone hard core | M2 | 292 | 292.61 |  | 292.61 | 85 | 24820 | 24871.85 | 0 | 24871.85
TOTAL CARRIED TO SUMMARY | [7 empty] | 94602 | 122198.85 | 0 | 122198.85
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete
| a) massonary foundation | M2 | 156 | 99.28 |  | 99.28 | 100 | 15600 | 9928 | 0 | 9928
2.2 | 10cm thick reinforced concrete floor slab | M2 | 292 | 292.61 |  | 292.61 | 350 | 102200 | 102413.5 | 0 | 102413.5
2.3 | Reinforced concrete floor slab class C-25
| a) In grade beam & step | M3 | 15 | 20.32 |  | 20.32 | 2900 | 43500 | 58928 | 0 | 58928
2.4 | form work or metal panel To:-
| a) In grade beam & step | M2 | 148 | 151.38 |  | 151.38 | 120 | 17760 | 18165.6 | 0 | 18165.6
| d) Steps | M2 | 0 | 0 |  | 0 | 130 | 0 | 0 | 0 | 0
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 1121 | 1858.98 |  | 1858.98 | 38 | 42598 | 70641.24 | 0 | 70641.24
| b) Dia. 12mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 1635 | 1783.46 |  | 1783.46 | 38 | 62130 | 67771.48 | 0 | 67771.48
2.6 | 12/2 cm chip wood expansion joint | m | 221 | 324.1 |  | 324.1 | 15 | 3315 | 4861.5 | 0 | 4861.5
TOTAL CARRIED TO SUMMARY | [7 empty] | 287103 | 332709.32 | 0 | 332709.32
3. Masonry Work
3.1 | stone masonrey BNGL | M3 | 111 | 99.28 |  | 99.28 | 1000 | 111000 | 99280 | 0 | 99280
3.2 | Ditto but ANGL | M3 | 156 | 0 |  | 0 | 1100 | 171600 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 282600 | 99280 | 0 | 99280
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25
| a) In elevation column | M3 | 2.4 | 1.19 |  | 1.19 | 2900 | 6960 | 3451 | 0 | 3451
| b) In beams | M3 | 9.3 | 12.56 |  | 12.56 | 2900 | 26970 | 36424 | 0 | 36424
| c) Lintel | M3 | 0.75 |  | 0.28 | 0.28 | 2900 | 2175 | 0 | 812 | 812
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 48 | 25.4 |  | 25.4 | 100 | 4800 | 2540 | 0 | 2540
| b) In beams | M2 | 148 | 168.43 |  | 168.43 | 100 | 14800 | 16843 | 0 | 16843
| c) Lintel | M2 | 8 |  | 4.65 | 4.65 | 101 | 808 | 0 | 469.65 | 469.65
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 1077 | 1367.98 | 25.4 | 1393.38 | 38 | 40926 | 51983.24 | 965.2 | 52948.44
| c) Dia. 8 mm deformed bar | Kg | 325 | 411.99 | 11.75 | 423.74 | 38 | 12350 | 15655.62 | 446.5 | 16102.12
| d) Dia. 6 mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 109789 | 126896.86 | 2693.35 | 129590.21
2. BLOCK WORK
| a) 20 cm thick | M2 | 180 | 300.39 |  | 300.39 | 320 | 57600 | 96124.8 | 0 | 96124.8
| b) 15 cm thick | M2 | 282 | 129.79 |  | 129.79 | 280 | 78960 | 36341.2 | 0 | 36341.2
TOTAL CARRIED TO SUMMARY | [7 empty] | 136560 | 132466 | 0 | 132466
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 392 | 391.82 |  | 391.82 | 230 | 90160 | 90118.6 | 0 | 90118.6
3.2 | G-30 Ribbed Sheet | M2 | 51 | 60.06 |  | 60.06 | 130 | 6630 | 7807.8 | 0 | 7807.8
3.4 | G-30 flat metal sheet gutter | m | 15 | 84.6 |  | 84.6 | 100 | 1500 | 8460 | 0 | 8460
TOTAL CARRIED TO SUMMARY | [7 empty] | 98290 | 106386.4 | 0 | 106386.4
4.CARPENTRY & JOINERY
4.1 | Carpentry swan eucalyptus truss
| a)diameter 10 -12cm | m | 686 | 619.38 |  | 619.38 | 22 | 15092 | 13626.36 | 0 | 13626.36
| b) diameter 8 - 10cm | m | 377 | 349.77 |  | 349.77 | 15 | 5655 | 5246.55 | 0 | 5246.55
| c) Purlin zigba size 5/7cm | m | 458 | 514.8 |  | 514.8 | 32 | 14656 | 16473.6 | 0 | 16473.6
4.2 | 25*2.5 cm Zigba wooden fascia board | m | 85 | 85.8 |  | 85.8 | 70 | 5950 | 6006 | 0 | 6006
4.3 | Wooden Door
| a) Type D1 size-80/210cm | No | 5 |  |  | 0 | 3192 | 15960 | 0 | 0 | 0
| b) Type D2 size -70/210cm | No | 7 | 7 |  | 7 | 2793 | 19551 | 19551 | 0 | 19551
| c) Type D7s size -120/210cm | No | 1 | 1 |  | 1 | 4788 | 4788 | 4788 | 0 | 4788
| d) Type DS6s size -140/210cm | No | 2 | 2 |  | 2 | 5586 | 11172 | 11172 | 0 | 11172
| e) Type DS2 size -80/210cm | No | 2 | 2 |  | 2 | 3192 | 6384 | 6384 | 0 | 6384
| f) Type D1 size-90/270cm | No | 0 | 0 | 4 | 4 | 4617 | 0 | 0 | 18468 | 18468
TOTAL CARRIED TO SUMMARY | [7 empty] | 99208 | 83247.51 | 18468 | 101715.51
5.METAL WORKS
5.1 | Windows
| a) W4 - 160/160cm | no | 9 | 10 |  | 10 | 3328 | 29952 | 33280 | 0 | 33280
| c) W7 - 1.0/160cm | no | 1 | 2 |  | 2 | 2080 | 2080 | 4160 | 0 | 4160
| d) WT1 - 80/60cm | no | 1 | 1 |  | 1 | 624 | 624 | 624 | 0 | 624
| e) WT2- 110/60cm | no | 1 | 1 |  | 1 | 858 | 858 | 858 | 0 | 858
| f) WT3 - 118/60cm | no | 2 | 2 |  | 2 | 920 | 1840 | 1840 | 0 | 1840
5.2 | Doors
| a) D2 - 80/270cm | no | 2 | 2 |  | 2 | 2808 | 5616 | 5616 | 0 | 5616
| b) D4 - 150/270cm | no | 2 | 2 |  | 2 | 5265 | 10530 | 10530 | 0 | 10530
| c) D7 - 120/270cm |  | 1 | 1 |  | 1 | 4212 | 4212 | 4212 | 0 | 4212
| d) D1- 90/270cm | no | 1 | 1 |  | 1 | 3159 | 3159 | 3159 | 0 | 3159
| TOTAL CARRIED TO SUMMARY |  |  |  |  | 0 |  | 58871 | 64279 | 0 | 64279
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | M2 | 180 | 155.49 |  | 155.49 | 90 | 16200 | 13994.1 | 0 | 13994.1
6.2 | Apply three coats of plastering | M2 | 744 | 852.44 |  | 852.44 | 100 | 74400 | 85244 | 0 | 85244
6.3 | 4mm thick best type plastic ceiling | M2 | 292 | 299.94 |  | 299.94 | 270 | 78840 | 80983.8 | 0 | 80983.8
6.4 | 200*300*6mm glazed ceramic wall till | M2 | 37 | 67.27 |  | 67.27 | 290 | 10730 | 19508.3 | 0 | 19508.3
6.5 | 8mm thick non slippery ceramic | M2 | 292 | 275.56 | 29.18 | 304.74 | 300 | 87600 | 82668 | 8754 | 91422
6.6 | Ceramic tile skiring 10/0.8cm | ml | 221 | 239.47 |  | 239.47 | 100 | 22100 | 23947 | 0 | 23947
6.7 | Terrazo window cill bedded on | ml | 34 | 20.7 |  | 20.7 | 150 | 5100 | 3105 | 0 | 3105
6.8 | 30/30/3mm angle iron corner protection | M2 | 6 | 6 |  | 6 | 70 | 420 | 420 | 0 | 420
6.9 | 10cm thick C-20 RC 1-2m wide pavement (including | M2 | 102 | 102.24 |  | 102.24 | 320 | 32640 | 32716.8 | 0 | 32716.8
6.1 | concret pipes of half diameter 30cm | ml | 86 | 62 |  | 62 | 100 | 8600 | 6200 | 0 | 6200
6.11 | 10X40cm curb stone around the building | ml | 86 | 0 |  | 0 | 105 | 9030 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 328030 | 348787 | 8754 | 357541
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 372 | 426.22 |  | 426.22 | 26 | 9672 | 11081.72 | 0 | 11081.72
7.2 | Ditto but oil paint to a height of 1.5m | M2 | 372 | 0 |  | 0 | 26 | 9672 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 180 | 155.49 |  | 155.49 | 26 | 4680 | 4042.74 | 0 | 4042.74
| TOTAL CARRIED TO SUMMARY | [6 empty] | 24024 | 15124.46 | 0 | 15124.46
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 3 | 27.52 |  | 27.52 | 220 | 660 | 6054.4 | 0 | 6054.4
8.2 | 4mm thick frosted glass | M2 | 50 |  |  | 0 | 360 | 18000 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 18660 | 6054.4 | 0 | 6054.4
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 20mm diameter;internal | lm | 15 | 16.85 |  | 16.85 | 75 | 1125 | 1263.75 | 0 | 1263.75
9.5 | Supply waste water pipes made of (upvc)
| 50mm diameter | lm | 5 | 16.1 |  | 16.1 | 60 | 300 | 966 | 0 | 966
| 75mm diameter | lm | 8 | 5.6 |  | 12.6 | 90 | 720 | 504 | 0 | 504
| 100mm diameter | lm | 9 | 10.7 |  | 10.7 | 120 | 1080 | 1284 | 0 | 1284
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 6 | 6 | 0 | 6 | 600 | 3600 | 3600 | 0 | 3600
9.7 | Supply and fix low flush white vitreous china water closet | No | 4 | 4 | 0 | 4 | 900 | 3600 | 3600 | 0 | 3600
9.9 | Supply and fix toilet paper holder made of metal | No | 4 | 4 | 0 | 4 | 90 | 360 | 360 | 0 | 360
9.1 | Supply and fix crystal glass mirror | No | 6 | 6 | 0 | 6 | 200 | 1200 | 1200 | 0 | 1200
9.16 | Supply and fix 50mm diameter floor drain | No | 4 | 4 | 22.8 | 26.8 | 120 | 480 | 480 | 2736 | 3216
9.18 | Supply and fix 100mm down pipes made | lm | 30 | 64 | 0 | 64 | 90 | 2700 | 5760 | 0 | 5760
9.2 | Supply & fix Stainless steel sink chemical resistant with Double bowl | No | 1 | 1 | 0 | 1 | 900 | 900 | 900 | 0 | 900
| TOTAL CARRIED TO SUMMARY | [6 empty] | 16065 | 19917.75 | 2736 | 22653.75
10. ELECTRICAL INSTALLATION
2. Feeder Cables & Pipes
2.2 | 5X6wq. Mm from SDB up to Coffee machine | M | 20 | 20 |  | 20 | 56 | 1120 | 1120 | 0 | 1120
2.3 | 3X4 sq. mm from SDB up to Stove PVC pipes. | M | 20 | 20 |  | 20 | 25.3 | 506 | 506 | 0 | 506
2.4 | 32mm diameter | M | 800 | 20 |  | 20 | 40 | 32000 | 800 | 0 | 800
5.` Light Points
5.1 | Flush mounted light points fed through | No | 43 | 44 |  | 44 | 200 | 244 | 8800 | 0 | 8800
6 | Extra Over Light Points for Flush Mounted Switches
6.1 | Flush mounting single switch, 774001+774041 | No | 6 |  |  | 0 | 75 | 75 | 0 | 0 | 0
6.2 | Flush mounting 2 gang single switch, 7740 05+774042 | No | 7 |  |  | 0 | 90 | 90 | 0 | 0 | 0
6.3 | Flush mounting two-way switch, 7740 06+774044 | No | 9 | 6 |  | 6 | 100 | 106 | 600 | 0 | 600
6.4 | Flush mounting Intermmediate switch, 7740 06+774044 | No | 1 |  |  | 0 | 120 | 120 | 0 | 0 | 0
7 | Flush Mounted Socket Outlet Paints
7.1 | 10-16A/1P socket outlet points fed through PVC | No | 26 | 20 |  | 20 | 200 | 220 | 4000 | 0 | 4000
7.2 | 32A/3p Soket outlet points fed through PVC | No | 4 | 4 |  | 4 | 200 | 204 | 800 | 0 | 800
7.3 | 32A/3P socket outlet points fed through PVC | No | 5 | 5 |  | 5 | 350 | 355 | 1750 | 0 | 1750
8 | Flush Mounted Socket Outlets with Earth Contact
8.1 | socket outlet of 10-16A/1p, 7740 20+7740 41. | No | 26 | 21 |  | 21 | 130 | 151 | 2730 | 0 | 2730
9 | Data/Telecom Points/Outlets
9.1 | Data/telephone points fed through 2x(twisted pair category 6 UTP cable) | No | 5 |  |  | 0 | 150 | 150 | 0 | 0 | 0
10 | Light Fittings and Lamps
10.1 | Type2=PHILIPS TMS 012/1181+1xTLD 18W/840 lamp. | No | 2 |  |  | 0 | 800 | 800 | 0 | 0 | 0
10.2 | Type 3=MASSIVE 70700/01/11 60W lamp(Chrome) | No | 9 |  |  | 0 | 500 | 500 | 0 | 0 | 0
10.3 | Type 4=MASSIVE 34015/11/102xG9/40W lamp (OCEAN).For Toilets | No | 3 |  |  | 0 | 600 | 600 | 0 | 0 | 0
10.4 | Type5=PHILIPS TMS 012/136+1 TLD 36W/840 LAMPS. | No | 9 |  |  | 0 | 600 | 600 | 0 | 0 | 0
10.5 | Type 6=PHILIPS TCW 097/236 I with 2xTLD 36W/33 | No | 1 |  |  | 0 | 550 | 550 | 0 | 0 | 0
10.6 | Type 7=PHILIPS TCS 098/236I+2x TLD 36W/840 lamp. | No | 21 |  |  | 0 | 650 | 650 | 0 | 0 | 0
7.01 | PHILPS TCS 098/236 IMK with 2xTLD 36W | Pcs |  | 6 | 6 | 12 | 700 | 0 | 4200 | 4200 | 8400
7.02 | PHILPS TCS 012/136 IMK with 1xTLD 36W | Pcs |  | 8 | 8 | 16 | 450 | 0 | 3600 | 3600 | 7200
7.03 | RZB 59251.002 with RZB 05-56150Q50W | Pcs |  | 5 | 5 | 10 | 250 | 0 | 1250 | 1250 | 2500
7.04 | RZB 59222.002 with /rzb 05-56150Q50W lamp or | Pcs |  | 2 | 2 | 4 | 250 | 0 | 500 | 500 | 1000
| TOTAL CARRIED TO SUMMARY | [6 empty] | 39041 | 30656 | 9550 | 40206

## TOS Adim (hidden)
TAKE OFF SHEET No8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Adminstration
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4. carpentry & joinery |  | 2.15
2 | 28.95 |  | 4.2 25x2.5 cm Fascial Board |  | 1.5
|  | 57.9 |  |  |  | 3.23
2 | 13.95 |  |  |  | 5.4
|  | 27.9 |  |  | 1.5
|  | 85.8 | Ml Totalof item no 4.2 |  |  | 8.1
|  |  | 6. Finishing works |  |  | 252.85 | M2 Totalof item no6.3
|  |  | 6.3:- 4 mm Thick Plastic celing |  |  |  | 6.5:- 8mm Thick ceramic tile flooring
| 4.8 |  |  |  | 4.3 |  | Office for CCD
| 4.3 |  |  |  | 4.8
|  | 20.64 |  |  |  | 20.64
| 4.8 |  |  |  | 0.9
| 3 |  |  |  | 0.2
|  | 14.4 |  |  |  | 0.18
| 4.8 |  |  |  | 0.8
| 4.8 |  |  |  | 0.2
|  | 23.04 |  |  |  | 0.16
| 4.8 |  |  |  |  | 20.98 | M2 Sub Total
| 4.3 |  |  |  | 3 |  | Secretary
|  | 20.64 |  |  | 4.8
| 4.8 |  |  |  |  | 14.4
| 4.8 |  |  |  | 0.9
|  | 23.04 |  |  | 0.2
| 5.4 |  |  |  |  | 0.18
| 4.8 |  |  |  | 0.8
|  | 25.92 |  |  | 0.2
| 5.4 |  |  |  |  | 0.16
| 4.75 |  |  |  |  | 14.74 | M2 Sub Total
|  | 25.65 |  |  | 4.8 |  | Office For CEO
| 5.4 |  |  |  | 4.8
| 2.55 |  |  |  |  | 23.04
|  | 13.77 |  |  | 1.1
| 5.4 |  |  |  | 0.2
| 4.25 |  |  |  |  | 0.22
|  | 22.95 |  |  |  | 23.26 | M2 Sub Total
| 5.4 |  |  |  | 4.3 |  | Personel
| 3 |  |  |  | 4.8
|  | 16.2 |  |  |  | 20.64
| 4.25 |  |  |  | 0.9
| 1.5 |  |  |  | 0.2
|  | 6.38 |  |  |  | 0.18
| 2.95 |  |  |  |  | 20.82 | M2 Sub Total
| 1.5 |  |  |  | 4.8 |  | Accountant And Purchaser
|  | 4.43 |  |  | 4.8
| 4.75 |  |  |  |  | 23.04
| 1.5 |  |  |  | 0.9
|  | 7.13 |  |  | 0.2
| 4.3 |  |  |  |  | 0.18
| 1.5 |  |  |  |  | 23.22 | M2 Sub Total
|  | 6.45 |  |  | 7.5 |  | Liberary
| 4.8 |  |  |  | 5.4
| 1.5 |  |  |  |  | 40.5
|  | 7.2 |  |  | 1.4
| 2.45 |  |  |  | 0.2
| 1.5 |  |  |  |  | 0.28
|  | 3.68 |  |  |  | 40.78 | M2 Sub Total
TAKE OFF SHEET No8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Adminstration
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 7.5 |  | Meeting Hall
5.4
40.5
1.5
0.2
0.3
|  | 40.8 | M2 Sub Total
| 5.7 |  | Corridor
1.5
8.55
1.2
0.25
0.3
|  | 8.85 | M2 Sub Total
| 7.55 |  | Cafteria
5.4
40.77
1.2
0.2
0.24
|  | 41.01 | M2 Sub Total
| 27.4 |  | Corridor
1.5
|  | 41.1 | M2 Sub Total
|  | 275.56 | M2 Total of item no 6.5
2 | 29.95 |  | 6.9 Pavement 1.2 cm
1.2
71.88
2 | 12.65
1.2
30.36
|  | 102.24 | Total to item no 6.9
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Adminstration
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 3
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A. SUB - STRUCTURE
1.6 cart away
1) Excavation & Earth Work
1 | 471.2 |  | site clearing
| 0.3 | 141.36
|  | 541.88 | bulk
|  | 187.8 | trench
|  | 871.04 | m3 Total 1.6
|  | 782.14 | Previous payment
|  | 88.9 | m3 Total 1.6 Remaining

## Adm TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION | [6 empty] | Block: - Adminstration
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | 6. FINISHING
|  |  | 1. CONCRETE WORKS |  |  |  | 6.5. Ceramic floor
|  |  | 1.1. Reinforced concrete class C-25 | 1 | 2.28 |  | Toilet area
|  |  | c) Lintel |  | 1.8 | 4.1
4 | 1.2 |  | D2
| 0.15 |  |  | 2 | 1.26 |  | "
| 0.3 | 0.22 |  |  | 1.13 | 2.85
1 | 1.4 |  | W7 | 1 | 4.85 |  | "
| 0.15 |  |  |  | 0.8 | 3.88
| 0.3 | 0.06
|  |  |  | 2 | 2.25 |  | "
|  | 0.28 | m3 net area item 1.1.c |  | 1.2 | 5.4
|  |  | 1.2. form work or metal panel. To:- | 2 | 1.8 |  | "
|  |  | c) Lintel |  | 1.2 | 4.32
4 | 1.2 |  | D2
| 0.75 | 3.6 |  | 1 | 4.05 |  | Kitchen arae
[5 empty] | 2.13 | 8.63
1 | 1.4 |  | W7
| 0.75 | 1.05 |  |  |  | 29.18 | m2 net area item 6.5
|  | 4.65 | m2 net area item 1.2.c |  |  |  | 9. SANITARY INSTALLATION
9.6. Hand wash basin
|  |  | 1.3. Reinforcement steel bars | 1 | 6
|  |  | b. ф12 mm deformed bars |  |  | 6 | Pcs net number item 9.6
1 | 25.4
|  | 25.4 | kg net wight item 1.3.b |  |  |  | 9.7. Water closet
|  |  |  | 1 | 4
1 | 11.75 |  | c. ф8 mm deformed bars |  |  | 4 | Pcs net number item 9.7
|  | 11.75 | kg net wight item 1.3.c
9.9. Toilet paper holder
|  |  | 4.CARPENTRY & JOINERY | 1 | 4
|  |  | 4.3. Wood framed door |  |  | 4 | Pcs net number item 9.9
f) Doors Type D1 size -90/270cm
1 | 4 | [5 empty] | 9.10. Crystal glass mirror
|  | 4 | Pcs net number item 4.3.f | 1 | 6
[6 empty] | 6 | Pcs net number item 9.10
9.16. 50mm diameter floor drain
|  |  |  | 1 | 4
[6 empty] | 4 | Pcs net number item 9.10
9.18. 100mm Down pipes
|  |  |  | 1 | 64
[6 empty] | 64 | Pcs net number item 9.18
9.20. Double Bowl Stainless Steel
|  |  |  | 1 | 1
[6 empty] | 1 | Pcs net number item 9.20
T | D | S | Item No. and Description | T | D | S | Item No. and Description
10. ELECTRICAL INSTALLATION
6. Extra Over Light Points for Flush Mounted Switches
6.10. Flush mounting single switch, 774001+774041
1 | 6
|  | 6 | Pcs net number item 6.10
6.20. Flush mounting 2 gang single switch, 7740 05+774042
1 | 7
|  | 7 | Pcs net number item 6.20
6.40. Flush mounting Intermmediate switch, 7740 06+774044
1 | 1
|  | 1 | Pcs net number item 6.40
9.00. Data/Telecom Points/Outlets
9.01. Data/telephone points fed through 2x(twisted pair category 6 UTP cable)
10. Light Fittings and Lamps
10.10. Type2=PHILIPS TMS 012/1181+1xTLD 18W/840 lamp.
1 | 5
|  | 5 | Pcs net number item 9.01
10.20. Type 3=MASSIVE 70700/01/11 60W lamp(Chrome)
10.30. Type 4=MASSIVE 34015/11/102xG9/40W lamp (OCEAN).For Toilets
10.40. Type5=PHILIPS TMS 012/136+1 TLD 36W/840 LAMPS.
10.50. Type 6=PHILIPS TCW 097/236 I with 2xTLD 36W/33
10.60. Type 7=PHILIPS TCS 098/236I+2x TLD 36W/840 lamp.
7.01. PHILPS TMS 012/136 IMK with 1xTLD 36W
1 | 6
|  | 6 | Pcs net number item 7.01
7.02. PHILPS TMS 012/236 IMK with 2xTLD 36W
1 | 8
|  | 8 | Pcs net number item 7.02
7.03. RZB 59251.002 with RZB 05-56150Q50W
1 | 5
|  | 5 | Pcs net number item 7.03
7.04. RZB 59222.002 with RZB 05-56150Q50W
1 | 2
|  | 2 | Pcs net number item 7.04
T | D | S | Item No. and Description | T | D | S | Item No. and Description

## Adm Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - Adminstration
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D2 |  | 12 | 1.65 | 4 | 2 | 8 |  |  |  | 13.2
|  |  | 12 | 1.15 | 4 | 2 | 8 | - | - | - | 9.2 | -
| Stirrups |  | 8 | 0.85 | 4 | 7 | 28 | - | 23.8 | - | - | -
| W7 |  | 12 | 1.75 | 1 | 2 | 2 | - | - | - | 3.5 | -
|  |  | 12 | 1.35 | 1 | 2 | 2 | - | - | - | 2.7 | -
| Stirrups |  | 8 | 0.85 | 1 | 7 | 7 | - | 5.95 | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
TOTAL LENGTH | [8 empty] | 29.75 | 0 | 28.6 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 11.75 | 0 | 25.4 | 0

## Staff Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Staff House - No 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A SUB STRUCTURE
2 | EXCAVATION & EARTH WORK | 43280 | 50457.08 | 0 | 50457.08
3 | STONE MASONRY | 45000 | 45885 | 0 | 45885
4 | CONCRETE WORK | 112342 | 117330.1 | 0 | 117330.1
TOTAL A |  | 200622 | 213672.18 | 0 | 213672.18
B SUPER STRUCTURE
1 | CONCRTE WORK | 47273 | 46741.22 | 6142.82 | 52884.04
2 | BLOCK WORK | 83110 | 73784.3 | 0 | 73784.3
3 | ROOFING WORK | 43460 | 38530.9 | 0 | 38530.9
4 | CARPENTRY & JOINERY | 74816 | 59416.48 | 30592 | 90008.48
5 | METAL WORK | 52112 | 52112 | 0 | 52112
6 | FINISHING ORK | 157675 | 107704.2 | 18233.6 | 125937.8
7 | GLAZING WORK | 6930 | 3801.6 | 0 | 3801.6
8 | PAINTING WORK | 21840 | 0 | 15564.38 | 15564.38
9 | SANITARY INSTALLATION | 51320 | 15544 | 33840 | 49384
10 | ELECTRICAL INSTALLATION | 57055 | 9800 | 0 | 9800
TOTAL B |  | 595591 | 407434.7 | 104372.8 | 511807.5
TOTAL A+ B |  | 796213 | 621106.88 | 104372.8 | 725479.68

## Staff Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for staff house - NO 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site to remov top soil to an average depth of 30cm | M2 | 196 | 196 |  | 196 | 6 | 1176 | 1176 | 0 | 1176
1.2 | Bulk Excavation in ordinary soil not exceeding 0.5m | M3 | 93 | 57.8 |  | 57.8 | 36 | 3348 | 2080.8 | 0 | 2080.8
1.3 | Ditto but | M3 | 36 | 0 |  | 0 | 36 | 1296 | 0 | 0 | 0
a)Soft rock
1.4 | b )Hard rock |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
1.5 | Trench Excavation to a depth of mts from the reduced ground level |  | 36 | 16.13 |  | 16.13 | 36 | 1296 | 580.68 | 0 | 580.68
1.6 | Selected backfill material brought from the site & filled under hardcore | M3 | 174 | 301.8 |  | 301.8 | 100 | 17400 | 30180 | 0 | 30180
1 | Car away surplus excavated material to an appropriate tip | M3 | 170 | 132.73 |  | 132.73 | 70 | 11900 | 9291.1 | 0 | 9291.1
1.8 | 25cm thick basaltic or equivalent stone hard core well | M2 | 96 | 84.1 |  | 84.1 | 85 | 8160 | 7148.5 | 0 | 7148.5
TOTAL CARRIED TO SUMMARY | [7 empty] | 44576 | 50457.08 | 0 | 50457.08
2. Masonry Work
3.1 | Construct 50cm thick stone masonry from basaltic | M3 | 34 | 34.5 |  | 34.5 | 1000 | 34000 | 34500 | 0 | 34500
3.2 | Ditto but roughly dressed above NGL. Price also includes pointing in 1:3 cement mortar. | M3 | 10 | 10.35 |  | 10.35 | 1100 | 11000 | 11385 | 0 | 11385
TOTAL CARRIED TO SUMMARY | [7 empty] | 45000 | 45885 | 0 | 45885
3. CONCRETE WORKS
3.1 | 5cm thick lean concrete class C-5, 150kg of cement/m3
| a) Under massonary foundation | M2 | 23 | 34.5 |  | 34.5 | 100 | 2300 | 3450 | 0 | 3450
| b) Ditto but under grade beam | M2 | 0 | 0 |  | 0 | 100 | 0 | 0 | 0 | 0
| c) Ditto but under footing pad | M2 | 0 | 0 |  | 0 | 260 | 0 | 0 | 0 | 0
3.2 | Reinforced concrete floor slab class C-25
| a) In grade beam & step | M3 | 0 | 6.45 |  | 6.45 | 2900 | 0 | 18705 | 0 | 18705
| b) In footing pad | M3 | 7 | 0 |  | 0 | 2900 | 20300 | 0 | 0 | 0
| c) In footing column | M3 | 1 | 0 |  | 0 | 2900 | 2900 | 0 | 0 | 0
3.3 | In 10cm thick RC ground slab in C-20, 320kg cement/m3 | M2 | 96 | 136.73 |  | 136.73 | 350 | 33600 | 47855.5 | 0 | 47855.5
3.4 | Provide, cut and fix in position wood or steel form work
| a) To grade beam & step | M2 | 66 | 58.6 |  | 58.6 | 120 | 7920 | 7032 | 0 | 7032
| b) To footing pad | M2 | 66 | 0 |  | 0 | 120 | 7920 | 0 | 0 | 0
| c) To footing column | M2 | 4 | 0 |  | 0 | 130 | 520 | 0 | 0 | 0
2.5 | Mild steel reinforcement according to St. drawing
| a) Dia. 14mm deformed bar | Kg | 583 | 492.69 |  | 492.69 | 38 | 22154 | 18722.22 | 0 | 18722.22
| b) Dia. 12mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 596 | 567.51 |  | 567.51 | 38 | 22648 | 21565.38 | 0 | 21565.38
TOTAL CARRIED TO SUMMARY | [7 empty] | 120262 | 117330.1 | 0 | 117330.1
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25
| a) In elevation column | M3 | 1.65 | 1.08 |  | 1.08 | 2900 | 4785 | 3132 | 0 | 3132
| b) In beams | M3 | 3.52 | 3.52 |  | 3.52 | 2900 | 10208 | 10208 | 0 | 10208
| c) In concrete roof slab (10cm thick) | M3 | 0.5 | 0 |  | 0 | 2900 | 1450 | 0 | 0 | 0
| d) Lintels | M3 | 0 | 0 | 0.51 | 0.51 | 2900 | 0 | 0 | 1479 | 1479
1.2 | Provide, cut and fix in position swan zigba wood or steel form work
| a) To elevation column | M2 | 33 | 21.6 |  | 21.6 | 100 | 3300 | 2160 | 0 | 2160
| b) To concrete roof slab (12cm thick) | M2 | 52 | 52.8 |  | 52.8 | 100 | 5200 | 5280 | 0 | 5280
| c) To Lintel | M2 | 1 | 0 | 7.92 | 7.92 | 100 | 100 | 0 | 792 | 792
1.3 | Mild steel reinforcements according to structural drawing
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 112 | 174.79 | 64.29 | 239.08 | 38 | 4256 | 6642.02 | 2443.02 | 9085.04
| c) Dia. 8 mm deformed bar | Kg | 242 | 508.4 | 37.6 | 546 | 38 | 9196 | 19319.2 | 1428.8 | 20748
| d) Dia. 6 mm deformed bar | Kg | 231 | 0 |  | 0 | 38 | 8778 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 47273 | 46741.22 | 6142.82 | 52884.04
2. BLOCK WORK
2.01 | Supply and construct 20cm thick hollow concrete block class "B" 1:3 both sides left for plastering | M2 | 215 | 166.24 |  | 166.24 | 320 | 68800 | 53196.8 | 0 | 53196.8
2.02 | Ditto as item 2.1 but 10cm thick HCB | M2 | 53 | 76.25 |  | 76.25 | 270 | 14310 | 20587.5 | 0 | 20587.5
TOTAL CARRIED TO SUMMARY | [7 empty] | 83110 | 73784.3 | 0 | 73784.3
3. ROOFING
3.01 | G-30 CIS Roof cover | M2 | 150 | 143.47 |  | 143.47 | 230 | 34500 | 32998.1 | 0 | 32998.1
3.02 | G-30 Ribbed Sheet | M2 | 34 | 21.84 |  | 21.84 | 120 | 4080 | 2620.8 | 0 | 2620.8
3.03 | G-30 Flashing | ml | 46 | 0 |  | 0 | 80 | 3680 | 0 | 0 | 0
3.04 | G-30 flat metal sheet | ml | 15 | 36.4 |  | 36.4 | 80 | 1200 | 2912 | 0 | 2912
TOTAL CARRIED TO SUMMARY | [7 empty] | 43460 | 38530.9 | 0 | 38530.9
4.CARPENTRY & JOINERY
4.01 | Construct and put in place eucalyptus truss from
| a) diameter 10-12cm eucalyptus top and bottom chord members | ml | 232 | 237.44 |  | 237.44 | 22 | 5104 | 5223.68 | 0 | 5223.68
| b) diameter 8-10cm eucalyptus vertical and diagonal chord members | ml | 184 | 125.44 |  | 125.44 | 15 | 2760 | 1881.6 | 0 | 1881.6
4.2 | Provide & fix 5x7cm Zigba roof purlin c/c 90cm. | ml | 205 | 170 |  | 170 | 32 | 6560 | 5440 | 0 | 5440
4.3 | Supply and fix 8mm thick chip wood celling | m2 | 98 | 193.44 |  | 193.44 | 230 | 22540 | 44491.2 | 0 | 44491.2
4.04 | Ditto as above but G-30 ribbed sheet soffit under eaves | m2 | 37 | 0 |  | 0 | 130 | 4810 | 0 | 0 | 0
4.05 | Supply and fix 2.5x20cm zigba fascia board fixed to feet rafter | ml | 35 | 34 |  | 34 | 70 | 2450 | 2380 | 0 | 2380
4.06 | Doors
| D4 78x208cm | No | 4 | 0 | 4 | 4 | 3083 | 12332 | 0 | 12332 | 12332
| D5 78x308cm | No | 4 | 0 | 4 | 4 | 4565 | 18260 | 0 | 18260 | 18260
TOTAL CARRIED TO SUMMARY | [7 empty] | 74816 | 59416.48 | 30592 | 90008.48
5.METAL WORK
5.1 | Window
| a) Type W7size -178/168cm | Pcs | 4 | 4 |  | 4 | 3890 | 15560 | 15560 | 0 | 15560
| b) Type W10 size -88/112cm | Pcs | 4 | 4 |  | 4 | 1282 | 5128 | 5128 | 0 | 5128
| c) Type W11 size -88/168cm | Pcs | 4 | 4 |  | 4 | 1920 | 7680 | 7680 | 0 | 7680
| d) Type W10 size -130/160cm | No | 0 |  |  |  | 2704 | 0 | 0 | 0 | 0
| e) Type W25size -290/60cm | No | 0 |  |  |  | 2262 | 0 | 0 | 0 | 0
| f) Type W18size -169/60cm | No | 0 | 0 |  | 0 | 1318 | 0 | 0 | 0 | 0
5.2 | Doors
| a) TypeED6 size -78/275cm | Pcs | 4 | 4 |  | 4 | 2790 | 11160 | 11160 | 0 | 11160
| b) Type MD2 size -88/275cm | Pcs | 4 | 4 |  | 4 | 3146 | 12584 | 12584 | 0 | 12584
TOTAL CARRIED TO SUMMARY | [7 empty] | 52112 | 52112 | 0 | 52112
6. FINISHING
6.01 | Apply three coats of plastering to internal HCB wall, exposed surface of columns and beams up to fine finish. | M2 | 607 | 501.87 |  | 501.87 | 100 | 60700 | 50187 | 0 | 50187
6.02 | Apply 2 coats of plaster in 1:3 mix ratio and tyrolean rendering | M2 | 90 | 96.76 |  | 96.76 | 90 | 8100 | 8708.4 | 0 | 8708.4
6.03 | Apply 2 coats of plaster and tyrolean rendering to ceramic wall tiles | M2 | 45 | 0 |  | 0 | 75 | 3375 | 0 | 0 | 0
| 8mm thick non slippery ceramic 30x30x8mm | M2 |  |  | 37.25 | 37.25 | 300 | 0 | 11175 | 11175 | 22350
6.04 | Plastic Tile Flooring | M2 | 56 | 0 |  | 0 | 150 | 8400 | 0 | 0 | 0
6.05 | Terrazzo Tile Flooring | M2 | 40 | 0 |  | 0 | 290 | 11600 | 0 | 0 | 0
6.06 | Plastic Tile Skirting | ml | 48 | 0 |  | 0 | 45 | 2160 | 0 | 0 | 0
6.07 | Terrazzo Tile Skiring | ml | 45 | 0 |  | 0 | 30 | 1350 | 0 | 0 | 0
6.08 | Apply pointing to exposed massonary wall in cement ratio 1:3 | M2 | 35 | 0 |  | 0 | 50 | 1750 | 0 | 0 | 0
6.09 | Apply 5cm thick coments and screed flooring bedded in cement sand | M2 | 56 | 0 |  | 0 | 150 | 8400 | 0 | 0 | 0
6.1 | Supply and lay throated and chamfered 3x25cm Terrazo window | ml | 16 | 14.4 |  | 14.4 | 150 | 2400 | 2160 | 0 | 2160
6.11 | Ditto as above but 30cm wide to threads of entrance steps | ml | 12 | 0 |  | 0 | 150 | 1800 | 0 | 0 | 0
6.12 | Ditto as above but 15cm wide to the risers of the entrance steps. | ml | 9 | 0 |  | 0 | 150 | 1350 | 0 | 0 | 0
6.13 | Supply and fix approved quality 15x15cm local ceramic wall | M2 | 45 | 0 |  | 0 | 290 | 13050 | 0 | 0 | 0
6.13 | 200*300*6mm glazed ceramic wall till | M2 |  | 59.7 | 24.34 | 84.04 | 290 | 0 | 17313 | 7058.6 | 24371.6
6.14 | 100cm wide and 10cm thick mass concrete payment | ml | 77 | 43.44 |  | 43.44 | 320 | 24640 | 13900.8 | 0 | 13900.8
6.15 | Concret pipes of half diameter 30cm | ml | 78 | 42.6 |  | 42.6 | 100 | 7800 | 4260 | 0 | 4260
6.16 | 10X40cm curb stone around the building | ml | 8 | 0 |  | 0 | 105 | 840 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 157715 | 107704.2 | 18233.6 | 125937.8
7.PAINTING
7.1 | Apply three coats of plastic paint to plastered surface of internal wall, external beams and columns. | M2 | 640 | 0 | 501.87 | 501.87 | 26 | 16640 | 0 | 13048.62 | 13048.62
7.2 | Ditto but to rendered surface | M2 | 90 | 0 | 96.76 | 96.76 | 26 | 2340 | 0 | 2515.76 | 2515.76
7.3 | Ditto but to chip wood ceiling | M2 | 110 | 0 |  | 0 | 26 | 2860 | 0 | 0 | 0
7.4 | External rendered surface | M2 | 0 | 0 |  | 0 | 26 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 21840 | 0 | 15564.38 | 15564.38
8.GLAZING
8.1 | 3mm thick clear glass | M2 | 28 | 17.28 |  | 17.28 | 220 | 6160 | 3801.6 | 0 | 3801.6
8.2 | 4mm thick clear glass | M2 | 3.5 | 0 |  | 0 | 220 | 770 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 6930 | 3801.6 | 0 | 3801.6
9.SANITARY INSTALLATION
9.1 | Water pipes for cold and/hot water shall be PP-R
| 20mm diameter;internal | lm | 18 | 73.6 |  | 73.6 | 75 | 1350 | 5520 | 0 | 5520
9.3 | SANITAEY FIXTURES & FITTINGS
Fix, test & commission hand wash basins
| a=saze=500x450mm | No | 0
| b=600x450mm | No | 8 |  | 4 | 4 | 600 | 4800 | 0 | 2400 | 2400
11.4 | Fix low level glazed vitreous china wash down water closite | No | 1 |  | 4 | 4 | 900 | 900 | 0 | 3600 | 3600
11.5 | Supply and fix shower plate made of cast iron or vitreous china including
| a-shower Tray-size 800x800 | No | 2 | 4 |  | 4 | 900 | 1800 | 3600 | 0 | 3600
| b-shower head | No | 2 | 2 | 2 | 4 | 500 | 1000 | 1000 | 1000 | 2000
| c-Mixing valve/lever actions | No | 2 |  | 4 | 4 | 400 | 800 | 0 | 1600 | 1600
11.6 | Supply and fix stainless steel sink chemial resisit with single bowl as | No | 4 |  | 4 | 4 | 900 | 3600 | 0 | 3600 | 3600
11.7 | Sypply & fix sope holder in white virtuous china | No | 2 |  | 8 | 8 | 90 | 180 | 0 | 720 | 720
11.8 | Supply and fix crystal glass mirror, Size 500x400mm | No | 10 |  | 4 | 4 | 200 | 2000 | 0 | 800 | 800
11.9 | Supply & fix toilet paper holder with metal roller | No | 2 |  | 4 | 4 | 90 | 180 | 0 | 360 | 360
11.1 | Towel hanger chrome plated with roller | No | 10 |  | 4 | 4 | 200 | 2000 | 0 | 800 | 800
11.11 | Supply and fix water heater of approved quality
| A/50 liters heartier | No | 5 |  | 4 | 4 | 2000 | 10000 | 0 | 8000 | 8000
| B/80 liters heartier | No | 1 |  | 4 | 4 | 2500 | 2500 | 0 | 10000 | 10000
11.1 | All domestic waste, vent and storm water pipe lines shall be UPVC
| 50mm | ml | 39 | 26.6 |  | 26.6 | 60 | 2340 | 1596 | 0 | 1596
| 80mm | ml | 4 | 18 |  | 18 | 90 | 360 | 1620 | 0 | 1620
| 110mm | ml | 10 | 18.4 |  | 18.4 | 120 | 1200 | 2208 | 0 | 2208
11.1 | Supply and fix floor drains made of polished steel of approved quality,
| 100mm | No | 8 |  | 8 | 8 | 120 | 960 | 0 | 960 | 960
TOTAL CARRIED TO SUMMARY | [7 empty] | 35970 | 15544 | 33840 | 49384
10. Electrical Installation
5 | Socket outlet
B | Ditto, but single socket outlet | No | 30 | 29 |  | 29 | 200 | 6000 | 5800 | 0 | 5800
6 | Electrical Connections
G | LIGHT POINT | No | 4 | 20 |  | 20 | 200 | 800 | 4000 | 0 | 4000
TOTAL CARRIED TO SUMMARY | [7 empty] | 6800 | 9800 | 0 | 9800

## Staff TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau | [6 empty] | Block: - Staff Residence
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1.3)Lintel |  |  |  | 6.13. 200x300x6mm Glazed Ceramic Wall
8 | 1.2 |  | D2 and D5 | 4 | 1.92 |  | Toilet area
| 0.15 |  |  |  | 1.5 | 11.52
| 0.2 | 0.29
|  |  |  | 4 | 1 |  | "
4 | 1.4 |  | Opening |  | 1.5 | 6
0.2
| 0.2 | 0.224 |  | 4 | 2.5 |  | "
[5 empty] | 1.5 | 15
|  | 0.514 | m3 net area item 1.1.c
|  |  |  | 4 | 1.7 |  | "
|  |  | 1.6)Lintel |  | 1.5 | 10.2
8 | 1.2 |  | D2 and D5
| 0.55 | 5.28 |  | 8 | 1.35 |  | "
[5 empty] | 1.8 | 19.44
4 | 1.2 |  | Opening
| 0.55 | 2.64 |  | 4 | 1.92 |  | "
[5 empty] | 1.8 | 13.82
|  | 7.92 | m2 net area item 1.2.c
|  |  |  | 4 | 1.12 |  | "
|  |  | 1.3. Reinforcement steel bars |  | 1.8 | 8.06
b. ф12 mm deformed bars
1 | 64.29 |  |  |  |  | 84.04 | m2 Total area
|  | 64.29 | kg net wight item 1.3.b
[6 empty] | 59.7 | Previous Payment
1 | 37.6 |  | c. ф8 mm deformed bars
|  | 37.6 | kg net wight item 1.3.c |  |  | 24.34 | m2 net area item 6.4
|  |  | 4.CARPENTRY & JOINERY |  |  |  | 7.PAINTING
|  |  | 4.3. Wood framed door |  |  |  | 7.1. Internal plastered wall ext beams & colmn
|  |  | a) Doors Type D4 78x208cm |  |  |  | Ditto Item no 6.1
1 | 4 |  |  | 1 | 501.87
|  | 4 | Pcs net number item 4.3.a |  |  | 501.87 | m2 net area to item no 7.1
|  |  | b) Doors Type D5 78x308cm |  |  |  | 7.4. External rendered surface
1 | 4 | [5 empty] | Ditto Item no 6.2
|  | 4 | Pcs net number item 4.3.b | 1 | 96.76
[6 empty] | 96.76 | m2 net area to item no 7.4
6.5. Ceramic floor 30x30x8cm
4 | 1.92 |  | Toilet area |  |  |  | 9.SANITARY INSTALLATION
| 2.5 | 19.2 |  |  |  |  | 11.5. Supply and fix shower plate made of cast iron or vitreous china including
b-shower head
4 | 1.35 |  | " | 1 | 2
| 1.92 | 10.37 |  |  |  | 2 | Pcs net number item 11.5
4 | 1.92 |  | " |  |  |  | c-Mixing valve/lever actions
| 1 | 7.68 |  | 1 | 4
[6 empty] | 4 | Pcs net number item 11.5
|  | 37.25 | m2 net area item 6.5
T | D | S | Item No. and Description | T | D | S | Item No. and Description
9.SANITARY INSTALLATION
|  | 9.3 | 9.3. SANITAEY FIXTURES & FITTINGS
Fix, test & commission hand wash basins
b=600x450mm
1 | 4
|  | 4 | Pcs net number item 9.3.b
11.4. Fix low level glazed vitreous china wash down water closite
1 | 4
|  | 4 | Pcs net number item 11.4
11.6. Supply and fix stainless steel sink chemial resisit with single bowl as
1 | 4
|  | 4 | Pcs net number item 11.6
11.7. Sypply & fix sope holder in white virtuous china
1 | 8
|  | 8 | Pcs net number item 11.7
11.8. Supply and fix crystal glass mirror, Size 500x400mm
1 | 4
|  | 4 | Pcs net number item 11.8
11.9. Supply & fix toilet paper holder with metal roller
1 | 4
|  | 4 | Pcs net number item 11.9
11.10. Towel hanger chrome plated with roller
1 | 4
|  | 4 | Pcs net number item 11.10
11.11. Supply and fix water heater of approved quality
A/50 liters heartier
1 | 4
|  | 4 | Pcs net number item 11.11.A
B/80 liters heartier
1 | 4
|  | 4 | Pcs net number item 11.11.B
11.12. 10mm Floor Drain
1 | 8
|  | 8 | Pcs net number item 11.12

## Staff Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - Staff Residence
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D2 and D5 |  | 12 | 1.75 | 8 | 2 | 16 |  |  |  | 28
|  |  | 12 | 1.15 | 8 | 2 | 16 | - | - | - | 18.4 | -
| Stirrups |  | 8 | 0.85 | 8 | 7 | 56 | - | 47.6 | - | - | -
[8 empty] | - | - | - | - | -
| Opening |  | 12 | 1.9 | 4 | 2 | 8 |  |  |  | 15.2
|  |  | 12 | 1.35 | 4 | 2 | 8 | - | - | - | 10.8 | -
| Stirrups |  | 8 | 0.85 | 8 | 7 | 56 | - | 47.6 | - | - | -
[5 empty] | 4 |  |  | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
TOTAL LENGTH | [8 empty] | 95.2 | 0 | 72.4 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 37.6 | 0 | 64.29 | 0

## SQ Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Service Quarter - NO 15
It No. | Describtion | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | Todate
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 30830 | 35591.4 | 0 | 35591.4
2 | CONCRETE WORKS | 43960 | 68159.14 | 0 | 68159.14
3 | MASONARY WORKS | 45000 | 34652 | 0 | 34652
TOTAL A |  | 119790 | 138402.54 | 0 | 138402.54
B. SUPER- STRUCTURE
1 | CONCRTE WORK | 32520 | 35504.5 | 0 | 35504.5
2 | BLOCK WORK | 37120 | 50795.2 | 0 | 50795.2
3 | ROOFING WORK | 19514 | 18473 | 2912 | 21385
4 | CARPENTRY & JOINERY | 20900 | 21524.93 | 0 | 21524.93
5 | METAL WORK | 35208 | 17604 | 0 | 17604
6 | FINISHING ORK | 58450 | 51858.7 | 0 | 51858.7
7 | PAINTING WORK | 2200 | 7607.86 | 0 | 7607.86
8 | GLAZING WORK | 11570 | 2112 | 0 | 2112
9 | SANITARY INSTALLATION
10 | ELECTRICAL INSTALLATION
TOTAL B |  | 217482 | 205480.19 | 2912 | 208392.19
TOTAL A+ B |  | 337272 | 343882.73 | 2912 | 346794.73

## SQ Mea
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Service Quarter - NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 120 | 121.2 |  | 121.2 | 6 | 720 | 727.2 | 0 | 727.2
1.2 | Bulk Excavation | M3 | 60 | 93.6 |  | 93.6 | 50 | 3000 | 4680 | 0 | 4680
1.5 | Trench Excavation | M3 | 28 | 38.1 |  | 38.1 | 50 | 1400 | 1905 | 0 | 1905
1.6 | Selected backfill | M3 | 143 | 129.96 |  | 129.96 | 100 | 14300 | 12996 | 0 | 12996
1 | Cart away | M3 | 112 | 168.06 |  | 168.06 | 70 | 7840 | 11764.2 | 0 | 11764.2
1.8 | 25cm thick stone hard core | M2 | 42 | 41.4 |  | 41.4 | 85 | 3570 | 3519 | 0 | 3519
TOTAL CARRIED TO SUMMARY | [7 empty] | 30830 | 35591.4 | 0 | 35591.4
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class
| a) Under massonary foundation | M2 | 19 | 26.05 |  | 26.05 | 100 | 1900 | 2605 | 0 | 2605
2.2 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 0 | 6.5 |  | 6.5 | 2900 | 0 | 18850 | 0 | 18850
2.3 | In 10cm thick RC ground slab in C-20, | M2 | 42 | 41.4 |  | 41.4 | 350 | 14700 | 14490 | 0 | 14490
2.4 | form work which ever is appropriate
| a) To grade beam & step | M2 | 0 | 52 |  | 52 | 120 | 0 | 6240 | 0 | 6240
2.5 | Mild steel reinforcement
| a) Dia. 14mm deformed bar | Kg | 503 | 389.18 |  | 389.18 | 38 | 19114 | 14788.84 | 0 | 14788.84
| b) Dia. 12mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 217 | 294.35 |  | 294.35 | 38 | 8246 | 11185.3 | 0 | 11185.3
TOTAL CARRIED TO SUMMARY | [7 empty] | 43960 | 68159.14 | 0 | 68159.14
3. Masonry Work
3.1 | Construct stone masonryBNGL | M3 | 34 | 26.05 |  | 26.05 | 1000 | 34000 | 26050 | 0 | 26050
3.2 | Ditto butANGL | M3 | 10 | 7.82 |  | 7.82 | 1100 | 11000 | 8602 | 0 | 8602
TOTAL CARRIED TO SUMMARY | [7 empty] | 45000 | 34652 | 0 | 34652
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 1.5 | 1.12 |  | 1.12 | 2900 | 4350 | 3248 | 0 | 3248
| b) In top beams | M3 | 2.5 | 2.34 |  | 2.34 | 2900 | 7250 | 6786 | 0 | 6786
| c) In Lintels | M3 | 0.5 | 0 |  | 0 | 2900 | 1450 | 0 | 0 | 0
1.2 | steel form work
| a) To elevation column | M2 | 21 | 22.4 |  | 22.4 | 100 | 2100 | 2240 | 0 | 2240
| b) To top beams | M2 | 25 | 32.71 |  | 32.71 | 100 | 2500 | 3271 | 0 | 3271
| c) To Lintel | M2 | 0.5 | 0 |  | 0 | 100 | 50 | 0 | 0 | 0
1.3 | Mild steel reinforcements
| a) Dia. 6 mm deformed bar | Kg | 60 | 386.17 |  | 386.17 | 38 | 2280 | 14674.46 | 0 | 14674.46
| b) Dia. 12 mm deformed bar | Kg | 330 | 139.08 |  | 139.08 | 38 | 12540 | 5285.04 | 0 | 5285.04
TOTAL CARRIED TO SUMMARY | [7 empty] | 32520 | 35504.5 | 0 | 35504.5
2. BLOCK WORK
| 20cm hollow concrete block class "B" | M2 | 81 | 138.89 |  | 138.89 | 320 | 25920 | 44444.8 | 0 | 44444.8
| Ditto as item 2.1 but 15cm thick HCB | M2 | 40 | 22.68 |  | 22.68 | 280 | 11200 | 6350.4 | 0 | 6350.4
TOTAL CARRIED TO SUMMARY | [7 empty] | 37120 | 50795.2 | 0 | 50795.2
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 67 | 66.3 |  | 66.3 | 230 | 15410 | 15249 | 0 | 15249
3.2 | G-30 Ribbed Sheet | M2 | 18.2 | 10.2 |  | 10.2 | 120 | 2184 | 1224 | 0 | 1224
3.3 | G-30 Flashing | m | 16 | 25 |  | 25 | 80 | 1280 | 2000 | 0 | 2000
3.4 | G-30 flat metal sheet | m | 8 | 0 | 36.4 | 36.4 | 80 | 640 | 0 | 2912 | 2912
TOTAL CARRIED TO SUMMARY | [7 empty] | 19514 | 18473 | 2912 | 21385
4.CARPENTRY & JOINERY
4.1 | Construct and put in place eucalyptus truss from
a) | diameter 10-12cm | m | 120 | 94.64 |  | 94.64 | 22 | 2640 | 2082.08 | 0 | 2082.08
b) | diameter 8-10cm | m | 60 | 24.83 |  | 24.83 | 15 | 900 | 372.45 | 0 | 372.45
4.02 | Zigba roof purlin c/c 90cm. | m | 110 | 91 |  | 91 | 32 | 3520 | 2912 | 0 | 2912
4.03 | Supply and fix 8mm thick chip wood ceiling machine cut panels on and | M2 | 40 | 65.08 |  | 65.08 | 230 | 9200 | 14968.4 | 0 | 14968.4
4.05 | Supply and fix 2.5x20cm zigba fascia board | ml | 18 | 17 |  | 17 | 70 | 1260 | 1190 | 0 | 1190
TOTAL CARRIED TO SUMMARY | [7 empty] | 17520 | 21524.93 | 0 | 21524.93
5.METAL WORKS
5.1 | Doors
| ED5= 98x250 | no | 8 | 4 |  | 4 | 1216 | 9728 | 4864 | 0 | 4864
5.2 | Window
| W8= 78x120 | no | 8 | 4 |  | 4 | 3185 | 25480 | 12740 | 0 | 12740
TOTAL CARRIED TO SUMMARY | [7 empty] | 35208 | 17604 | 0 | 17604
6. FINISHING
6.01 | Apply three coats of plastering to internal wall | m2 | 200 | 171.26 |  | 171.26 | 100 | 20000 | 17126 | 0 | 17126
6.02 | Rendering | m2 | 100 | 121.35 |  | 121.35 | 90 | 9000 | 10921.5 | 0 | 10921.5
6.04 | Throated and chamfered 3x25cm Terrazo window | Ml | 6 | 4.8 |  | 4.8 | 150 | 900 | 720 | 0 | 720
6.05 | 10 cm thick mass concrete payment | ml | 55 | 56.16 |  | 56.16 | 320 | 17600 | 17971.2 | 0 | 17971.2
6.06 | concret pipes of half diameter 30cm | ml | 54 | 51.2 |  | 51.2 | 100 | 5400 | 5120 | 0 | 5120
6.11 | 10X40cm curb stone around the building | ml | 54 |  |  | 0 |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 52900 | 51858.7 | 0 | 51858.7
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 305 | 171.26 |  | 171.26 | 26 | 7930 | 4452.76 | 0 | 4452.76
7.2 | Ditto but oil paint to a height of 1.5m | M2 | 100 |  |  | 0 | 26 | 2600 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 40 | 121.35 |  | 121.35 | 26 | 1040 | 3155.1 | 0 | 3155.1
TOTAL CARRIED TO SUMMARY | [7 empty] | 11570 | 7607.86 | 0 | 7607.86
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 6 | 9.6 |  | 9.6 | 220 | 1320 | 2112 | 0 | 2112
8.2 | 4mm thick frosted glass | M2 | 4 |  |  | 0 | 360 | 1440 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 2760 | 2112 | 0 | 2112

## TOS SQ (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Service Quarter
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2. Block Works
2.1:- 20cm Thick HCB
1 | 17 |  | ( for Coping
0.2
3.4
2 | 4
0.2
1.6
|  | 5 | m2 Total of item 2.1
3. Roofing work
| 17 |  | 3.3 :- G-30 Fashing
17
2 | 4
8
|  | 25 | ml Total of item 3.3
4. Carpentery & Joinery
| 17 |  | 4.05 2.5x20 cm Fascial Board
17
|  | 17 | ml Total of item 4.05
6. Finishing work
2 | 19.4 |  | 6.05 Pavement 1.2 cm
1.2
46.56
2 | 4
1.2
9.6
|  | 56.16 | m2 Total of item 6.05
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Service Quarter
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A)SUB-STRUCTURE
1) EXCAVATION & EARTH WORK
1.6 Cart away surplus excavation material
|  | 129.96 | Ditto to item 1.5
|  | 129.96 | m3 total of item 1.6
|  | 168.06 | Previous payment
|  | -38.1 | m3 total of item 1.6 Remaining

## SQ TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau | [6 empty] | Block: - Service Quarter
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3. ROOFING
3.4. G-30 flat metal sheet gutter
2 | 18.2
|  | 36.4 | m net length item 3.4
Note on B62: New User:

## Gen Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Generator House- NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 14990 | 11577.08 | 0 | 11577.08
2 | CONCRETE WORKS | 41496 | 23147.66 | 0 | 23147.66
3 | MASONRY WORKS | 28500 | 8350 | 0 | 8350
TOTAL A |  | 84986 | 43074.74 | 0 | 43074.74
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 26590 | 14504.52 | 0 | 14504.52
2 | BLOCK WORK | 17400 | 18513.6 | 0 | 18513.6
3 | ROOFING | 13350 | 10548.8 | 0 | 10548.8
4 | CARPENTRY & JOINERY | 3790 | 5180.6 | 0 | 5180.6
5 | METAL WORKS | 8160 | 0 | 0 | 0
6 | FINISHING WORKS | 30940 | 19969.2 | 0 | 27984.2
8 | PAINTING WORK | 1820 | 0 | 2971.8 | 0
TOTAL B |  | 102050 | 68716.72 | 2971.8 | 76731.72
TOTAL A+ B |  | 187036 | 111791.46 | 2971.8 | 119806.46

## Gen Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Generator House - NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 65 | 58.38 |  | 58.38 | 6 | 390 | 350.28 | 0 | 350.28
1.2 | Bulk Excavation | M3 | 35 | 57.21 |  | 57.21 | 50 | 1750 | 2860.5 | 0 | 2860.5
1.4 | Trench Excavation | M3 | 15 | 7.85 |  | 7.85 | 40 | 600 | 314 | 0 | 314
1.5 | Selected backfill | M3 | 60 | 8.24 |  | 8.24 | 100 | 6000 | 824 | 0 | 824
1.6 | Cart away | M3 | 65 | 82.57 |  | 82.57 | 70 | 4550 | 5779.9 | 0 | 5779.9
1.7 | 25cm thickt stone hard core | M2 | 20 | 17.04 |  | 17.04 | 85 | 1700 | 1448.4 | 0 | 1448.4
| TOTAL CARRIED TO SUMMARY | [6 empty] | 14990 | 11577.08 | 0 | 11577.08
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class C-7,
| a) masonry foundation | M2 | 12 | 8.35 |  | 8.35 | 100 | 1200 | 835 | 0 | 835
2.2 | 10cm thick reinforced concrete floor slab class C-20, | M2 | 20 | 17.04 |  | 17.04 | 350 | 7000 | 5964 | 0 | 5964
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 2.5 | 1.77 |  | 1.77 | 2900 | 7250 | 5133 | 0 | 5133
2.4 | form work or metal panel. To:-
| a) In grade beam & step | M2 | 16 | 14.16 |  | 14.16 | 120 | 1920 | 1699.2 | 0 | 1699.2
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 180 | 142.9 |  | 142.9 | 38 | 6840 | 5430.2 | 0 | 5430.2
| b) Dia. 12mm deformed bar | Kg |  | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 447 | 101.02 |  | 101.02 | 38 | 16986 | 3838.76 | 0 | 3838.76
2.6 | 10/2 cm chip wood expansion joint | m | 20 | 16.5 |  | 16.5 | 15 | 300 | 247.5 | 0 | 247.5
| TOTAL CARRIED TO SUMMARY | [6 empty] | 41496 | 23147.66 | 0 | 23147.66
3. Masonry Work
3.1 | 50cm high stone masonry BNGL | M3 | 12 | 8.35 |  | 8.35 | 1000 | 12000 | 8350 | 0 | 8350
3.2 | Ditto but ANGL | M3 | 15 | 0 |  | 0 | 1100 | 16500 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 28500 | 8350 | 0 | 8350
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 1.5 | 0.43 |  | 0.43 | 2900 | 4350 | 1247 | 0 | 1247
| b) In beams | M3 | 2 | 1.07 |  | 1.07 | 2900 | 5800 | 3103 | 0 | 3103
| c) In concrete roof slab (10cm thick) | M3 | 0 | 0 |  | 0 | 2900 | 0 | 0 | 0 | 0
| d) Lintels | M3 | 0 | 0 |  | 0 | 2900 | 0 | 0 | 0 | 0
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 15 | 8.64 |  | 8.64 | 100 | 1500 | 864 | 0 | 864
* | b) In beams |  |  | 14.04 |  | 14.04 | 100 | 0 | 1404 | 0 | 1404
| b) In concrete roof slab (12cm thick) | M2 | 0 | 0 |  | 0 | 1000 | 0 | 0 | 0 | 0
| c) Lintel | M2 | 24 | 0 |  | 0 | 100 | 2400 | 0 | 0 | 0
1.3 | Reinforcement steel bar
| b) Dia. 12mm deformed bar | Kg | 250 | 158.95 |  | 158.95 | 38 | 9500 | 6040.1 | 0 | 6040.1
| c) Dia. 8 mm deformed bar | Kg | 80 | 48.59 |  | 48.59 | 38 | 3040 | 1846.42 | 0 | 1846.42
| TOTAL CARRIED TO SUMMARY | [6 empty] | 26590 | 14504.52 | 0 | 14504.52
2. BLOCK WORK
Concrete block wall class "B" bedded in cement mortar
| b) 20 cm thick | M2 | 60 | 63.84 |  | 63.84 | 290 | 17400 | 18513.6 | 0 | 18513.6
| a) 10 cm thick | M2 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 17400 | 18513.6 | 0 | 18513.6
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 40 | 32.96 |  | 32.96 | 230 | 9200 | 7580.8 | 0 | 7580.8
3.2 | G-30 Ribbed Sheet | M2 | 15 | 0 |  | 0 | 130 | 1950 | 0 | 0 | 0
3.3 | G-30 Flashing | m | 14 | 11.2 |  | 11.2 | 100 | 1400 | 1120 | 0 | 1120
3.4 | G-30 flat metal sheet | m | 10 | 23.1 |  | 23.1 | 80 | 800 | 1848 | 0 | 1848
| TOTAL CARRIED TO SUMMARY | [6 empty] | 13350 | 10548.8 | 0 | 10548.8
4.CARPENTRY & JOINERY
4.1 | Eucalyptus truss
| a)diameter 10 -12cm | m | 65 | 60 |  | 60 | 22 | 1430 | 1320 | 0 | 1320
| b) diameter 8 - 10cm | m | 40 | 40 |  | 40 | 15 | 600 | 600 | 0 | 600
| c) Purlin zigba size 5/7cm | m | 55 | 44.8 |  | 44.8 | 32 | 1760 | 1433.6 | 0 | 1433.6
4.4 | 25*2.5cm thick fascia board | m |  | 26.1 |  | 26.1 | 70 | 0 | 1827 | 0 | 1827
TOTAL CARRIED TO SUMMARY | [7 empty] | 3790 | 5180.6 | 0 | 5180.6
5.METAL WORKS
5.1 | Windows
| a) W7- 110/160cm | no | 5 | 0 |  | 0 | 228 | 1140 | 0 | 0 | 0
5.2
| a) D3 - 2.0/2.7m | no | 1 | 0 |  | 0 | 7020 | 7020 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 8160 | 0 | 0 | 0
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendering | M2 | 50 | 63.84 |  | 63.84 | 90 | 4500 | 5745.6 | 0 | 5745.6
6.2 | Apply three coats of plastering | M2 | 50 | 50.46 |  | 50.46 | 100 | 5000 | 5046 | 0 | 5046
6.07 | 10cm thick c-20 RC 1.2m wide pavement | M2 | 40 | 28.68 |  | 28.68 | 320 | 12800 | 9177.6 | 0 | 9177.6
6.1 | concert pipes of half diameter 30cm | ml |  | 56.25 |  | 56.25 | 100 | 7800 | 0 | 0 | 3710
6.11 | 10X40cm curb stone around the building | ml |  | 41 |  | 41 | 105 | 840 | 0 | 0 | 4305
TOTAL CARRIED TO SUMMARY | [7 empty] | 30940 | 19969.2 | 0 | 27984.2
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 50 | 0 | 63.84 | 63.84 | 26 | 1300 | 0 | 1659.84 | 1659.84
7.3 | External rendered surface | M2 | 20 | 0 | 50.46 | 50.46 | 26 | 520 | 0 | 1311.96 | 1311.96
TOTAL CARRIED TO SUMMARY | [7 empty] | 1820 | 0 | 2971.8 | 2971.8

## TOS Gen (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Generator House
CONTRACTOR :- Trust Construction | [5 empty] | Page:-
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3. Roofing work
4 | 2.8 |  | 3.4 G-30 Flashing
11.2
|  | 11.2 | Ml total to item 3.4
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Generator House
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A)SUB-STRUCTURE
1) EXCAVATION & EARTH WORK
1.6 Cart away surplus excavation material
|  | 82.57 | Ditto to item 1.5
|  | 82.57 | total m3 1.6
|  | 82.57 | Previous payment
|  | 0 | m3 total of item 1.6 Remaining

## Gen TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Payment 15
Client:- Oromia Regional State Health Bureau | [6 empty] | Block: - Generator House
T | D | S | Item No. and Description | T | D | S | Item No. and Description
7.PAINTING
7.1. External rendered surface
Ditto Item no 6.1
1 | 63.84
|  | 63.84 | n2 net area to item no 7.1
7.3. Internal plastered wall ext beams & colmn
Ditto Item no 6.2
1 | 50.46
|  | 50.46 | n2 net area to item no 7.3

## Sum Trans
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Transformer House - NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | EXCAVATION & EARTH WORK | 16448.7 | 16527.8 | 0 | 16527.8
2 | STONE MASONRY | 13920 | 19180 | 0 | 19180
3 | CONCRETE WORK | 31574 | 34847.7 | 0 | 34847.7
TOTAL A |  | 61942.7 | 70555.5 | 0 | 70555.5
B SUPER STRUCTURE
1 | CONCRTE WORK | 109997 | 123187.9 | 0 | 123187.9
8 | PAINTING WORK | 5769.66 | 0 | 4187.56 | 4187.56
TOTAL B |  | 109997 | 123187.9 | 4187.56 | 127375.46
TOTAL A+ B |  | 171939.7 | 193743.4 | 4187.56 | 197930.96

## Meas Trans
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Transformer House - No- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 68.25 | 94.4 |  | 94.4 | 6 | 409.5 | 566.4 | 0 | 566.4
1.2 | Bulk Excavation | M3 | 102.38 | 94.4 |  | 94.4 | 50 | 5119 | 4720 | 0 | 4720
1.4 | Trench Excavation | M3 | 34.13 | 24.1 |  | 24.1 | 40 | 1365.2 | 964 | 0 | 964
1.6 | Car away surplus excavated material | M3 | 136.5 | 146.82 |  | 146.82 | 70 | 9555 | 10277.4 | 0 | 10277.4
TOTAL CARRIED TO SUMMARY | [7 empty] | 16448.7 | 16527.8 | 0 | 16527.8
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class C-7
| a) massonary foundation | M2 | 11 | 12.8 |  | 12.8 | 100 | 1100 | 1280 | 0 | 1280
2.2 | 10cm thick reinforced concrete floor slab class C-20, | M2 | 38 | 30.81 |  | 30.81 | 350 | 13300 | 10783.5 | 0 | 10783.5
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 2.44 | 2.86 |  | 2.86 | 2900 | 7076 | 8294 | 0 | 8294
2.4 | form work or metal panel. To:-
| a) In grade beam & step | M2 | 6.8 | 19.68 |  | 19.68 | 120 | 816 | 2361.6 | 0 | 2361.6
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 125 | 235.76 |  | 235.76 | 38 | 4750 | 8958.88 | 0 | 8958.88
| b) Dia. 12mm deformed bar | Kg | 58 | 0 |  | 0 | 38 | 2204 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 51 | 73.94 |  | 73.94 | 38 | 1938 | 2809.72 | 0 | 2809.72
2.6 | 12/2 cm chip wood expansion joint between | m | 26 | 24 |  | 24 | 15 | 390 | 360 | 0 | 360
TOTAL CARRIED TO SUMMARY | [7 empty] | 31574 | 34847.7 | 0 | 34847.7
3. Masonry Work
3.1 | 50cm stone masonryB NGL | M3 | 10.4 | 19.18 |  | 19.18 | 1000 | 10400 | 19180 | 0 | 19180
3.2 | Ditto but ANGL | M3 | 3.2 | 0 |  | 0 | 1100 | 3520 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 13920 | 19180 | 0 | 19180
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 1 | 0.65 |  | 0.65 | 2900 | 2900 | 1885 | 0 | 1885
| b) In beams | M3 | 1.22 | 3.76 |  | 3.76 | 2900 | 3538 | 10904 | 0 | 10904
| c) In concrete roof slab (10cm thick) | M3 | 5.57 | 6.4 |  | 6.4 | 2900 | 16153 | 18560 | 0 | 18560
| d) Lintels | M3 | 0.8 | 0 |  | 0 | 2900 | 2320 | 0 | 0 | 0
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 57.13 | 14.58 |  | 14.58 | 100 | 5713 | 1458 | 0 | 1458
* | b) In beams | M2 |  | 44.03 |  | 44.03 | 100 | 0 | 4403 | 0 | 4403
| b) In concrete roof slab (12cm thick) | M2 | 50 | 46.76 |  | 46.76 | 1000 | 50000 | 46760 | 0 | 46760
| c) Lintel | M2 | 3.41 | 0 |  | 0 | 100 | 341 | 0 | 0 | 0
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg |  | 600.63 |  | 600.63 | 38 | 0 | 22823.94 | 0 | 22823.94
| b) Dia. 12mm deformed bar | Kg | 217 | 0 |  | 0 | 38 | 8246 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 330 | 431.42 |  | 431.42 | 38 | 12540 | 16393.96 | 0 | 16393.96
| d) Dia. 6 mm deformed bar | Kg | 217 | 0 |  | 0 | 38 | 8246 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 109997 | 123187.9 | 0 | 123187.9
7.PAINTING
7.1 | External rendered surface | M2 | 75.5 | 0 | 63.84 | 63.84 | 26 | 1963 | 0 | 1659.84 | 1659.84
7.2 | Internal plastered surfaceand external beams & columns | M2 | 100 | 0 | 50.46 | 63.84 | 26 | 2600 | 0 | 1311.96 | 1311.96
7.3 | Concrete celling surface | M2 | 46.41 | 0 | 46.76 | 50.46 | 26 | 1206.66 | 0 | 1215.76 | 1215.76
TOTAL CARRIED TO SUMMARY | [7 empty] | 5769.66 | 0 | 4187.56 | 4187.56

## TOS Trans (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :-Transformer House
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3 Masonery wall
2 | 3.5 |  | 3.1 50 cm thick stone massonery
| 0.5 |  | For electrical cable work
0.75
2.63
2 | 4
0.5
0.75
3
|  | 5.63 | Total of item 3.1
6. Finishing
2 | 10.7 |  | 6.7 1.2 m pavement
1.2
25.68
2 | 4.5
1.2
10.8
|  | 36.48 | Total of item 6.7

## TOS Tran
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Payment 14
Client:- Oromia Regional State Health Bureau | [6 empty] | Block: - Transformer House
T | D | S | Item No. and Description | T | D | S | Item No. and Description
7.PAINTING
7.1. External rendered surface
Ditto Item no 6.1
1 | 63.84
|  | 63.84 | n2 net area to item no 7.1
7.2. Internal plastered wall ext beams & colmn
Ditto Item no 6.2
1 | 50.46
|  | 50.46 | n2 net area to item no 7.2
7.3. Concrete Ceiling
Ditto Item no 1.2.b
1 | 46.76
|  | 46.76 | n2 net area to item no 7.3

## Sum Kit
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for KITCHEN - No 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 158702.47 | 132085.35 | 0 | 132085.35
2 | CONCRETE WORKS | 290036.91 | 246525.28 | 0 | 246525.28
3 | MASONARY WORKS | 194000 | 158765 | 0 | 158765
TOTAL A |  | 642739.38 | 537375.63 | 0 | 537375.63
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 138910.74 | 94373.42 | 2107.89 | 96481.31
2 | Block Work | 135130 | 113946 | 0 | 113946
3 | ROOFING | 97398.3 | 90441.8 | 0 | 90441.8
4 | CARPENTRY & JOINERY | 61495 | 35419.67 | 77976 | 113395.67
5 | METAL WORKS | 82173 | 81965 | 0 | 81965
6 | Finishing Work | 325665.4 | 302068.2 | 4194 | 306262.2
7 | GLAZING WORK | 16220 | 5632 | 0 | 5632
8 | PAINTING WORK | 33103.46 | 14777.1 | 0 | 14777.1
9 | SANITARY INSTALLATION | 29525 | 8699.75 | 22844 | 31543.75
10 | ELECTRICAL INSTALLATION | 204245 | 111875 | 0 | 111875
TOTAL B |  | 1123865.9 | 859197.94 | 107121.89 | 966319.83
TOTAL A + B |  | 1766605.28 | 1396573.57 | 107121.89 | 1503695.46

## Meas Kit
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Kitchen - NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 403.52 | 401.45 |  | 401.45 | 6 | 2421.12 | 2408.7 | 0 | 2408.7
1.2 | Bulk Excavation | M3 | 432.03 | 353.28 |  | 353.28 | 50 | 21601.5 | 17664 | 0 | 17664
1.4 | Trench Excavation | M3 | 150 | 94.5 |  | 94.5 | 40 | 6000 | 3780 | 0 | 3780
1.5 | Selected backfill | M3 | 500 | 476.62 |  | 476.62 | 100 | 50000 | 47662 | 0 | 47662
1.6 | Car away | M3 | 697.1 | 568.22 |  | 568.22 | 70 | 48797 | 39775.4 | 0 | 39775.4
1.7 | 25cm thick stone hard core | M2 | 279.21 | 244.65 |  | 244.65 | 85 | 23732.85 | 20795.25 | 0 | 20795.25
| TOTAL CARRIED TO SUMMARY | [6 empty] | 152552.47 | 132085.35 | 0 | 132085.35
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class C-7
| a) massonary foundation | M2 | 95 | 91.6 |  | 91.6 | 100 | 9500 | 9160 | 0 | 9160
2.2 | 10cm thick reinforced concrete floor slab | M2 | 279.21 | 244.65 |  | 244.65 | 350 | 97723.5 | 85627.5 | 0 | 85627.5
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 20.59 | 18.9 |  | 18.9 | 2900 | 59711 | 54810 | 0 | 54810
2.4 | wood form work or metal panel. To:-
| a) In grade beam & step | M2 | 148.74 | 73.8 |  | 73.8 | 120 | 17848.8 | 8856 | 0 | 8856
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 1415.66 | 1393.49 |  | 1393.49 | 38 | 53795.08 | 52952.62 | 0 | 52952.62
| b) Dia. 12mm deformed bar | Kg | 1264.81 | 0 |  | 0 | 38 | 48062.78 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 0 | 820.57 |  | 820.57 | 38 | 0 | 31181.66 | 0 | 31181.66
2.6 | 10/2 cm chip wood expansion joint between | m | 183.05 | 262.5 |  | 262.5 | 15 | 2745.75 | 3937.5 | 0 | 3937.5
| TOTAL CARRIED TO SUMMARY | [6 empty] | 289386.91 | 246525.28 | 0 | 246525.28
3. Masonry Work
3.1 | 50cm stone masonrey BNGL | M3 | 95 | 127.58 |  | 127.58 | 1000 | 95000 | 127580 | 0 | 127580
3.2 | Ditto but ANGL | M3 | 90 | 28.35 |  | 28.35 | 1100 | 99000 | 31185 | 0 | 31185
| TOTAL CARRIED TO SUMMARY | [6 empty] | 194000 | 158765 | 0 | 158765
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 3.6 | 3.24 |  | 3.24 | 2900 | 10440 | 9396 | 0 | 9396
| b) In beams | M3 | 11.16 | 10.55 |  | 10.55 | 2900 | 32364 | 30595 | 0 | 30595
| d) Lintels | M3 | 0 |  | 0.21 | 0.21 | 2901 | 0 | 0 | 609.21 | 609.21
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 84.48 | 64.8 |  | 64.8 | 100 | 8448 | 6480 | 0 | 6480
| b) In concrete roof slab (12cm thick) | M2 | 148.74 | 0 |  | 0 | 100 | 14874 | 0 | 0 | 0
| b) In beams | M2 |  | 140.6 |  | 140.6 | 100 | 0 | 14060 | 0 | 14060
| c) Lintel | M2 | 9.3 | 0 | 3.45 | 3.45 | 100 | 930 | 0 | 345 | 345
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 1381.07 | 668.56 | 20.96 | 689.52 | 38 | 52480.66 | 25405.28 | 796.48 | 26201.76
| c) Dia. 8 mm deformed bar | Kg | 441.16 | 222.03 | 9.4 | 231.43 | 38 | 16764.08 | 8437.14 | 357.2 | 8794.34
| d) Dia. 6 mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 136300.74 | 94373.42 | 2107.89 | 96481.31
2. BLOCK WORK
Concrete block wall class "B" beded in cement mortar
| a) 20 cm thick | M2 | 349.63 | 277.41 |  | 277.41 | 320 | 111881.6 | 88771.2 | 0 | 88771.2
| b) 150 cm thick | M2 | 83.03 | 89.91 |  | 89.91 | 280 | 23248.4 | 25174.8 | 0 | 25174.8
| TOTAL CARRIED TO SUMMARY | [6 empty] | 135130 | 113946 | 0 | 113946
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 230 | 337.77 |  | 337.77 | 230 | 52900 | 77687.1 | 0 | 77687.1
3.2 | G-30 Ribbed sheet ceiling under eave | M2 | 45.84 | 51.59 |  | 51.59 | 130 | 5959.2 | 6706.7 | 0 | 6706.7
3.4 | G-30 flat metal sheet gutter | ml | 76.4 | 75.6 |  | 75.6 | 80 | 6112 | 6048 | 0 | 6048
| TOTAL CARRIED TO SUMMARY | [6 empty] | 64971.2 | 90441.8 | 0 | 90441.8
4.CARPENTRY & JOINERY
4.1 | by 6mm plain bar carpentry swan eucalyptus truss
| a) diameter 10 -12cm | m | 503.5 | 486.71 |  | 486.71 | 22 | 11077 | 10707.62 | 0 | 10707.62
| b) diameter 8 - 10cm | m | 506 | 365.03 |  | 365.03 | 15 | 7590 | 5475.45 | 0 | 5475.45
| c) Purlin zigba size 5/7cm | m | 414 | 433.8 |  | 433.8 | 32 | 13248 | 13881.6 | 0 | 13881.6
4.2 | 25*2.5 cm Zigba wooden fascia board | m | 70.8 | 76.5 |  | 76.5 | 70 | 4956 | 5355 | 0 | 5355
4.3 | Supply and fix 40mm thick wood framed door
| a) Type D1 size-90/270cm | No | 2 | 0 | 2 | 2 | 4617 | 9234 | 0 | 9234 | 9234
| b) Type D2 size -80/270cm | No | 2 | 0 | 8 | 8 | 7695 | 15390 | 0 | 61560 | 61560
| c) Type D3 size -70/270cm | No | 0 | 0 | 2 | 2 | 3591 | 0 | 0 | 7182 | 7182
| e) Type D7 size -120/270cm | No | 0 | 0 |  | 0 | 6156 | 0 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 61495 | 35419.67 | 77976 | 113395.67
5.METAL WORKS
5.1 | Windows
| a) W1- 1.20/1.60m | no | 5 | 5 |  | 5 | 2496 | 12480 | 12480 | 0 | 12480
| b) W2- 1.40/1.60m | no | 6 | 7 |  | 7 | 2912 | 17472 | 20384 | 0 | 20384
| c) W3- 1.50/1.60m | no | 2 | 1 |  | 1 | 3120 | 6240 | 3120 | 0 | 3120
| d)WT - 0.90/0.60m | no | 4 | 4 |  | 4 | 702 | 2808 | 2808 | 0 | 2808
5.2 | Doors
| a) D2- 80/2.70cm | no | 8 | 8 |  | 8 | 2808 | 22464 | 22464 | 0 | 22464
| b)D3 - 70/2.70cm | no | 2 | 2 |  | 2 | 2457 | 4914 | 4914 | 0 | 4914
| C) D4 - 1.50/2.70cm | no | 1 | 1 |  | 1 | 5265 | 5265 | 5265 | 0 | 5265
| d) D5 - 1.80/2.70cm | no | 1 | 1 |  | 1 | 6318 | 6318 | 6318 | 0 | 6318
| e) D5 - 1.20/2.70cm | no | 1 | 1 |  | 1 | 4212 | 4212 | 4212 | 0 | 4212
| TOTAL CARRIED TO SUMMARY | [6 empty] | 82173 | 81965 | 0 | 81965
6. FINISHING
6.1 | Apply two coats of plastering and one coat of renering | M2 | 174.3 | 144.57 |  | 144.57 | 90 | 15687 | 13011.3 | 0 | 13011.3
6.2 | Apply three coats of plastering | M2 | 664 | 716.66 |  | 716.66 | 100 | 66400 | 71666 | 0 | 71666
6.3 | Chip wood ceiling | M2 | 279.21 | 279.21 |  | 279.21 | 240 | 67010.4 | 67010.4 | 0 | 67010.4
6.4 | 200*300*6mm glazed ceramic wall | M2 | 61.2 | 185.83 |  | 185.83 | 290 | 17748 | 53890.7 | 0 | 53890.7
6.5 | 8mm thick non slippery ceramic | M2 | 288 | 198.77 | 13.98 | 212.75 | 300 | 86400 | 59631 | 4194 | 63825
6.6 | Ceramic tile skiring 10/0.8cm | ml | 243 | 77.9 |  | 77.9 | 100 | 37800 | 7790 | 0 | 7790
6.7 | Terrazo window cill bedded on | ml | 22 | 32.25 |  | 32.25 | 150 | 10950 | 4837.5 | 0 | 4837.5
6.8 | 30/30/3mm angle iron corner protection | M2 | 6 | 6 |  | 6 | 70 | 252 | 420 | 0 | 420
6.9 | 10cm thick c-20 RC 1.2m wide pavement | M2 | 87.5 | 90.84 |  | 90.84 | 320 | 28000 | 29068.8 | 0 | 29068.8
6.1 | concret pipes of half diameter 30cm | ml | 80 |  |  | 0 | 100 | 8000 | 0 | 0 | 0
6.11 | 10X40cm curb stone around the building | ml | 80 |  |  | 0 | 105 | 8400 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 346647.4 | 302068.2 | 4194 | 306262.2
7.PAINTING
Prepare and apply by brush three coats of plastic emulsion paint to:
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 398 | 144.57 |  | 144.57 | 26 | 10348 | 3758.82 | 0 | 3758.82
7.2 | Dito to Chip wood ceiling surface | M2 | 279.21 | 279.21 |  | 279.21 | 26 | 7259.46 | 7259.46 | 0 | 7259.46
7.3 | Oil paint to a height of 150cm | M2 | 398 | 0 |  | 0 | 17.33 | 6897.34 | 0 | 0 | 0
7.4 | Ditto to External rendered surface | M2 | 198 | 144.57 |  | 144.57 | 26 | 5148 | 3758.82 | 0 | 3758.82
TOTAL CARRIED TO SUMMARY | [7 empty] | 29652.8 | 14777.1 | 0 | 14777.1
8.GLAZING
Supply and fix quality clear and forested glass glazed to metal beads and putty
8.1 | 4mm thick clear glass | M2 | 5 | 25.6 |  | 25.6 | 220 | 1100 | 5632 | 0 | 5632
8.2 | 4mm thick frosted glass | M2 | 42 |  |  | 0 | 360 | 15120 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 16220 | 5632 | 0 | 5632
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R/GS water pipes
| 20mm diameter;internal | lm | 15 | 45.05 |  | 45.05 | 75 | 1125 | 3378.75 | 0 | 3378.75
9.5 | Supply and install waste water pipes made of rigid plastic pipe (upvc)
| 50mm diameter | lm | 16 | 30.85 |  | 30.85 | 60 | 960 | 1851 | 0 | 1851
| 75mm diameter | lm | 10 | 16.6 |  | 12.6 | 90 | 900 | 1494 | 0 | 1494
| 100mm diameter | lm | 14 | 9.8 |  | 9.8 | 120 | 1680 | 1176 | 0 | 1176
9.6 | Supply and fix 500x400mm white vitreous china hand wash basin | No | 4 |  | 4 | 4 | 600 | 2400 | 0 | 2400 | 2400
9.7 | Supply and fix low flush white vitreous china water closet | No | 2 |  | 2 | 2 | 900 | 1800 | 0 | 1800 | 1800
9.9 | Supply and fix toilet paper holder | No | 2 |  | 2 | 2 | 90 | 180 | 0 | 180 | 180
9.1 | Supply and fix crystal glass mirror | No | 4 |  | 4 | 4 | 200 | 800 | 0 | 800 | 800
9.11 | Supply and install shower units made of chrome-plated shower | No | 2 | 2 |  | 2 | 400 | 800 | 800 | 0 | 800
9.12 | Supply and fix 600mm long towel hanger for showers | No | 2 |  | 2 | 2 | 200 | 400 | 0 | 400 | 400
9.14 | Supply and install electric water heater | No | 2 |  | 4 | 4 | 2000 | 4000 | 0 | 8000 | 8000
9.16 | Supply and fix 80mm diameter floor drain | No | 7 |  | 4 | 4 | 120 | 840 | 0 | 480 | 480
9.18 | Supply and fix 100mm 3.2mm thickness down pipes mode | ml | 36 |  | 57.6 | 57.6 | 90 | 3240 | 0 | 5184 | 5184
9.2 | Supply & fix Stainless steel sink chemical resistant with Double | No | 3 |  | 4 | 4 | 900 | 2700 | 0 | 3600 | 3600
| TOTAL CARRIED TO SUMMARY | [6 empty] | 21825 | 8699.75 | 22844 | 31543.75
10. ELECTRICAL INSTALLATION
2. Feeder Cables & Pipes
2.2 | 5x16 sq. mm from SDB up to Laundary machine | M | 20 | 20 |  | 20 | 325 | 6500 | 6500 | 0 | 6500
2.3 | 5X10 sq. mm from SDB up to Ironing machine | M | 20 | 20 |  | 20 | 200 | 4000 | 4000 | 0 | 4000
2.4 | 5X6 sq. mm from SDB up to Stove PVC pipes | M | 50 | 45 |  | 45 | 140 | 7000 | 6300 | 0 | 6300
PVC Pipes
2.4 | 32 mm diameter. | M | 600 | 45 |  | 45 | 50 | 30000 | 2250 | 0 | 2250
2.5 | 50mm diameter | M | 180 | 20 |  | 20 | 60 | 10800 | 1200 | 0 | 1200
2.6 | 75mm diameter | M | 60 | 20 |  | 20 | 70 | 4200 | 1400 | 0 | 1400
| 100mm diameter | M |  | 900 |  | 900 | 85 | 0 | 76500 | 0 | 76500
5 | Light Points
5.1 | Flush mounted light points fed through PVC | No | 38 | 38 |  | 38 | 200 | 7600 | 7600 | 0 | 7600
6 | Extra Over Light Points for Flush Mounted Switches
6.3 | Flush mounted Socket Outlet Points | No | 6 | 5 |  | 5 | 85 | 510 | 425 | 0 | 425
7. Flush Mounted Socket Outlet Points
7.1 | 10-16A/1P socket outlet points fed through PVC | No | 26 | 26 |  | 26 | 200 | 5200 | 5200 | 0 | 5200
7.2 | 20-25A/1P socket outlet points fed through PVC | No | 1 | 1 |  | 1 | 200 | 200 | 200 | 0 | 200
7.2 | 32A/3P socket outlet points fed through PVC | No | 1 | 1 |  | 1 | 300 | 300 | 300 | 0 | 300
| TOTAL CARRIED TO SUMMARY | [6 empty] | 76310 | 111875 | 0 | 111875

## TOS Kichen (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Kitchen
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6. Finishing Works | 1 | 22.7 |  | Corridor
|  |  | 6.5:- 8mm Thick CeramicTile Flooring |  | 1.45
1 | 5.1 |  | Disinfection |  |  | 32.915
| 2.75 |  |  | 1 | 1.25
|  | 14.025 |  |  | 0.25
1 | 0.8 |  |  |  |  | 0.3125
| 0.25 |  |  |  |  | 33.2275 | m2 sub total
|  | 0.2 |  | 1 | 4.95 |  | Cooking / Food Prep
|  | 14.225 | m2 sub total |  | 7.95
1 | 5.15 |  | Receving /Storeing |  |  | 39.3525
| 2.8 |  |  | 2 | 1.5
|  | 14.42 |  |  | 0.25
1 | 0.8 |  |  |  |  | 0.75
| 0.25 |  |  |  |  | 40.1025 | m2 sub total
|  | 0.2 |  | 1 | 4.95 |  | Store
|  | 14.62 | m2 sub total |  | 2.95
2 | 3 |  | Office 1&2 |  |  | 14.6025
| 2.45 |  |  | 1 | 0.8
|  | 14.7 |  |  | 0.25
2 | 0.8 |  |  |  |  | 0.2
| 0.25 |  |  |  |  | 14.8025 | m2 sub total
|  | 0.4 |  |  |  | 198.7725 | Total of item 6.5
|  | 15.1 | m2 sub total
1 | 5.7 |  | Corridor
1.75
|  | 9.975 | m2 sub total
1 | 2.7 |  | Server
5.15
13.905
1 | 2.65
0.25
0.6625
|  | 14.5675 | m2 sub total
1 | 2.7 |  | Baciling
5.1
13.77
2 | 2
0.2
0.8
|  | 14.57 | m2 sub total
1 | 5.1 |  | Dough
2.8
14.28
1 | 3.45
0.25
0.8625
|  | 15.1425 | m2 sub total
1 | 5.1 |  | Store
2.4
12.24
1 | 0.8
0.25
0.2
|  | 12.44 | m2 sub total
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Kitchen
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A)SUB-STRUCTURE
1) EXCAVATION & EARTH WORK
1.6 Cart away surplus excavation material
| 401.45 |  | From item 1.1
0.3
120.44
|  | 353.27 | From item 1.2
|  | 94.5 | From item 1.4
|  | 568.21 | Total 1.6
|  | 568.22 | Previous payment
|  | -0.01 | m3 total of item 1.6 Remaining

## TOS Kit
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [6 empty] | Block: - Kitchen
Client: - Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | 6.5. 8mm thick non slippery ceramic 30x30x8cm
|  |  | 1. CONCRETE WORKS | 2 | 2.5 |  | Toilet Ladies & Gentes Corridor
|  |  | 1.1. Reinforced concrete class C-25 |  | 1.5 | 7.5
c) Lintel
2 | 1.2 |  | D2 | 4 | 1.35 |  | "
| 0.15 |  |  |  | 1.2 | 6.48
| 0.3 | 0.11
[6 empty] | 13.98 | m2 net area item 6.5
2 | 1.1 |  | D3
| 0.15 | [5 empty] | 6.6. Ceramic tile skirling 10/0.8cm
| 0.3 | 0.1 |  | 4 | 5.1 |  | Disinfection & Receiving Room
20.4
|  | 0.21 | m3 net area item 1.1.c
|  |  |  | 2 | 2.82 |  | "
|  |  | 1.2. form work or metal panel. To:- |  |  | 5.64
c) Lintel
2 | 1.2 |  | D2 | 2 | 2 |  | "
| 0.75 | 1.8 |  |  |  | 4
2 | 1.1 |  | D2 | 3 | 3.1 |  | Office
| 0.75 | 1.65 |  |  |  | 9.3
|  | 3.45 | m2 net area item 1.2.c | 3 | 2.4 |  | "
7.2
1.3. Reinforcement steel bars
|  |  | b. ф12 mm deformed bars | 1 | 2.3 |  | "
1 | 20.96 |  |  |  |  | 2.3
|  | 20.96 | kg net wight item 1.3.b
|  |  |  | 1 | 1.6 |  | "
1 | 9.4 |  | c. ф8 mm deformed bars |  |  | 1.6
|  | 9.4 | kg net wight item 1.3.c
|  |  |  | 2 | 5.1 |  | Store
|  |  | 4.CARPENTRY & JOINERY |  |  | 10.2
4.3. Wood framed door
|  |  | a) Doors Type D1 size -90/270cm | 1 | 2.4 |  | "
1 | 2 |  |  |  |  | 2.4
|  | 2 | Pcs net number item 4.3.a
|  |  |  | 1 | 1.5 |  | "
|  |  | b) Doors Type D2 size -80/270cm |  |  | 1.5
1 | 8
|  | 8 | Pcs net number item 4.3.b | 1 | 15 |  | Main Corridor
15
c) Doors Type D3 size -70/270cm
1 | 2 |  |  | 1 | 11.2 |  | "
|  | 2 | Pcs net number item 4.3.c |  |  | 11.2
|  |  |  | 1 | 5.5 |  | Office Corridor
5.5
|  |  |  | 1 | 4.7 |  | "
4.7
[6 empty] | 100.94 | m net Length item 6.6
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 9. SANITARY INSTALLATION | 1 | 1.5 |  | "
|  |  | 9.6. Hand wash basin |  |  | 1.5
1 | 4
|  | 4 | Pcs net number item 9.6 | 1 | 15 |  | Main Corridor
15
9.7. Water closet
1 | 2 |  |  | 1 | 11.2 |  | "
|  | 2 | Pcs net number item 9.7 |  |  | 11.2
|  |  | 9.9. Toilet paper holder | 1 | 5.5 |  | Office Corridor
1 | 2 |  |  |  |  | 5.5
|  | 2 | Pcs net number item 9.9
|  |  |  | 1 | 4.7 |  | "
|  |  | 9.10. Crystal glass mirror |  |  | 4.7
1 | 4
|  | 4 | Pcs net number item 9.10 |  |  | 77.9 | m net Length item 6.6
|  |  | 9.12. Towel hanger |  |  |  | 7.PAINTING
1 | 2 | [5 empty] | 7.1. Internal plastered wall ext. beams & column
|  | 2 | Pcs net number item 9.12 |  |  |  | Ditto Item no 6.2
|  |  |  | 1 | 144.57
|  |  | 9.14. Electric water heater |  |  | 144.57 | n2 net area to item no 7.1
1 | 5
|  | 5 | Pcs net number item 9.14 |  |  |  | 7.2. Chip wood Celling
Ditto Item no 6.3
|  |  | 9.16. 50mm diameter floor drain | 1 | 279.21
1 | 4 |  |  |  |  | 279.21 | n2 net area to item no 7.2
|  | 4 | Pcs net number item 9.10
7.4. External rendered surface
|  |  | 9.18. 100mm Down pipes |  |  |  | Ditto Item no 6.1
1 | 57.6 |  |  | 1 | 144.57
|  | 57.6 | Pcs net number item 9.18 |  |  | 144.57 | n2 net area to item no 7.4
|  |  | 9.20. Double Bowl Stainless Steel |  |  |  | 8.GLAZING
1 | 4 | [5 empty] | 8.1. 4mm thick clear glass
|  | 4 | Pcs net number item 9.20 | 4 | 1.2 |  | W1
2 | 2 |  | " |  | 1.6 | 7.68
4
|  |  |  | 8 | 1.4 |  | W2
3 | 3.1 |  | Office |  | 1.6 | 17.92
9.3
[6 empty] | 25.6 | m2 net area to item no 8.1
3 | 2.4 |  | "
7.2
1 | 2.3 |  | "
2.3
1 | 1.6 |  | "
1.6
2 | 5.1 |  | Store
10.2
1 | 2.4 |  | "
2.4

## Kit Bar
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [9 empty] | Block : - Kitchen
Client: - Oromia Regional State Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Lintel
| D2 |  | 12 | 1.75 | 2 | 2 | 4 |  |  |  | 7
|  |  | 12 | 1.15 | 2 | 2 | 4 | - | - | - | 4.6 | -
| Stirrups |  | 8 | 0.85 | 2 | 7 | 14 | - | 11.9 | - | - | -
[8 empty] | - | - | - | - | -
| D3 |  | 12 | 1.75 | 2 | 2 | 4 |  |  |  | 7
|  |  | 12 | 1.25 | 2 | 2 | 4 | - | - | - | 5 | -
| Stirrups |  | 8 | 0.85 | 2 | 7 | 14 | - | 11.9 | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
TOTAL LENGTH | [8 empty] | 23.8 | 0 | 23.6 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 9.4 | 0 | 20.96 | 0

## Sum Sto
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for STORE - No 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A. SUB-STRUCTURE
1 | EXCAVATION & EARTH WORKS | 53013.4 | 19493.65 | 9913.4 | 29407.05
2 | CONCRETE WORKS | 94381.36 | 80492.32 | 0 | 80492.32
3 | MASONARY WORKS | 73500 | 25250 | 0 | 25250
TOTAL A |  | 220894.76 | 125235.97 | 9913.4 | 135149.37
B. SUPER- STRUCTURE
1 | CONCRETE WORKS | 83514.36 | 61913.2 | 0 | 61913.2
2 | BLOCK WORK | 66072.8 | 79254.4 | 3100.8 | 82355.2
3 | ROOFING | 35946.6 | 22859.6 | 1520 | 24379.6
4 | CARPENTRY & JOINERY | 38784 | 8493.21 | 0 | 8493.21
5 | METAL WORKS | 16458 | 16458 | 0 | 16458
6 | FINISHING | 181950 | 89907.1 | 2280 | 92187.1
7 | GLAZING WORK | 19100
8 | PAINTING WORK | 34672.04 |  | 0
9 | SANITARY INSTALLATION | 28325
10 | ELECTRICAL INSTALLATION | 26625
TOTAL B |  | 531447.8 | 278885.51 | 6900.8 | 285786.31
TOTAL A + B |  | 752342.56 | 404121.48 | 16814.2 | 420935.68

## Meas Sto
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Store - NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear of site | M2 | 144.5 | 144.5 |  | 144.5 | 6 | 867 | 867 | 0 | 867 | 867 | 0
1.2 | Bulk Excavation | M3 | 115.5 | 124.27 |  | 124.27 | 50 | 5775 | 6213.5 | 0 | 6213.5 | 5775 | 0
1.4 | Trench Excavation | M3 | 38.5 | 22.75 |  | 22.75 | 40 | 1540 | 910 | 0 | 910 | 1540 | 0
1.5 | Selected backfill | M3 | 205 | 26.09 |  | 26.09 | 100 | 20500 | 2609 | 0 | 2609 | 20500 | 0
1.6 | Cart away | M3 | 197.35 | 48.75 | 141.62 | 190.37 | 70 | 13814.5 | 3412.5 | 9913.4 | 13325.9 | 13814.5 | 0
1.7 | 25cm thick stone hard core | M2 | 73.14 | 64.49 |  | 64.49 | 85 | 6216.9 | 5481.65 | 0 | 5481.65 | 6216.9 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 48713.4 | 19493.65 | 9913.4 | 29407.05 | 53013.4 | 0
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete class C-7
| a) massonary foundation | M2 | 35 | 25.25 |  | 25.25 | 100 | 3500 | 2525 | 0 | 2525 | 3500 | 0
2.2 | 10cm thick floor slab class C-20, | M2 | 73.14 | 64.49 |  | 64.49 | 350 | 25599 | 22571.5 | 0 | 22571.5 | 25599 | 0
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 7.55 | 5.3 |  | 5.3 | 2900 | 21895 | 15370 | 0 | 15370 | 21895 | 0
2.4 | form work or metal panel. To:- | [10 empty] | 0 | 0
| a) In grade beam & step | M2 | 44.4 | 41.8 |  | 41.8 | 120 | 5328 | 5016 | 0 | 5016 | 5328 | 0
2.5 | Reinforcement steel bar | [10 empty] | 0 | 0
| a) Dia. 14mm deformed bar | Kg | 343.41 | 469.12 |  | 469.12 | 38 | 13049.58 | 17826.56 | 0 | 17826.56 | 13049.58 | 0
| b) Dia. 12mm deformed bar | Kg | 471.81 | 0 |  | 0 | 38 | 17928.78 | 0 | 0 | 0 | 17928.78 | 0
| c) Dia. 8 mm deformed bar | Kg | 0 | 431.27 |  | 431.27 | 38 | 0 | 16388.26 | 0 | 16388.26 | 0 | 0
2.6 | 12/2 cm chip wood expansion | m | 70.4 | 53 |  | 53 | 15 | 1056 | 795 | 0 | 795 | 1056 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 88356.36 | 80492.32 | 0 | 80492.32 | 94381.36 | 0
3. Masonry Work
3.1 | stone masonrey BNGL | M3 | 35 | 25.25 |  | 25.25 | 1000 | 35000 | 25250 | 0 | 25250 | 35000 | 0
3.2 | Ditto but BNGL | M3 | 35 | 0 |  | 0 | 1100 | 38500 | 0 | 0 | 0 | 38500 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 73500 | 25250 | 0 | 25250 | 73500 | 0
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 2.4 | 1.08 |  | 1.08 | 2900 | 6960 | 3132 | 0 | 3132 | 6960 | 0
| b) In beams | M3 | 9.99 | 6.42 |  | 6.42 | 2900 | 28971 | 18618 | 0 | 18618 | 28971 | 0
1.2 | form work or metal panel. To:- | [10 empty] | 0 | 0
| a) In elevation column | M2 | 26.4 | 21.6 |  | 21.6 | 100 | 2640 | 2160 | 0 | 2160 | 2640 | 0
| b) In beams | M2 |  | 79.68 |  | 79.68 | 100 | 0 | 7968 | 0 | 7968 | 0 | 0
1.3 | Reinforcement steel bars | [10 empty] | 0 | 0
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 696.41 | 536.81 |  | 536.81 | 38 | 26463.58 | 20398.78 | 0 | 20398.78 | 26463.58 | 0
| c) Dia. 8 mm deformed bar | Kg | 276.31 | 253.59 |  | 253.59 | 38 | 10499.78 | 9636.42 | 0 | 9636.42 | 10499.78 | 0
| d) Dia. 6 mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 75534.36 | 61913.2 | 0 | 61913.2 | 83514.36 | 0
| 2. BLOCK WORK | [6 empty] | 0
| a) 20 cm thick | M2 | 171.04 | 208.54 | 9.69 | 218.23 | 320 | 54732.8 | 66732.8 | 3100.8 | 69833.6
| b) 15 cm thick | M2 | 40.5 | 44.72 |  | 44.72 | 280 | 11340 | 12521.6 | 0 | 12521.6
TOTAL CARRIED TO SUMMARY | [7 empty] | 66072.8 | 79254.4 | 3100.8 | 82355.2
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 106.26 | 85.4 |  | 85.4 | 230 | 24439.8 | 19642 | 0 | 19642
3.2 | G-30 Ribbed Sheet | M2 | 26.76 | 9.12 |  | 9.12 | 130 | 3478.8 | 1185.6 | 0 | 1185.6
3.3 | G-30 Flashing | m | 44.6 | 25.4 |  | 25.4 | 80 | 3568 | 2032 | 0 | 2032
3.4 | G-30 flat metal sheet gutter | ml | 44.6 | 0 | 15.2 | 15.2 | 100 | 4460 | 0 | 1520 | 1520
TOTAL CARRIED TO SUMMARY | [7 empty] | 35946.6 | 22859.6 | 1520 | 24379.6 | 0 | 0
4.CARPENTRY & JOINERY
4.1 | by 6mm plain bar carpentry swan eucalyptus truss
| a)Upper & lower chord size-diameter 10 -12cm | m | 226 | 127.08 |  | 127.08 | 22 | 4972 | 2795.76 | 0 | 2795.76 | 7436 | 0
| b) Diagonal & vertical Members size diameter 8 - 10cm | m | 201 | 74.63 |  | 74.63 | 15 | 3015 | 1119.45 | 0 | 1119.45 | 4290 | 0
| c) Purlin zigba size 5/7cm | m | 316 | 112 |  | 112 | 32 | 10112 | 3584 | 0 | 3584 | 9216 | 0
4.2 | 25*2.5 cm Zigba wooden fascia board | m | 39 | 14.2 |  | 14.2 | 70 | 2730 | 994 | 0 | 994 | 4480 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 20829 | 8493.21 | 0 | 8493.21 | 25422 | 0
5.METAL WORKS
5.1 | Windows
| a) W1 - 120/150cm | no | 1 | 1 |  | 1 | 2340 | 2340 | 2340 | 0 | 2340
| b) W2 - 150/60cm | no | 1 | 1 |  | 1 | 1170 | 1170 | 1170 | 0 | 1170
| c) W3 - 200/60cm | no | 2 | 2 |  | 2 | 1560 | 3120 | 3120 | 0 | 3120
5.2 | Doors |  |  | 0
| a) D1 - 280/270cm | no | 1 | 1 |  | 1 | 9828 | 9828 | 9828 | 0 | 9828
TOTAL CARRIED TO SUMMARY | [7 empty] | 16458 | 16458 | 0 | 16458
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendering | M2 | 169.32 | 125.34 |  | 125.34 | 90 | 15238.8 | 11280.6 | 0 | 11280.6
6.2 | Apply three coats of plastering | M2 | 229.98 | 246.6 |  | 246.6 | 100 | 22998 | 24660 | 0 | 24660
6.3 | Chip wood celling | M2 | 73.14 | 61.03 |  | 61.03 | 230 | 16822.2 | 14036.9 | 0 | 14036.9
6.5 | 8mm thick non slippery ceramic | M2 | 288 | 73.5 |  | 73.5 | 300 | 86400 | 22050 | 0 | 22050
6.6 | Terrazo window cill bedded on | ml | 60 | 6.5 |  | 6.5 | 100 | 6000 | 650 | 0 | 650
6.7 | Size 27/3 cm | m | 12 | 1.2 |  | 1.2 | 150 | 1800 | 180 | 0 | 180
6.9 | 10 cm thick C-20 RC wide pavement | M | 24.3 | 53.28 |  | 53.28 | 320 | 7776 | 17049.6 | 0 | 17049.6
6.1 | storm water concret pipes of half | ml | 21.9 |  | 22.8 | 22.8 | 100 | 2190 | 0 | 2280 | 2280
TOTAL CARRIED TO SUMMARY | [7 empty] | 159225 | 89907.1 | 2280 | 92187.1
7.PAINTING
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 664 |  | 0 | 0 | 26 | 17264 | 0 | 0 | 0
7.2 | Chip wood ceiling surface | M2 | 73.14 |  |  | 0 | 26 | 1901.64 | 0 | 0 | 0
7.3 | Ditto but iol paint to the light of 150cm | M2 | 398.4 |  |  | 0 | 26 | 10358.4 | 0 | 0 | 0
7.4 | External rendered surface | M2 | 198 |  | 0 | 0 | 26 | 5148 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 34672.04 | 0 | 0 | 0

## TOS Store (hidden)
TAKE OFF SHEET No8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Store
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2. Block work
2.1 Concreat block wall classB (for coping walls
1 | 14.2 |  | 20 cm Thick
0.2
2.84
2 | 5.6
0.2
2.24
|  | 5.08 | M2 Total of item 2.1
3. Roofing works
1 | 14.2 | 14.2 | 3.3 G30 Flashing
2 | 5.6 | 11.2
|  | 25.4 | Ml Total of item 3.3
4. Carperntery & joinery
4.2 25x2.5 Fasical Boared
1 | 14.2 | 14.2
|  | 14.2 | Ml Total of item 4.2
6. Finishing Work
6.9 1.2 cm pavment
2 | 16.6
1.2
39.84
2 | 5.6
1.2
13.44
|  | 53.28 | m2 Total of item6.9
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Store
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A)SUB-STRUCTURE
1) EXCAVATION & EARTH WORK
1.6 Cart away surplus excavation material
1 | 144.5 |  | site clearing
| 0.3 | 43.35
|  | 127.925 | bulk
|  | 46.5 | trench
|  | 217.775 | m3 Total 1.6
|  | 48.75 | Previous payment
|  | 169.03 | m3 total of item 1.6 Remaining

## TOS Sto
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Store
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2. BLOCK WORK
a) 20 cm thick
2 | 2.3 |  | on axis 3 &4 above intermidiate beam
| 1.3 | 5.98
1 | 2.85
| 1.3 | 3.71
|  | 9.69 | m2 net area item 2.b
3. ROOFING
3.4. G-30 flat metal sheet gutter
1 | 15.2
15.2
|  | 15.2 | m net length item 3.4
6. FINISHING
6.15. Concrete Pipe half 30cm
1 | 16.4
16.4
1 | 6.4
6.4
|  | 22.8 | m net length item 6.15
7.PAINTING
7.1. Internal plastered wall ext beams & colmn
Ditto Item no 6.2
1 | 246.6
|  | 0 | n2 net area to item no 7.1
7.4. External rendered surface
Ditto Item no 6.1
1 | 125.34
|  | 0 | n2 net area to item no 7.4

## Mor Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for MORGUE No 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | EXCAVATION & EARTH WORK | 8409 | 13339.16 | 4764.9 | 18104.06
2 | STONE MASONRY | 38000 | 11067 | 0 | 11067
3 | CONCRETE WORK | 29872 | 20776.74 | 0 | 20776.74
TOTAL A |  | 76281 | 45182.9 | 4764.9 | 49947.8
B SUPER STRUCTURE
1 | CONCRTE WORK | 16550 | 12978.64 | 0 | 12978.64
2 | BLOCK WORK | 14080 | 11977.6 | 0 | 11977.6
3 | ROOFING WORK | 14030 | 14666.8 | 1648 | 16314.8
4 | CARPENTRY & JOINERY | 4202 | 7352.64 | 0 | 7352.64
5 | METAL WORKS | 6591 | 6591 | 0 | 6591
6 | FINISHING ORK | 49085 | 38770.4 | 1270 | 40040.4
7 | GLAZING WORK | 1080
8 | PAINTING WORK | 2730 |  | 0
9 | SANITARY INSTALLATION | 13415
10 | ELECTRICAL INSTALLATION | 4725
TOTAL B |  | 126488 | 92337.08 | 2918 | 95255.08
TOTAL A + B |  | 202769 | 137519.98 | 7682.9 | 145202.88

## Mor Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Morgue NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear off site | M2 | 34 | 49.56 |  | 49.56 | 6 | 204 | 297.36 | 0 | 297.36
1.2 | Bulk Excavation | M3 | 17 | 50.8 |  | 50.8 | 50 | 850 | 2540 | 0 | 2540
1.4 | Trench Excavation | M3 | 8 | 18.08 |  | 18.08 | 40 | 320 | 723.2 | 0 | 723.2
1.5 | Selected backfill | M3 | 14 | 76.61 |  | 76.61 | 100 | 1400 | 7661 | 0 | 7661
1.6 | Car away surplus excavated material | M3 | 39 | 15.68 | 68.07 | 83.75 | 70 | 2730 | 1097.6 | 4764.9 | 5862.5
1.7 | 25cm thick stone hard corecrushed stones. | M2 | 11 | 12 |  | 12 | 85 | 935 | 1020 | 0 | 1020
TOTAL CARRIED TO SUMMARY | [7 empty] | 6439 | 13339.16 | 4764.9 | 18104.06
2. CONCRETE WORKS
2.1 | 5cm thick lean concrete
| a) massonary foundation | M2 | 9 | 8.3 |  | 8.3 | 100 | 900 | 830 | 0 | 830
2.2 | 10cm thick reinforced concrete floor slab | M2 | 11 | 12 |  | 12 | 350 | 3850 | 4200 | 0 | 4200
2.3 | Reinforced concrete floor slab class C-25,
| a) In grade beam & step | M3 | 3 | 1.58 |  | 1.58 | 2900 | 8700 | 4582 | 0 | 4582
2.4 | wood form work or metal panel. To:-
| a) In grade beam & step | M2 | 15 | 12.64 |  | 12.64 | 120 | 1800 | 1516.8 | 0 | 1516.8
| b) In footing pad | M2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| c) In footing column | M2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Reinforcement steel bar
| a) Dia. 14mm deformed bar | Kg | 163 | 142.9 |  | 142.9 | 38 | 6194 | 5430.2 | 0 | 5430.2
| b) Dia. 12mm deformed bar | Kg |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 101 | 105.23 |  | 105.23 | 38 | 3838 | 3998.74 | 0 | 3998.74
2.6 | 12/2 cm chip wood expansion joint | Ml | 16 | 14.6 |  | 14.6 | 15 | 240 | 219 | 0 | 219
TOTAL CARRIED TO SUMMARY | [7 empty] | 25522 | 20776.74 | 0 | 20776.74
3. Masonry Work
3.1 | 50cm stone masonreyBNGL | M3 | 16 | 7.14 |  | 7.14 | 1000 | 16000 | 7140 | 0 | 7140
3.2 | Ditto but ANGL | M3 | 20 | 3.57 |  | 3.57 | 1100 | 22000 | 3927 | 0 | 3927
TOTAL CARRIED TO SUMMARY | [7 empty] | 38000 | 11067 | 0 | 11067
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 0.9 | 0.43 |  | 0.43 | 2900 | 2610 | 1247 | 0 | 1247
| b) In beams | M3 | 1 | 0.63 |  | 0.63 | 2900 | 2900 | 1827 | 0 | 1827
1.2 | form work or metal panel. To:-
| a) In elevation column | M2 | 9 | 8.64 |  | 8.64 | 100 | 900 | 864 | 0 | 864
| b) In concrete roof slab (12cm thick) | M2 | 14 | 0 |  | 0 | 100 | 1400 | 0 | 0 | 0
* | b) In beams
| c) Lintel | M2 | 0 | 6.32 |  | 6.32 | 100 | 0 | 632 | 0 | 632
1.3 | Reinforcement steel bars
| a) Dia. 14mm deformed bar | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| b) Dia. 12mm deformed bar | Kg | 190 | 158.24 |  | 158.24 | 38 | 7220 | 6013.12 | 0 | 6013.12
| c) Dia. 8 mm deformed bar | Kg | 40 | 63.04 |  | 63.04 | 38 | 1520 | 2395.52 | 0 | 2395.52
| d) Dia. 6 mm deformed bar | Kg | 0 | 0 |  | 0 | 38 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 16550 | 12978.64 | 0 | 12978.64
2. BLOCK WORK
| a) 20 cm thick | M2 | 44 | 37.43 |  | 37.43 | 320 | 14080 | 11977.6 | 0 | 11977.6
TOTAL CARRIED TO SUMMARY | [7 empty] | 14080 | 11977.6 | 0 | 11977.6
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 25 | 59.16 |  | 59.16 | 230 | 5750 | 13606.8 | 0 | 13606.8
3.3 | G-30 Flashing | m | 76.4 | 10.6 |  | 10.6 | 100 | 7640 | 1060 | 0 | 1060
3.4 | G-30 flat metal sheet | m | 8 |  | 20.6 | 20.6 | 80 | 640 | 0 | 1648 | 1648
TOTAL CARRIED TO SUMMARY | [7 empty] | 14030 | 14666.8 | 1648 | 16314.8
4.CARPENTRY & JOINERY
4.1 | carpentry swan eucalyptus truss
| a)diameter 10 -12cm | m | 45 | 92.72 |  | 92.72 | 22 | 990 | 2039.84 | 0 | 2039.84
| b) diameter 8 - 10cm | m | 24 | 56 |  | 56 | 15 | 360 | 840 | 0 | 840
| c) Purlin zigba size 5/7cm | m | 41 | 86.4 |  | 86.4 | 32 | 1312 | 2764.8 | 0 | 2764.8
4.2 | Zigba wooden fascia board | m | 22 | 24.4 |  | 24.4 | 70 | 1540 | 1708 | 0 | 1708
TOTAL CARRIED TO SUMMARY | [7 empty] | 4202 | 7352.64 | 0 | 7352.64
5.METAL WORKS
5.1 | Windows
| a) W1 - 110/60cm | no | 4 | 4 |  | 4 | 858 | 3432 | 3432 | 0 | 3432
5.2 | Doors
| a) D3 - 90/270cm | no | 1 | 1 |  | 1 | 3159 | 3159 | 3159 | 0 | 3159
TOTAL CARRIED TO SUMMARY | [7 empty] | 6591 | 6591 | 0 | 6591
6. FINISHING
6.1 | Apply 2 coats of plastering and 1 coat of rendering | M2 | 40 | 37.43 |  | 37.43 | 90 | 3600 | 3368.7 | 0 | 3368.7
6.2 | Apply three coats of plastering | M2 | 40 | 35.43 |  | 35.43 | 100 | 4000 | 3543 | 0 | 3543
6.3 | 4mm thick best type plastic ceiling | M2 | 11 | 11.04 |  | 11.04 | 270 | 2970 | 2980.8 | 0 | 2980.8
6.4 | 200X300X6mm glazed ceramic wall | M2 | 26 | 33.27 |  | 33.27 | 290 | 7540 | 9648.3 | 0 | 9648.3
6.6 | Approved type Terrazo window cill | ml | 4.5 | 4.4 |  | 4.4 | 150 | 675 | 660 | 0 | 660
6.7 | 10cm thick C-20 RC 1-2m wide pavement | M2 | 87.5 | 53.28 |  | 53.28 | 320 | 28000 | 17049.6 | 0 | 17049.6
6.8 | Supply and lay storm water concret pipes of half 30cm | ml | 23 | 15.2 | 12.7 | 27.9 | 100 | 2300 | 1520 | 1270 | 2790
TOTAL CARRIED TO SUMMARY | [7 empty] | 49085 | 38770.4 | 1270 | 40040.4
7.PAINTING
Prepare and apply by brush three coats of plastic emulsion paint to:
7.1 | Internal plastered surfaceand external beams & coloumns | M2 | 40 | 0 | 0 | 0 | 26 | 1040 | 0 | 0 | 0
7.2 | Oil paint to a height of 1.5mts | M2 | 25 | 0 |  | 0 | 26 | 650 | 0 | 0 | 0
7.3 | External rendered surface | M2 | 40 | 0 | 0 | 0 | 26 | 1040 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 2730 | 0 | 0 | 0

## Tos Morgue (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Morgue
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3. Roofing works
4 | 2.65 | 10.6 | 3.3 G30 Flashing
|  | 10.6 | Ml Total of item 3.3
4. Carperntery & joinery
4.2 25x2.5 Fasical Boared
2 | 6.9 | 13.8
4 | 2.65 | 10.6
|  | 24.4 | Ml Total of item 4.2
6. Finishing Work
6.9 1.2 cm pavment
2 | 7.85
1.2
39.84
2 | 2.95
1.2
13.44
|  | 53.28 | m2 Total of item6.9
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- | Morgue
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A)SUB-STRUCTURE
1) EXCAVATION & EARTH WORK
1.6 Cart away surplus excavation material
1 | 49.56 |  | site clearing
| 0.3 | 14.87
|  | 50.8 | bulk
|  | 18.08 | trench
|  | 83.75 | m3 Total 1.6
|  | 15.68 | Previous payment
|  | 68.07 | m3 total of item 1.6 Remaining

## TOS Mor
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Morgue
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3. ROOFING
3.4. G-30 flat metal sheet gutter
2 | 6.4
12.8
2 | 3.9
7.8
|  | 20.6 | m net length item 3.4
6. FINISHING
6.15. Concrete Pipe half 30cm
1 | 7.6
7.6
1 | 5.1
5.1
|  | 12.7 | m net length item 6.15
7.PAINTING
7.1. Internal plastered wall ext beams & colmn
Ditto Item no 6.2
1 | 35.43
|  | 0 | n2 net area to item no 7.1
7.3. External rendered surface
Ditto Item no 6.1
1 | 37.43
|  | 0 | n2 net area to item no 7.3

## Gua Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Guard House NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | EXCAVATION & EARTH WORK | 6524 | 19959.95 | 6806.8 | 26766.75
2 | STONE MASONRY | 13800 | 13850 | 0 | 13850
3 | CONCRETE WORK | 72992 | 55587.62 | 0 | 55587.62
TOTAL A |  | 93316 | 89397.57 | 6806.8 | 96204.37
B SUPER STRUCTURE
1 | CONCRTE WORK | 115966 | 14632.34 | 0 | 14632.34
2 | BLOCK WORK | 14480 | 12217.6 | 0 | 12217.6
3 | ROOFING WORK | 9420 | 13606.8 | 0 | 13606.8
4 | CARPENTRY & JOINERY | 11912 | 5644.64 | 0 | 5644.64
5 | METAL WORK | 12496 | 9056 | 0 | 9056
6 | FINISHING ORK | 17540 | 7824 | 0 | 7824
7 | GLAZING WORK | 550 |  |  | 0
8 | PAINTING WORK | 2860 |  | 2118.22 | 2118.22
9 | SANITARY INSTALLATION |  |  |  | 0
10 | ELECTRICAL INSTALLATION | 7180
TOTAL B |  | 192404 | 62981.38 | 2118.22 | 65099.6
TOTAL A + B |  | 285720 | 152378.95 | 8925.02 | 161303.97

## Gua Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Guard House NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. SUB-STRUCTURE
1. EXCAVATION & EARTH WORKS
1.1 | Clear off site | M2 | 14 | 45.9 |  | 45.9 | 6 | 84 | 275.4 | 0 | 275.4
1.2 | Bulk Excavation | M3 | 13 | 84.63 |  | 84.63 | 50 | 650 | 4231.5 | 0 | 4231.5
1.4 | Trench Excavation | M3 | 7 | 23.84 |  | 23.84 | 50 | 350 | 1192 | 0 | 1192
1.5 | Selected backfill | M3 | 26 | 113.78 |  | 113.78 | 100 | 2600 | 11378 | 0 | 11378
1.6 | Car away | M3 | 26 | 25 | 97.24 | 122.24 | 70 | 1820 | 1750 | 6806.8 | 8556.8
1.7 | 25cm thick stone hard core | M2 | 12 | 13.33 |  | 13.33 | 85 | 1020 | 1133.05 | 0 | 1133.05
TOTAL CARRIED TO SUMMARY | [7 empty] | 6524 | 19959.95 | 6806.8 | 26766.75
2. CONCRETE WORKS
3.01 | 5cm thick lean concrete
| a) massonary foundation | M2 | 7 | 8.9 |  | 8.9 | 100 | 700 | 890 | 0 | 890
3.03 | In 10cm thick RC ground slab | M2 | 12 | 13.33 |  | 13.33 | 2900 | 34800 | 38657 | 0 | 38657
3.02 | Reinforced concrete c-25
| a) In grade beam & step | M3 | 1.2 | 1.73 |  | 1.73 | 2900 | 3480 | 5017 | 0 | 5017
2.4 | l form work which
| a) In grade beam & step | M2 | 5 | 13.84 |  | 13.84 | 120 | 600 | 1660.8 | 0 | 1660.8
| a) To elevation column | M2 | 26 | 0 |  | 0 | 110 | 2860 | 0 | 0 | 0
2.5 | Mild steel reinforcements
| a) Dia. 14mm deformed bar | Kg | 43 | 142.9 |  | 142.9 | 38 | 1634 | 5430.2 | 0 | 5430.2
| b) Dia. 12mm deformed bar | Kg | 176 |  |  |  | 38 | 6688 | 0 | 0 | 0
| c) Dia. 8 mm deformed bar | Kg | 110 | 103.49 |  | 103.49 | 38 | 4180 | 3932.62 | 0 | 3932.62
| d) Dia. 6 mm deformed bar | Kg | 475 |  |  |  | 38 | 18050 | 0 | 0 | 0
2.6 | 12/2 cm chip wood expansion joint | Ml | 0 | 0 |  | 0 | 15 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 72992 | 55587.62 | 0 | 55587.62
3. Masonry Work
3.1 | Construct 50cm BNGL | M3 | 5 | 8.46 |  | 8.46 | 1000 | 5000 | 8460 | 0 | 8460
3.2 | Ditto but ANGL | M3 | 8 | 4.9 |  | 4.9 | 1100 | 8800 | 5390 | 0 | 5390
TOTAL CARRIED TO SUMMARY | [7 empty] | 13800 | 13850 | 0 | 13850
B. SUPER STRUCTURE
1. CONCRETE WORKS
1.1 | Reinforced concrete class C-25,
| a) In elevation column | M3 | 1.8 | 0.43 |  | 0.43 | 2900 | 5220 | 1247 | 0 | 1247
| b) In beams | M3 | 1.4 | 0.69 |  | 0.69 | 2900 | 4060 | 2001 | 0 | 2001
| c) Lintels | M3 | 22 | 0.18 |  | 0.18 | 2900 | 63800 | 522 | 0 | 522
1.2 | form work which
| a) To elevation column | M2 | 26 | 8.64 |  | 8.64 | 100 | 2600 | 864 | 0 | 864
* | b) In beams | M2 |  | 6.92 |  | 6.92 | 100 | 0 | 692 | 0 | 692
| c) To Lintel | M2 | 20 | 1.89 |  | 1.89 | 100 | 2000 | 189 | 0 | 189
| d) 10 cm thick parapet wall | M2 | 26 | 0 |  | 0 | 100 | 2600 | 0 | 0 | 0
1.3 | Steel bars
| a) Dia. 6mm deformed bar | Kg | 43 | 0 |  | 0 | 38 | 1634 | 0 | 0 | 0
| b) Dia. 8mm deformed bar | Kg | 176 | 173.16 |  | 173.16 | 38 | 6688 | 6580.08 | 0 | 6580.08
| c) Dia. 10 mm deformed bar | Kg | 110 | 63.04 |  | 63.04 | 38 | 4180 | 2395.52 | 0 | 2395.52
| d) Dia.12mm deformed bar | Kg | 110 | 3.73 |  | 3.73 | 38 | 4180 | 141.74 | 0 | 141.74
TOTAL CARRIED TO SUMMARY | [7 empty] | 96962 | 14632.34 | 0 | 14632.34
2. BLOCK WORK
2.01 | Supply and construct 20cm thick hollow concrete block | M2 | 40 | 38.18 |  | 38.18 | 320 | 12800 | 12217.6 | 0 | 12217.6
2.02 | Ditto as item 2.1 but 15cm thick HCB | M2 | 6 | 0 |  | 0 | 280 | 1680 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 14480 | 12217.6 | 0 | 12217.6
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 20 | 59.16 |  | 59.16 | 230 | 4600 | 13606.8 | 0 | 13606.8
TOTAL CARRIED TO SUMMARY | [7 empty] | 4600 | 13606.8 | 0 | 13606.8
4.CARPENTRY & JOINERY
4.01 | diameter 10-12cms | m | 43 | 92.72 |  | 92.72 | 22 | 946 | 2039.84 | 0 | 2039.84
4.2 | diameter 8-10cms | m | 27 | 56 |  | 56 | 15 | 405 | 840 | 0 | 840
4.3 | 5x7cm Zigba roof purlin c/c 90cm | m | 36 | 86.4 |  | 86.4 | 32 | 1152 | 2764.8 | 0 | 2764.8
TOTAL CARRIED TO SUMMARY | [7 empty] | 2503 | 5644.64 | 0 | 5644.64
5.METAL WORKS
5.1 | Windows
| a) D1 - .98/2.0 m | no | 2 | 1 |  | 1 | 3440 | 6880 | 3440 | 0 | 3440
5.2 | Doors
| a) D1 - .90/2.70 m | no | 1 | 1 |  | 1 | 3159 | 3159 | 3159 | 0 | 3159
| b) D1 - .70/2.70 m | no | 1 | 1 |  | 1 | 2457 | 2457 | 2457 | 0 | 2457
TOTAL CARRIED TO SUMMARY | [7 empty] | 12496 | 9056 | 0 | 9056
6. FINISHING
6.01 | Apply three coats of plastering | M2 | 50 | 49.17 |  | 49.17 | 100 | 5000 | 4917 | 0 | 4917
6.3 | Apply 2 coats of plaster & rendering | M2 | 30 | 32.3 |  | 32.3 | 90 | 2700 | 2907 | 0 | 2907
TOTAL CARRIED TO SUMMARY | [7 empty] | 7700 | 7824 | 0 | 7824
7.PAINTING
7.1 | Apply three coats of plastic paint to plastered surface of internal wall, external beams and columns. | M2 | 50 |  | 49.17 | 49.17 | 26 | 1300 | 0 | 1278.42 | 1278.42
7.2 | Ditto but to rendered surface | M2 | 30 |  | 32.3 | 32.3 | 26 | 780 | 0 | 839.8 | 839.8
7.3 | Ditto but to chip wood celling | M2 | 8 |  |  | 0 | 26 | 208 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 2288 | 0 | 2118.22 | 2118.22

## Tos Guard house (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Guard House
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1. CONCREAT WORK
1.01 Rc -25 concreat
1 | 2.1 |  | c) In lntels
0.25
0.2
0.105
1 | 1.4
0.25
0.2
0.07
|  | 0.175 | M3 Total to item no 1.01
1.02 Formwork
1 | 1.8 |  | c) to lintels
0.2
0.36
2 | 1.8
0.25
0.9
1 | 0.9
0.2
0.18
2 | 0.9
0.25
0.45
|  | 1.89 | M2Total to item no 1.02
1.03 Steel Rainforcement
| 3.73 |  | a) 6mm plain bars
|  | 3.73 | Kg
| 14.92 |  | a) 12mm
|  | 14.92 | Kg
6.Finishing Work
6.8 30cm Dia1/2 stor water concreat pipe
2 | 6.45
12.9
2 | 7.75
15.5
1 | 1.2
1.2
|  | 29.6 | Total to item no 6.8
TAKE OFF SHEET No 8
PROJECT :- Dhedhesa Primary Hospital |  | Project:- Dhedhesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Guard House
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
A)SUB-STRUCTURE
1) EXCAVATION & EARTH WORK
1.6 Cart away surplus excavation material
1 | 45.9 |  | site clearing
| 0.3 | 13.77
|  | 84.63 | bulk
|  | 23.84 | trench
|  | 122.24 | m3 Total 1.6
|  | 25 | Previous payment
|  | 97.24 | m3 total of item 1.6 Remaining

## TOS Gur
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Guard House
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
7.PAINTING
7.1. Internal plastered wall ext beams & colmn
Ditto Item no 6.2
1 | 49.17
|  | 49.17 | n2 net area to item no 7.1
7.3. External rendered surface
Ditto Item no 6.1
1 | 32.3
|  | 32.3 | n2 net area to item no 7.3

## Dry Lat Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Dry Latrine NO 1
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | EXCAVATION & EARTH WORK | 14434 | 9347.56 | 11653.6 | 21001.16
2 | STONE MASONRY | 44000 | 52180 | 0 | 52180
TOTAL A |  | 58434 | 61527.56 | 11653.6 | 73181.16
B.SUPERSTRUCTURE
1 | CONCRTE WORK | 29354 | 29784.58 | 0 | 29784.58
2 | BLOCK WORK | 49300 | 25891.2 | 0 | 25891.2
3 | ROOFING WORK | 16700 | 10919.8 | 0 | 10919.8
4 | CARPENTRY & JOINERY | 7828 | 26496 | 0 | 26496
5 | METAL WORK | 19872 | 4880.18 | 0 | 4880.18
6 | FINISHING ORK | 26840 | 0 | 0 | 0
7 | GLAZING WORK
8 | PAINTING WORK | 2834 |  | 0
9 | SANITARY INSTALLATION
10 | ELECTRICAL INSTALLATION | 3790
TOTAL B |  | 156518 | 97971.76 | 0 | 97971.76
TOTAL A + B |  | 214952 | 159499.32 | 11653.6 | 171152.92

## Dry Lat Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Dry Latrine NO 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A.sub-structure
1. EXCAVATION & EARTH WORKS
1.1 | Excavate for site clearing | M2 | 54 | 59.36 |  | 59.36 | 6 | 324 | 356.16 | 0 | 356.16
1.2 | pit excavation150cm from reduced level | M3 | 25 | 80.35 |  | 80.35 | 36 | 900 | 2892.6 | 0 | 2892.6
1.3 | Ditto but over 1.50mts but not exceding 4m | M3 | 52 | 68.32 |  | 68.32 | 40 | 2080 | 2732.8 | 0 | 2732.8
1.3.1 | Ditto to Soft rock | M3 | 4 | 0 |  | 0 | 120 | 480 | 0 | 0 | 0
1.3.2 | Ditto to Soft rock | M3 | 3 | 0 |  | 0 | 250 | 750 | 0 | 0 | 0
1.4 | Back fill | M3 | 29 | 33.66 |  | 33.66 | 100 | 2900 | 3366 | 0 | 3366
1.5 | cart away | M3 | 100 | 0 | 166.48 | 166.48 | 70 | 7000 | 0 | 11653.6 | 11653.6
| TOTAL CARRIED TO SUMMARY | [6 empty] | 14434 | 9347.56 | 11653.6 | 21001.16
2. Masonry Work
2.3 | Construct stone masonry | M3 | 44 | 52.18 |  | 52.18 | 1000 | 44000 | 52180 | 0 | 52180
| TOTAL CARRIED TO SUMMARY | [6 empty] | 44000 | 52180 | 0 | 52180
B. Super structure
1.1 | C-25 Reinforced concret
| a) in elevation Column | m3 | 2 | 0.65 |  | 0.65 | 2900 | 5800 | 1885 | 0 | 1885
| b) In beam | m3 | 2 | 1.3 |  | 1.3 | 2900 | 5800 | 3770 | 0 | 3770
| c) In concret roof slab | m3 | 1 | 0 |  | 0 | 2900 | 2900 | 0 | 0 | 0
| d) Lintel | m3 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
1.2 | Form Work
| a) in elevation Column | m2 | 16 | 12.96 |  | 12.96 | 100 | 1600 | 1296 | 0 | 1296
| b) In concret roof slab | m2 | 20 | 17.28 |  | 17.28 | 100 | 2000 | 1728 | 0 | 1728
| c) Lintel | m2 | 5 | 0 |  | 0 | 100 | 500 | 0 | 0 | 0
1.3 | Re-Bar
| a) dia 14mm | Kg |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| b) dia 12mm | Kg | 143 | 303.39 |  | 303.39 | 38 | 5434 | 11528.82 | 0 | 11528.82
| c) dia 10mm | Kg | 100 | 0 |  | 0 | 38 | 3800 | 0 | 0 | 0
| d) dia 6mm | Kg | 40 | 252.02 |  | 252.02 | 38 | 1520 | 9576.76 | 0 | 9576.76
| TOTAL CARRIED TO SUMMARY | [6 empty] | 29354 | 29784.58 | 0 | 29784.58
2. BLOCK WORK
| HCB | M2 | 170 | 89.28 |  | 89.28 | 290 | 49300 | 25891.2 | 0 | 25891.2
| TOTAL CARRIED TO SUMMARY | [6 empty] | 49300 | 25891.2 | 0 | 25891.2
3. ROOFING
3.1 | G-30 CIS Roof cover | M2 | 58 | 43.86 |  | 43.86 | 230 | 13340 | 10087.8 | 0 | 10087.8
3.2 | G-30 Ribbed Sheet | M2 | 14 | 0 |  | 0 | 80 | 1120 | 0 | 0 | 0
3.3 | G-30 Flashing | m | 18 | 10.4 |  | 10.4 | 80 | 1440 | 832 | 0 | 832
3.4 | G-30 flat metal sheet | m | 10 | 0 |  | 0 | 80 | 800 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 16700 | 10919.8 | 0 | 10919.8
5.METAL WORKS
5.1 | Windows
| a) D6 - 98/2.60cm | no | 6 | 8 |  | 8 | 3312 | 19872 | 26496 | 0 | 26496
| TOTAL CARRIED TO SUMMARY | [6 empty] | 19872 | 26496 | 0 | 26496
4.CARPENTRY & JOINERY
4.1 | All wooden member
| a)-diameter 10 -12cm | ml | 60 | 71.49 |  | 71.49 | 22 | 1320 | 1572.78 | 0 | 1572.78
| b) diameter 8 - 10cm | ml | 60 | 76.76 |  | 76.76 | 15 | 900 | 1151.4 | 0 | 1151.4
| c) Purlin zigba size 5/7cm | ml | 114 | 0 |  | 0 | 32 | 3648 | 0 | 0 | 0
4.2 | Supply and fix 25x2.5cm Kerrer facia board | ml | 28 | 30.8 |  | 30.8 | 70 | 1960 | 2156 | 0 | 2156
| TOTAL CARRIED TO SUMMARY | [6 empty] | 7828 | 4880.18 | 0 | 4880.18
| 6. FINISHING | [6 empty] | 0 | 0 | 0 | 0
6.3 | 100cm wide and 10 cm thick mass concrete payment | ml | 26 |  |  |  | 320 | 8320 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 8320 | 0 | 0 | 0
7.PAINTING
Prepare and apply by brush three coats of plastic emulsion paint to:
7.1 | Apply three coats of plastic paint to plastered surface of internal wall, external beams and columns. | M2 | 41 |  | 0 | 0 | 26 | 1066 | 0 | 0 | 0
7.2 | Ditto but to rendered surfac | M2 | 68 |  | 0 | 0 | 26 | 1768 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 2834 | 0 | 0 | 0

## TOS DRY Latrine (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Dry Latrine
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| . |  | 3. Roofing works
4 | 2.6 |  | 3.3 G 30 Flashing
10.4
|  | 10.4 | Total of Item 3.3
4. Carpentery & joinery
2 | 10.2 |  | 4.2 25x25 cm Fascial Board
20.4
4 | 2.6
10.4
|  | 30.8 | Total of Item 4.2
5.Metal works
5.21 Doors
| 2 |  | a) D6- 98x260
2
|  | 2 | Total of Item 5.21
6.Finishing work
2 | 11.2 |  | 6.5 Pavement 1.2cm
1.2
26.88
2 | 3.5
1.2
8.4
|  | 35.28 | Total of Item 6.5

## TOS Dry
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Dry Lattrin
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
7.PAINTING
7.1. Internal plastered wall ext beams & colmn
Ditto Item no 6.2
1 | 49.17
|  | 0 | n2 net area to item no 7.1
7.2. External rendered surface
Ditto Item no 6.1
1 | 32.3
|  | 0 | n2 net area to item no 7.3

## Civil Site Work Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT for Civil Site Work NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | Road & Parking | 132200 | 352328 | 125984.8 | 478312.8
2 | Fence Work | 1128300 | 468359.52 | 0 | 468359.52
3 | Steps & RAMPS | 106420 | 0 | 83156 | 83156
4 | Retaining Wall | 517260 | 242711.52 | 0 | 242711.52
5 | Covered Walkway | 846455 | 1579380.59 | 193305.92 | 1772686.51
6 | Flag Pole | 16000 | 0 |  | 0
7 | Uncovered walkway | 231100 | 159609.75 | 0 | 159609.75
8 | Cloth Hanger | 91800 | 0 |  | 0
9 | Miscellaneous Work | 52150 | 0 |  | 0
10 | Mounument | 21408 | 0 |  | 0
11 | Incinetor | 37055.1 | 0 |  | 0
12 | Placenta Pit | 55216 | 137664.72 | 0 | 137664.72
13 | Ash & Niddle | 161060 | 109817.5 |  | 109817.5
TOTAL |  | 3396424.1 | 3049871.6 | 402446.72 | 3452318.32

## Site Civil Meas.
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Civil Site Work NO 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
1 ROAD & PARKING
1. EXCAVATION & EARTH WORKS
1.1 | Bulk excavation for average depth of 600mm | M3 | 120 | 1642.9 |  | 1642.9 | 50 | 6000 | 82145 | 0 | 82145
1.2 | Remove And Spread surplus excavated matrial | M3 | 120 | 1642.9 |  | 1642.9 | 70 | 8400 | 115003 | 0 | 115003
1.3 | Selected material back fill with selectedy granual material brought form approved quarry | M3 | 150 | 428.15 |  | 428.15 | 200 | 30000 | 85630 | 0 | 85630
1.4 | The sub-base of the road shall consist 25cm thick hard basaltic stone | M3 | 120 | 0 | 0 | 0 | 80 | 9600 | 0 | 0 | 0
1.5 | 10cm thick gravel of 2/5cm watered and well rolled with 10(ten) tone roller in five passes | M3 | 120 | 0 | 213.83 | 213.83 | 60 | 7200 | 0 | 12829.8 | 12829.8
1.6 | 5cm thick final surface coarse | M2 | 120 | 0 | 2138.3 | 2138.3 | 50 | 6000 | 0 | 106915 | 106915
1.7 | Construct of 12x35cm curbstone along the drive way, walk way | Ml | 500 | 535 | 48 | 583 | 130 | 65000 | 69550 | 6240 | 75790
TOTAL CARRIED TO SUMMARY | [7 empty] | 132200 | 352328 | 125984.8 | 478312.8
2) Fence work
A) Berbed wire fence
1.1 Excavation and earth work
1.1.1 | pit excavation to insert poles for the fence with a 50x50cm and to depth of 60cm spred the excavated soil on the site | m3 | 200 | 56.4 |  | 56.4 | 50 | 10000 | 2820 | 0 | 2820
1.1.2 | Supply and fix fence with 300cm high angle iron | m3 | 1750 | 2250 |  | 2250 | 100 | 175000 | 225000 | 0 | 225000
1.1.3 | Hard Bsaltic well dressed masonary pillars | No | 6 | 0 |  | 0 | 1800 | 10800 | 0 | 0 | 0
1.2 Metal work
1.2.1 | The gate is made of 40x40x3mm RHS profite. | No | 2 | 0 | 0 | 0 | 10000 | 20000 | 0 | 0 | 0
size: 400x250cm
1.2.2 | Ditto as above but for the pedestrine gate with 40x40x3mm RHS pillar size 120x250cm | No | 2 | 0 | 0 | 0 | 5000 | 10000 | 0 | 0 | 0
| TOTAL CARRIED TO SUMMARY | [6 empty] | 225800 | 227820 | 0 | 227820
| B) Front side Masonary work | [6 empty] | 0
2.1 | Trench Excavation depth not exceeding 100cm | M3 | 150 | 79.17 |  | 79.17 | 36 | 5400 | 2850.12 | 0 | 2850.12
2.2 | cartaway surplus material | M3 | 150 | 79.17 |  | 79.17 | 70 | 10500 | 5541.9 | 0 | 5541.9
2.3 | 50cm thick masonary BNGL | M3 | 150 | 56.55 |  | 56.55 | 1000 | 150000 | 56550 | 0 | 56550
2.4 | ditto but well dressed | M3 | 150 | 33.93 |  | 33.93 | 1100 | 165000 | 37323 | 0 | 37323
2.5 | 50cm thick masonary (column) | M3 | 190 | 0 |  | 0 | 1500 | 285000 | 0 | 0 | 0
2.6 | 20cm thick HCB wall | M2 | 250 | 78.27 |  | 78.27 | 350 | 87500 | 27394.5 | 0 | 27394.5
2.7 | Provide and fix fence grill out of RHS 40x40x3mm and RHS 20x20x2mm | m2 | 181 | 100.8 |  | 100.8 | 1100 | 199100 | 110880 | 0 | 110880
TOTAL CARRIED TO SUMMARY | [7 empty] | 902500 | 240539.52 | 0 | 240539.52
FENCE GRAND SUMMARY | [7 empty] | 1128300 | 468359.52 | 0 | 468359.52
3. Ramps & Steps,
1.STEPS AND RAMPS
A. Excavation and Masnory Works
1.1 | Excavation in 50cm from NGL | m3 | 40 |  | 46 | 46 | 40 | 1600 | 0 | 1656 | 1656
1.2 | Stone masonry foundation wall with 50cm thick below NGL with cement morter 1:3 | m3 | 40 |  | 23 | 23 | 1000 | 40000 | 0 | 23000 | 23000
1.3 | Ditto but semi-dressed stone massonry including pointing with 1:2 cement sand morter | m3 | 20 |  | 38 | 38 | 1100 | 22000 | 0 | 41800 | 41800
1.4 | Cartaway surplus excavated material (2km away) | m3 | 40 |  | 46 | 46 | 70 | 2800 | 0 | 3220 | 3220
1.5 | Fill granular approved type selected | m3 | 15 |  | 56.93 | 56.93 | 100 | 1500 | 0 | 5693 | 5693
1.6 | 25cm thick Hard core for ramps | m3 | 12 |  | 119.8 | 119.8 | 65 | 780 | 0 | 7787 | 7787
TOTAL CARRIED TO SUMMARY | [7 empty] | 68680 | 0 | 83156 | 83156
B. CONCRETE WORK
3.7 | 7cm thick lean concrete | m2 | 15 |  |  | 0 | 100 | 1500 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 1500 | 0 | 0 | 0
STEPS & Ramps GRAND SUMMARY | [7 empty] | 70180 | 0 | 83156 | 83156
4. Retainimg wall
1. Excavation & earth work
1.1 | Removal of 20cm thick top soil | m2 | 300 | 264.4 |  | 264.4 | 6 | 1800 | 1586.4 | 0 | 1586.4
a | Excavation of black cottons soil up to 35cm | m3 | 110 | 362.92 |  | 362.92 | 36 | 3960 | 13065.12 | 0 | 13065.12
2 | Selected material back fill around retaining | m3 | 300 | 46.36 |  | 46.36 | 100 | 30000 | 4636 | 0 | 4636
3 | Caraway surplus excavated material (2km away) | m3 | 300 | 415.8 |  | 415.8 | 70 | 21000 | 29106 | 0 | 29106
TOTAL CARRIED TO SUMMARY | [7 empty] | 56760 | 48393.52 | 0 | 48393.52
| 2. concrete work |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
2.1 | C-7 lean concrete | m2 | 55 | 131.85 |  | 131.85 | 100 | 5500 | 13185 | 0 | 13185
TOTAL CARRIED TO SUMMARY | [7 empty] | 5500 | 13185 | 0 | 13185
3.stone masonry
3.1 | stone masonrty below NGL | m3 | 250 | 46.9 |  | 46.9 | 1000 | 250000 | 46900 | 0 | 46900
3.2 | stone masonrty above NGL | m3 | 150 | 122.03 |  | 122.03 | 1100 | 165000 | 134233 | 0 | 134233
TOTAL CARRIED TO SUMMARY | [7 empty] | 415000 | 181133 | 0 | 181133
4- Finisihing Work
4.1 | Pointing | m2 | 150 | 0 |  | 0 | 50 | 7500 | 0 | 0 | 0
4.2 | Copping | ml | 300 | 0 |  | 0 | 75 | 22500 | 0 | 0 | 0
4.3 | PVC weep hole | ml | 40 | 0 |  | 0 | 250 | 10000 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 40000 | 0 | 0 | 0
GRAND SUMMARY | [7 empty] | 517260 | 242711.52 | 0 | 242711.52
5. Covered walk way
A. Sub structure
1. Excavation & earth work
1.1 | Removal of 20cm thick top soil | m2 | 375 | 1065.25 |  | 1065.25 | 6 | 2250 | 6391.5 | 0 | 6391.5
| Bulk excavation for average depth of 600mm | m3 |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0
1.2 | Excavation of black cottons soil up to 35cm | m3 | 135 | 315.15 |  | 315.15 | 36 | 4860 | 11358.36 | 0 | 11358.36
1.3 | Excavation of trench | m3 | 150 | 263.85 |  | 263.85 | 36 | 5400 | 9498.6 | 0 | 9498.6
1.4 | Selected material back fill under floor slab | m3 | 90 | 174.34 |  | 174.34 | 100 | 9000 | 17434 | 0 | 17434
1.5 | Cart away (2kms away) | m3 | 397.5 | 0 | 0 | 0 | 70 | 27825 | 0 | 0 | 0
1.6 | 25cm thick Hard core | m2 | 300 | 1051.45 |  | 1051.45 | 65 | 19500 | 68344.25 | 0 | 68344.25
TOTAL CARRIED TO SUMMARY | [7 empty] | 68835 | 113026.71 | 0 | 113026.71
2. Concrete work
2.1 | C-7 lean concrete | m2 | 150 | 376.93 |  | 376.93 | 100 | 15000 | 37693 | 0 | 37693
2.2 | C-25 RC Concrete in grade beam | m3 | 15 | 47.85 |  | 47.85 | 2900 | 43500 | 138765 | 0 | 138765
2.3 | C-20 10cm thick RC concrete slab | m2 | 300 | 1051.45 |  | 1051.45 | 260 | 78000 | 273377 | 0 | 273377
2.4 | form work | m2 | 150 | 381.65 |  | 381.65 | 90 | 13500 | 34348.5 | 0 | 34348.5
2.5 | Steel reinforcment
| a) Diameter 12 plain box | kg | 1100 | 2772.51 |  | 2772.51 | 38 | 41800 | 105355.38 | 0 | 105355.38
| b) Diameter 8 deformed bars | kg | 1250 | 3234.11 |  | 3234.11 | 38 | 47500 | 122896.18 | 0 | 122896.18
| c) Diameter 6 deformed bars | kg | 270 | 890.11 |  | 890.11 | 38 | 10260 | 33824.18 | 0 | 33824.18
2.6 | Masonery wall below NGL pric shall includes pointing | m3 | 150 | 208.51 |  | 208.51 | 1300 | 195000 | 271063 | 0 | 271063
TOTAL CARRIED TO SUMMARY | [7 empty] | 444560 | 1017322.24 | 0 | 1017322.24
B. Super Structure
1. Steel structure
Supply & fix steel structure fabricated according to structural detal
drawings with two coats of anti-rust paint three coats of syntetuc paint
1.1 | Diam 60mm CHS post 2.5mm thick | kg | 1450 | 2832.6 |  | 2832.6 | 28 | 40600 | 79312.8 | 0 | 79312.8
1.2 | Plates (150mx150mmx3mm) | No | 304 | 930 | 280 | 1210 | 35 | 10640 | 32550 | 9800 | 42350
1.3 | Ancher 'J' bolts
| a) diam 16mm length 30cm | No | 1216 | 1220 |  | 1220 | 30 | 36480 | 36600 | 0 | 36600
1.4 | 40x60x2.5mm RHS beam welded to plate | kg | 1080 | 1080 | 1771.2 | 2851.2 | 28 | 30240 | 30240 | 49593.6 | 79833.6
1.5 | 40x30x2mm RHS for upper & lower trusses | kg | 1230 | 577.42 | 1660.51 | 2237.93 | 28 | 34440 | 16167.76 | 46494.28 | 62662.04
1.6 | Ditto but 30x20x2mm diagonal member | kg | 320 | 225.76 | 274.18 | 499.94 | 28 | 8960 | 6321.28 | 7677.04 | 13998.32
TOTAL CARRIED TO SUMMARY | [7 empty] | 161360 | 201191.84 | 113564.92 | 314756.76
2. ROOFING
2.1 | Roof cover G-30 C-I-S | m2 | 525 | 787.15 | 232.85 | 1020 | 260 | 136500 | 204659 | 60541 | 265200
2.2 | 5x7cm sawn zigba wood purlin wood | ml | 1100 | 1349.4 | 600 | 1949.4 | 32 | 35200 | 43180.8 | 19200 | 62380.8
TOTAL CARRIED TO SUMMARY | [7 empty] | 171700 | 247839.8 | 79741 | 327580.8
3. ELECTRICAL INSTALLATION
3.1 | Light points | No | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 0 | 0 | 0 | 0
Grand TOTAL CARRIED TO SUMMARY | [7 empty] | 846455 | 1579380.59 | 193305.92 | 1772686.51
7. Uncovered walk way
7.1 | Bulck excavation to the depth of 50cm | M3 | 150 | 139.5 |  | 139.5 | 36 | 5400 | 5022 | 0 | 5022
7.2 | Cart away to the distance of 2kms awy | M3 | 150 | 139.5 |  | 139.5 | 70 | 10500 | 9765 | 0 | 9765
7.3 | selected material back fill with selected granular material | M3 | 150 | 78.71 |  | 78.71 | 100 | 15000 | 7871 | 0 | 7871
7.4 | 25cm thick hard core blinded with crushed stone | M2 | 440 | 307.83 |  | 307.83 | 65 | 28600 | 20008.95 | 0 | 20008.95
7.5 | 8cm thick mass concrete in C-20 pavement flooring spaned at every one meter | M2 | 440 | 249.33 |  | 249.33 | 260 | 114400 | 64825.8 | 0 | 64825.8
7.6 | Construct out of 12x35cm curbstone along the drive way, walk way bed | ml | 440 | 400.9 |  | 400.9 | 130 | 57200 | 52117 | 0 | 52117
TOTAL CARRIED TO SUMMARY | [7 empty] | 231100 | 159609.75 | 0 | 159609.75

## TOS site civil work (hidden)
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Road and parking
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 Road and Parking
Excavation and earth work
1.101 Bulk excavation 600mm
| 41.9 |  | Morgue to inter.gate
4
0.6
|  | 100.56 | m3
1.02 Cart away
|  | 100.56 | Ditto above
|  | 100.56 | m3
1.03 Back fill
41.9
3.25
| 0.6 | 81.71 | m3
1.04 Curb stone
2 | 41.9 | 83.8 | ml
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Uncovered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
7 Un Coverd waik way
Morgue b/n IPD & OR Block
| 18 |  | 7.11 Bulk excavation
2.5
0.5
|  | 22.5 | m3
7.21 Cart away
22.5
|  | 22.5 | m3 ditto above
7.31 Back fill
18
2.25
0.5
|  | 20.25 | m3
7.041 25cm hard core
18
2.25
|  | 40.5 | m2
7.51 8cm Mass Concrete
18
| 2.25 | 40.5 | m2
7.61 Curb stone
2 | 18
|  | 36 | ml
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-1
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | Sub Structure | 1 | 13.2 |  | Up to IPD- kichen block
|  |  | 1.11 Removal of top soil |  | 2.7
|  |  | up to waiting and registration |  |  | 35.64
| 12.2 |  |  | 1 | 17.6
| 2.7 | 0 |  |  | 2.7
|  | 32.9 |  |  |  | 47.52
| 18.05 |  |  | 1 | 2
| 2.7 |  |  |  | 2.7
|  | 48.7 |  |  |  | 5.4
|  | 81.6 | m2 sub total |  |  | 88.56 | m2 sub total
| 2.95 |  | IPD Block back side |  |  | 714.2 | m2 Total of 1.11
| 2.7 | [5 empty] | 1.21 Excavation up to 35cm
|  | 8 |  |  |  |  | up to waiting and registration |  | 266.2
| 15.65 |  |  |  | 12.2 |  |  |  | 92.97
| 2.7 |  |  |  | 2.7 | [5 empty] | 0.08
|  | 42.3 |  |  | 0.35 |  |  |  | 448.78 | -265.56
|  | 50.3 | m2 sub total |  |  | 11.53
| 1.9 |  | OR and Delivery back side
| 2.7 |  |  |  | 18.05
|  | 5.1 |  |  | 2.7
| 13.25 |  |  |  | 0.35
| 2.7 |  |  |  |  | 17.06
|  | 35.8 |  |  |  | 28.59 | m2 sub total
|  | 40.9 | m2 sub total |  |  |  | IPD Block back side
|  |  | Cross Center |  | 2.95
| 2.65 |  |  |  | 2.7
| 2.1 | 5.57 | m2 sub total |  | 0.35
|  |  | B/N IPD & OR Delivery |  |  | 2.79
| 50.85 |  |  |  | 15.65
| 2.7 |  |  |  | 2.7
|  | 137.3 | m2 sub total |  | 0.35
| 5.8 |  |  |  |  | 14.79
| 2.7 |  |  |  |  | 17.58 | m2 sub total
|  | 15.66 |  |  |  |  | OR and Delivery back side
| 33 |  |  |  | 1.9
| 2.7 |  |  |  | 2.7
|  | 89.1 |  |  | 0.35
| 10.5 |  |  |  |  | 1.8
| 2.7 |  |  |  | 13.25
|  | 28.35 |  |  | 2.7
|  | 133.11 | m2 sub total |  | 0.35
3 | 3.85 |  | Or Delivery Internce gate |  |  | 12.52
| 2.7 |  |  |  |  | 14.32 | m2 sub total
|  | 31.19 | m2 sub total |  | 2.65 |  | Cross Center
1 | 16.8 |  | OR DeliveryTo Admins-Block |  | 2.1
| 2.7 |  |  |  | 0.35
|  | 45.36 |  |  |  | 1.95 | m2 sub total
1 | 6
| 2.7 | [5 empty] | B/N IPD & OR Delivery
|  | 16.2 |  |  | 50.85
1 | 17.65 |  |  |  | 2.7
| 2.7 |  |  |  | 0.35
|  | 47.66 |  |  |  | 48.05 | m2 sub total
1 | 13.5 |  | To Diagonestic Block |  | 5.8 |  | Front Side IPD & OR Delivery
| 2.7 |  |  |  | 2.7
|  | 36.45 |  |  | 0.35
|  | 145.67 | m2 sub total |  |  | 5.48
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-2
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 33 | [5 empty] | IPD Block back side | [7 empty] | OR and Delivery back side
| 2.7 |  |  | 2 | 2.95 | [7 empty] | 1.9
| 0.35 |  |  |  | 0.7 | [7 empty] | 1.5
|  | 31.19 |  |  | 0.5 | [7 empty] | 0.35 | 1
| 10.5 |  |  |  |  | 2.065 | [6 empty] | 13.25
| 2.7 |  |  | 2 | 14.8 | [7 empty] | 1.5
| 0.35 |  |  |  | 0.7 | [7 empty] | 0.35 | 6.96
|  | 9.92 |  |  | 0.5 | [8 empty] | 7.96 | m3
|  | 46.59 | m2 sub total |  |  | 10.36 | [8 empty] | Cross Center
3 | 3.85 |  | Or Delivery Internce gate |  |  | 12.43 | m2 sub total | [5 empty] | 2.65
| 2.7 |  |  |  | 1.9 |  | OR and Delivery back side | [5 empty] | 2.1
| 0.35 |  |  |  | 0.7 | [7 empty] | 0.35 | 1.95
|  | 10.91 | m2 sub total |  | 0.5 | [8 empty] | 1.95 | m3
1 | 16.8 |  | OR DeliveryTo Admins-Block |  |  | 0.665 | [8 empty] | B/N IPD & OR Delivery
| 2.7 |  |  |  | 4.2 | [7 empty] | 50.85
| 0.35 |  |  |  | 0.7 | [7 empty] | 1.5
|  | 15.88 |  |  | 0.5 | [7 empty] | 0.35 | 26.7 | m3
1 | 6 |  |  |  |  | 1.47 | [8 empty] | Front Side IPD & OR Delivery
| 2.7 |  |  |  | 12.75 | [7 empty] | 5.8
| 0.35 |  |  |  | 0.7 | [7 empty] | 1.5
|  | 5.67 |  |  | 0.5 | [7 empty] | 0.35 | 3.05
1 | 17.65 |  |  |  |  | 4.4625
| 2.7 |  |  |  | 11.35
| 0.35 |  |  |  | 0.7
|  | 16.68 |  |  | 0.5
1 | 13.5 |  | To Diagonestic Block |  |  | 3.9725
| 2.7 |  |  |  |  | 10.57 | m2 sub total
| 0.35 |  |  | 2 | 50.85 |  | B/N IPD & OR Delivery
|  | 12.76 |  |  | 0.7
|  | 50.99 | m2 sub total |  | 0.5 |  |  |  | 137.28
1 | 13.2 |  | Up to IPD- kichen block |  |  | 35.595 | m2 sub total
| 2.7 |  |  |  | 8.3 |  | Front Side IPD & OR Delivery
| 0.35 |  |  |  | 0.7
|  | 12.47 |  |  | 0.5
1 | 17.6 |  |  |  |  | 2.905
| 2.7 |  |  |  | 5.8
| 0.35 |  |  |  | 0.7
|  | 16.63 |  |  | 0.5
1 | 2 |  |  |  |  | 2.03
| 2.7 |  |  |  | 12 |  |  | 92.97
| 0.35 |  |  |  | 0.7
|  | 1.89 |  |  | 0.5
|  | 30.99 | m2 sub total |  |  | 4.2
|  | 249.97 | m3 Total 1.21 |  | 32 |  |  | 157.08
|  |  | 1.31 Excavation for Trench |  | 0.7
|  |  | up to waiting and registration |  | 0.5
2 | 12.2 |  |  |  |  | 11.2
| 0.7 |  |  |  | 12.45
| 0.5 |  |  |  | 0.7
|  | 8.54 |  |  | 0.5
2 | 18.05 |  |  |  |  | 4.3575
| 0.7 |  |  |  | 10.5
| 0.5 |  |  |  | 0.7
|  | 12.64 |  |  | 0.5
|  | 21.18 | m3 |  |  | 3.675
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-3
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 12.95 |  |  | 1 | 15.6
| 0.7 |  |  |  | 0.7
| 0.5 |  |  |  | 0.5
|  | 4.5325 |  |  |  | 5.46
|  | 32.9 | m2 sub total | 1 | 2
6 | 3.85 |  | Or Delivery Internce gate |  | 0.7
| 0.7 |  |  |  | 0.5
| 0.5 |  |  |  |  | 0.7
|  | 8.09 | m2 sub total | 1 | 4
1 | 16.8 |  | OR DeliveryTo Admins-Block |  | 0.7
| 0.7 |  |  |  | 0.5
| 0.5 |  |  |  |  | 1.4
|  | 5.88 |  |  |  | 19.67 | m2 sub total
1 | 6 |  |  |  |  | 179.06 | m3 Total 1.31
| 0.7 | [5 empty] | 1.41 Back fill | 112.68 | 140.44
| 0.5 |  |  |  | 12.2 |  | up to waiting and registration
|  | 2.1 |  |  | 1.5
1 | 16.3 |  |  |  | 0.35
| 0.7 |  |  |  |  | 6.41
| 0.5 |  |  |  | 18.05
|  | 5.71 |  |  | 1.5
1 | 8.3 |  |  |  | 0.35
| 0.7 |  |  |  |  | 9.48
| 0.5 |  |  |  |  | 15.89 | m3
|  | 2.91 |  |  | 2.95 |  | IPD Block back side
1 | 2 |  |  |  | 1.5
| 0.7 |  |  |  | 0.35
| 0.5 |  |  |  |  | 1.55
|  | 0.7 |  |  | 15.65
1 | 17.65 |  | To Diagonestic Block |  | 1.5
| 0.7 |  |  |  | 0.35
| 0.5 |  |  |  |  | 8.22
|  | 6.18 |  |  |  | 9.77 | m3
1 | 15.15 | [5 empty] | OR and Delivery back side
| 0.7 |  |  |  | 1.9
| 0.5 |  |  |  | 1.5
|  | 5.3 |  |  | 0.35
1 | 14.7 |  |  |  |  | 1
| 0.7 |  |  |  | 13.25
| 0.5 |  |  |  | 1.5
|  | 5.15 |  |  | 0.35
1 | 13.4 |  |  |  |  | 6.96
| 0.7 |  |  |  |  | 7.96 | m2 sub total
| 0.5 |  |  |  | 2.65 |  | Cross Center
|  | 4.69 |  |  | 1.5
|  | 38.62 | m2 sub total |  | 0.35
1 | 3 |  | Up to IPD- kichen block |  |  | 1.39 | m2 sub total
0.7
| 0.5 | [5 empty] | B/N IPD & OR Delivery
|  | 1.05 |  |  | 50.85
1 | 1 |  |  |  | 1.5
| 0.7 |  |  |  | 0.35
| 0.5 |  |  |  |  | 26.7 | m2 sub total
|  | 0.35 |  |  | 5.8 |  | Front Side IPD & OR Delivery
1 | 30.6 |  |  |  | 1.5
| 0.7 |  |  |  | 0.35
| 0.5 |  |  |  |  | 3.05
10.71
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-4
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 33 |  |  |  | 15.65
| 1.5 |  |  |  | 2
| 0.35 |  |  |  |  | 31.3
|  | 17.33 |  |  |  | 37.2 | m2
| 10.5 |  |  |  | 1.9 |  | OR and Delivery back side
| 1.5 |  |  |  | 2
| 0.35 |  |  |  |  | 3.8
|  | 5.51 |  |  | 13.25
|  | 25.89 | m2 sub total |  | 2
3 | 3.85 |  | Or Delivery Internce gate |  |  | 26.5
| 1.5 |  |  |  |  | 30.3
| 0.35 |  |  |  | 2.65 |  | Cross Center
|  | 6.06 | m2 sub total |  | 2.1
1 | 16.55 |  | OR DeliveryTo Admins-Block |  |  | 5.57
| 1.5 |  |  |  | 50.85 |  | B/N IPD & OR Delivery
| 0.35 |  |  |  | 2 |  | m2
|  | 8.69 |  |  |  | 101.7
1 | 6 |  |  |  | 5.8 |  | Front Side IPD & OR Delivery
| 1.5 |  |  |  | 2
| 0.35 |  |  |  |  | 11.6
|  | 3.15 |  |  | 33
1 | 16.4 |  |  |  | 2
| 1.5 |  |  |  |  | 66
| 0.35 |  |  |  | 10.5
|  | 8.61 |  |  | 2
1 | 13.4 |  | To Diagonestic Block |  |  | 21
| 1.5 |  |  |  |  | 98.6 | m2
| 0.35 |  |  | 3 | 3.85 |  | Or Delivery Internce gate
|  | 7.04 |  |  | 2
|  | 27.49 | m2 sub total |  |  | 23.1 | m2 sub total
1 | 30.6 |  | Up to IPD- kichen block | 1 | 16.55 |  | OR DeliveryTo Admins-Block
| 1.5 |  |  |  | 2
| 0.35 |  |  |  |  | 33.1
|  | 16.07 |  | 1 | 6
1 | 2 |  |  |  | 2
| 1.5 |  |  |  |  | 12
| 0.35 |  |  | 1 | 16.14
|  | 1.05 |  |  | 2
|  | 17.12 | m2 sub total |  |  | 32.28 |  |  | 86.21
|  | 136.88 | m3 Total 1.41 | 1 | 13.4 |  | To Diagonestic Block
|  |  | 1.51 Cart away |  | 2
|  | 142.84 | From site clearing |  |  | 26.8
|  | 249.97 | From Bulk excvation |  |  | 104.18 | m2 sub total |  | 333.87
|  | 179.06 | From Trench | 1 | 30.6 |  | Up to IPD- kichen block
|  | 571.87 | m3 Total 1.51 |  | 2 |  |  |  | 192.48
|  |  | 1.61 25cm Thick hard core |  |  | 61.2
|  |  | up to waiting and registration | 1 | 2
| 12.2 |  |  |  | 2 |  |  |  | 376.87
| 2 |  |  |  |  | 4
|  | 24.4 |  |  |  | 65.2 | m2 sub total
| 18.05 |  |  |  |  | 526.35 | m2 Total 1.61
| 2 | [5 empty] | 2 Concrete work |  |  | 91.56
| 0.5 | 36.1 |  |  |  |  | 2.11 C-5 Lean concrete |  |  | 157.08
|  | 60.5 | m2 sub total | 2 | 12.1 |  |  |  |  | 112.48
| 2.95 |  | IPD Block back side |  | 0.5
| 2 |  |  |  |  | 12.1
|  | 5.9 |  | 2 | 18.05
0.5
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 5
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  | 18.05 |  | 1 | 6
|  | 30.15 | m2 sub total |  | 0.5
2 | 2.95 |  | IPD Block back side |  |  | 3
| 0.5 |  | m2 sub total | 1 | 8.3
|  | 2.95 |  |  | 0.5
2 | 14.8 |  |  |  |  | 4.15
| 0.5 |  |  | 1 | 17.65
|  | 14.8 |  |  | 0.5
|  | 17.75 | m2 sub total |  |  | 8.83
1 | 1.9 |  | OR and Delivery back side | 1 | 15.15
| 0.5 |  |  |  | 0.5
|  | 0.95 |  |  |  | 7.58
1 | 4.2 |  |  | 1 | 14.7
| 0.5 |  |  |  | 0.5
|  | 2.1 |  |  |  | 7.35
1 | 11.35 |  |  | 1 | 13.4
| 0.5 |  |  |  | 0.5
|  | 5.68 |  |  |  | 6.7
1 | 12.75 |  |  |  |  | 55.16 | m2 sub total
| 0.5 |  |  | 1 | 3 |  | Up to IPD- kichen block
|  | 6.38 |  |  | 0.5
|  | 15.11 | m2 sub total |  |  | 1.5
2 | 50.85 |  | B/N IPD & OR Delivery | 1 | 1
| 0.5 |  |  |  | 0.5
|  | 50.85 |  |  |  | 0.5
| 5.8 |  | Front Side IPD & OR Delivery | 1 | 30.6
| 0.5 |  |  |  | 0.5
|  | 2.9 |  |  |  | 15.3
| 8.3 |  |  | 1 | 13.2
| 0.5 |  |  |  | 0.5
|  | 4.15 |  |  |  | 6.6
| 12 |  |  | 1 | 15.6
| 0.5 |  |  |  | 0.5
|  | 6 |  |  |  | 7.8
| 32 |  |  | 1 | 2
| 0.5 |  |  |  | 0.5 |  | m3
|  | 16 |  |  |  | 1
| 12.45 |  |  | 1 | 4
| 0.5 |  |  |  | 0.5
|  | 6.23 |  |  |  | 2
| 10.5 |  |  |  |  | 34.7 | m2 sub total
| 0.5 |  |  |  |  | 255.8 | m2 total To item 2.11
|  | 5.25 | [6 empty] | 154.39
|  | 40.53 | m2 sub total
6 | 3.85 |  | Or Delivery Internce gate
0.5
|  | 11.55 | m2 sub total
1 | 16.8 |  | Up toTo Admins-Block &Diagonestic Block
0.5
8.4
1 | 2
0.5
1
1 | 16.3
0.5
8.15
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 6
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.21 C-25 RC Concrete work in grade beam |  | 0.25
2 | 12.2 |  | up to waiting and registration |  |  | 0.52
| 0.25 |  |  |  | 12.5
| 0.25 |  |  |  | 0.25
|  | 1.53 |  |  | 0.25
2 | 17.8 |  |  |  |  | 0.78
| 0.25 |  |  |  | 32.5
| 0.25 | 2.23 |  |  | 0.25
|  | 3.76 | m3 sub total |  | 0.25
1 | 4.1 |  | IPD Block back side |  |  | 2.03
| 0.25 |  |  |  | 12.45
0.25
| 0.25 |  |  |  | 0.25
|  | 0.26 |  |  |  | 0.78
1 | 1.8 |  |  |  | 10.5
| 0.25 |  |  |  | 0.25 |  |  |  |  | 154.39
| 0.25 |  |  |  | 0.25
|  | 0.11 |  |  |  | 0.66
2 | 14.8 |  |  |  | 13.45
| 0.25 |  |  |  | 0.25
| 0.25 |  |  |  | 0.25
|  | 1.85 |  |  |  | 0.84
|  | 2.22 | m3 sub total |  |  | 5.97 | m3 sub total
| 1.9 |  | OR and Delivery back side | 6 | 3.85 |  | Or Delivery Internce gate
| 0.25 |  |  |  | 0.25
| 0.25 |  |  |  | 0.25
|  | 0.12 |  |  |  | 1.44 | m3 sub total
| 4.2 |  |  |  | 2 |  | Up toTo Admins-Block &Diagonestic Block
| 0.25 |  |  |  | 0.25
| 0.25 |  |  |  | 0.25
|  | 0.26 |  |  |  | 0.13
| 11.6 |  |  |  | 16.3
| 0.25 |  |  |  | 0.25
| 0.25 |  |  |  | 0.25
|  | 0.73 |  |  |  | 1.02
| 13 |  |  |  | 6
| 0.25 |  |  |  | 0.25 |  |  |  |  | 0.12
| 0.25 |  |  |  | 0.25
|  | 0.81 |  |  |  | 0.38
|  | 1.92 | m3 sub total |  | 15.8
0.25
2 | 50.6 |  | B/N IPD & OR Delivery |  | 0.25
| 0.25 |  |  |  |  | 0.99
| 0.25 |  |  |  | 8.3
|  | 6.33 | m3 sub total |  | 0.25
| 5.8 |  | Front Side IPD & OR Delivery |  | 0.25
| 0.25 |  |  |  |  | 0.52
| 0.25 |  |  |  | 17.15
|  | 0.36 |  |  | 0.25
| 8.3 |  |  |  | 0.25
| 0.25 |  |  |  |  | 1.07
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 7
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 15.15 |  |  |  | 1.9 |  | OR and Delivery back side
| 0.25 |  |  |  | 2
| 0.25 |  |  |  |  | 3.8
|  | 0.95 |  |  | 13.25
| 13.15 |  |  |  | 2
| 0.25 |  |  |  |  | 26.5 |  |  | 20.2985
| 0.25 |  |  |  |  | 30.3 | m2 sub total
|  | 0.82 |  |  | 2.65 |  | Road Crossing
| 14.7 |  |  |  | 2.1 | [6 empty] | m2
| 0.25 |  |  |  |  | 5.57 | m2 sub total
| 0.25 |  |  |  | 50.85 |  | B/N IPD & OR Delivery
|  | 0.92 |  |  | 2
|  | 6.8 | m3 sub total |  |  | 101.7 | m2 sub total
| 3 |  | Up to IPD- kichen block |  | 5.8 |  | Front Side IPD & OR Delivery
| 0.25 |  |  |  | 2
| 0.25 |  |  |  |  | 11.6
|  | 0.19 |  |  | 33
| 1 |  |  |  | 2
| 0.25 |  |  |  |  | 66
| 0.25 |  |  |  | 10.5
|  | 0.06 |  |  | 2
| 12.95 |  |  |  |  | 21
| 0.25 |  |  |  |  | 98.6 | m2 sub total
| 0.25 |  |  | 3 | 3.85 |  | Or Delivery Internce gate
|  | 0.81 |  |  | 2
| 15.35 |  |  |  |  | 23.1 | m2 sub total
| 0.25 |  |  | 1 | 16.55 |  | OR DeliveryTo Admins-Block
| 0.25 |  |  |  | 2
|  | 0.96 |  |  |  | 33.1
| 4 |  |  | 1 | 6
| 0.25 |  |  |  | 2
| 0.25 |  |  |  |  | 12
|  | 0.25 |  | 1 | 16.4
| 2 |  |  |  | 2
| 0.25 |  |  |  |  | 32.8
| 0.25 |  |  | 1 | 13.4 |  | To Diagonestic Block
|  | 0.13 |  |  | 2 |  |  |  | 20.78
| 30.1 |  |  |  |  | 26.8
| 0.25 |  |  |  |  | 104.7 | m2 sub total
| 0.25 |  |  |  | 30.6 |  | Up to IPD- kichen block
|  | 1.88 |  |  | 2
|  | 4.28 | m3 sub total |  |  | 61.2
|  | 32.7 | m3 Total of item no 2.2 |  | 2 |  |  | 20.66
|  | 2.31 C-20 concrete work |  |  | 2
| 12.1 |  | up to waiting and registration |  |  | 4 |  |  | 20.3
| 2 |  |  |  |  | 65.2 | m2 sub total
|  | 24.2 |  |  |  | 524.97 | m2 Totalto item 2.31
| 18.05 |  |  |  |  | 2.41 Form work
| 2 |  |  |  |  | OPD to waiting and registration
|  | 36.1 |  | 4 | 12.2
|  | 60.3 | m2 sub total |  | 0.25
| 2.95 |  | IPD Block back side |  |  | 12.2
| 2 |  |  | 4 | 17.8
|  | 5.9 |  |  | 0.25
| 14.8 |  |  |  |  | 17.8 |  |  |  | 193
| 2 |  |  |  |  | 30 | m2 sub total
29.6
|  | 35.5 | m2 sub total
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 8
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
4 | 2.95 |  | IPD Block back side | 12 | 3.85 |  | Or Delivery Internce gate
| 0.25 |  |  |  | 0.25
|  | 2.95 |  |  |  | 11.55 | m2 sub total
4 | 14.55 |  |  | 2 | 2 |  | upTo Admins-Block & Diagonstic
| 0.25 |  |  |  | 0.25
|  | 14.55 |  |  |  | 1
|  | 17.5 | m2 sub total | 2 | 16.3
2 | 1.9 |  | OR and Delivery back side |  | 0.25
| 0.25 |  |  |  |  | 8.15
|  | 0.95 |  | 2 | 6
2 | 4.2 |  |  |  | 0.25
| 0.25 |  |  |  |  | 3
|  | 2.1 |  | 2 | 15.8
2 | 11.6 |  |  |  | 0.25
| 0.25 |  |  |  |  | 7.9
|  | 5.8 |  | 2 | 8.3
2 | 13.25 |  |  |  | 0.25
| 0.25 |  |  |  |  | 4.15
|  | 6.63 |  | 2 | 17.15
|  | 15.48 | m2 sub total |  | 0.25
2 | 50.6 |  | B/N IPD & OR Delivery |  |  | 8.58
| 0.25 |  |  | 2 | 15.15
|  | 25.3 |  |  | 0.25
2 | 50.85 |  |  |  |  | 7.58
| 0.25 |  |  | 2 | 13.15
|  | 25.43 |  |  | 0.25
|  | 50.73 |  |  |  | 6.58
|  |  | Front Side IPD & OR Delivery | 2 | 14.7
2 | 5.8 |  |  |  | 0.25
| 0.25 |  |  |  |  | 7.35
|  | 2.9 |  |  |  | 54.29 | m2 sub total
1 | 8.3 |  |  | 2 | 3
| 0.25 |  |  |  | 0.25
|  | 2.08 |  |  |  | 1.5
1 | 8.05 |  |  | 2 | 1
| 0.25 |  |  |  | 0.25
|  | 2.01 |  |  |  | 0.5
2 | 13 |  |  | 2 | 30.1
| 0.25 |  |  |  | 0.25
|  | 6.5 |  |  |  | 15.05
1 | 33 |  |  | 2 | 12.95
| 0.25 |  |  |  | 0.25
|  | 8.25 |  |  |  | 6.48
1 | 32.5 |  |  | 2 | 15.35
| 0.25 |  |  |  | 0.25
|  | 8.13 |  |  |  | 7.68
1 | 12.45 |  |  | 2 | 4
| 0.25 |  |  |  | 0.25
|  | 3.11 |  |  |  | 2
1 | 12.2 |  |  | 2 | 2
| 0.25 |  |  |  | 0.25
|  | 3.05 |  |  |  | 1
2 | 10.5 |  |  |  |  | 34.21 | m2 sub total |  |  | 161.97
| 0.25 |  |  |  |  | 262.02 | m2 total to item 2.4
|  | 5.25 | [6 empty] | 161.97
2 | 13.95
| 0.25 | [7 empty] | 161.97
6.98
|  | 48.26 | m2 sub total
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 9
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 12.2 |  | 2.6 Masonery wall | 1 | 33
| 0.5 |  | OPD to waiting and registration |  | 0.5
| 0.8 |  |  |  | 0.5
|  | 9.76 |  |  |  | 8.25
2 | 17.55 |  |  | 1 | 11.95
| 0.5 |  |  |  | 0.5
| 0.8 |  |  |  | 0.5
|  | 14.04 |  |  |  | 2.99
|  | 23.8 | m3 sub total | 1 | 10.5
1 | 4.1 |  | IPD Block back side |  | 0.5
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  |  | 2.63
|  | 1.03 |  | 1 | 12.95
1 | 1.8 |  |  |  | 0.5
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  |  | 3.24
|  | 0.45 |  |  |  | 23.89 | m3 sub total
2 | 14.3 |  |  | 6 | 3.85 |  | Or Delivery Internce gate
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  | 0.5
|  | 7.15 |  |  |  | 5.78 | m3 sub total
|  | 8.63 | m3 sub total |  | 2 |  | Up toTo Admins-Block &Diagonestic Block
1 | 1.9 |  | OR and Delivery back side |  | 0.5
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  |  | 0.5
|  | 0.48 |  |  | 16.8
1 | 4.2 |  |  |  | 0.5
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  |  | 4.2
|  | 1.05 |  |  | 16.3
1 | 11.35 |  |  |  | 0.5
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  |  | 4.08
|  | 2.84 |  |  | 6
1 | 12.75 |  |  |  | 0.5
| 0.5 |  |  |  | 0.5
| 0.5 |  |  |  |  | 1.5
|  | 3.19 |  |  | 8.3
|  | 7.56 | m3 sub total |  | 0.5
2 | 50.35 |  | B/N IPD & OR Delivery |  | 0.5
| 0.5 |  |  |  |  | 2.08
| 0.5 |  |  |  | 17.65
|  | 25.18 | m3 sub total |  | 0.5
1 | 5.8 |  | Front Side IPD & OR Delivery |  | 0.5
| 0.5 |  |  |  |  | 4.41
| 0.5 |  |  |  | 15.15
|  | 1.45 |  |  | 0.5
1 | 8.3 |  |  |  | 0.5
| 0.5 |  |  |  |  | 3.79
| 0.5 |  |  |  | 14.7
|  | 2.08 |  |  | 0.5
1 | 13 |  |  |  | 0.5
| 0.5 |  |  |  |  | 3.68
| 0.5 |  |  |  | 13.4
|  | 3.25 |  |  | 0.5
0.5
TAKE OFF SHEET No 8
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- covered walkway
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :- 10
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3.35
|  | 27.59 | m3 sub total
| 3 |  | Up to IPD- kichen block
0.5
0.5
0.75
1
0.5
0.5
0.25
30.6
0.5
0.5
7.65
15.6
0.5
0.5
|  | 3.9 | [6 empty] | 43.18
|  | 12.55 | m3 sub total |  |  |  |  | 89.06
|  | 134.98 | Total to item 2.6
2.5 Steel reinforcment
Dia 6
|  | #REF! | Kg
Dia 8
|  | #REF! | Kg
Dia 12
|  | #REF! | Kg

## Civil Site TOS
Project: - Dhedhesa Primary Hospital
Contractor: - TRUST CONSTRUCTION
Consultant: - Oromia Health Bureau | [6 empty] | Block: - Civil Site Work
Client: - Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1 ROAD & PARKING | 1 | 12 |  | Junction in Front of Store
|  |  | 1. EXCAVATION & EARTH WORKS |  | 12 | 144
1.4. The sub-base of the road
1 | 85 |  | Main Gate to Waiting | 1 | 26 |  | from store to generator
| 4 | 340 |  |  | 4.3 | 111.8
1 | 21 |  | Waiting Parking Area | 1 | 171 |  | Gable Side of Emergency Block
| 10 | 210 |  |  | 0.5 | 85.5
1 | 13 |  | Junction to Staff, Waiting & Store | 1 | 41.33 |  | from Kitchen to Generator
| 11 | 143 |  |  | 4.3 | 177.72
1 | 72 |  | Main Gate to Staff | 1 | 13 |  | In Front of Kitchen
| 4 | 288 |  |  | 8 | 104
1 | 15 |  | Staff Parking Area |  |  | 213.83 | m2 net area item 1.5
| 10 | 150
1.6. 5cm thick final surface coarse
1 | 39 |  | Main Gate to Store | 1 | 85 |  | Main Gate to Waiting
| 10 | 390 |  |  | 4 | 340
1 | 12 |  | Junction in Front of Store | 1 | 21 |  | Waiting Parking Area
| 12 | 144 |  |  | 10 | 210
1 | 26 |  | from store to generator | 1 | 13 |  | Junction to Staff, Waiting & Store
| 4.3 | 111.8 |  |  | 11 | 143
1 | 171 |  | Gable Side of Emergency Block | 1 | 72 |  | Main Gate to Staff
| 0.5 | 85.5 |  |  | 4 | 288
1 | 41.33 |  | from Kitchen to Generator | 1 | 15 |  | Staff Parking Area
| 4.3 | 177.72 |  |  | 10 | 150
1 | 13 |  | In Front of Kitchen | 1 | 39 |  | Main Gate to Store
| 8 | 104 |  |  | 10 | 390
|  | 0 | m2 net area item 1.4 | 1 | 12 |  | Junction in Front of Store
[5 empty] | 12 | 144
1.5. 10cm thick gravel of 2/5cm watered and well rolled with 10(ten) tone roller in five passes
1 | 85 |  | Main Gate to Waiting | 1 | 26 |  | from store to generator
| 4 | 340 |  |  | 4.3 | 111.8
1 | 21 |  | Waiting Parking Area | 1 | 171 |  | Gable Side of Emergency Block
| 10 | 210 |  |  | 0.5 | 85.5
1 | 13 |  | Junction to Staff, Waiting & Store | 1 | 41.33 |  | from Kitchen to Generator
| 11 | 143 |  |  | 4.3 | 177.72
1 | 72 |  | Main Gate to Staff | 1 | 13 |  | In Front of Kitchen
| 4 | 288 |  |  | 8 | 104
1 | 15 |  | Staff Parking Area |  |  | 2138.3 | m2 net area item 1.6
| 10 | 150
1 | 39 |  | Main Gate to Store
| 10 | 390
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1.7. Construct of 12x35cm curbstone |  |  |  | 1.3. Semi-dressed stone massonry
1 | 18 |  | Staff Parking Area | 6 | 10 |  | Waiting Ramp
|  | 18 |  |  | 0.5
[5 empty] | 0.5 | 15
1 | 6 |  | " | 2 | 8 |  | "
|  | 6 |  |  | 0.5
[5 empty] | 0.5 | 4
1 | 18 |  | Waiting Parking Area | 6 | 10 |  | Store Ramp
|  | 18 |  |  | 0.5
[5 empty] | 0.5 | 15
1 | 6 |  | " | 2 | 8 |  | Generator & Transformer Ramp
|  | 6 |  |  | 0.5
[5 empty] | 0.5 | 4
|  | 48 | m net length item 1.7
[6 empty] | 38 | m3 net volume item 1.3
2/ Fecce Work
|  |  | 1.2 Metal work |  |  |  | 1.4. Cartaway surplus excavated material
|  |  | 1.2.1. The gate is made of approved type 40x40x3mm RHS profite. |  |  |  | Ditto item no 1.1
1 | 2 |  |  |  |  | 46 | m net length item 1.7
|  | 0 | no net number item 1.2.1
1.5. Fill granular approved type selected
|  |  | 1.2.2. Pedestrine gate size 120x250cm | 2 | 10 |  | Waiting
1 | 2 |  |  |  | 0.65
|  | 0 | no net number item 1.2.2 |  | 2.5 | 32.5
|  |  | 3. Ramps & Steps | 1 | 10 |  | "
|  |  | 1.STEPS AND RAMPS |  | 0.35
|  |  | A. Excavation and Masnory Works |  | 2.5 | 8.75
1.1. Excavation in 50cm from NGL
6 | 10 |  | Waiting | 1 | 8 |  | Store
| 1 |  |  |  | 0.35
| 0.5 | 30 |  |  | 2.4 | 6.72
2 | 8 |  | Store | 1 | 4 |  | Generator
| 1 |  |  |  | 0.35
| 0.5 | 8 |  |  | 2.1 | 2.94
4 | 4 |  | Generator & Transformer | 1 | 4.3 |  | Transformer Ramp
| 1 |  |  |  | 0.35
| 0.5 | 8 |  |  | 4 | 6.02
|  | 46 | m3 net volume item 1.1 |  |  | 56.93 | m3 net volume item 1.5
|  |  | 1.2. Stone masonry BNGL |  |  |  | 1.6. 25cm thick Hard core for ramps
6 | 10 |  | Waiting Ramp | 3 | 10 |  | Waiting
| 0.5 |  |  |  | 2.5 | 75
| 0.5 | 15
|  |  |  | 1 | 8 |  | Store
2 | 8 |  | Store Ramp |  | 2.4 | 19.2
0.5
| 0.5 | 4 |  | 1 | 4 |  | Generator
[5 empty] | 2.1 | 8.4
4 | 4 |  | Generator & Transformer Ramp
| 0.5 |  |  | 1 | 4.3 |  | Transformer Ramp
| 0.5 | 4 |  |  | 4 | 17.2
|  | 23 | m3 net volume item 1.2 |  |  | 119.8 | m2 net area item 1.6
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. CONCRETE WORK |  |  |  | B. Super Structure
|  |  | 3.7. 7cm thick lean concrete |  |  |  | 1. Steel structure
6 | 10 |  | Waiting Ramp |  |  |  | 1.2. Plates (150mx150mmx3mm)
| 0.5 | 30 |  | 2 | 54 |  | Diagno. To OR
108
2 | 8 |  | Store Ramp
| 0.5 | 8 |  | 2 | 32 |  | Beside Diagno. To OR
64
4 | 4 |  | Generator & Transformer Ramp
| 0.5 | 8 |  | 2 | 28 |  | OR to Kitchen
56
|  | 46 | m2 net area item 3.7
|  |  |  | 2 | 26 |  | IPD to Kitchen
|  |  | 5. Covered walk way |  |  | 52
1. Excavation for Covered walk ditch
|  |  | 1.1. Bulk Excavation |  |  | 280 | ml net length item 1.2
2 | 30.4 |  | OPD to Waiting
| 0.6 | [5 empty] | 1.4. 40x60x2.5mm RHS beam
| 0.5 | 18.24 |  | 2 | 70 |  | Diagno. To IPD & OR
140
2 | 27.2 |  | Waiting to Diagno
| 0.6 |  |  | 6 | 4 |  | Ditto above Extended to OR Gate
| 0.5 | 16.32 |  |  |  | 24
2 | 43.4 |  | Waiting to Diagno | 2 | 41 |  | IPD to OR Gable Side
| 0.6 |  |  |  |  | 82
| 0.5 | 26.04
|  |  |  | 2 | 20 |  | IPD to Kitchen Gable Side
2 | 11.7 |  | Extend to Emergency |  |  | 40
0.6
| 0.5 | 7.02 |  | 2 | 10 |  | Extended to IPD
20
2 | 12.2 |  | Extend to OPD
| 0.6 |  |  | 2 | 33 |  | OR to Kitchen
| 0.5 | 7.32 |  |  |  | 66
2 | 50.5 |  | Beside Diagno. Along OR Block | 2 | 60 |  | Beside Diagno. Along OR Block
| 0.6 |  |  |  |  | 120
| 0.5 | 30.3
[6 empty] | 492 | ml net length
1 | 16.5 |  | IPD to Kitchen |  |  |  | 3.6 kg/m conversion factor
| 0.6 |  |  |  |  | 1771.2 | kg net weight item 1.4
| 0.5 | 4.95
1.5. 40x30x2mm RHS
2 | 33 |  | OR to Kitchen | 54 | 7.06 |  | Diagno. To OR
| 0.6 |  |  |  |  | 381.24
| 0.5 | 19.8
|  |  |  | 32 | 7.06 |  | Beside Diagno. Along OR Block
2 | 56 |  | Diagno. To IPD b/n OR Block |  |  | 225.92
0.6
| 0.5 | 33.6 |  | 28 | 7.06 |  | OR to Kitchen
197.68
|  | 0 | m3 net volume
|  |  |  | 26 | 7.06 |  | IPD to Kitchen
183.56
[6 empty] | 988.4 | ml net length
1.68 kg/m conversion factor
[6 empty] | 1660.51 | kg net weight item 1.5
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1.6. 30x20x2mm diagonal member
54 | 1.44 |  | Diagno. To OR
77.76
32 | 1.44 |  | Beside Diagno. Along OR Block
46.08
28 | 1.44 |  | OR to Kitchen
40.32
26 | 1.44 |  | IPD to Kitchen
37.44
|  | 201.6 | ml net length
1.36 kg/m conversion factor
|  | 274.18 | kg net weight item 1.6
2. ROOFING
2.1. Roof cover G-30 C-I-S
2 | 70 |  | IPD to OR
| 1.75 | 245
2 | 20 |  | IPD to Kitchen Gable
| 1.75 | 70
2 | 10 |  | Extend to IPD
| 1.75 | 35
|  | 232.85 | m2 net area item 2.1
2.2. 5x7cm purlin
2 | 210 |  | Diagno. To IPD b/n OR Block
420
2 | 60 |  | IPD to Kitchen
120
2 | 30 |  | Extend to IPD
60
|  | 600 | m net length item 2.2
3. ELECTRICAL INSTALLATION
3.1. Light points
1 | 68
|  | 0 | PCS net number item no 3.1

## Pla Sum
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT PLACENTA PIT NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | EXCAVATION & EARTH WORKS | 9140 | 34167.16 | 0 | 34167.16
2 | CONCRETE WORKS | 19436 | 19907.56 | 0 | 19907.56
3 | MASONRY WORKS | 19000 | 83590 | 0 | 83590
TOTAL |  | 47576 | 137664.72 | 0 | 137664.72

## Pla Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Civil Site Work - Placenta Pit NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
A. Sub-Structure
1. EXCAVATION AND EARTH WORK
1.1 | Excavate for the pit not exceeding 150cm from | M3 | 30 | 144.06 |  | 144.06 | 36 | 1080 | 5186.16 | 0 | 5186.16
1.2 | Ditto over 150cm but not exceeding 300cm | M3 | 32 | 163.26 |  | 163.26 | 40 | 1280 | 6530.4 | 0 | 6530.4
1.3 | Backfill arround retaining wall | M3 | 14 | 64.37 |  | 64.37 | 100 | 1400 | 6437 | 0 | 6437
1.5 | Cart away | M3 | 62 | 206.48 |  | 206.48 | 70 | 4340 | 14453.6 | 0 | 14453.6
1.6 | 25cm thick Hardcore | M2 | 16 | 24 |  | 24 | 65 | 1040 | 1560 | 0 | 1560
TOTAL CARRIED TO SUMMARY | [7 empty] | 9140 | 34167.16 | 0 | 34167.16
2. CONCRETE WORKS
2.1 | 5cm thick concrete in class C-5, | M2 | 16 | 20.01 |  | 20.01 | 100 | 1600 | 2001 | 0 | 2001
2.2 | Reinforced concrete in class C-20
| a) In 15cm. Thick RC top slab | M2 | 14 | 20.75 |  | 20.75 | 260 | 3640 | 5395 | 0 | 5395
| a)RC top roof slab | M2 | 10 | 13.88 |  | 13.88 | 120 | 1200 | 1665.6 | 0 | 1665.6
2.4 | Reinforcement steel bars
| a) Diameter 8mm deformed bar | Kg | 106 | 122.62 |  | 122.62 | 38 | 4028 | 4659.56 | 0 | 4659.56
| b) Diameter 10mm deformed bar | Kg | 212 | 162.8 |  | 162.8 | 38 | 8056 | 6186.4 | 0 | 6186.4
| c) Diameter 12mm deformed bar | Kg | 24 | 0 |  | 0 | 38 | 912 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 19436 | 19907.56 | 0 | 19907.56
| 3. MASONRY WORK |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
3.1 | 60cm thick hard traychaltic or equivalent stone masonry | M3 | 19 | 83.59 |  | 83.59 | 1000 | 19000 | 83590 | 0 | 83590
TOTAL CARRIED TO SUMMARY | [7 empty] | 19000 | 83590 | 0 | 83590

## TOS placenta (hidden)
TAKE OFF SHEET No 4
PROJECT :- Dhedesa Primary Hospital
CLIENT :- Oromia Health Bureau
CONSULTANT :- Oromia Health Bureau | [5 empty] | Block :- Placenta Pit
CONTRACTOR :- Trust Construction | [5 empty] | Page No. :-
LOCATION :- Dhedesa
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1. SUB STRUCTURE |  |  | 34.94 | TOTAL
1 | 6.18 |  | 1. Earth work |  |  |  | 2.3 form work
| 5.18 |  | 1.1 Excavate for the pit in exceeding 150cm from NGL. | 1 | 4 |  | a) for top slab
| 1.5 | 48.02 | m3 |  | 3 | 12
1 | 6.18 |  | 1.2 Ditto over 150 cm but not exceeding 300 cm. | 2 | 5.18
| 5.18 |  |  |  | 0.1 | 1.04
| 2.55 | 81.63 | m3 | 2 | 4.18
2 | 7.36 |  | 1.3 Backfill around retaining wall |  | 0.1 | 0.84
| 0.59 |  | W=1.09-.5=.59 |  |  | 13.88
| 4.05 | 35.17 | L=6.16+2*.59=7.36 | 4 | 0.5 |  | b) for inspection manhole
2 | 5.18 |  | d=4.05+.20+.1=4.35 |  | 0.5 | 1
| 0.59 |  |  | 4 | 0.6 |  | c) to removable cover
| 4.05 | 24.76 |  |  | 0.1 | 0.24
|  | 59.93 | m3 |  |  |  | 2.4 reinforcement
|  |  | 1.4 Backfill on top of RC roof slab |  |  |  | 2.5 Reinforcement Steel Bar
|  |  | Not shown on drawing |  |  | 122.62 | a) Dia. 8mm deformed bar
|  |  | 1.5 Cart away surplus excavated material |  |  |  | Kg
|  | 129.65 |  |  |  | 162.8 | a) Dia. 10mm deformed bar
|  |  | 1.6 hard core |  |  |  | Kg
1 | 4
| 3 | 12 | m2
2 | 5.18 |  | 2.1 lean concrete |  |  |  | no detail drawing
| 1.09 | 11.29 | m2 | 2 | 5.59 |  | 3 MASONRY WORK
2 | 4 |  |  |  | 4.05 |  | detail=average=0.795 spec.=60cm
| 1.09 | 8.72 | m2 |  | 4.05 | 183.38
|  | 20.01 |  | 2 | 3
1 | 4.18 |  | 2.2 Reinforced concrete. |  | 4.05
| 3.18 |  | a) for top slab |  | 4.05 | 98.42
|  | 13.29 | at bottom |  |  | 281.8
1 | 4.18
| 5.18 | 21.65
34.94
4 | 0.5 |  | b) for inspection manhole
| 0.5 | 1

## rebar PLACENTA (hidden)
Reinforcement Bar Schedule
Contractor :- Trust Construction | [8 empty] | Block :- PLACENTA PIT
Project :- Dhedessa Primary Hospital | [8 empty] | page :- 1
Client :- Oromiya Health Bureau | [8 empty] | Date:-
Location | Axis | Ø In mm | Length | No of bars | Members | Total length of Re-bars |  |  |  |  | Remark
[6 empty] | 6 | 8 | 10 | 12 | 14
Placenta | [6 empty] | " | " | " | "
top |  | 8 | 1.3 | 21 | 1 |  | 27.3 | " | " | "
|  | 8 | 1.3 | 19 | 1 |  | 24.7 | " | " | "
|  | 8 | 1.3 | 6 | 1 |  | 7.8 | " | " | "
|  | 8 | 1.65 | 13 | 2 | " | 42.9 | " | " | "
|  | 8 | 3.45 | 9 | 1 | " | 31.05 | " | " | "
|  | 8 | 0.965 | 9 | 1 | " | 8.685 | " | " | "
|  | 10 | 5.15 | 16 | 1 | " | " | 82.4 | " | "
|  | 10 | 3.65 | 10 | 1 | " | " | 36.5 | " | "
|  | 10 | 1.15 | 10 | 1 | " | " | 11.5 | " | "
|  | 10 | 4.15 | 23 | 1 | " | " | 95.45 | " | "
|  | 10 | 2.65 | 10 | 1 | " | " | 26.5 | " | "
|  | 10 | 1.15 | 10 | 1 | " | " | 11.5 | " | "
[6 empty] | " | " | " | " | "
bottom slab |  | 8 | 4 | 21 | 1 | " | 84 | " | " | "
|  | 8 | 4 | 21 | 1 | " | 84 | " | " | "
[6 empty] | " | " | " | " | "
|  |  | Total Length |  |  | 0 | 310.435 | 263.85 | 0 | 0
|  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209
|  |  | Total Weight |  |  | 0 | 122.6218 | 162.7954 | 0 | 0
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " | " | " | "
[6 empty] | " | " |  | " | "
|  |  | Total Length |  |  | 0 | 0 | 0 | 0 | 0
|  |  | Unit Wt.(kg/mL) |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.209
|  |  | Total Weight |  |  | 0 | 0 | 0 | 0 | 0

## placenta pit (hidden)
TRUST CONSTRUCTION
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for PLACENTA PIT
Item | Description of Work | Unit | Contract |  | Executed |  |  |  | Amount
| PLACENTA PIT |  |  |  | previous | current | total | Rate | Previous | Current | Total
EXCAVATION AND EARTH WORK
1.1 | Excavate for the pit in ordinary soil to a depth not exceeding 150cm from | M3 | 30 | 1080 |  |  | 0 | 36 |  | 0 | 0
1.2 | Ditto over 150cm but not exceeding 300cm | M3 | 32 | 1280 |  |  | 0 | 40
1.3 | Backfill arround retaining wall with granular material from a quarry | M3 | 14 | 1400 |  |  | 0 | 100
1.4 | Backfill on top of RC roof slab to a depth of 50cm with good excavated | M2 | 9 | 900 |  |  | 0 | 100
1.5 | Cart away surplus excavated material and deposit to where the engineer | M3 | 62 | 4340 |  |  | 0 | 70
1.6 | 25cm thick Hardcore | M2 | 16 | 1040 |  |  | 0 | 65
| TOTAL CARRIED TO SUMMARY |  |  | 10040 | [5 empty] | 0 | 0
| 2. CONCRETE WORKS | [5 empty] | 0
2.1 | 5cm thick concrete in class C-5, cement 150kg/m3 stone masonry retaining wall | M2 | 16 | 1600 |  |  | 0 | 100
2.2 | Reinforced concrete in class C-20 cement 320 kg/m3 filled into form |  |  | 0 |  |  | 0
| work and vibrated around rod reinforcement. Steel and formwork |  |  | 0 |  |  | 0
| measured separately. |  |  | 0 |  |  | 0
| a) In 15cm. Thick RC top slab | M2 | 14 | 3640 |  |  | 0 | 260
| b) In 10cm. Thick RC wall around an inspection hole of septic tank | M2 | 5 | 1300 |  |  | 0 | 260
| c) In 8cm thick RC removable cover for the manhole with handle in size | No | 3 | 900 |  |  | 0 | 300
2.3 | Provide, cut and fix in position sawn zigba wood form work to |  |  | 0 |  |  | 0
| a)RC top roof slab | M2 | 10 | 1200 |  |  | 0 | 120
| b) RC wall around an inspection hole of the pit | M2 | 10 | 1200 |  |  | 0 | 120
| d) removable cover | M2 | 2 | 240 |  |  | 0 | 120
2.4 | Reinforcement steel bars according to structural drawings. Price shall |  |  | 0 |  |  | 0
| a) Diameter 8mm deformed bar | Kg | 106 | 4028 |  |  | 0 | 38
| b) Diameter 10mm deformed bar | Kg | 212 | 8056 |  |  | 0 | 38
| c) Diameter 12mm deformed bar | Kg | 24 | 912 |  |  | 0 | 38
| TOTAL CARRIED TO SUMMARY |  |  | 23076 |  |  | 0 |  |  |  | 0
3 | MASONRY WORK | [5 empty] | 0
3.1 | 60cm thick hard traychaltic or equivalent stone masonry | M3 | 19 | 19000 |  |  | 0 | 1000
| retaining wall bedded in cement mortar 1:3 internal part | [5 empty] | 0
| left for plastering | [5 empty] | 0
| TOTAL CARRIED TO SUMMARY |  |  | 19000 |  |  | 0
4 | PIPE WORK | [5 empty] | 0
4.1 | Dia. 110mm pvc pipe with vent cap over it | Ml | 6 | 600 |  |  | 0 | 100
| TOTAL CARRIED TO SUMMARY |  |  | 600 |  |  | 0
5 | FENCE WORK | [5 empty] | 0
5.1 | Fence for plocenta pit, and ash pit. Dia 10cm impregnated | Ml | 50 | 2500 |  |  | 0 | 50
| Eucalyptus poles erceted to c/c distance of 200cm and iter | [5 empty] | 0
| connected with 14 rows of bar bed wire and two diagonals. | [5 empty] | 0
| Price shall include diagonal eucalyptus bracing at every | [5 empty] | 0
| corner (both directions), mass every concrete base of C-15 | [5 empty] | 0
| with diameter 30cm and depth of 50cm including excavation | [5 empty] | 0
| & earth work. | [5 empty] | 0
| TOTAL CARRIED TO SUMMARY |  |  | 2500 |  |  | 0

## Sum Ash
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT ASH AND NEDDLE PIT NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | EXCAVATION & EARTH WORK | 11060 | 8977.5 | 0 | 8977.5
2 | BLOCK WORK | 110000 | 100840 | 0 | 100840
TOTAL |  | 121060 | 109817.5 | 0 | 109817.5

## Meas Ash
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for Civil Site Work - ASH & NIDDLE Pit NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
1. EXCAVATION AND EARTH WORK
1.1 | Bulk excavation ordinary soil to a depth not exceeding 150cm. | M3 | 110 | 52.5 |  | 52.5 | 36 | 3960 | 1890 | 0 | 1890
1.2 | Ditto but not exceeding a depth of 30cm | M3 | 65 | 52.5 |  | 52.5 | 40 | 2600 | 2100 | 0 | 2100
1.3 | Ditto but not exceeding a depth of 450cm | M3 | 50 | 52.5 |  | 52.5 | 45 | 2250 | 2362.5 | 0 | 2362.5
1.4 | Ditto but not exceeding a depth of 550cm | M2 | 45 | 52.5 |  | 52.5 | 50 | 2250 | 2625 | 0 | 2625
1.5 | Cart away | M3 |  | 0 |  | 0 | 70 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 11060 | 8977.5 | 0 | 8977.5
| 2. BLOCK WORKS |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
2.1 | 60cm thick har trachytic or equivalents stone masonry retaining wall bedded in cement mortar 1:4 (Cement sand) | M3 | 110 | 100.84 |  | 100.84 | 1000 | 110000 | 100840 | 0 | 100840
TOTAL CARRIED TO SUMMARY | [7 empty] | 110000 | 100840 | 0 | 100840

## Site Sani Sum
TRUST CONSTRUCTION
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT SITE SANITARY INSTALLATION- NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
1 | GENERTATOR SITE WORK | 496150 | 94530 | 13500 | 108030
2 | 50 M3 CAPACITY PIONNER WORK | 350000 |  | 0 | 0
3 | 50 M3 SEPTIC TANK | 151242 | 151241.44 | 20125 | 171366.44
4 | 30M3 SEPTIC TANK | 136227 | 118628.2 | 0 | 118628.2
5 | Elevated Water Tanker 4m3 | 160696
6 | SOAK AWAY PIT FOR 5 UNIT | 277550 | 387370.5 | 0 | 387370.5
TOTAL |  | 1571865 | 751770.14 | 33625 | 785395.14

## Site Sani Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for SITE SANITARY NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
1. GENERATOR SITE WORK
1.5 | Construct manholes on the sanitary sewer drainage systems (on all blocks & l
| a) size: 600x600mm avrage depht=850mm | No | 333 |  | 27 | 27 | 500 | 166500 | 0 | 13500 | 13500
1.6 | Construct open ditch out of half precast concrete round pipes
| a) Ditch size 1/2 Diameter 300mm | ml | 1148 | 945.3 |  | 945.3 | 100 | 114800 | 94530 | 0 | 94530
TOTAL CARRIED TO SUMMARY | [7 empty] | 281300 | 94530 | 13500 | 108030
3 | SEPTIC TANK 50M3 CAPACITY
drawing including all incidental works
3.1 EARTH WORK
3.1.1 | Excvate pit for not exceeding 1.5mt | M3 | 72 | 86.25 |  | 86.25 | 36 | 2592 | 3105 | 0 | 3105
3.1.2 | Ditto over 1.5 mt but not exceeding 3.5 mt | M3 | 102 | 115 |  | 115 | 40 | 4080 | 4600 | 0 | 4600
3.1.3 | Rock excavation
| a) Soft rock | M3 | 7 | 0 |  | 0 | 120 | 840 | 0 | 0 | 0
| b) Bed (hard rock) | M3 | 5 | 0 |  | 0 | 150 | 750 | 0 | 0 | 0
| c) Bolder rock | M3 | 6 | 0 |  | 0 | 200 | 1200 | 0 | 0 | 0
3.1.4 | Back fill around the masonry wall | M3 | 20 | 31.5 |  | 31.5 | 100 | 2000 | 3150 | 0 | 3150
3.1.5 | Back fill on top R.C slab | M3 | 23 | 0 |  | 0 | 100 | 2300 | 0 | 0 | 0
| well compacted in layers not exceeding 25cm Thick. |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
3.1.6 | Cart away surplus excavated material | M3 | 128 | 201.25 | 201.25 | 402.5 | 100 | 12800 | 20125 | 20125 | 40250
TOTAL CARRIED TO SUMMARY | [7 empty] | 26562 | 30980 | 20125 | 51105
| 3.2 CONCRETE WORK |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
3.2.1 | 5cm, Thick lean concrete | M2 | 42 | 42 |  | 42 | 100 | 4200 | 4200 | 0 | 4200
3.2.2 | Reinforced concrete in C-20 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
3.2.3 | In 20cm. Thick top slanb | M3 | 8.4 | 8.4 |  | 8.4 | 2800 | 23520 | 23520 | 0 | 23520
3.2.4 | In 15cm. Thick inspection manhole wall | M2 | 5 | 0.86 |  | 0.86 | 390 | 1950 | 335.4 | 0 | 335.4
3.2.5 | ditto but concrete cover to inspection manhole | M2 | 1.5 | 0.15 |  | 0.15 | 390 | 585 | 58.5 | 0 | 58.5
3.2.6 | form work |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| a) To 20cm. Bottom slab | M2 | 6 | 5.8 |  | 5.8 | 100 | 600 | 580 | 0 | 580
| b) To 15cm. Top slab | M2 | 30 | 3.15 |  | 3.15 | 100 | 3000 | 315 | 0 | 315
| c) To 10cm. Wall | M2 | 12 | 30.39 |  | 30.39 | 100 | 1200 | 3039 | 0 | 3039
| d) To R.C removable cover | M2 | 1.5 | 10.56 |  | 10.56 | 100 | 150 | 1056 | 0 | 1056
3.2.7 | Mild stone reinforcement according to the drawing |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| a) Dia 8mm. Deformed bar | Kg | 235 | 176.13 |  | 176.13 | 38 | 8930 | 6692.94 | 0 | 6692.94
| b) Dia 10mm " | Kg | 165 | 247.34 |  | 247.34 | 38 | 6270 | 9398.92 | 0 | 9398.92
| c) Dia 12mm " | Kg | 510 | 614.71 |  | 614.71 | 38 | 19380 | 23358.98 | 0 | 23358.98
TOTAL CARRIED TO SUMMARY | [7 empty] | 69785 | 72554.74 | 0 | 72554.74
| 3.3 MASONRY WORK |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
3.3.1 | Supply and construct concealed stone masonry | M3 | 44 | 37.67 |  | 37.67 | 1000 | 44000 | 37670 | 0 | 37670
3.3.2 | 15cm. Thick H.C.B pation wall | M2 | 13 | 12.88 |  | 12.88 | 290 | 3770 | 3735.2 | 0 | 3735.2
TOTAL CARRIED TO SUMMARY | [7 empty] | 47770 | 41405.2 | 0 | 41405.2
| 3.4 PLASTERING WORK |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
3.4.1 | platering to internal stone massonry wall surface | M2 | 61 | 60.5 |  | 60.5 | 75 | 4575 | 4537.5 | 0 | 4537.5
3.4.2 | Ditto but to both sides of H.C.B partiion walls. | M2 | 26 | 23.52 |  | 23.52 | 75 | 1950 | 1764 | 0 | 1764
TOTAL CARRIED TO SUMMARY | [7 empty] | 6525 | 6301.5 | 0 | 6301.5
| 3.5 PIPE WORK |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
3.5.1 | Provide and instaal installation inpositon PVC "T" pipe Ø 200cm | No | 2 | 0 |  | 0 | 150 | 300 | 0 | 0 | 0
3.5.2 | Provide and instaal elbow Ø 200mm | No | 2 | 0 |  | 0 | 150 | 300 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 600 | 0 | 0 | 0
SEPIC TANK 50M3 GRAND TOTAL CARRIED TO SUMMARY | [7 empty] | 151242 | 151241.44 | 20125 | 171366.44
4. SEPTIC TANK 30M3
4.1 EARTH WORK
4.1.1 | Excavate pit for septic thank to a dp not exceding 1.5m | M3 | 54 | 65.48 |  | 65.48 | 36 | 1944 | 2357.28 | 0 | 2357.28
4.1.2 | Ditto over 1.5mt but not exceeding 3.5mt | M3 | 71 | 87.3 |  | 87.3 | 40 | 2840 | 3492 | 0 | 3492
4.1.4 | Rock excavation
| a) Soft rock | M3 | 7 | 0 |  | 0 | 120 | 840 | 0 | 0 | 0
| b) Bed (hard rock) | M3 | 5 | 0 |  | 0 | 150 | 750 | 0 | 0 | 0
| c) Bolder rock | M3 | 6 | 0 |  | 0 | 200 | 1200 | 0 | 0 | 0
4.1.5 | Back fill around the masonry wall | M3 | 17 | 42.7 |  | 42.7 | 100 | 1700 | 4270 | 0 | 4270
4.1.6 | Back fill on top R.C slab to a depth of 50cm. | M3 | 17 | 0 |  | 0 | 100 | 1700 | 0 | 0 | 0
4.1.7 | Cart away surplus excavated material | M3 | 97 | 152.78 |  | 152.78 | 70 | 6790 | 10694.6 | 0 | 10694.6
TOTAL CARRIED TO SUMMARY | [7 empty] | 17764 | 20813.88 | 0 | 20813.88
| 4.2 CONCRETE WORK |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
4.2.1 | 5cm, Thick lean concrete | M2 | 31 | 30.45 |  | 30.45 | 100 | 3100 | 3045 | 0 | 3045
4.2.2 | Reinforced concrete in C-20
4.2.3 | In 20cm. Thick top slanb | M3 | 6.2 | 6.09 |  | 6.09 | 2900 | 17980 | 17661 | 0 | 17661
4.2.4 | In 10cm. Thick inspection manhole wall | M3 | 4.7 | 2.19 |  | 2.19 | 2900 | 13630 | 6351 | 0 | 6351
4.2.5 | Provide, cut and fix in position sawn zigba form work
| a) To 20cm. Bottom disb | M2 | 5 | 4.88 |  | 4.88 | 100 | 500 | 488 | 0 | 488
| b) To 15cm. Top slab | M2 | 21 | 3.66 |  | 3.66 | 100 | 2100 | 366 | 0 | 366
| c) To 10cm. Wall | M2 | 11 | 20.91 |  | 20.91 | 100 | 1100 | 2091 | 0 | 2091
| d) To R.C removable cover | M2 | 1.5 | 10.44 |  | 10.44 | 110 | 165 | 1148.4 | 0 | 1148.4
4.2.6 | Mild stone reinforcement according to the drawing
| a) dis. 8mm. Deformed bar | Kg | 221 | 111.31 |  | 111.31 | 38 | 8398 | 4229.78 | 0 | 4229.78
| b) dia 10mm " | Kg | 300 | 23.14 |  | 23.14 | 38 | 11400 | 879.32 | 0 | 879.32
| c) dia 12mm " | Kg | 480 | 620.09 |  | 620.09 | 38 | 18240 | 23563.42 | 0 | 23563.42
TOTAL CARRIED TO SUMMARY | [7 empty] | 76613 | 59822.92 | 0 | 59822.92
| 4.3 MASONRY WORK |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
4.3.1 | Supply and construct concealed stone masonry | M3 | 34 | 30.36 |  | 30.36 | 1000 | 34000 | 30360 | 0 | 30360
4.3.2 | 10cm. Think H.C.B partion wall | M2 | 10 | 9.66 |  | 9.66 | 290 | 2900 | 2801.4 | 0 | 2801.4
TOTAL CARRIED TO SUMMARY | [7 empty] | 36900 | 33161.4 | 0 | 33161.4
4.4.1 | platering to internal stone massonry wall surface | M2 | 46 | 45.08 |  | 45.08 | 75 | 3450 | 3381 | 0 | 3381
4.4.2 | Ditto but to both sides of H.C.B partiion walls. | M2 | 20 | 19.32 |  | 19.32 | 75 | 1500 | 1449 | 0 | 1449
TOTAL CARRIED TO SUMMARY | [7 empty] | 4950 | 4830 | 0 | 4830
SEPIC TANK 30M3 GRAND TOTAL CARRIED TO SUMMARY | [7 empty] | 136227 | 118628.2 | 0 | 118628.2
| 6. SOAKAWAY PIT |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
| 6.1 .Execavation and Earth work |  |  | 0 |  | 0 |  | 0 |  |  | 0
6.1.1 | Execcavte pit for septic tank to deth not exceeding 1.5m | M3 | 26 | 12.05 |  | 12.05 | 36 | 936 | 433.8 | 0 | 433.8
6.1.2 | Ditto but to not exceeding a depth of 30cm | M3 | 26 | 2.41 |  | 2.41 | 40 | 1040 | 96.4 | 0 | 96.4
6.1.3 | Ditto but to not exceeding a depth of 45cm | M3 | 26 | 3.62 |  | 3.62 | 45 | 1170 | 162.9 | 0 | 162.9
6.1.4 | Ditto but to not exceeding a depth of 55cm | M3 | 18 | 4.42 |  | 4.42 | 50 | 900 | 221 | 0 | 221
6.1.5 | Cart away surplus excavated material | M3 |  | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 4046 | 914.1 | 0 | 914.1
6.2 | 6.2 Stone Masonary retaining wall area | M3 | 22 | 17.97 |  | 17.97 | 1000 | 22000 | 17970 | 0 | 17970
TOTAL CARRIED TO SUMMARY | [7 empty] | 22000 | 17970 | 0 | 17970
6.3.FILLWORK
6.3.1 | Fill pit from the bottom upto a depth of 1.8m with water absorbent light and clean coarse gravel | M3 | 9 | 74.61 |  | 74.61 | 600 | 5400 | 44766 | 0 | 44766
| a) Ditto but with coarse gravel to a depth of 30cm | M3 | 1.5 | 5.08 |  | 5.08 | 600 | 900 | 3048 | 0 | 3048
| b) Ditto but with coarse gravel to a depth of 30cm | M3 | 1.5 | 5.08 |  | 5.08 | 600 | 900 | 3048 | 0 | 3048
| c) Ditto but with coarse gravel to a depth of 30cm | M3 | 1.5 | 5.08 |  | 5.08 | 600 | 900 | 3048 | 0 | 3048
TOTAL CARRIED TO SUMMARY | [7 empty] | 8100 | 53910 | 0 | 53910
6.4. Concrete work
| C-20 with minimum cement content of 320kg/m2 | M3 | 6.5 | 1.6 |  | 1.6 | 2800 | 18200 | 4480 | 0 | 4480
6.4.1 | Reinforcement bars |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| a) Dia 8mm. Deformed bar | Kg | 71 | 0 |  | 0 | 34 | 2414 | 0 | 0 | 0
6.4.2 | form work for concrete | M2 | 7 | 2 |  | 2 | 100 | 700 | 200 | 0 | 200
6.4.3 | To manhole cover slab(Size 60x60x60cm) | No | 1 | 0 |  | 0 | 50 | 50 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 21364 | 4680 | 0 | 4680
SOACK AWAY GRAND TOTAL CARRIED TO SUMMARY | [7 empty] | 55510 | 77474.1 | 0 | 77474.1
SOACK AWAY Pit For Five unit | [7 empty] | 277550 | 387370.5 | 0 | 387370.5

## Site Sani TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Site Sanitary
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1. GENERATOR SITE WORK
1.5. Sanitary manhole
a) Size 600x600x85cm
1 | 4 |  | OPD
4
1 | 4 |  | Diagno.
4
1 | 9 |  | IPD
9
1 | 10 |  | OR & Delivery
10
|  | 27 | no net number item 1.5.a

## Site Elec Sum
TRUST CONSTRUCTION
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
SUMMARY OF STATEMENT SITE SANITARY INSTALLATION- NO 15
It No. | Description | Contract Amount (birr) | Executed Amount (birr)
|  |  | Previous | Current | To date
A SUB STRUCTURE
1 | DISTRIBUTION BOARD | 19000 |  |  | 0
2 | MANHOLE & DUCT | 194250 |  | 0 | 0
3 | FEEDER CABLE | 1109500 |  |  | 0
4 | COMPOUND LIGHTING | 98500 |  |  | 0
5 | LIGHT FIXTURES | 153370 |  |  | 0
6 | LOW VOLTAGE SYSTEMS | 28080 |  |  | 0
TOTAL |  | 1602700 | 0 | 0 | 0

## Site Elec Meas
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau
Client:- Oromia Regional State Health Bureau
Summary of Measurement for SITE ELECTRICAL NO- 15
Item | Description of Work | Unit | Contract Qty | Executed Qty |  |  | Rate | Contract Amount | Executed Amount
|  |  |  | previous | current | Total to date |  |  | Previous | Current | Total To Date
ELECTRICAL SITE WORK
2.1 | Manhole in brick or masonry, internally, plastered including reinforced concrete
2.1.1 | 1200x1000x700mm | No | 1 | 1 |  | 1 | 3500 | 3500 | 3500 | 0 | 3500
2.1.2 | Ditto, but with 1000x1000x700mm | No | 9 | 9 |  | 9 | 2500 | 22500 | 22500 | 0 | 22500
2.1.3 | Ditto, but with 600x600x500mm | No | 9 | 9 |  | 9 | 1800 | 16200 | 16200 | 0 | 16200
2.2 | Cement pipe of dia. 110mm diameter to main power distribution. Price include digging and back fill | M | 20 | 211 |  | 211 | 415 | 8300 | 87565 | 0 | 87565
2.3.a | PVC pipe of dia 50mm diameter to main Tele system distribution price shall include digging and back fill | M | 50 | 1108 |  | 1108 | 985 | 49250 | 1091380 | 0 | 1091380
2.3.b | PVC pipe of dia 110mm diameter to main Tele system distribution price shall include digging and back fill | M | 0 | 0 |  | 0 | 120 | 0 | 0 | 0 | 0
| 3. FEEDER CABLES |  |  |  |  | 0 |  |  | 0 | 0 | 0
3.5 | 4x6mm2 | ML | 160 | 0 |  | 0 | 310 | 49600 | 0 | 0 | 0
3.7 | 3x4mm2 | ML | 280 | 0 |  | 0 | 485 | 135800 | 0 | 0 | 0
3.9 | 4x10mm2 | ML |  | 0 |  | 0 | 165 | 0 | 0 | 0 | 0
3.1 | 4x16mm3 | ML |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
TOTAL CARRIED TO SUMMARY | [7 empty] | 285150 | 1221145 | 0 | 1221145

## Site Elec TOS
Project:- Dhedhesa Primary Hospital
Contractor:- TRUST CONSTRUCTION
Consultant:- Oromia Health Bureau | [6 empty] | Block: - Site Electrical
Client:- Oromia Regional State Health Bureau | [6 empty] | Payment 15
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | ELECTRICAL SITE WORK | 1 | 60 |  | From G.H to Store & Generator Comp. Light
|  |  | 2. MANHOLE AND DUCTS |  |  | 60
2.1. Manhole in brick or masonry
|  |  | 2.1.1. 1200x1000x700mm | 1 | 55 |  | From Generator to Kitchen
1 | 1 |  |  |  |  | 55
|  | 1 | Pcs net number
|  |  |  | 1 | 140 |  | From G.H to Store & Kitchen around
|  |  | 2.1.2. 1000x1000x700mm |  |  | 140 | masonary fence at right side
1 | 9
|  | 9 | Pcs net number | 1 | 180 |  | Ditto above from kitchen to morgue
180
|  |  | 2.1.3. 600x600x500mm | 1 | 150 |  | Ditto above from inclinator to morgue
1 | 9 |  |  |  |  | 150
|  | 9 | Pcs net number | 1 | 100 |  | Ditto above side of fence
100
|  |  | 2.2. Cement pipe of dia. 110mm diameter | 1 | 100 |  | Ditto above from inclinator to Admin
1 | 12 |  | Guard House to Staff Road Crossing |  |  | 100
|  | 12 |  | 1 | 70 |  | Around left side of masonary Pillars
70
1 | 18 |  | Road crossing to Staff | 1 | 162 |  | AROUND FENCE WORK
|  | 18 |  |  |  | 162
|  |  |  | 1 | 265 |  | FOR BLOCK TELE INTRY
1 | 12 |  | Road crossing to Waiting |  |  | 265
12
[6 empty] | 1108 | m net length item 2.3.a
1 | 6 |  | Road crossing to Kitchen
|  | 6 |  |  |  |  | 2.3.b. PVC pipe of dia 110mm diameter
|  |  |  | 1 | 20 |  | for Kitchen Power Cable
1 | 12 |  | Road crossing to Store |  |  | 20
12
|  |  |  | 1 | 130 |  | From G.H to Store
1 | 14 |  | Road crossing to in front of Emergency |  |  | 130
14
|  |  |  | 1 | 240 |  | From Generator to Staff
1 | 27 |  | From main Power to Generator |  |  | 240
27
|  |  |  | 1 | 204 |  | From Generator to Kitchen
1 | 11 |  | for Dry Latrine |  |  | 204
11
|  |  |  | 6 | 21 |  | From Diagno. to Kitchen
9 | 11 |  | Kitchen Block for main Power 9 block |  |  | 126
99
|  |  |  | 3 | 33 |  | From Diagno. to Admin.
|  | 211 | m net length item 2.2 |  |  | 99
|  |  | 2.3.a. PVC pipe of dia 50mm diameter | 2 | 17 |  | From OPD to Admin.
1 | 75 |  | From Guard House to Waiting |  |  | 34
75
|  |  |  | 2 | 18 |  | From Diagno. to Emerg.
1 | 117 |  | From G.H to Staff Compound Light |  |  | 36
117
|  |  |  | 2 | 14 |  | From Waiting to Emerg.
1 | 110 |  | From Staff to OPD Compound Light |  |  | 28
110
[6 empty] | 0 | m net length item 2.3.b
T | D | S | Item No. and Description | T | D | S | Item No. and Description
3. Feeder Cables
3.5. 4x6mm2
1 | 95
|  | 95 | ml net length item 3.5
3.7. 3x4mm2
1 | 715
|  | 715 | ml net length item 3.5
3.. 4x10mm2
1 | 64
|  | 64 | ml net length item 3.5