## Grand summary
Summary of Statement - Final Payment
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Grand summary
No | Block type | Cost
1 | General ward (IPD) | 3288999.9291
2 | OPD | 2200274.4216
3 | Staff Residence+SQ | 979705.3515
4 | OR and Delivery | 3138317.4965
5 | Emergency & Waiting | 1982728.444
6 | Administration | 1414606.5381
7 | Diagnostic service | 1251408.5223
8 | Generator and transformer house | 249100.478
9 | Kitchen | 1701012.2635
10 | Gurad house | 112901.3504
11 | Morgue | 110891.594
12 | Site work | 5254274.5471
| Grand total | 21684220.936
VAT
| Total Including VAT(15%) | 21684220.936

## IPD Sum
Summary of Statement - Faynal Payment
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-IPD
Details of Works executed
Bill No. | Description |  | Sub Total Birr |  | Total Birr
|  |  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  |  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work |  | 576659.7 | 719720.3868 | 576659.7 | 719720.3868
2 | Concrete Work |  | 779929 | 651787.9224 | 779929 | 651787.9224
3 | Masonry work |  | 397600 | 51010.89 | 397600 | 51010.89
| sub total A |  | 1754188.7 | 1422519.1992 | 1754188.7 | 1422519.1992
B. Super Structure
1 | Concrete Work |  | 267667 | 258437.4338 | 267667 | 258437.4338
2 | Block work |  | 297700 | 308625.007 | 297700 | 308625.007
3 | Roofing |  | 282846.4 | 309876.6 | 282846.4 | 309876.6
4 | Carpentary & joinery |  | 166993.75 | 182297.98 | 166993.75 | 182297.98
5 | Metal work |  | 268423.4 | 89319.75 | 143800 | 89319.75
6 | Finishing |  | 844620 | 517404.9 | 844620 | 517404.9
7 | Painting |  | 55160 | 44824.7091 | 55160 | 44824.7091
8 | Glazing |  | 14745 | 0 | 14745 | 0
9 | Sanitory Installation |  | 109510 | 48724.95 | 109510 | 48724.95
10 | Electrical Installation |  | 138842.68 | 106969.4 | 138842.68 | 106969.4
| sub total B |  | 2446508.23 | 1866480.7299 | 2321884.83 | 1866480.7299
| Total A+B |  | 4200696.93 | 3288999.9291 | 4076073.53 | 3288999.9291
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  | Suppervisor :- ______________ |  |  | Consultant:- _____________

## IPD Meas.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [6 empty] | Block : IPD
CLIENT:-ANRS Health Bureau
Item | Description | Unit | QTY | Contract |  |  | Executed
|  |  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 |  | 826 | 8 | 6608 | 827.22 | 6617.76
1.2 | Bulk excavation in ordinary | m3 | 708 | 1072 | 645.83 | 692329.76 | 542.1667 | 350147.536
1.3 | Ditto but exceeding 1.5m less than 2m | m3 |  | 357.3333 | 669.75 | 239324 | 223.2 | 149488.2
1.4 | Selected borrowed fill brought from out side | m3 | 708 | 1429.3333 | 150 | 214400 | 114.354 | 17153.1
1.5 | Cart away surplus excavated material to an | m3 | 708 | 1677.1333 | 70 | 117399.3333 | 1013.5327 | 70947.2908
1.6 | 25cm thick basaltic or equivalent stone hard core | m2 | 557 | 691 | 200 | 138200 | 626.8325 | 125366.5
Total to summary ………Birr | [5 empty] | 1408261.0933 |  | 719720.3868
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 188 | 188 | 150 | 28200 | 129.58 | 19437
2.2 | Ditto but under footing pad | m2 |  | 32 | 150 | 4800 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 557 | 691 | 400 | 276400 | 665.59 | 266236
2.4 | In grade beam&Steps | m3 | 38 | 38 | 3200 | 121600 | 34.09 | 109088
2.5 | In footing pad | m3 |  | 6.5 | 3200 | 20800 |  | 0
2.6 | In footing coloumn | m3 |  | 5.3 | 3200 | 16960 |  | 0
Provide cut and fix in position swan zigzag woodform work
2.7 | Grade beam | m2 | 302 | 302 | 120 | 36240 | 259.384 | 31126.08
2.1 | Steps | m2 | 5 | 4.5 | 120 | 540 |  | 0
| Reinforcement steel bar according to St.drawing |  |  |  | 150 | 0 |  | 0
price includes cutting, bending, placing in
2.11 | Dia 14 mm deformed bar | kg | 2734 | 2734 | 36 | 98424 | 2630.5884 | 94701.1824
2.12 | Dia. 12mm deformed bar | kg |  | 610 | 36 | 21960 |  | 0
2.13 | Dia 8 mm deformed bar | kg | 3430 | 3430 | 36 | 123480 | 3200.685 | 115224.66
2.14 | 10/2 cm chip wood expansion joint between | m | 485 | 485 | 30 | 14550 | 532.5 | 15975
Total to summary ………Birr | [5 empty] | 763954 |  | 651787.9224
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 188 | 274 | 1250 | 342500 | 36.1766 | 45220.75
3.2 | Ditto but above natural ground level externally | m3 | 38 | 38 | 1450 | 55100 | 3.9932 | 5790.14
Total to summary ………Birr | [5 empty] | 397600 |  | 51010.89
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 5 | 4.5 | 3200 | 14400 | 5.2416 | 16773.12
1.2 | In beams& steps | m3 | 23 | 23 | 3200 | 73600 | 19.974 | 63916.8
1.3 | Lintel | m3 |  | 1.3 | 3200 | 4160 | 1.346 | 4307.2
| Provide cut and fix in position swan zigzag wood form work |  |  |  |  | 0 |  | 0
1.4 | Elevation column | m2 | 108 | 108 | 130 | 14040 | 104.832 | 13628.16
1.5 | Beam | m2 | 302 | 302 | 130 | 39260 | 263.12 | 34205.6
1.6 | Lintel | m2 |  | 10.7 | 130 | 1391 | 23.67 | 3077.1
Reinforcement steel bar according to St.drawing
1.7 | Dia 14mm deformed bar | kg | 0 | cp | 36 |  |  | 0
1.8 | Dia 12mm deformed bar | kg | 2577 | 2577 | 36 | 92772 | 2633.7014 | 94813.2518
1.9 | Dia 8 mm deformed bar | kg | 779 | 779 | 36 | 28044 | 769.8945 | 27716.202
Total to summary ………Birr | [5 empty] | 239623 |  | 258437.4338
2. BLOCK WORK
Concrete block wall class "C" bedded in cement
2.1 | 20cm thick | m2 | 661 | 494 | 350 | 172900 | 594.5285 | 208084.975
2.2 | 15cm thick | m2 |  | 390 | 320 | 124800 | 314.1876 | 100540.032
Total to summary ………Birr | [5 empty] | 297700 |  | 308625.007
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 696.74 | 696.74 | 360 | 250826.4 | 790.03 | 284410.8
3.2 | G-28 ribbed sheet ceiling under eave nailed to Zigba purlins. | m2 | 66 | 66 | 160 | 10560 | 58.54 | 9366.4
3.3 | Flashing in flat metal sheet fixed as shown | m | 110 | 110 | 110 | 12100 | 59.74 | 6571.4
3.4 | Supply and fix G-28 flat metal sheet gutter | m | 78 | 78 | 120 | 9360 | 79.4 | 9528
Total to summary ………Birr | [5 empty] | 282846.4 |  | 309876.6
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12cm | m | 927.45 | 927.45 | 23 | 21331.35 | 1216.8 | 27986.4
4.2 | Vertical & Diagonal memberes size-diameter 8-10cm | m | 534.6 | 534.6 | 16 | 8553.6 | 1735.2 | 27763.2
4.3 | Purlin zigba size 5/7cm | m | 714.6 | 714.6 | 33 | 23581.8 | 952.8 | 31442.4
4.4 | Zigba wooden fascia board price includes three coats | m | 79.4 | 79.4 | 71 | 5637.4 | 119.48 | 8483.08
Doors
4.5 | Type D5 size - 100/273cm | Nº | 2 | 2 | 5187 | 10374 | 4 | 20748
4.6 | Type D7 size-80/273cm | Nº | 7 | 7 | 1800 | 12600 |  | 0
4.7 | Type D8 size-70/273cm | Nº | 6 | 6 | 3630.9 | 21785.4 | 6 | 21785.4
4.8 | Type D9 size-90/273cm | Nº | 10 | 10 | 4668.3 | 46683 | 8 | 37346.4
4.9 | Type D11 ,Size 130/273 |  |  |  | 6743.1 |  | 1 | 6743.1
Total to summary ………Birr | [5 empty] | 150546.55 |  | 182297.98
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 17 | 17 | 3892.5 | 66172.5 | 12 | 46710
5.2 | Type W4 size-130/173cm | Nº | 1 | 1 | 3373.5 | 3373.5 | 5 | 16867.5
5.3 | Type W5 size-75/173cm | Nº | 1 | 1 | 1946.25 | 1946.25 | 1 | 1946.25
5.4 | Type W6 size-280/60cm | Nº | 2 | 2 | 2520 | 5040 |  | 0
5.5 | Type W15 size-130/60cm | Nº | 2 | 2 | 1170 | 2340 | 6 | 7020
5.6 | Type W18 size-600/60cm | Nº | 1 | 1 | 5400 | 5400 | 1 | 5400
* | Type W size-900/60cm | Nº |  |  | 8100 | 0 | 1 | 8100
Doors
5.16 | Type D4 size - 120/273cm | Nº | 3 | 3 | 4914 | 14742 |  | 0
5.17 | Type D6 size - 90/273cm | Nº | 4 | 4 | 3685.5 | 14742 |  | 0
5.18 | Type D10 size - 80/273cm | Nº | 3 | 3 | 3276 | 9828 | 1 | 3276
Total to summary ………Birr | [5 empty] | 123584.25 |  | 89319.75
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 249 | 140 | 90 | 12600 | 260.511 | 23445.99
6.2 | Apply three coats of plastering to internal walls& | m2 | 1164 | 150 | 90 | 13500 | 1502.5857 | 135232.713
6.3 | Chip wood ceiling nailed on & including | m2 | 557 | 310 | 180 | 55800 | 638.227 | 114880.86
6.4 | Approved type 6mm thick glazed ceramic wall tile | m2 | 192 | 370 | 270 | 99900 | 39.03 | 10538.1
6.5 | Approved type 9mm thick non slippery ceramic tile floor | m2 | 557 | 300 | 280 | 84000 | 624.367 | 174822.76
6.6 | Approved type Ceramic tile skirting | m | 485 | 100 | 100 | 10000 | 323.91 | 23445.99
6.7 | Approved type Terrazo window cill .size 27/3cm | m | 0 | 150 | 80 | 12000 | 42.45 | 3396
6.8 | 30/30/3mm angle iron corner protection | m | 42 | 42 | 70 | 2940
6.9 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 |  | 550 | 380 | 209000 | 70.08 | 26630.4
6.1 | Supply and lay concrete pipes of half diameter 30cm | ml |  | 100 | 150 | 15000 | 101.15 | 15172.5
6.11 | Construction of 10x40 cm curb stone | ml |  |  | 210 | 0 | 44.5 | 9345
Total to summary ………Birr | [5 empty] | 514740 |  | 517404.9
7. PAINTING
7.1 | Internal plastered surfaceand external beams& | m2 | 1164 | 1164 | 18.6667 | 21728 | 1502.5857 | 28048.2664
7.2 | Chip wood ceiling surface | m2 | 557 | 557 | 18.6667 | 10397.3333 | 638.227 | 11913.5707
7.3 | External rendered surface | m2 | 249 | 249 | 18.6667 | 4648 | 260.511 | 4862.872
Total to summary ………Birr | [5 empty] | 36773.3333 |  | 44824.7091
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R water pipes for water
shall be coated by HDPE layer & PN=20bar
ALL INTERNAL DIAMETER
| 15mm diameter ;internal | LM | 15 | 15 | 70 | 1050 |  | 0
| 20mm diameter ;internal | LM | 25 | 25 | 80 | 2000 | 119.08 | 9526.4
| 25mm diameter ;internal | LM | 100 | 100 | 95 | 9500 | 32.03 | 3042.85
| 32mm diameter ;internal | LM | 20 | 20 | 125 | 2500 | 32.03 | 4003.75
9.2 | Supply and fix chrome angle valves complete
| 15mm diameter | No | 72 | 72 | 105 | 7560 |  | 0
9.3 | Supply and fix bronze gate valves complete with unions,
All valves shall be compatible to PP-R pipes
| 15mm diameter | No | 37 | 37 | 95 | 3515 |  | 0
| 20mm diameter | No | 8 | 8 | 155 | 1240 | 24 | 3720
| 25mm diameter | No | 0 | 0 | 150 | 0 |  | 0
9.4 | Ditto item 3,but chrome plated 15mm water tap | No | 0
9.5 | Supply and install waste water pipes made of rigid
| 50mm diameter of min. wall thickness=2mm | LM | 15 | 15 | 65 | 975 | 49.32 | 3205.8
| 75mm diameter of min. wall thickness=3mm | LM | 21 | 21 | 95 | 1995 | 48.67 | 4623.65
| 100 mm diameter of min. wall thickness=3.2mm | LM | 100 | 100 | 125 | 12500 | 50.42 | 6302.5
9.7 | Supply and fix low flush white vitreous china W C | No | 11 | 11 | 1300 | 14300 | 11 | 14300
Total to summary ………Birr | [5 empty] | 57135 |  | 48724.95
10. ELECTRICAL INSTALLATION
1.02 | Flush mounted Sub distribution board SDB-WARD | PCs | 1 | 1 | 7000 | 7000 |  | 0
2 | Light points | [6 empty] | 0
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 83 | 83 | 200 | 16600 | 92 | 18400
3 | Switches | [6 empty] | 0
3.01 | single(774001+774041) | PCs | 30 | 30 | 81.25 | 2437.5 | 51 | 4143.75
3.02 | Duoble(774005+774042) | " | 9 | 9 | 131.25 | 1181.25 | 16 | 2100
3.03 | Two-Way(774006+774041) | " | 32 | 32 | 80 | 2560 | 4 | 320
3.04 | Intermediate(774007+774041) | " | 10 | 10 | 120 | 1200 | 10 | 1200
4 | Socket outlet points | [6 empty] | 0
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 54 | 54 | 200 | 10800 | 54 | 10800
4.02 | Ditto as 4.01 but for water heater points | PCs | 12 | 12 | 785 | 9420 | 12 | 9420
5 | Socket outlets | [6 empty] | 0
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 54 | 54 | 90 | 4860 | 46 | 4140
5.03 | weather proof socket Legrand Suno 774022+774041 | PCs | 12 | 12 | 281.25 | 3375 |  | 0
6 | Telephone/Data points | [6 empty] | 0
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 12 | 12 | 1500 | 18000 | 12 | 18000
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 12 | 12 | 1200 | 14400 |  | 0
7 | Type of Light Fitting With lamp |  |  |  |  | 0 |  | 0
7.01 | PHILIPS TMS 012/236 IMKwith 2xTLD 36W | PCs | 16 | 16 | 1500 | 24000 | 6 | 9000
7.02 | PHILIPS TMS 012/136 IMKwith 1xTLD 36W | PCs | 8 | 8 | 1200 | 9600 |  | 0
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 23 | 23 | 220 | 5060 |  | 0
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 12 | 12 | 220 | 2640 |  | 0
7.05 | MASSIVE 3202/02/67/1XE27/75W | PCs | 8 | 8 | 1375 | 11000 | 20 | 27500
8 | TV points |  |  |  |  | 0 |  | 0
8.01 | TV points fed through RG6 Coaxial 75ohm TV | PCs | 5 | 5 | 266.25 | 1331.25 | 5 | 1331.25
8.02 | Flush mounted TV outlets type Legrand Suno | PCs | 5 | 5 | 200 | 1000 |  | 0
10 | Cable way and Manhole |  |  |  |  | 0 |  | 0
10.03 | Rigid pvc pipe dia. 50mm to telephone |  |  | 12 | 60 | 720 | 10.24 | 614.4
Total to summary ………Birr | [5 empty] | 147185 |  | 106969.4

## IPD Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - IPD Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE | 1 | 4.85 |  | B/n axis X/03 & X/04 on axis Y/08 & Y/07
|  |  | 1) EXCAVATION & EARTH WORK |  | 7.4
|  |  | 1.1 Clear off site to remove top soil |  | 0.8 | 28.712
L=38.5+3=41.50
1 | 40.55 |  | W=18.55+3=21.55 | 1 | 4.85 |  | B/n axis Y/07 & Y/08 on axis X/01 & X/08
| 20.4 | 827.22 |  |  | 2.7
[5 empty] | 0.55 | 7.2023
|  | 827.22 | m2 Total to item 1.1
|  |  |  | 1 | 6.05 |  | B/n axis X/01 & X/02 on axis Y/03 & Y/04
|  |  | 1.2 Bulk Excavation in ordinary soil |  | 6.1
|  |  | Hard Rock |  | 0.65 | 23.9882
1 | 6.2 |  | B/n axis Y/01 & Y/02 on axis X/04
| 2.2 |  |  | 1 | 6.2 |  | B/n axis X/03 & X/04 on axis Y/01 & Y/02
| 0.8 | 10.912 |  |  | 7.4
[5 empty] | 0.8 | 36.704
1 | 2.65 |  | B/n axis Y/02 & Y/03 on axis X/04
| 2.2 |  |  | 1 | 6.2
| 0.7 | 4.081 |  |  | 2.7
[5 empty] | 0.8 | 13.392
1 | 6.1 |  | B/n axis Y/04 & Y/03 on axis X/04
| 2.2 |  |  | 1 | 2.65
| 0.6 | 8.052 |  |  | 2.7
[5 empty] | 0.8 | 5.724
1 | 6.2 |  | B/n axis Y/04 & Y/05 on axis X/04
| 2.2 |  |  | 1 | 6.2
| 0.8 | 10.912 |  |  | 6.05
[5 empty] | 0.8 | 30.008
1 | 6.1 |  | B/n axis Y/06 & Y/05 on axis X/04
| 2.2 |  |  | 1 | 6.1
| 0.6 | 8.052 |  |  | 6.05
[5 empty] | 0.8 | 29.524
1 | 6.2 |  | B/n axis Y/06 & Y/07 on axis X/04
| 2.2 |  |  | 1 | 6.2
| 0.85 | 11.594 |  |  | 2.7
[5 empty] | 0.8 | 13.392
1 | 4.85 |  | B/n axis Y/08 & Y/07 on axis X/04
| 2.2 |  |  | 1 | 6.1
| 0.9 | 9.603 |  |  | 2.7
[5 empty] | 0.8 | 13.176
1 | 2.85 |  | B/n axis X/03 & X/04 on axis Y/03
| 7.4 |  |  | 1 | 6.2
| 0.7 | 14.763 |  |  | 2.7
[5 empty] | 0.8 | 13.392
1 | 6.1 |  | B/n axis X/03 & X/04 on axis Y/03 & Y/02
| 7.4 |  |  | 1 | 6.2
| 0.8 | 36.112 |  |  | 6.05
[5 empty] | 0.8 | 30.008
1 | 6.2 |  | B/n axis X/03 & X/04 on axis Y/03 & Y/02
| 7.4 |  |  | 1 | 2.65
| 0.65 | 29.822 |  |  | 6.05
[5 empty] | 0.85 | 13.6276
1 | 6.1 |  | B/n axis X/03 & X/04 on axis Y/03 & Y/02
| 2.7 |  |  | 1 | 6.2
| 0.96 | 15.8112 |  |  | 6.05
[5 empty] | 0.8 | 30.008
1 | 6.1 |  | B/n axis X/03 & X/04 on axis Y/03 & Y/02
| 7.4 |  |  | 1 | 4.85
| 0.72 | 32.5008 |  |  | 6.05
[5 empty] | 0.8 | 23.474
1 | 6.2 |  | B/n axis X/03 & X/04 on axis Y/06 & Y/07
| 7.4 |  |  |  |  | 542.1667 | m3 net volume to item 1.2
| 0.82 | 37.6216
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1.3 Ditto to Item 1.2 but exceeding 1.5 |  |  |  | C-bulk fill and compaction
|  |  | and less than 2m | 1 | 37.75 |  | L=39.05-0.5-0.8=37.75
5 | 39.05 |  | along x-axis |  | 17.6 |  | W=18.9-0.5-0.8=17.6
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=39.05 d=0. |  | 0 | 0
| 0.8 | 140.58
DEDUCTION
8 | 15.3 |  | along y-axis | 3 | 39.5 |  | along x-axis
| 0.9 |  | L=18.9-(4*.9)=15.3 |  | 0.4 |  | L=39.05 W=0.4m
| 0.75 | 82.62 | W=0.4+0.25+0.25=0.90, d= |  | 0 | 0
|  | 223.2 | m3 Total to item 1.3 | 6 | 16.8 |  | along y-axis
[5 empty] | 0.4 |  | L=18.9-0.5-0.8-(2*0.4)=16.8
|  |  | 1.4 Selected Borrowed Fill |  | 0 | 0
|  |  | A- fill under masonary |  |  | 114.354 | m3 Total to item 1.4
5 | 39.05 |  | for axis x01-x05
| 0.9 |  | L=39.05 |  |  |  | 1.5 Cart away excavated material
| 0.4 | 70.29 |  | 1 | 40.55
20.4
8 | 15.3 |  | for axis y01-y08 |  | 0.3 | 248.166 | from item no 1.1
| 0.9 |  | L=15.30 , W=0.9, d=0.3
| 0.4 | 44.064 | 15.3 |  |  | 542.1667 | from item no 1.2
|  |  | B-backfill and compaction in side |  |  | 223.2 | from item no 1.3
masonary along x-axis
8 | 36.55 |  | L=39.05-0.25-0.25-0.8-(3*0.4)=36.55 |  |  | 1013.5327 | m3 Total to item 1.4
| 0.25 |  | W=0.25 ,d=
| 0 | 0 |  | 1 | 38.05 |  | 1.6- 25cm thick hard rock
[5 empty] | 17.9 | 681.095
along y-axis
14 | 15.3 |  | L=18.9-0.25-0.25-0.8-(2*0.25)-(2*.9) |  |  |  | Deduction
| 0.25 |  | 15.3 | 3 | 38.05 |  | along X axis
| 0 | 0 | W=0.25 ,d=. |  | 0.25 | 28.5375
|  |  |  | 6 | 17.15 |  | along Y axis
[5 empty] | 0.25 | 25.725
[6 empty] | 626.8325 | m3 Total to item 1.6
2- CONCRETE WORK
|  |  |  | 5 | 38.55 |  | 2.1- 5cm thick lean concrete
[5 empty] | 0.4 | 77.1
|  |  |  | 8 | 16.4
[5 empty] | 0.4 | 52.48
[6 empty] | 129.58 | m2 Total to item 2.1
|  |  |  | 1 | 38.05 |  | 2.3- 10cm thick RC Slab
[5 empty] | 18.55 | 705.8275
Deduction
|  |  |  | 3 | 38.05 |  | along X axis
[5 empty] | 0.25 | 28.5375
|  |  |  | 6 | 7.8 |  | along Y axis
[5 empty] | 0.25 | 11.7
[6 empty] | 665.59 | m3 Total to item 2.3
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.4 In grade beam |  |  |  | 3.12 masonary work above NGL
5 | 38.5 |  |  | 1 | 27.25 |  | on axis x01
| 0.25 |  |  |  | 0.4 |  | L=6.2+2.65+6.1+6.2+6.1=27.25
| 0.4 | 19.25 |  |  | 0.3 | 3.27 | w=0.4, d=0.3
8 | 18.55 |  |  | 1 | 5.65 |  | on axis y01
| 0.25 |  |  |  | 0.4 |  | L=5.65 W=.4 d=.32
| 0.4 | 14.84 |  |  | 0.32 | 0.7232
[6 empty] | 3.9932 | m3Total to item 3.12
|  | 34.09 | m3 Total to item 2.4
Provide, cut and fix in position
2.7 In grade beam
2 | 38.58
| 0.4 | 30.864
8 | 36.5
| 0.4 | 116.8
2 | 18.55
| 0.4 | 14.84
14 | 17.3
| 0.4 | 96.88
|  | 259.384 | m2 Total to item 2.7
Reinforcement steel bars
2.11)ф14 mm deformed bars
|  | 2630.5884 | kg net wight item 2.11
2.13)ф8 mm deformed bars
|  | 3200.685 | kg net wight item 2.13
2.14) 10/2cm chipwood expansion joint
along x-axis
8 | 36.55 |  | L=39.05-0.25-0.25-0.25-0.25-(.25*6)=36.55
292.4
along y-axis
14 | 17.15 |  | L=18.9-0.25-0.25-0.25-0.25-0.75=17.15
|  | 240.1 | [5 empty] | #REF!
|  | 532.5 | mTotal to item 2.14
3. Masonry Work
3.1 Trychltic stone masonry
5 | 38.55 |  | axis x01,x02,x03,x05
| 0.4 |  | L=39.05-0.5=38.55
| 0.31 | 23.901
8 | 16.4 |  | axis y01,y02,y03……y08
| 0.4 |  | L=18.9-0.5-(5*0.4)=16.4 |  |  |  |  | #REF!
| 0.31 | 16.2688
|  | 36.1766 | m3Total to item 3.1

## IPD Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - IPD SUPER STRUCTURE
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B. SUPER STRUCTURE |  |  |  | Form Work
|  |  | 1. CONCRETE WORK |  |  |  | 1.4)Elevation column
48 | 0.2 |  | 1.1. In elevation column | 48 | 0.8
| 0.2 |  |  |  | 2.73
| 2.73 |  |  |  |  | 104.832 | m2 net area item 1.4
|  | 5.2416 | m3 net volume Item 1.1
1.5)Beam
|  |  | 1.2)In beam & step | 2 | 38.5 |  | TTB1=2Pcs
2 | 38.5 |  | TTB1=2Pcs |  | 0.8 | 61.6 | Axis x/01 & x/o4 from (y/01 - y/08)
| 0.3 |  | Axis x/01 & x/o4 from (y/01 - y/08) |  |  |  | Dev.L=0.30*2+0.20=0.80mt
| 0.2 | 4.62
|  |  |  | 3 | 36.9 |  | TTB2=3Pcs
3 | 38.5 |  | TTB2=3Pcs |  | 0.8 | 88.56 | Axis x/02,x/03 & x/04 from ( y/01 - y/08)
| 0.3 |  | Axis x/02,x/03 & x/04 |  |  |  | Dev.L=0.30*2+0.20=0.80mt
| 0.2 | 6.93 | from ( y/01 - y/08)
|  |  |  | 2 | 18.55 |  | TTB3=2Pcs
2 | 17.55 |  | TTB3=2Pcs |  | 0.8 | 29.68 | Axis y/01 & y/08 from ( x/01 - x/04)
| 0.3 |  | Axis y/01 & y/08 from ( x/01 - x/04) |  |  |  | Dev.L=0.30*2+0.20=0.80mt
| 0.2 | 2.106
|  |  |  | 6 | 17.35 |  | TTB4=6Pcs
6 | 17.55 |  | TTB4=6Pcs |  | 0.8 | 83.28 | Axis y/02 - y/07 from ( x/01 - x/04)
| 0.3 |  | Axis y/02-y/07 from (x/01 - x/04) |  |  |  | Dev.L=0.30*2+0.20=0.80mt
| 0.2 | 6.318
[6 empty] | 263.12 | m2 net area item 1.5
|  | 19.974 | m3 net volume item 1.2
1.6)Lintel
|  |  | 1.3)Lintel | 2 | 1.4 |  | D5(2Pcs)
2 | 1.4 |  | D5(2Pcs) |  | 0.6 | 1.68 | L=0.2X2+0.2=0.60mt
0.2
| 0.2 | 0.112 |  | 10 | 1.3 |  | D8(1Pcs)
[5 empty] | 0.55 | 7.15 | L=0.2X2+0.15=0.55mt
10 | 1.1 |  | D8(2Pcs)
| 0.15 |  |  | 5 | 1.2 |  | D7(5Pcs)
| 0.2 | 0.33 |  |  | 0.55 | 3.3 | L=0.2X2+0.15=0.55mt
5 | 1.2 |  | D7(5Pcs) | 5 | 1.3 |  | D9(5PCS)
| 0.15 |  |  |  | 0.6 | 3.9 | L=0.2X2+0.2=0.60mt
| 0.2 | 0.18
|  |  |  | 4 | 1.3 |  | W7(4PCS)
5 | 1.3 |  | D9(5PCS) |  | 0.55 | 2.86 | L=0.2X2+0.15=0.55mt
0.2
| 0.2 | 0.26 |  | 1 | 1.6 |  | W20(1PC)
[5 empty] | 0.55 | 0.88 | L=0.2X2+0.15=0.55mt
4 | 1.3 |  | W7(4PCS)
| 0.15 |  |  | 5 | 1.3 |  | D10(5Pcs)
| 0.2 | 0.156 |  |  | 0.6 | 3.9
1 | 1.6 |  | W20(1PC) |  |  | 23.67 | m2 net area item 1.6
0.15
| 0.2 | 0.048 |  |  |  |  | 1.8)ф12 mm deformed bars
[6 empty] | 2633.7014 | kg net wight item 1.7
5 | 1.3 |  | D10(5Pcs)
0.2
| 0.2 | 0.26
|  | 1.346 | m3 net volume item 1.3
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1.9)ф8mm deformed bars | 1 | 0.9 |  | D9(1Pc)
|  | 769.8945 | kg net wight item 1.8 |  | 2.73 | -2.457
|  |  | 2.1)20cm thick HCB wall | 1 | 3
1 | 36.9 |  | Axis X/01 from (Y/01 - Y/08) |  | 2.73 | 8.19
| 2.73 | 100.737
|  |  | ddt | 1 | 36.9 |  | Axis X/04 from (Y/01 - Y/08)
5 | 1.5 |  | W2(5Pcs) |  | 2.73 | 100.737
| 1.73 | -12.975
|  |  |  | 3 | 3.5 |  | WD3(3Pcs)
3 | 1.3 |  | W4 (3Pcs) |  | 2.73 | -28.665
| 1.73 | -6.747
|  |  |  | 2 | 3.4 |  | WD4(2Pcs)
1 | 0.75 |  | W5 (1Pcs) |  | 2.73 | -18.564
| 1.73 | -1.2975
|  |  |  | 3 | 1.5 |  | W2(3Pcs)
1 | 0.9 |  | W7(1Pc) |  | 1.73 | -7.785
| 0.6 | -0.54
|  |  |  | 5 | 2.5 |  | Axis X/05 from (Y/01 - Y/08)
2 | 1.3 |  | W15 (2Pcs) |  | 2.73 | 34.125 | Toilet
| 0.6 | -1.56
|  |  |  | 5 | 1.3 |  | W15(5Pcs)
1 | 6 |  | W18 (1Pc) |  | 0.6 | -3.9
| 0.6 | -3.6
|  |  |  | 1 | 17.55 |  | Axis Y/01 from (X/01 - X/05)
1 | 1.2 |  | W20 (1Pcs) |  | 2.73 | 47.9115
| 1.73 | -2.076
|  |  |  | 1 | 2.5 |  | Opening
1 | 2.3 |  | Axis X/01' from (Y/01 - Y/01') |  | 2.73 | -6.825
| 2.73 | 6.279
|  |  |  | 1 | 1.5 |  | W2(1Pc)
1 | 30.95 |  | Axis X/02 from (Y/02' - Y/02) |  | 1.73 | -2.595
| 2.73 | 84.4935
|  |  |  | 7 | 2 |  | Toilet area b/n X04 & X/05
4 | 0.8 |  | D7(4Pcs) |  | 3.06 | 42.84
| 2.73 | -8.736
|  |  |  | 5 | 0.8 |  | D10(5Pcs)
3 | 0.9 |  | D9(3Pcs) |  | 2.73 | -10.92
| 2.73 | -7.371 |  |  |  |  | Axis Y/01', Y/02,Y/03&Y/03'
|  |  |  | 4 | 5.85 |  | from (X/01 - X/02)
1 | 1.3 |  |  |  | 3.06 | 71.604 | 260.511 | 797.1637
| 2.73 | -3.549 | D11(1Ps) |  |  |  | 1502.5857
|  |  |  | 2 | 0.9 |  | 638.227
1 | 1.85 |  |  |  | 2.73 | -4.914 | 39.03
| 2.73 | -5.0505 | Opening |  |  |  | 624.367
|  |  | Axis X/03 from (Y/01 - Y/08) | 1 | 5.85 |  | 323.91
3 | 4.7 |  | WD1(3Pcs) |  | 2.73 | 15.9705 | 42.45
| 1 | 14.1
|  |  |  | 2 | 1 |  | 70.08
2 | 4.7 |  | WD2(2Pcs) |  | 2.73 | -5.46 | 101.15
| 1 | 9.4 |  |  |  |  | 44.5
|  |  |  | 1 | 7.2 | 77.2005 | Axis Y/07 from (X/03 - X/04) | 797.1637
1 | 2.5 |  | Nurse station |  | 2.73 | 19.656
| 2.73 | 6.825
T | D | S | Item No. and Description | T | D | S
1 | 17.55 |  | Axis Y/08 from (X/01 - X/05) | 1 | 19.31 |  | D7(3Pcs)
| 2.73 | 47.9115 |  |  | 3.06 | 59.0886
3 | 1.5 |  | W2(3Pcs) | 3 | 0.8 |  | D8(3Pcs)
| 1.73 | -7.785 |  |  | 2.73 | -6.552
|  |  | Gable side |  |  |  | D7(2Pcs)
2 | 18.55 |  | Axis Y/O1&Y/08 from (X/01 - X/05) | 2 | 0.7
| 1.2 | 44.52 |  |  | 2.73 | -3.822
2 | 38.5 |  | Axis X/01 &X/05 from (Y/01 - Y/08) |  |  | 314.1876 | m2 net area item 2.2
| 0.2 | 15.4
119.08
|  | 594.5285 | m2 net area item 2.1 |  |  |  | 32.03
|  |  |  | 1 | 39.7 |  | 32.03
|  |  | 2.2)15cm thick HCB wall |  | 19.9 | 790.03 | L=18.70+0.60x2=19.90mt
5 | 7.2 |  | Axis Y/02 - Y/07 from (X/03 - X/04)
| 2.73 | 98.28 |  |  |  | 790.03 | m2 net area item 3.1
1 | 7.2 |  | Axis Y/07' from (X/03 - X/04)
| 3.06 | 22.032 |  | 4 | 10.02 |  | 24
[5 empty] | 0.5 | 20.04 | 49.32
2 | 1 |  | D5(2Pcs)
| 2.73 | -5.46 |  | 2 | 38.5
[5 empty] | 0.5 | 38.5
1 | 5.85 |  | Axis Y/01' from (X/01 - X/02)
| 3.06 | 17.901 |  |  |  | 58.54 | m2 net area item 3.2
2 | 0.9 |  | D9(2Pcs) |  |  |  | 3.3)Flashing in metal sheet
| 2.73 | -4.914 |  | 1 | 39.7 |  | Dev. Length 33cm
|  |  | Axis Y/04',04'' ,Y/05',05'',05''' , |  |  | 39.7 | Ridge cover
7 | 5.85 |  | y/06',06'' from (X/01- X/02)
| 3.06 | 125.307 |  | 4 | 10.02 | 0
[5 empty] | 0.5 | 20.04 | flashing
2 | 0.8 |  | D7(2Pcs)
| 2.73 | -4.368 |  |  |  | 59.74 | ml net length item 3.3
4 | 0.9 |  | W7(4Pcs) |  |  |  | 3.4)Supply & fix G-28 gutter dev.
| 0.6 | -2.16 |  | 2 | 39.7 |  | length=50cm
1 | 2.5 |  | Axis b/n X/03 & X/04 from (Y/01-03) |  |  | 79.4 | ml net length item 3.4
| 3.06 | 7.65
4)CARPENTRY
1 | 0.9 |  | D9(1Pc) |  |  |  | 4.1)Uper & lower chord size 10-12cm
| 2.73 | -2.457 |  | 30 | 21.22 |  | upper=10.61X2=21.22mt
[6 empty] | 636.6 | lower=9.67x2=19.34mt
1 | 3 |  | Axis b/n X/03 & X/04 from (Y/07'-08) | 30 | 19.34
| 3.06 | 9.18 |  |  |  | 580.2
1 | 1.7 |  | Axis b/n X/01 & X/02 from (Y/01''-02) |  |  | 1216.8 | ml net length item 4.1
| 3.06 | 5.202
4.2)Vertical & Diagonal member
1 | 1.2 |  | Axis b/n X/01 & X/02 from (Y/04'-08) | 30 | 23.7 |  | V=23.70mt
| 0.6 | -0.72 |  |  |  | 711 | H=29.17mt
|  |  |  | 30 | 34.14
1024.2
[6 empty] | 1735.2 | ml net length item 4.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4.3) Purlin zigba 5/7cm |  |  |  | DOORS
|  |  | No .pur =10.02/0.9+1=12.13=12 |  |  |  | 5.18)Type D10 ,Size 80/273
24 | 39.7 |  | L=38.50+1.00=38.50mt | 1 | 1
|  | 952.8 | ml net length item 4.3 |  |  | 1 | Pcs net number item 5.17
|  |  | 4.4) Zigba wooden fascia board |  |  |  | 6)FINISHING WORK
4 | 10.02 | [5 empty] | 6.1)Apply two coats of plastering &
|  | 40.08 |  | 2 | 17.55 |  | one coat rendering
[5 empty] | 2.73 | 95.823 | Axis Y/01 & Y/08 from (X/01- 05)
2 | 39.7 |  |  | 4 | 9.28 |  | Gable side
|  | 79.4 |  |  | 1.2 | 44.544 | h=2.2+0.2/2=1.2mt
|  |  |  | 1 | 2.5 |  | Opening
|  | 119.48 | ml net length item 4.4 |  | 2.73 | -6.825
|  |  |  | 4 | 1.5 |  | W2(4Pcs)
|  |  | 4.5) Type D5 ,Size 100/273 |  | 1.63 | -9.78
1 | 4
|  | 4 | Pcs net number item 4.5 | 1 | 36.9 |  | Axis X/01 from (Y/01- 08)
[5 empty] | 2.73 | 100.737
|  |  | 4.7) Type D8 ,Size 70/273 | 5 | 1.5 |  | W2(5Pcs)
1 | 6 |  |  |  | 1.63 | -12.225
|  | 6 | Pcs net number item 4.7 | 3 | 1.3 |  | W4(3Pcs)
[5 empty] | 1.63 | -6.357
4.8) Type D9 ,Size 90/273
1 | 8 |  |  | 1 | 0.75 |  | W5(1Pc)
|  | 8 | Pcs net number item 4.8 |  | 0.6 | -0.45
|  |  |  | 1 | 0.9 |  | W7(1Pc)
|  |  | 4.9) Type D11 ,Size 130/273 |  | 0.6 | -0.54
1 | 1 |  |  | 2 | 1.3 |  | W15(2Pcs)
|  | 1 | Pcs net number item 4.9 |  | 0.6 | -1.56
|  |  |  | 1 | 6 |  | W18(1Pc)
|  |  | 5) METAL WORK |  | 0.6 | -3.6
|  |  | 5.1) Type W2 ,Size 150/173 | 1 | 1.2 |  | W20(1Pc)
1 | 12 |  |  |  | 1.63 | -1.956
|  | 12 | Pcs net number item 5.1
|  |  |  | 1 | 36.9 |  | Axis X/04 from (Y/01- 08)
|  |  | 5.2)Type W4 ,Size 130/173 |  | 2.73 | 100.737
1 | 5 |  |  | 5 | 1.3 |  | W15(5Pcs)
|  | 5 | Pcs net number item 5.2 |  | 0.6 | -3.9
|  |  |  | 3 | 3.5 |  | WD3(3Pcs)
|  |  | 5.3)Type W5 ,Size 75/173 |  | 2.73 | -28.665
1 | 1
|  | 1 | Pcs net number item 5.3 | 2 | 3.4 |  | WD4(2Pcs)
[5 empty] | 2.73 | -18.564
|  |  | 5.5)Type W15 ,Size 130/60 | 3 | 1.5 |  | W2(3Pcs)
1 | 6 |  |  |  | 1.63 | -7.335
|  | 6 | Pcs net number item 5.5
|  |  |  | 5 | 0.9 |  | D6(5Pcs)
|  |  | 5.6)Type W18 ,Size 600/60 |  | 2.73 | -12.285
1 | 1 |  |  | 6 | 2.4 |  | Axis B/n X/04 & X/05
|  | 1 | Pcs net number item 5.6 |  | 3.03 | 43.632
|  |  |  | 5 | 0.8 |  | D10(5Pcs)
|  |  | 5.7)Type W ,Size 90/60 |  | 2.73 | -10.92
1 | 1
|  | 1 | Pcs net number item 5.6 |  |  | 260.511 | m2 net area item 6.1
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 9.2 |  | 6.2)Plastering to int. wall, ext.beam & colu. | 1 | 7.2 |  | Clean utility room
| 3.06 | 28.152 | Linen/pajama store |  | 3.06 | 22.032 | L=2.30x2+1.30x2=7.70mt
L=2.30x2+2.3x2=9.20mt
1 | 0.9 |  |  | 1 | 0.8 |  | D7(1Pc)
| 2.73 | -2.457 | D9(1Pc) |  | 2.73 | -2.184
1 | 1.3 |  | W4(1Pc) | 1 | 13.4 |  | Duity
| 1.73 | -2.249 |  |  | 3.06 | 41.004 | L=2.30x2+4.4x2=13.40mt
1 | 9.4 |  | REC. | 1 | 0.8 |  | D7(1Pc)
| 3.06 | 28.764 | L=3.55x2+2.3=9.40mt |  | 2.73 | -2.184
1 | 0.9 |  | D9(1Pc) | 1 | 1.5 |  | W2(1Pc)
| 2.73 | -2.457 |  |  | 1.73 | -2.595
1 | 1.5 |  | W2(1Pc) | 1 | 9.46 |  | Toilet
| 1.73 | -2.595 |  |  | 3.06 | 28.9476 | L=1.33x2+3.40x2=9.46mt
1 | 13.6 |  | Corridor | 1 | 7.26
| 3.06 | 41.616 | L=6.05x2+1.50=13.60mt |  | 1.13 | 8.2038 | "
L=1.33x2+2.30x2=7.26mt
4 | 0.9 |  | D9(4Pcs) | 1 | 0.9 |  | D9(1Pc)
| 2.73 | -9.828 |  |  | 2.73 | -2.457
2 | 9.1 |  | Changing room | 2 | 0.7 |  | D8(2Pcs)
| 3.06 | 55.692 | L=1.70x2+2.85x2=9.10mt |  | 0.83 | -1.162
2 | 0.9 |  | D9(1Pc) | 2 | 0.8 |  | D7(2Pc)
| 2.73 | -4.914 |  |  | 2.73 | -4.368
2 | 1.2 |  | W20(2Pc) | 1 | 0.9 |  | W7(1Pc)
| 0.6 | -1.44 |  |  | 0.6 | -0.54
1 | 16.3 |  | Pharmacy | 1 | 6.86 |  | Sluice
| 3.06 | 49.878 | L=2.30x2+5.85x2=16.30mt |  | 3.06 | 20.9916 | L=2.13x2+1.30x2=6.86mt
1 | 0.9 |  | D9(1Pc) | 1 | 13.06 |  | duity room
| 2.73 | -2.457 |  |  | 3.06 | 39.9636 | L=2.13x2+4.40x2=13.06mt
1 | 1.3 |  | W4(1Pc) | 2 | 0.8 |  | D7(2Pc)
| 1.73 | -2.249 |  |  | 2.73 | -4.368
1 | 21.2 |  | Procedure | 1 | 1.5 |  | W2(1Pc)
| 3.06 | 64.872 | L=4.75x2+5.85x2=21.20mt |  | 1.73 | -2.595
1 | 1.3 |  | D11(1Pc) | 1 | 10.15 |  | Nurse station dupty room
| 2.73 | -3.549 |  |  | 3.06 | 31.059 | L=2.15+4x2=10.15mt
1 | 1.3 |  | W4(1Pc) | 1 | 8.26 |  | Store
| 1.73 | -2.249 |  |  | 3.06 | 25.2756 | L=2.15x2+1.98x2=8.26mt
1 | 19.6 |  | Doctors Room | 2 | 0.8 |  | D7(2Pc)
| 3.06 | 59.976 | L=3.95x2+5.85x2=19.60mt |  | 2.73 | -4.368
1 | 0.9 |  | D9(1Pc) | 1 | 1.5 |  | W2(1Pc)
| 2.73 | -2.457 |  |  | 1.73 | -2.595
2 | 1.3 |  | W15(2Pcs) | 2 | 0.9 |  | W7(2Pcs)
| 1.73 |  |  |  | 0.6 | -1.08
-4.498
T | D | S | Item No. and Description | T | D | S | Item No. and Description
4 | 2.1 |  | TOILET | 1 | 7.1
| 1.43 | 12.012 |  |  | 1.13 | 8.023 | L=1.85x2+1.70x2=7.10mt
0
4 | 2.1 |  | " | 1 | 0.7 | 0 | D8(1Pc)
| 1.13 | 9.492 |  |  | 0.8 | -0.56
4 | 0.7 |  | D8 | 1 | 1.85 |  | Opening
| 1.13 | -3.164 |  |  | 2.73 | -5.0505
4 | 0.7 |  | D8 | 2 | 1 |  | D5(2Pc)
| 0.83 | -2.324 |  |  | 2.73 | -5.46
4 | 0.9 |  | D9 | 2 | 0.9 |  | W7(2Pcs)
| 0.6 | -2.16 |  |  | 0.6 | -1.08
6 | 1.2 |  | TOILET | 2 | 15 |  | Isolation rooms
| 0.8 | 5.76 |  |  | 3.06 | 91.8 | L=4.65x2+2.85x2=15.00mt
6 | 1.2 |  | " | 2 | 1 |  | D5(2Pc)
| 0.5 | 3.6 |  |  | 2.73 | -5.46
2 | 1.2 |  | " | 3 | 1.5 |  | W2(3Pcs)
| 1.43 | 3.432 |  |  | 1.73 | -7.785
Main corridor
2 | 1.2 |  | " | 1 | 79.1 |  | l=38.3*2+2.5=79.10mt
| 1.13 | 2.712 |  |  | 3.06 | 242.046
TOILET
2 | 11.2 |  | L=1.25x2+4.35x2=11.20mt | 4 | 0.9 |  | D9(4Pcs)
| 1.43 | 32.032 |  |  | 2.73 | -9.828
4 | 0.8 |  | D7(4Pc) | 1 | 1.3 |  | D11(1Pc)
| 1.13 | -3.616 |  |  | 2.73 | -3.549
8 | 0.7 |  | D8(16Pc) | 4 | 0.8 |  | D7(4Pc)
| 1.13 | -6.328 |  |  | 2.73 | -8.736
2 | 7.7 |  | Janitor | 1 | 1.3 |  | W2(1Pc)
| 3.06 | 47.124 | L=2.50x2+1.35x2=7.70mt |  | 1.73 | -2.249
2 | 0.8 |  | D7(2Pcs) | 3 | 4.79 |  | WD1(3Pcs)
| 2.73 | -4.368 |  |  | 1.73 | -24.8601
1 | 0.75 |  | W5(1Pc) | 3 | 1.2 |  | "
| 0.6 | -0.45 |  |  | 2.73 | -9.828
1 | 6 |  | W18(1Pc) | 2 | 4.69 |  | WD2(2Pcs)
| 0.6 | -3.6 |  |  | 1.73 | -16.2274
1 | 12.1 |  | Toilet | 2 | 1.2 |  | "
| 3.06 | 37.026 | L=4.20x2+1.85x2=12.10mt |  | 2.73 | -6.552
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 1.5 |  | OPENING | 2 | 1 |  | D5(2Pc)
| 2.73 | -8.19 |  |  | 2.73 | -5.46
1 | 1.85 |  | OPENING | 2 | 13.04 |  | Assisted bath
| 2.73 | -5.0505 |  |  | 1.13 | 29.4704 | L=3x2+3.52x2=13.04mt
1 | 2.15 |  | " | 2 | 1 |  | D5(2Pc)
| 2.73 | -5.8695 |  |  | 0.83 | -1.66
1 | 2.3 |  | " | 2 | 1.5 |  | W2(2Pcs)
| 2.73 | -6.279 |  |  | 0.83 | -2.49
3 | 26.5 |  | Maternity ward | 5 | 10.8 |  | Toilet
| 3.06 | 243.27 | L=6x2+7.2x2=26.40mt |  | 3.06 | 165.24 | L=2.3x2+2x2+2.20=10.80mt
3 | 4.79 |  | WD1(1Pc) | 5 | 1.3 |  | W15(5Pcs)
| 1.73 | -24.8601 |  |  | 0.6 | -3.9
3 | 1.2 |  | " | 10 | 0.8 |  | D10(5Pcs)
| 2.73 | -9.828 |  |  | 2.73 | -21.84
3 | 4.4 |  | WD3(3Pcs) | 2 | 18.7 |  | Grade beam
| 2.73 | -36.036 |  |  | 0.4 | 14.96
1 | 12.6 |  | Nurse station room | 2 | 38.5 |  | "
| 3.06 | 38.556 | L=2.50x2+3.80x2=12.60mt |  | 0.4 | 30.8
1 | 11.5 |  | Store | 2 | 19 |  | Top tie beam
| 3.06 | 35.19 | L=2.50x2+3.25x2=11.50mt |  | 0.3 | 11.4
3 | 0.9 |  | D9(3Pcs) | 3 | 38.7 |  | "
| 2.73 | -7.371 |  |  | 0.3 | 34.83
1 | 1.5 |  | W2(1Pc) | 26 | 0.2 |  | Column
| 1.73 | -2.595 |  |  | 2.73 | 14.196
2 | 26.3 |  | General ward | 4 | 0.8 |  | Column
| 3.06 | 160.956 | L=5.9x2+7.20x2=26.20mt |  | 2.73 | 8.736
Below grade beam
2 | 4.69 |  | WD1(2Pcs) | 8 | 0.2 |  | Column
| 1.73 | -16.2274 |  |  | 0.7 | 1.12
2 | 1.2 |  | " | 6 | 2.5 |  | Isolated beam
| 2.73 | -6.552 |  |  | 0.8 | 12 | corridor
2 | 4.4 |  | WD4(2Pcs) | 4 | 5.85 |  | Axis Y/03-Y/06 from X/01-X/02
| 2.73 | -24.024 |  |  | 0.8 | 18.72
1 | 16.3 |  | Corridor | 3 | 8.4 |  | Axis x/05 from y/01-y/08
| 3.06 | 49.878 | L=1.50+7.40x2=16.30mt |  | 0.5 | 12.6
1 | 1.5 |  | W2(1Pc) | 1 | 38 |  | Axis x/04 Corrider
| 1.73 | -2.595 |  |  | 0.5 |  | L =38.50-0.20*4 =37.90
19
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | Window edge | 1 | 3.35 |  | REC.
12 | 4.96 |  | W1 =12pcs |  | 2.3 | 7.705
| 0.2 | 11.904
|  |  |  | 1 | 2.3 |  | Linen/pajama store
3 | 4.76 |  | W4 =3pcs |  | 2.3 | 5.29
| 0.2 | 2.856
|  |  |  | 1 | 5.85 |  | Corridor
1 | 1.95 |  | W5 =1pcs |  | 1.5 | 8.775
| 0.2 | 0.39
|  |  |  | 2 | 2.85 |  | Changing room
5 | 2.1 |  | W7 =5pcs |  | 1.7 | 9.69
| 0.2 | 2.1
|  |  |  | 1 | 5.85 |  | Pharmacy
7 | 3.9 |  | W15 =7pcs |  | 2.3 | 13.455
| 0.2 | 5.46
|  |  |  | 1 | 4.75 |  | Procedure
1 | 7.2 |  | W18 =1pcs |  | 5.85 | 27.7875
| 0.2 | 1.44
|  |  |  | 1 | 3.95 |  | Doctors Room
1 | 2.4 |  | W20=1pcs |  | 5.85 | 23.1075
| 0.2 | 0.48
|  |  |  | 1 | 2.3 |  | Clean utility room
10 | 1.73 |  | Wd1-wd5= |  | 1.3 | 2.99
| 0.2 | 3.46
|  |  | Door | 1 | 2.3 |  | Duity Room
27 | 2.73 |  |  |  | 4.4 | 10.12
| 0.2 | 14.742
|  |  |  | 1 | 3.4 |  | Toilet
|  | 1502.5857 | m2 net area item 6.2 |  | 1.33 | 4.522
|  |  | 6.3)Chipwood ceiling | 1 | 2.3
[5 empty] | 1.33 | 3.059 | "
2 | 6 |  | Maternity ward
| 7.2 | 86.4 |  | 1 | 2.13 |  | Duity Room
[5 empty] | 4.4 | 9.372
1 | 2.5 |  | Nurse station room
| 3.8 | 9.5 |  | 1 | 2.13 |  | Sluice
[5 empty] | 1.3 | 2.769
1 | 2.5 |  | Store
| 3.25 | 8.125 |  | 1 | 2.15 |  | Nurse station room
[5 empty] | 4 | 8.6
3 | 6 |  | General ward
| 7.2 | 129.6 |  | 1 | 2.15 |  | Store
[5 empty] | 1.7 | 3.655
1 | 7.2 |  | corridor
| 1.5 | 10.8 |  | 2 | 2.5 |  | Toilet
[5 empty] | 4.35 | 21.75
2 | 3 |  | Assisted bath
| 3.53 | 21.18 |  | 2 | 1.35 |  | Janitors
[5 empty] | 2.5 | 6.75
1 | 36.9 |  | Main corridor
| 2.5 | 92.25 |  | 1 | 1.85 |  | Toilet
[5 empty] | 1.7 | 3.145
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 4 |  | Corridor | 1 | 38.3 |  | Main corridor
| 1.85 | 7.4 |  |  | 2.5 | 95.75
2 | 4.65 | 26.505 | Isolation rooms | 1 | 3.55 |  | REC.
| 2.85 |  |  |  | 2.3 | 8.165
5 | 2.15 |  | Toilet | 1 | 2.3 |  | Linen/pajama store
| 2.3 | 24.725 |  |  | 2.3 | 5.29
1 | 24.6 |  | Varenda | 1 | 6.05 |  | Corridor
| 2 | 49.2 |  |  | 1.5 | 9.075
|  | 638.227 | m2 net area item 6.3 | 2 | 2.85 |  | Changing room
[5 empty] | 1.7 | 9.69
6.4)Approved 6mm thick ceramic wall
1 | 143 |  |  | 1 | 5.85 |  | Pharmacy
| 0.06 | 8.58 |  |  | 2.3 | 13.455
1 | 187.5 |  |  | 1 | 4.75 |  | Procedure
| 0.06 | 11.25 |  |  | 5.85 | 27.7875
1 | 320 |  |  | 1 | 3.95 |  | Doctors Room
| 0.06 | 19.2 |  |  | 5.85 | 23.1075
|  |  |  | 1 | 2.3 |  | Clean utility room
| 0.06 | 0 |  |  | 1.3 | 2.99
|  |  |  | 1 | 2.3 |  | Duty room
| 0.06 | 0 |  |  | 4.4 | 10.12
|  |  |  | 1 | 3.4 |  | Toilet
| 0.06 | 0 |  |  | 1.33 | 4.522
|  | 39.03 | m2 net area item 6.4 | 1 | 2.3
[5 empty] | 1.33 | 3.059 | "
6.5)Approved 9mm thick non slipery cearmic floor
|  |  |  | 1 | 2.13 |  | Sluice
2 | 6 |  | Maternity ward |  | 1.3 | 2.769
| 7.2 | 86.4
|  |  |  | 1 | 2.13 |  | Bed room
1 | 2.5 |  | Nurse station room |  | 4.4 | 9.372
| 3.8 | 9.5
|  |  |  | 1 | 2.15 |  | Nurse station room
1 | 2.5 |  | Store |  | 4 | 8.6
| 3.25 | 8.125
|  |  |  | 1 | 2.15 |  | Store
3 | 6 |  | General ward |  | 1.9 | 4.085
| 7.2 | 129.6
|  |  |  | 8 | 1.05 |  | Janitors
1 | 7.4 |  | corridor |  | 1.2 | 10.08
| 1.5 | 11.1
|  |  |  | 2 | 1.25 |  | Toilet
2 | 3 |  | Assisted bath |  | 4.35 | 10.875
| 3.53 | 21.18
|  |  |  | 2 | 1.35 |  | Toilet
[5 empty] | 2.5 | 6.75
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 1.85 |  | Toilet | 3 | 21.7 |  | General ward
| 1.7 | 3.145 |  |  |  | 65.1 | L=6*2+7.20*2+0.40-3.50-1.20=21.70mt
1 | 4.2 |  | Corridor | 1 | 14.3 |  | Assisting bath corridor
| 1.85 | 7.77 |  |  |  | 14.3 | L=7.4*2+1.50-1.0*2=14.30mt
2 | 4.65 |  | Isolation rooms | 1 | 55.7 |  | Main corridor
| 2.85 | 26.505 |  |  |  | 55.7 | l=55.70mt
5 | 2.15 |  | Toilet | 1 | 8.1 |  | REC.
| 2.3 | 24.725 |  |  |  | 8.1 | L=3.35*2+2.30-0.9=8.10mt
1 | 25.2 |  | Varanda | 1 | 8.3 |  | Linen/pajama store
| 2.35 | 59.22 |  |  |  | 8.3 | L=2.30*4-0.9=8.30mt
4 | 1 |  | D5 | 1 | 10 |  | Corridor
| 0.15 | 0.6 |  |  |  | 10 | L=6.05*2+1.5-0.9*4=10.00ml
9 | 0.8 |  | D7 | 2 | 8.2 |  | Changing room
| 0.15 | 1.08 |  |  |  | 16.4 | L=2.85*2+1.7*2-0.9=8.20mt
6 | 0.7 |  | D8 | 1 | 15.3 |  | Pharmacy
| 0.15 | 0.63 |  |  |  | 15.3 | L=2.30*2+5.85*2-0.9=15.30mt
8 | 0.9 |  | D9 | 1 | 19.9 |  | Procedure
| 0.2 | 1.44 |  |  |  | 19.9 | L=4.75*2+5.85*2-1.30=19.90mt
1 | 1.3 |  | D11 | 1 | 18.7 |  | Doctors Room
| 0.2 | 0.26 |  |  |  | 18.7 | L=3.95*2+5.85*2-0.90=18.70mt
5 | 1.2 |  | WD1 - WD3 | 1 | 6.4 |  | Clean utility room
| 0.2 | 1.2 |  |  |  | 6.4 | L=1.3*2+2.3*2-0.80=6.40mt
5 | 0.9 |  | D6 | 1 | 12.6 |  | Duity room
| 0.2 | 0.9 |  |  |  | 12.6 | L=2.3*2+4.4*2-0.80=12.60mt
5 | 0.8 |  | D10 | 1 | 6.26 |  | Toilet corridor
| 0.2 | 0.8 |  |  |  | 6.26 | L=1.33*2+3.4*2-0.80*2+0.9+0.7=6.26mt
5 | 3.45 |  | WD3& WD4 | 1 | 6.06 |  | Sluice
| 0.2 | 3.45 |  |  |  | 6.06 | L=1.3*2+2.13*2-0.80=6.06mt
|  | 624.367 | m2 net area item 6.5 | 1 | 12.26 |  | Bed room
[6 empty] | 12.26 | L=2.13*2+4.4*2-0.80=12.26mt
6.6)Approved type cearmic skirting 10/0.9
|  |  |  | 1 | 9.35 | 9.35 | Nurse station room
2 | 21.7 |  | Maternity ward |  |  |  | L=2.15+4.00*2-0.80=9.35mt
|  | 43.4 | l=6*2+7.20*2+0.4-3.5-1.20=21.70mt
|  |  |  | 1 | 7.5 |  | Store
1 | 11 |  | Nurse station room |  |  | 7.5 | L=2.15*2+2.00*2-0.80=7.50mt
|  | 11 | L=2.5*2+3.8*2+0.1X2-0.9*2=11.00mt
|  |  |  | 2 | 6.9 |  | Janitors
1 | 10.5 |  | Store |  |  | 13.8 | L=2.5*2+1.35*2-1.00=6.90mt
|  | 10.5 | L=2.5*2+3.2*2-0.90=10.50mt
|  |  |  | 2 | 14 |  | Isolation rooms
[6 empty] | 28 | L=2.35*2+4.65*2-0.80=14mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 7.85 | 7.85 | corridor L=1.85+4.35*2-2-0.7=7.85ml |  |  |  | 9)SANITARY INSTALLATION
9.1)Supplay & install PP-R water pipe
1 | 18.6 | 18.6 | L=3.05+4.95+0.3+1.45*5+2.35+0.6*4=20.30 | 1 | 119.08 |  | Internal ф 20mm
|  |  | Assisted bath |  |  | 119.08 | m net length 9.1.b
2 | 11.04 | 22.08 | L =3.52*2+3*2-1*2 =11.04 |  |  |  | Internal ф 25mm
|  |  |  | 5 | 1.9 |  | Verenda Toilet
|  | 323.91 | ml net lengt item 6.6 |  |  | 9.5
6.7) Window cill Size, 27/3cm
12 | 1.6 |  |  | 2 | 9.99 |  | Toilet (M) & Toilet(F)
|  | 19.2 | W2(12Pcs) |  |  | 19.98
3 | 1.4
|  | 4.2 | W4(3Pcs) | 1 | 2.55 |  | Dutty room Toilet
1 | 0.85 |  |  |  |  | 2.55
|  | 0.85 | W5(1Pc)
1 | 1 |  |  |  |  | 32.03 | m net length 9.1.c
|  | 1 | W7(1Pc)
7 | 1.4 | [5 empty] | Internal ф 32mm
|  | 9.8 | W15(7Pcs) | 2 | 3.55 |  | Toilet (M) & Toilet(F)
1 | 6.1 |  |  |  |  | 7.1 | m net length 9.1.d
|  | 6.1 | W18(1Pc)
1 | 1.3 | [5 empty] | 9.3- Supply & fix Bronze Gate Valve
|  | 1.3 | W20(1Pc) |  |  |  | Dia ф 20mm
|  | 42.45 | ml net length item no 6.7 | 5 | 2 |  | Verenda Toilet
|  |  | 6.9)1.2mt wide pavement |  |  | 10
1 | 39.7 |  | L=38.50+1.2=39.70mt
| 1.2 | 47.64 |  | 1 | 2 |  | Toilet beside Iso. Room
2
1 | 18.7 |  | L=18.55mt
| 1.2 | 22.44 |  | 2 | 4 |  | Toilet (M) & Toilet(F)
|  | 70.08 | m2 net area item 6.9 |  |  | 8
6.10) Concrete pipe of 1/2 ф30cm
2 | 40.1 |  | Right & Left side | 1 | 4 |  | Dutty room Toilet
|  | 80.2 |  |  |  | 4
1 | 20.95 |  | Front side |  |  | 24 | № net number item 9.3
20.95
|  | 101.15 | ml net lengt item 6.10 |  |  |  | 9.5) Install waste water pipe made of Upvc
|  |  | 6.11)Constructe 10/40 cm curb stone | 1 | 49.32 |  | ф 50mm
1 | 19.5 |  | Left Side |  |  | 49.32 | № net number item 9.5.a
19.5
1 | 0 |  | L=18.55+1.2X2+.4X2+.15x2=22.50mt |  |  |  | ф 75mm
|  | 0 |  | 1 | 48.67
|  | 44.5 | ml net lengt item 6.11 |  |  | 48.67 | № net number item 9.5.b
7)Painting
|  |  | 7.1)Int. plastered surface & ext beam & colun |  |  |  | ф 100mm
|  |  |  | 1 | 50.42
|  | 1502.5857 | m2 net area item 7.1 |  |  | 50.42 | № net number item 9.5.c
7.2)Chip wood ceiling surface
|  | 638.227 | m2 net area item 7.2
7.3)External rendered surface
|  | 260.511 | m2 net area item 7.3
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 9.9. Toilet Paper Holder |  |  |  | 6.00)Telephone data point
6.01)Telephone points fed though cat 5E
5 | 1 |  | Verenda Toilet | 1 | 12
|  | 5 |  |  |  | 12 | № net number item 6.01
1 | 1 |  | Toilet beside Iso. Room |  |  |  | 7. Type of light fittings
|  | 1 |  |  |  |  | 7.01)Philips TMS012/136 2*TLD 36W
|  |  |  | 1 | 6
2 | 2 |  | Toilet (M) & Toilet(F) |  |  | 6 | № net number item 7.01
4
7.05)Massive
1 | 1 |  | Dutty room Toilet | 1 | 20
|  | 1 |  |  |  | 20 | № net number item 7.05
|  | 11 | № net number item 9.9 |  |  |  | 8.00)TV point
TV points fed thoughRG6 coaxial 75ohm
|  |  | 10. Electrical Installations | 1 | 5 |  | TV cable in a rigid conduit ф25mm
|  |  | 2.Light point |  |  | 5 | № net number item 8.00
2.01. Light pts
1 | 92 | [5 empty] | 10.00. Cable way and Manhole
|  | 92 | № net number item 2.01 |  |  |  | 10.03. Riged pvc Dia. 50mm telephone frame
|  |  |  | 1 | 10.24
|  |  | 3.00. Switches |  |  | 10.24 | № net number item 10.03
3.01)Single
1 | 51
|  | 51 | № net number item 3.01
3.02)Double
1 | 16
|  | 16 | № net number item 3.02
3.03)Two way
1 | 4
|  | 4 | № net number item 3.03
3.04)Intermidiate
1 | 10
|  | 10 | № net number item 3.03
4.)Socket outlet point
4.01)Socket outlet point 3x2.5mm2
1 | 54
|  | 54 | № net number item 4.01
4.02)Ditto 4.01 but water heater
1 | 12
|  | 12 | № net number item 4.02
5. Socket out lets
5.01)Socket out lets 16A1ph
1 | 46
|  | 46 | № net number item 5.01

## IPD Bar
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [9 empty] | Block : IPD
CLIENT:-ANRS Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | Total bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | On Axis X/01, X/04,X/03 & X/05 | 14 | 11.35 | 3 | 5 | 15 | - | - | - | - | 170.25
|  |  | 14 | 10.9 | 3 | 5 | 15 | - | - | - | - | 163.5
|  |  | 14 | 9.7 | 3 | 5 | 15 | - | - | - | - | 145.5
|  |  | 14 | 8.93 | 3 | 5 | 15 | - | - | - | - | 133.95
|  |  | 14 | 7.05 | 3 | 5 | 15 | - | - | - | - | 105.75
|  |  | 14 | 11.05 | 3 | 5 | 15 | - | - | - | - | 165.75
|  |  | 14 | 9.65 | 3 | 5 | 15 | - | - | - | - | 144.75
|  |  | 14 | 9.97 | 3 | 5 | 15 | - | - | - | - | 149.55
|  |  | 14 | 11.05 | 3 | 8 | 24 | - | - | - | - | 265.2
|  |  | 14 | 9.53 | 3 | 8 | 24 | - | - | - | - | 228.72
|  |  | 14 | 9.38 | 3 | 8 | 24 | - | - | - | - | 225.12
|  |  | 14 | 11.5 | 3 | 8 | 24 | - | - | - | - | 276
| stirrups |  | 8 | 1.2 | 189 | 5 | 945 | - | 1134 | - | - | -
|  |  | 8 | 1.2 | 91 | 8 | 728 | - | 873.6 | - | - | -
| floor mesh |  | 8 | 2.35 | 188 | 1 | 188 | - | 441.8 | - | - | -
|  |  | 8 | 7.05 | 188 | 1 | 188 | - | 1325.4 | - | - | -
|  |  | 8 | 2.35 | 188 | 1 | 188 | - | 441.8 | - | - | -
|  |  | 8 | 5.7 | 188 | 1 | 188 | - | 1071.6 | - | - | -
|  |  | 8 | 5.85 | 236 | 1 | 236 | - | 1380.6 | - | - | -
|  |  | 8 | 5.75 | 156 | 1 | 156 | - | 897 | - | - | -
|  |  | 8 | 2.3 | 79 | 1 | 79 | - | 181.7 | - | - | -
|  |  | 8 | 4.5 | 79 | 1 | 79 | - | 355.5 | - | - | -
TOTAL LENGTH | [8 empty] | 8103 | 0 | 0 | 2174.04
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 3200.685 | 0 | 0 | 2630.5884
0
| Super structure | [7 empty] | 0
Elevation Column
0
| C1 |  | 12 | 3.68 | 4 | 36 | 144 | - | - | - | 529.92 | -
| Stirrup |  | 8 | 0.7 | 15 | 36 | 540 | - | 378 | - | - | -
| C2 |  | 14 | 3.68 | 4 | 4 | 16 | - | - | - | - | 58.88
| Stirrup |  | 8 | 0.7 | 15 | 4 | 60 | - | 42 | - | - | -
[7 empty] | 0 | - | - | - | - | -
[7 empty] | 0 | - | - | - | - | -
[7 empty] | 0 | - | - | - | - | -
| top tie beam |  | 12 | 10.28 | 3 | 8 | 24 | - | - | - | 246.72 | -
|  |  | 12 | 9.43 | 3 | 8 | 24 | - | - | - | 226.32 | -
|  |  | 12 | 10.83 | 3 | 8 | 24 | - | - | - | 259.92 | -
|  |  | 12 | 9.28 | 3 | 8 | 24 | - | - | - | 222.72 | -
|  |  | 12 | 11.35 | 3 | 5 | 15 | - | - | - | 170.25 | -
|  |  | 12 | 7.05 | 3 | 5 | 15 | - | - | - | 105.75 | -
|  |  | 12 | 10.9 | 3 | 5 | 15 | - | - | - | 163.5 | -
|  |  | 12 | 11.05 | 3 | 5 | 15 | - | - | - | 165.75 | -
|  |  | 12 | 9.7 | 3 | 5 | 15 | - | - | - | 145.5 | -
|  |  | 12 | 9.65 | 3 | 5 | 15 | - | - | - | 144.75 | -
|  |  | 12 | 8.83 | 3 | 5 | 15 | - | - | - | 132.45 | -
|  |  | 12 | 9.97 | 3 | 5 | 15 | - | - | - | 149.55 | -
| stirrups | x-axis | 8 | 0.9 | 189 | 5 | 945 | - | 850.5 | - | - | -
|  | y-axis | 8 | 0.9 | 91 | 8 | 728 | - | 655.2 | - | - | -
TOTAL LENGTH | [8 empty] | 1925.7 | 0 | 2663.1 | 58.88
UINT WEIGHT in KG/ML | [8 empty] | 0.395 |  | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 760.6515 | 0 | 2364.8328 | 71.2448
Lintel
|  |  | 12 | 1.45 | 3 | 2 | 6 |  |  |  | 8.7
| D7 |  | 12 | 1.15 | 3 | 2 | 6 | - | - | - | 6.9 | -
| Stirrups |  | 8 | 0.6 | 3 | 7 | 21 | - | 12.6 | - | - | -
|  |  | 12 | 2.2 | 2 | 2 | 4 |  |  |  | 8.8
| On top of D8 |  | 12 | 1.9 | 2 | 2 | 4 | - | - | - | 7.6 | -
| Stirrups |  | 8 | 0.6 | 2 | 11 | 22 | - | 13.2 | - | - | -
|  |  | 12 | 1.35 | 1 | 2 | 2 | - | - | - | 2.7 | -
| Ditto on D8 |  | 12 | 1.05 | 1 | 2 | 2 | - | - | - | 2.1 | -
| Stirrups |  | 8 | 0.6 | 1 | 5 | 5 | - | 3 | - | - | -
|  |  | 12 | 1.35 | 1 | 2 | 2 |  | - |  | 2.7 | -
| D9 |  | 12 | 1.25 | 1 | 2 | 2 |  | - |  | 2.5 | -
|  |  | 8 | 0.7 | 1 | 7 | 7 |  | 4.9 |  | - | -
|  |  | 12 | 1.95 | 1 | 2 | 2 |  | - |  | 3.9 | -
| W9 |  | 12 | 1.65 | 1 | 2 | 2 |  | - |  | 3.3 | -
|  |  | 8 | 0.5 | 1 | 9 | 9 |  | 4.5 |  | - | -
-
TOTAL LENGTH | [8 empty] | 38.2 | 0 | 49.2 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 15.089 | 0 | 43.6896 | 0

## OPD Sum
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-OPD
Details of Works executed
Bill No. | Description |  | Sub Total Birr |  | Total Birr
|  |  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  |  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work |  | 321385 | 162975.0039 | 321385 | 162975.0039
2 | Concrete Work |  | 496608 | 410133.8814 | 496608 | 410133.8814
3 | Masonry work |  | 184800 | 99382.512 | 184800 | 99382.512
| sub total A |  | 1002793 | 672491.3973 | 1002793 | 672491.3973
B. Super Structure
1 | Concrete Work |  | 242703 | 171327.0594 | 242703 | 171327.0594
2 | Block work |  | 169290 | 197408.898 | 169290 | 197408.898
3 | Roofing |  | 153292 | 174072.4 | 153292 | 174072.4
4 | Carpentry & Joinery |  | 147919.28 | 161282.4 | 147919.28 | 161282.4
5 | Metal work |  | 154418 | 86788.5 | 85300 | 86788.5
6 | Finishing |  | 592950 | 583973.529 | 592950 | 583973.529
7 | Painting |  | 40516 | 46331.838 | 40516 | 46331.838
8 | Glazing |  | 9560 |  | 9560 | 0
9 | Sanitory Installation |  | 33460 | 5009.65 | 33460 | 5009.65
10 | Electrical Installation |  | 118513.89 | 101588.75 | 118513.89 | 101588.75
| sub total B |  | 1662622.17 | 1527783.0244 | 1593504.17 | 1527783.0244
| Total A+B |  | 2665415.17 | 2200274.4216 | 2596297.17 | 2200274.4216
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  | Suppervisor :- ______________ |  |  | Consultant:- _____________

## OPD Meas.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [5 empty] | Block: - OPD
CLIENT:-ANRS Health Bureau
Item | Description | Unit | QTY | Contract |  |  | Executed
|  |  |  | Qty | Rate | amount | Qty | amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 485 | 485 | 8 | 3880 | 490.78 | 3926.24
1.2 | Bulk excavation in ordinary | m3 | 106 | 591 | 70 | 41370 | 80.8398 | 5658.7895
1.3 | Ditto but exceeding 1.5 m but less than 2m. | m3 |  | 197 | 70 | 13790 | 171.6941 | 12018.5856
1.4 | Selected borrowed fill brought from out side | m3 | 389 | 788 | 150 | 118200 | 227.6654 | 34149.816
1.5 | Selected borrowed fill brought frominsotu | m3 |  |  | 56.66 | 0 | 50.3885 | 2855.0113
1.6 | Cart away surplus excavated material to an | m3 | 389 | 933.5 | 70 | 65345 | 349.3794 | 24456.5615
1.7 | 25cm thick basaltic or equivalent stone hard | m2 | 243 | 394 | 200 | 78800 | 399.55 | 79910
Total to summary ………Birr | [5 empty] | 321385 |  | 162975.0039
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 120 | 120 | 150 | 18000 | 86.944 | 13041.6
2.2 | Ditto but under footing pad | m2 |  | 32 | 150 | 4800 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 243 | 394 | 400 | 157600 | 399.55 | 159820
Reinforced concrete class C -25, with minimum
2.4 | In grade beam&Steps | m3 | 24 | 24 | 3200 | 76800 | 22.216 | 71091.2
2.5 | In footing pad | m3 |  | 6.5 | 3200 | 20800 |  | 0
2.6 | In footing coloumn | m3 |  | 5 | 3200 | 16000 |  | 0
Provide cut and fix in position swan zigzag wood form work
2.7 | Grade beam | m2 | 120 | 120 | 120 | 14400 | 173.328 | 20799.36
2.8 | In footing pad | m2 |  | 26 | 120 | 3120 |  | 0
2.9 | In footing coloumn | m2 |  | 100 | 120 | 12000 |  | 0
2.1 | Steps | m2 | 5 | 5 | 150 | 750
Reinforcement steel bar according to St.drawing
2.11 | Dia 14 mm deformed bar | kg | 1243 | 1243 | 36 | 44748 | 1761.276 | 63405.936
2.12 | Dia. 12mm deformed bar | kg |  | 950 | 36 | 34200 |  | 0
2.13 | Dia 8 mm deformed bar | kg | 2111 | 2320 | 36 | 83520 | 1992.6052 | 71733.7854
2.14 | 10/2 cm chip wood expansion joint between | m | 329 | 329 | 30 | 9870 | 341.4 | 10242
Total to summary ………Birr | [5 empty] | 496608 |  | 410133.8814
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 120 | 120 | 1250 | 150000 | 67.6339 | 84542.4
3.2 | Ditto but above natural ground level externally | m3 | 24 | 24 | 1450 | 34800 | 10.2346 | 14840.112
| Total to summary ………Birr |  |  |  |  | 184800 |  | 99382.512
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 4.3 | 4.5 | 3200 | 14400 | 3.4944 | 11182.08
1.2 | In beams& steps | m3 | 14 | 14 | 3200 | 44800 | 13.4208 | 42946.56
1.3 | Lintel | m3 |  | 1.1 | 3200 | 3520 | 0.338 | 1081.6
Provide cut and fix in position swan zigzag wood form work
1.4 | Elevation column | m2 | 29 | 29 | 130 | 3770 | 69.888 | 9085.44
1.5 | Beam | m2 | 192 | 192 | 130 | 24960 | 175.264 | 22784.32
1.6 | Lintel | m2 |  | 10.1 | 130 | 1313 | 7.86 | 1021.8
Reinforcement steel bar according to St.drawing
| position and tying wires. |  |  |  | 36
1.7 | Dia 14mm deformed bar | kg | 0 | 1900 | 36 | 68400
1.8 | Dia 12mm deformed bar | kg | 1727 | 1727 | 36 | 62172 | 1767.5818 | 63632.9434
1.9 | Dia 8 mm deformed bar | kg | 538 | 538 | 36 | 19368 | 544.231 | 19592.316
1.1 | Dia 6 mm deformed bar | kg | 0 | 0 | 36 | 0 |  | 0
Total to summary ………Birr | [5 empty] | 242703 |  | 171327.0594
2. BLOCK WORK
2.1 | 20cm thick | m2 | 498 | 331 | 350 | 115850 | 336.4566 | 117759.81
2.2 | 15cm thick | m2 | 0 | 167 | 320 | 53440 | 248.9034 | 79649.088
Total to summary ………Birr | [5 empty] | 169290 |  | 197408.898
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 452.13 | 451 | 300 | 135300 | 500.94 | 150282
3.2 | G28 ribbed sheet ceiling under eave | m2 | 56 | 39.2 | 160 | 6272 | 59.04 | 9446.4
3.3 | Flashing in flat metal sheet fixed as shown | m | 93 | 28 | 110 | 3080 | 51.2 | 5632
3.4 | Supply and fix G-28 flat metal sheet gutter | m | 70 | 72 | 120 | 8640 | 72.6 | 8712
Total to summary ………Birr | [5 empty] | 153292 |  | 174072.4
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 529.8 | 529 | 23 | 12167 | 724.68 | 16667.64
4.2 | Diagonal & vertical Members size-diameter 8 - 10 cm | m | 376.8 | 376 | 16 | 6016 | 774.9 | 12398.4
4.3 | Purlin zigba size 5/7cm | m | 506.38 | 506.38 | 33 | 16710.54 | 714.6 | 23581.8
4.4 | Zigba wooden fascia board price includes three coats | m | 72.34 | 72.34 | 71 | 5136.14 | 98.16 | 6969.36
Doors
4.5 | Type D5 size - 100/273cm | Nº | 2 | 2 | 5187 | 10374 | 1 | 5187
4.6 | Type D7 size-80/273cm | Nº | 7 | 7 | 4149.6 | 29047.2 | 2 | 8299.2
4.7 | Type D8 size-70/273cm | Nº | 6 | 6 | 3630.9 | 21785.4 | 5 | 18154.5
4.8 | Type D9 size-90/273cm | Nº | 10 | 10 | 4668.3 | 46683 | 15 | 70024.5
Total to summary ………Birr | [5 empty] | 147919.28 |  | 161282.4
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 16 | 6 | 3892.5 | 23355 | 14 | 54495
5.2 | Type W4 size-130/173cm | Nº | 1 | 16 | 3373.5 | 53976 | 5 | 16867.5
5.3 | Type W23 size-180/60cm | Nº | 2 | 1 | 1620 | 1620 | 1 | 1620
5.4 | Type W24 size-100/60cm | Nº | 8 | 2 | 900 | 1800 |  | 0 | #REF! | #REF! | #REF! | #REF!
| Type Wsize-130/60cm | Nº |  |  | 1170 | 2340 | 2 | 2340
| Doors | [6 empty] | 0
5.6 | Type D2 size - 140/273cm | Nº | 3 | 3 | 5733 | 17199 | 2 | 11466
Total to summary ………Birr | [5 empty] | 100290 |  | 86788.5
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 |  | 208 | 140 | 29120 | 211.6496 | 29630.944
6.2 | Apply three coats of plastering to internal walls& | m2 |  | 789 | 150 | 118350 | 1103.5714 | 165535.71
6.3 | 8mm Chip wood ceiling nailed on & including | m2 | #REF! | 394 | 310 | 122140 | 339.4875 | 105241.125
6.4 | Approved type 6mm thick glazed ceramic wall tile | m2 | 0 | 65 | 370 | 24050 | 73.92 | 27350.4
6.5 | Approved type 9mm thick non slippery ceramic tile floor | m2 | 329 | 394 | 300 | 118200 | 357.3655 | 107209.65
6.6 | Approved type Ceramic tile skirting | ml |  | 329 | 100 | 32900 | 305.58 | 30558
6.7 | Approved type Terrazo window cill size 27/3cm | m | 43 | 43 | 150 | 6450 | 29.5 | 4425
6.8 | 30/30/3mm angle iron corner protection | m | 72 | 72 | 70 | 5040 |  | 0
6.9 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 |  | 177 | 550 | 97350 | 116.904 | 64297.2
6.1 | Supply storm water concrete pipes of half diameter 30cm | ml |  | 155 | 265 | 41075 | 104.42 | 27671.3
6.11 | Construction of 10x40 cm curb stone | ml |  | 155 | 210 | 32550 | 105.02 | 22054.2
Total to summary ………Birr | [5 empty] | 627225 |  | 583973.529
7. PAINTING
7.1 | Internal plastered surfaceand external beams& | m2 | 243 | 789 | 28 | 22092 | 1103.5714 | 30899.9992
7.2 | Chip wood ceiling surface | m2 | 208 | 450 | 28 | 12600 | 339.4875 | 9505.65
7.3 | External rendered surface | m2 |  | 208 | 28 | 5824 | 211.6496 | 5926.1888
Total to summary ………Birr | [5 empty] | 40516 |  | 46331.838
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R water pipes for water
| 15mm diameter ;internal | LM | 20 | 70 | 30 | 2100 | 9.65 | 289.5
| 20mm diameter ;internal | LM | 14 | 80 | 35 | 2800 |  | 0
| 25mm diameter ;internal | LM | 0 | 95 | 40 | 40 | 3.8 | 152
| 32mm diameter ;internal | LM | 37 | 125 | 50 | 6250 | 8 | 400
| 50mm diameter ;internal | LM | 0 | 0 | 50 |  | 6.55 | 327.5
9.2 | Supply and fix chrome angle valves complete | [6 empty] | 0
| 15mm diameter | No | 14 | 14 | 105 | 1470 |  | 0
9.3 | Supply and fix bronze gate valves complete with unions,
| 15mm diameter | No | 12 | 12 | 0 | 0 |  | 0
| 20mm diameter | No | 0 | 0 | 0 | 70 |  | 0
9.5 | Supply and install waste water pipes made of rigid | [6 empty] | 0
| 50mm diameter of min. wall thickness=2mm | LM | 5 | 5 | 65 | 325 | 22.31 | 1450.15
| 75mm diameter of min. wall thickness=3mm | LM | 8 | 8 | 95 | 760 | 7.9 | 750.5
| 100 mm diameter of min. wall thickness=3.2mm | LM | 20 | 20 | 125 | 2500 | 11.6 | 1450
9.6 | Supply and fix 500x400 mm white vitreous | No | 7 | 7 | 800 | 5600 |  | 0
9.7 | Supply and fix low flush white vitreous china | No | 5 | 6 | 1300 | 7800 |  | 0
9.9 | Supply and fix toilet paper holder made of metal | No | 5 | 6 | 95 | 570 | 2 | 190
Total to summary ………Birr | [5 empty] | 30285 |  | 5009.65
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 58 | 58 | 200 | 11600 | 60 | 12000
3 | Switches
3.01 | single(774001+774041) | PCs | 9 | 9 | 81.25 | 731.25 | 15 | 1218.75
3.02 | Duoble(774005+774042) | " | 16 | 16 | 131.25 | 2100 | 19 | 2493.75
3.03 | Two-Way(774006+774041) | " | 4 | 4 | 80 | 320 | 4 | 320
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 30 | 30 | 200 | 6000 | 32 | 6400
5 | Socket outlets
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs |  |  | 90 |  | 32 | 2880
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 14 | 14 | 130 | 1820 | 14 | 1820
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 14 | 14 | 70 | 980 |  | 0
7 | Type of Light Fitting With lamp
7.01 | PHILIPS TMS 012/236 IMKwith 2xTLD 36W | PCs | 18 | 18 | 1500 | 27000 | 30 | 45000
7.02 | PHILIPS TMS 012/136 IMKwith 1xTLD 36W | PCs | 30 | 30 | 1200 | 36000 | 20 | 24000
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 5 | 5 | 406.25 | 2031.25 | 7 | 2843.75
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 5 | 5 | 406.25 | 2031.25 | 5 | 2031.25
8 | TV points
8.01 | TV points fed through RG6 Coaxial 75ohm TV | PCs | 1 | 1 | 266.25 | 266.25 | 1 | 266.25
8.02 | Flush mounted TV outlets type Legrand Suno | PCs | 1 | 1 | 120 | 120 |  | 0
9 | Power Cables(XLPE 0.6/KV or approved equ.) |  |  |  |  | 0 |  | 0
9.01 | 5x10mm2 | ML | 20 | 20 | 220 | 4400 |  | 0
9.02 | 4x6mm2 from SDB-OPD to SDB-EMRG | ML | 26 | 26 | 90 | 2340 |  | 0
10 | Cable way and Manhole | [6 empty] | 0
10.01 | Rigid pvc pipe of dia.40mm From CMDB | mt | 11 | 11 | 50 | 550 |  | 0
10.02 | Rigid pvc pipe of dia.32mm For 4x6mm2 | " | 24 | 24 | 40 | 960 |  | 0
10.03 | Rigid pvc pipe dia. 50mm to | " | 12 | 8 | 60 | 480 | 5.25 | 315
Total to summary ………Birr | [5 empty] | 99730 |  | 101588.75

## OPD TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - OPD
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | Deduction
|  |  | 1) EXCAVATION & EARTH WORK | 2 | 33.74 |  | along x-axis
|  |  | 1.1 Clear off site to remove top soil |  | 0.4 |  | L=33.74 W=0.4m
|  |  | L=35.1+3=38.10, W=11.2+3=14.20 |  | 0.74 | 19.9741
1 | 37.04
| 13.25 | 490.78 | m2 net area item 1.1 | 6 | 9.65 |  | along y-axis
[5 empty] | 0.4 |  | L=11.75-0.5-0.8-(2*0.4)=9.65
|  |  | 1.2 Bulk Excavation in ordinary soil |  | 0.74 | 17.1384
1 | 33.74 |  | L=35.54-0.25-0.25-0.4-0.4-0.5=33.74
| 9.95 |  | W=11.75-0.25-0.25-0.4-0.4-0.5=9.95 |  |  | 227.6654 | m3 net volume item 1.4 (Borrowed)
| 0.35 | 117.4995
1.5 Cart away
|  |  | Deduction | 1 | 37.04
2 | 33.74 |  | along x-axis |  | 13.25
| 0.9 |  | L=35.54-0.25-0.25-0.4-0.4-0.5=33.74 |  | 0.3 | 147.234 | from item no 1.1
| 0.35 | 21.2562
[6 empty] | 80.8398 | from item no 1.2
6 | 8.15 |  | along y-axis
| 0.9 |  | W=11.75-0.25-0.25-0.4-0.4-0.5-(2*0.9)=8.15 |  |  | 171.6941 | from item no 1.3
| 0.35 | 15.4035
[6 empty] | 50.3885 | deduction backfill
|  | 80.8398 | m3 net Volume item 1.2
[6 empty] | 349.3794 | m3 net volume item 1.5
1.3 Ditto to Item 1.2 but exceeding 1.5
|  |  | and less than 2m |  |  |  | 1.6 Hard Core
4 | 35.54 |  | along x-axis | 2 | 3.7 |  | b/n axis y/01-02
| 0.9 |  | W=0.4+0.25+0.25=0.90, L=35.54,d=0.92 |  | 4 | 29.6
| 0.92 | 117.7085
|  |  |  | 10 | 4.8 |  | b/n axis x/02-07
8 | 8.15 |  | along y-axis |  | 4 | 192
| 0.9 |  | L=11.75-(4*.9)=8.15
| 0.92 | 53.9856 | W=0.4+0.25+0.25=0.90, d=.92 | 2 | 5.8 |  | b/n axisy/07-08
[5 empty] | 4 | 46.4
|  | 171.6941 | m3 Total to item 1.3
|  |  |  | 1 | 3.7 |  | b/n axisy/02-03
|  |  | 1.4 Selected Fill |  | 2.4 | 8.88
A- fill under masonary (insitu material)
4 | 35.54 |  | for axis x01-x04 | 5 | 4.8 |  | b/n axisx/02-07
| 0.9 |  | L=35.54 |  | 2.4 | 57.6
| 0.27 | 34.5449
|  |  |  | 1 | 5.8 |  | b/n axiy/07-08
8 | 8.15 |  | for axis y01-y08 |  | 2.4 | 13.92
| 0.9 |  | L=8.15 , W=0.9, d=0.3
| 0.27 | 15.8436 |  | 1 | 34.1 |  | verendah
[5 empty] | 1.5 | 51.15
|  | 50.3885 | m3 net volume item 1.4 (insitu)
[6 empty] | 399.55 | m2 total Item 1.6
B-bulk fill and compaction (Borrowed )
1 | 34.24 |  | under hard core
10.45
| 0.74 | 264.7779 | L=35.54-0.5-0.8=34.24, W=11.75-0.5-0.8=10.45
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2) CONCRETE WORK |  |  |  | 2.14)10/2cm chipwoodexpantion
|  |  | 2.1 5cm thick lean concrete class C-7 | 6 | 33.1 |  | on axis x01-x04 b/ny01-y08
4 | 35.04 |  | L=35.54-0.5=35.04 |  |  | 198.6 | L=35.1-8*.25=33.1m
| 0.4 | 56.064
|  |  |  | 14 | 10.2 |  | on axis y01-y08 b/n x01-x04
8 | 9.65 |  | L=11.75-0.5-(4*0.4)=9.65 |  |  | 142.8 | L=11.2-4*.25=10.2m
| 0.4 | 30.88
[6 empty] | 341.4 | ml net length item 2.14
|  | 86.944 | m2 total Item 2.1
3. Masonry Work
|  |  | 2.3) 10cm thick rei. Concrete floor slab |  |  |  | 3.1 Trychltic stone masonry (total)
|  |  | The same as item no 1.6 | 4 | 35.04 |  | axis x01,x02,x03,x04
1 | 399.55 |  |  |  | 0.4 |  | L=35.54-0.5=35.04
|  | 399.55 | m2 total Item 2.3 |  | 0.87 | 48.7757
|  |  | 2.4 In grade beams and steps | 8 | 10.45 |  | axis y01,y02,y03……y09
4 | 35.04 |  | L=35.54-0.25-0.25=35.04 |  | 0.4 |  | L=11.75-0.5-(4*0.4)=9.65
| 0.25 |  |  |  | 0.87 | 29.0928
| 0.4 | 14.016
[6 empty] | 77.8685 | m3 net volume item 3.1
8 | 10.25 |  | L=11.75-0.25-0.25-(4*.25)=10.25
| 0.25 |  |  | 1 | 15.49 |  | 3.12 masonary work above NGL
| 0.4 | 8.2 |  |  | 0.4 |  | on axis x01 L=4.92+5+5.97-0.4=15.49
[5 empty] | 0.44 | 2.7262
|  | 22.216 | m3 net volume item 2.4
|  |  |  | 1 | 15.49 |  | on axis x04 L=4.92+5+5.97-0.4=15.49
|  |  | provide form work or panel metal |  | 0.4
|  |  | 2.7 In grade beams |  | 0.52 | 3.2219
8 | 35.04 |  | L=35.54-0.25-0.25=35.04 (x-axis)
| 0.4 | 112.128 |  | 1 | 11.4 |  | on axis y08 L=4.2+2.6+4.2+0.4=11.4
0.4
16 | 10.75 |  | L=11.75-0.25-0.25-(2*.25)=10.75 |  | 0.94 | 4.2864
| 0.4 | 68.8
[6 empty] | 10.2346 | m3 net volume item 3.2
76 | 0.4 |  | DEDUCTION
| 0.25 | 7.6 |  |  |  | 67.6339 | m3 net volume item 3.1
|  | 173.328 | m2 net area item no 2.7
reinforcement steel bar work
2. 11 Dia .14mm deformed bar
1 | 1761.276
|  | 1761.276 | kg net weight item 2.11
2.13 Dia .8 mm deformed bar
1 | 1992.6052
|  | 1992.6052 | kg net weight item 2.13
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE |  |  |  | 1.5)Beam
|  |  | 1.CONCRETE WORK |  | 33.5 |  | TTB1=2Pcs
|  |  | 1.1)In elevation column | 2 | 0.8 |  | Axis x/01 & x/o4 from (y/01 - y/08)
32 | 0.2 |  | C1=32Pcs (0.2x0.2) |  |  | 53.6 | Dev.L=0.30*2+0.20=0.80mt
| 0.2 |  |  |  | 0.3
| 2.73 | 3.4944 |  | 16 | 0.2
0.96
|  | 3.4944 | m3 net volume item 1.1 |  | 33.5 |  | TTB2=3Pcs
|  |  |  | 2 | 0.8 |  | Axis x/02 & x/03 from ( y/01 - y/08)
|  |  | 1.2)In beam & step |  |  | 53.6 | Dev.L=0.30*2+0.20=0.80mt
| 35.1 |  | TTB1=2Pcs |  | 10.41 |  | TTB3=2Pcs
2 | 0.3 |  | Axis x/01 & x/o4 from (y/01 - y/08) | 2 | 0.8 |  | Axis y/01 & y/08 from ( x/01 - x/04)
| 0.2 |  |  |  |  | 16.656 | Dev.L=0.30*2+0.20=0.80mt
|  | 4.212 |  |  | 0.3
| 35.1 |  | TTB2=3Pcs | 8 | 0.2
2 | 0.3 |  | Axis x/02 & x/03 from ( y/01 - y/08) |  |  | 0.48 | TTB4=6Pcs
| 0.2 |  |  |  | 10.41 |  | Axis y/02 - y/07 from ( x/01 - x/04)
|  | 4.212 |  | 6 | 0.8 |  | Dev.L=0.30*2+0.20=0.80mt
| 10.41 |  | TTB3=2Pcs |  |  | 49.968
2 | 0.3 |  | Axis y/01 & y/08 from ( x/01 - x/04) |  |  | 175.264 | m2 net area item 1.5
0.2
|  | 1.2492 |  |  |  |  | 1.6)Lintel
| 10.41 |  | TTB4=7Pcs |  | 1.2
6 | 0.3 |  | Axis y/02 - y/07 from ( x/01 - x/04) | 4 | 0.6 |  | D7(3Pcs)
| 0.2 |  |  |  |  | 2.88
|  | 3.7476 |  |  | 1.1
|  |  |  | 5 | 0.6 |  | D8(5Pcs)
|  | 13.4208 | m3 net volume item 1.2 |  |  | 3.3
1.3
|  |  | 1.3)Lintel | 1 | 0.6 |  | D9(1Pcs)
4 | 1.2 |  | D7(3Pcs) |  |  | 0.78
| 0.15 |  |  |  | 1.5 |  | W9(1Pcs)
| 0.2 | 0.144 |  | 1 | 0.6
5 | 1.1 |  | D8(5Pcs) |  |  | 0.9
0.1
| 0.2 | 0.11 |  |  |  | 7.86 | m2 net area item 1.6
1 | 1.3 |  | D9(1Pcs) |  |  |  | 1.8) ф12 mm deformed bars
| 0.15 |  |  | 1 | 1767.5818
| 0.2 | 0.039 |  |  |  | 1767.5818 | kg net weight item 1.7
1 | 1.5 |  | W9(1Pcs) |  |  |  | 1.9) ф8mm deformed bars
| 0.15 |  |  | 1 | 544.231
| 0.2 | 0.045 |  |  |  | 544.231 | kg net weight item 1.9
|  | 0.338 | m3 net Volume item 1.3
FORM WORK
1.4)Elevation column
0.8
32 | 2.73 |  | C1=32Pcs (0.2x0.2)
69.888
|  | 69.888 | m2 net area item 1.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2)BLOCK WORK | 2 | 36.1 |  | Axis y/01&Y/04 from (X/01 - X/08)
|  |  | 2.1)20cm thick HCB wall |  | 0.2 | 14.44
1 | 33.9 |  | Axis y/01 from (X/01 - X/08)
| 2.73 | 92.547 |  |  |  | 336.4566 | m2 net area item 2.1
6 | 1.5 |  | W2(6Pcs) |  |  |  | 2.2)15cm thick HCB wall
| 1.73 | -15.57 |  | 1 | 8.7 |  | Axis Y/03 from (X/01 - X/03)
[5 empty] | 2.73 | 23.751
3 | 1.3 |  | W4(3Pcs)
| 1.73 | -6.747 |  | 1 | 1.3 |  | D11(1Pcs)
[5 empty] | 2.73 | -3.549
1 | 1.69 |  | W7(1Pc)
| 0.6 | -1.014 |  | 1 | 33.5 |  | Axis Y/02 from (X/01 - X/08)
[5 empty] | 2.73 | 91.455
1 | 1.25 |  | W9(1Pc)
| 0.6 | -0.75 |  | 10 | 0.9 |  | D9(10Pcs)
[5 empty] | 2.73 | -24.57
1 | 1.8 |  | W23(1Pc)
| 0.6 | -1.08 |  | 1 | 0.8 |  | D7(1Pc)
[5 empty] | 2.73 | -2.184
1 | 2.9 |  | W25(1Pc)
| 0.6 | -1.74 |  | 1 | 1 |  | D5(1Pc)
[5 empty] | 2.73 | -2.73
1 | 33.9 |  | Axis y/04 from (X/01 - X/08)
| 2.73 | 92.547 |  | 1 | 2.53 |  | Axis b/n y/02 &y/03 from (x/01- x/02)
[5 empty] | 3.06 | 7.7418
7 | 1.5 |  | W2(7Pcs)
| 1.73 | -18.165 |  | 1 | 5.86 |  | Axis b/n y/01 &y/02 from (x/07- x/08)
[5 empty] | 3.06 | 17.9316
2 | 1.3 |  | W4(2Pcs)
| 1.73 | -4.498 |  | 2 | 0.8 |  | D7(2Pcs)
[5 empty] | 2.73 | -4.368
1 | 25 |  | Axis y/03 from (X/03 - X/08)
| 2.73 | 68.25 |  | 1 | 1.25 |  | W9(1Pc)
[5 empty] | 0.6 | -0.75
5 | 0.9 |  | D9(5Pcs)
| 2.73 | -12.285 |  | 8 | 4 |  | Axis X/02 - X/07 from (Y/01 - Y/02)
[5 empty] | 3.06 | 97.92
1 | 2.3 |  | Opening
| 2.73 | -6.279 |  | 2 | 2 |  | B/n Axis x/07 - x/08 from y/01 - y/02
[5 empty] | 3.06 | 12.24
5 | 4 |  | Axis y/03',04', 05',06' &07,from (X/03 - X/04)
| 3.06 | 61.2 |  | 1 | 4 |  | AxisX/07 from (Y/01 - Y/02)
[5 empty] | 2.73 | 10.92
2 | 11.41 |  | Axis X/01 &X/08 from (Y/01 - Y/04)
| 2.73 | 62.2986 |  | 2 | 4 |  | Axis X/01' & X/02' from (Y/03 - Y/04)
[5 empty] | 3.06 | 24.48
2 | 1.4 |  | D1(2Pcs)
| 2.73 | -7.644 |  | 1 | 2.35
[5 empty] | 3.06 | 7.191
1 | 1.5 |  | W2(1Pc)
| 1.73 | -2.595 |  | 1 | 0.8 |  | D7(1Pc)
[5 empty] | 2.76 | -2.208
2 | 11.21 |  | Axis X/01 &X/08 from (Y/01 - Y/04)
| 1.05 | 23.541
T | D | S | Item No. and Description | T | D | S | Item No. and Description
4.3)Purlin zigba 5/7cm
1 | 0.7 |  | D8(1Pc) |  |  |  | No .pur =7.39/0.9+1=9x2=18Pcs
| 2.73 | -1.911 |  | 18 | 39.7 |  | L=38.50+1.2=39.70mt
714.6
1 | 0.9 |  | D9(1Pc)
| 2.73 | -2.457 |  |  |  | 714.6 | lm net length item 4.3
|  | 248.9034 | m2 net area item 2.2
4.4)Zigba wooden fascia board
|  |  | 3)ROOFING WORK | 4 | 6.39
|  |  | 3.1)G-28 CIS Roof covering |  |  | 25.56
1 | 36.3 |  | L=35.10+1.20=36.30mt | 2 | 36.3
| 13.8 |  |  |  |  | 72.6
|  | 500.94 | m2 net area item 3.1
[6 empty] | 98.16 | lm net length item 4.4
3.2/ G28 rebbed sheet
2 | 36.3 |  | L=35.1+0.6+0.6=36.3m |  |  |  | 4.5)Type D5 ,Size 100/273
| 0.6 | 43.56 |  | 1 | 1
[6 empty] | 1 | pcs net number item 4.5
4 | 6.45 |  | L=11.20+0.6+0.6=12.40m
| 0.6 | 15.48 | l=12.4/2=6.2m |  |  |  | 4.6)Type D7 ,Size 80/273
|  |  |  | 1 | 2
|  | 59.04 | m2 net area item 3.2 |  |  | 2 | pcs net number item 4.6
|  |  | 3.3- Flashing |  |  |  | 4.7)Type D8 ,Size 70/273
1 | 36.3 |  |  | 1 | 5
|  | 36.3 |  |  |  | 5 | pcs net number item 4.7
4 | 7.45 |  | Gable Side |  |  |  | 4.8)Type D9 ,Size 90/273
| 0.5 |  | l = (1.9^2+7.21^2)^0.5 = 7.45m | 1 | 15
|  | 14.9 |  |  |  | 15 | pcs net number item 4.8
|  | 51.2 | lm net length item 3.3 |  |  |  | 5)METAL WORK
5.1)Type W2 ,Size 150/273
|  |  | 3.4- Gutter | 1 | 14
2 |  |  | Left & Right side |  |  | 14 | pcs net number item 5.1
36.3
|  | 72.6 |  |  |  |  | 5.2)Type W4 ,Size 130/273
|  |  |  | 1 | 5
|  | 72.6 | m net length item 3.4 |  |  | 5 | pcs net number item 5.2
|  |  | 4)CARPENTRY |  |  |  | 5.5)Type W23 ,Size 180/60
27 | 14.84 |  | 4.1)Upper & lower chord | 1 | 1
|  | 400.68 |  |  |  | 1 | pcs net number item 5.5
27 | 12 |  | Upper=7.42x2=14.84mt |  |  |  | 5.5)Type W23 ,Size 130/60
|  | 324 | Lower=6.00x2=12.00mt | 1 | 2
[6 empty] | 2 | pcs net number item 5.5
|  | 724.68 | m net length item 4.1
5.7)Type D1 ,Size 140/273
|  |  | 4.2)Vertical & Diagonal member | 1 | 2
[6 empty] | 2 | pcs net number item 5.7
27 | 12.76 |  | V=12.76mt
|  | 344.52 |  |  |  |  | 6)FINISHING
27 | 15.94 |  | D=15.94mt |  |  |  | 6.1)Apply two coats of plastering
|  | 430.38 |  |  |  |  | & one coat rendering to ext. walls
|  |  |  | 2 | 33.5 |  | Axis y/01&Y/04 from (X/01 - X/08)
|  | 774.9 | m net length item 4.2 |  | 2.73 | 182.91
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 10.41 |  | Axis X/01 &X/08 from (Y/01 - Y/04) | 1 | 16.1 |  | EPI/Growth monitoring room
| 2.73 | 56.8386 |  |  | 3.06 | 49.266 | L=4.05*2+4*2=16.10mt
2 | 13.21 |  | Axis X/01 &X/08 from (Y/01 - Y/04) | 1 | 0.9 |  | D9(1Pc)
| 1.2 | 31.704 |  |  | 2.73 | -2.457
14 | 1.5 |  |  | 1 | 1.5 |  | W2(1Pcs)
| 1.73 |  | W2(14Pcs) |  | 1.73 | -2.595
-36.33
5 | 1.3 |  |  | 1 | 12.4 |  | Injection room
| 1.73 |  | W4(5Pcs) |  | 3.06 | 37.944 | L=3.95*2+2.25*2=12.40mt
-11.245
1 | 1.69 |  |  | 1 | 0.9 |  | D9(1Pc)
| 0.6 |  | W7(1Pc) |  | 2.73 | -2.457
-1.014
1 | 1.25 |  |  | 1 | 1.3 |  | W4(2Pcs)
| 0.6 |  | W9(1Pc) |  | 1.73 | -2.249
|  | -0.75 |  |  |  |  | Examination Room 1,2&3
1 | 1.8 |  |  | 3 | 13.6 |  | L=3.95*2+2.85*2=13.60mt
| 0.6 |  | W23(1Pc) |  | 3.06 | 124.848
-1.08
1 | 2.9 |  |  | 3 | 0.9 |  | D9(1Pcs)
| 0.6 |  | W25(1Pc) |  | 2.73 | -7.371
-1.74
2 | 1.4 |  |  | 3 | 1.5 |  | W2(1Pcs)
| 2.73 |  | D1(2Pcs) |  | 1.73 | -7.785
-7.644
|  |  |  | 1 | 12.06 |  | Store
|  | 211.6496 | m2 net area item 6.1 |  | 3.06 | 36.9036 | L=3.95*2+2.08*2=12.06mt
|  |  | 6.2)Apply three coats of plastering | 1 | 0.8 |  | D7(1Pcs)
|  |  | to int. wall & ext. beam & colu. |  | 2.73 | -2.184
1 | 17.24 |  | ANC/PNC PMTCT ROOM
| 2.73 | 47.0652 | L=3.95*2+4.67*2=17.24mt | 1 | 1.8 |  | W23(1Pcs)
[5 empty] | 1.73 | -3.114
1 | 0.9 |  | D9(1Pcs)
| 2.73 | -2.457 |  | 2 | 5.2 |  | Toilet
[5 empty] | 3.06 | 31.824 | L=1.2*2+2*1.44=5.mt
2 | 1.3 |  | W4(2Pcs)
| 1.73 | -4.498 |  | 2 | 0.8 |  | D7(2Pcs)
[5 empty] | 2.73 | -4.368
1 | 14.1 |  | Family planning
| 3.06 | 43.146 | L=4.05*2+3*2=14.10mt | 2 | 0.9 |  | D9(4Pcs)
[5 empty] | 2.73 | -4.914
1 | 0.9 |  | D9(1Pc)
| 2.73 | -2.457 |  | 2 | 8.28 |  | L=2x2.7+1.44x2=8.28mt
[5 empty] | 1.73 | 28.6488
1 | 1.5 |  | W2(1Pcs)
| 1.73 | -2.595 |  | 2 | 0.8 |  | D7(2Pcs)
[5 empty] | 1.13 | -1.808
1 | 14.1 |  | Under 5 clinic
| 3.06 | 43.146 | L=4.05*2+3*2=14.10mt | 4 | 0.7 |  | D8(4Pcs)
[5 empty] | 1.13 | -3.164
1 | 0.9 |  | D9(1Pc)
| 2.73 | -2.457 |  | 2 | 1 |  | W7&W9(2Pcs)
[5 empty] | 0.6 | -1.2
1 | 1.5 |  | W2(1Pcs)
| 1.73 | -2.595 |  | 1 | 27.6 |  | Toilet room
[5 empty] | 1.73 | 47.748 | L=8x1.45+8x2=27.60mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
4 | 0.7 |  | D8(4Pcs) | 1 | 1.3 |  | W4(1Pcs)
| 1.13 | -3.164 |  |  | 1.73 | -2.249
1 | 2.9 |  | W25 | 1 | 16 |  | Dispensary
| 0.6 | -1.74 |  |  | 3.06 | 48.96 | L=4*4=16.00mt
1 | 1.25 |  | W9 | 1 | 0.8 |  | D7(1Pcs)
| 0.6 | -0.75 |  |  | 2.73 | -2.184
Handicape
1 | 9.2 |  | L=2x2.7+2x1.9=9.20mt | 1 | 0.7 |  | D8(1Pcs)
| 1.73 | 15.916 |  |  | 2.73 | -1.911
1 | 1 |  | D5(1Pc) | 1 | 1.2 |  | D11(1Pc)
| 1.13 | -1.13 |  |  | 2.73 | -3.276
1 | 1.25 |  | W9(1Pc) | 1 | 0.9 |  | D9(1Pcs)
| 0.6 | -0.75 |  |  | 2.73 | -2.457
4 | 0.6 |  | Handicape support | 1 | 1.3 |  | W4(1Pcs)
| 0.7 | 1.68 |  |  | 1.73 | -2.249
1 | 75.2 |  | Corridor | 1 | 18.74 |  | Medicine Store
| 3.06 | 230.112 | L=35.1*2+2.5*2=75.20mt |  | 3.06 | 57.3444 | L=4*2+5.37*2=18.74mt
15 | 0.9 |  | D9(15Pc) | 1 | 0.8 |  | D7(1Pcs)
| 2.73 | -36.855 |  |  | 2.73 | -2.184
2 | 1.4 |  | D1(4Pcs) | 1 | 0.9 |  | D9(1Pcs)
| 2.73 | -7.644 |  |  | 2.73 | -2.457
1 | 1.2 |  | D11(1Pc) | 1 | 1.5 |  | W2(1Pcs)
| 2.73 | -3.276 |  |  | 1.73 | -2.595
1 | 1 |  | D5(1Pc) | 1 | 15.2 |  | Waiting area
| 2.73 | -2.73 |  |  | 3.06 | 46.512 | L=4*2+3.60x2=15.20mt
1 | 2.3 |  | Opening | 1 | 2.3 |  | Opening
| 2.73 | -6.279 |  |  | 2.73 | -6.279
1 | 9.46 |  | Consultation | 1 | 1.5 |  | W2(1Pcs)
| 3.06 | 28.9476 | L=2.2*2+2.53*2=9.46mt |  | 1.73 | -2.595
1 | 0.9 |  | D9(1Pc) | 1 | 17.5 |  | Procedure room 1
| 2.73 | -2.457 |  |  | 3.06 | 53.55 | L=4*2+4.75*2=17.50mt
1 | 1.5 |  | W2(1Pcs) | 1 | 0.9 |  | D9(1Pcs)
| 1.73 | -2.595 |  |  | 2.73 | -2.457
1 | 8.36 |  | Cashier | 2 | 1.5 |  | W2(2Pcs)
| 3.06 | 25.5816 | L=1.65*2+2.53*2=8.36mt |  | 1.73 | -5.19
1 | 0.7 |  | D8(1Pc) | 1 | 15.1 |  | Procedure room 2
| 2.73 | -1.911 |  |  | 3.06 | 46.206 | L=4*2+3.55*2=15.10mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 0.9 |  | D9(1Pcs) | 1 | 4 |  | Injection room
| 2.73 | -2.457 |  |  | 2.25 | 9
1 | 1.5 |  | W2(2Pcs) | 2 | 4 |  | Examination Room 1&2
| 1.73 | -2.595 |  |  | 2.65 | 21.2
1 | 17.6 |  | Ophthalmology | 1 | 4 |  | Store
| 3.06 | 53.856 | L=4*2+4.80*2=17.60mt |  | 2.08 | 8.32
1 | 0.9 |  | D9(1Pcs) | 2 | 3.8 |  | Toilet
| 2.73 | -2.457 |  |  | 1.43 | 10.868
1 | 1.5 |  | W2(2Pcs) | 1 | 3.7 |  | Toilet
| 1.73 | -2.595 |  |  | 2.7 | 9.99
1 | 17.6 |  | Dental | 1 | 33.3 |  | Corridor
| 3.06 | 53.856 | L=4*2+4.80*2=17.60mt |  | 2.5 | 83.25
1 | 0.9 |  | D9(1Pcs) | 1 | 2.2 |  | Consultation
| 2.73 | -2.457 |  |  | 2.53 | 5.566
1 | 1.5 |  | W2(2Pcs) | 1 | 1.95 |  | Cashier
| 1.73 | -2.595 |  |  | 2.53 | 4.9335
24 | 0.2 |  | Column | 1 | 4 |  | Dispensary
| 2.73 | 13.104 |  |  | 3.8 | 15.2
2 | 35.1 |  |  | 1 | 4 |  | Medicine Store
| 0.3 | 21.06 | Top tie beam at y axis |  | 5.17 | 20.68
2 | 11.21 |  |  | 1 | 4 |  | Waiting area
| 0.3 | 6.726 | Top tie beam at x axis |  | 3.4 | 13.6
5 | 10.5 |  |  | 1 | 4 |  | Procedure room 1
| 0.8 | 42 | On Axis x2,x3,x4,x5 &x6 |  | 4.55 | 18.2
1 | 6.5 |  |  | 1 | 4 |  | Procedure room 2
| 0.8 | 5.2 |  |  | 3.35 | 13.4
|  | 1166.5914 | m2 before deduction | 1 | 4 |  | Ophthalmology
[5 empty] | 4.6 | 18.4
|  | 63.02 | DDT Ceramic wall tiles
|  |  |  | 1 | 4 |  | Dental
|  | 1103.5714 | m2 net area item 6.2 |  | 4.8 | 19.2
|  |  | 6.3)Chip wood ceiling | 1 | 4 |  | Examination Room 3
1 | 4 |  | ANG/PNC PMTCT ROOM |  | 2.85 | 11.4
| 4.47 | 17.88 |  |  |  | 339.4875 | m2 net area item 6.3
1 | 4 |  | Family planning
| 3 | 12
1 | 4 |  | Under 5 clinic
| 2.8 | 11.2
1 | 4 |  | EPI/Growth monitoring room
| 3.8 | 15.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.4)Approved 6mm thick ceramic wall tiles | 1 | 4 |  | Dispensary
|  |  | Toilet Male & female |  | 4 | 16
1 | 129
| 0.12 | 15.48 |  | 1 | 4 |  | Medicine Store
[5 empty] | 5.37 | 21.48
1 | 80
| 0.12 | 9.6 |  | 1 | 4 |  | Waitting area
[5 empty] | 3.6 | 14.4
1 | 80 |  | DDT
| 0.12 | 9.6 |  | 1 | 4 |  | Procedure room 1
[5 empty] | 4.75 | 19
1 | 136
| 0.12 | 16.32 |  | 1 | 4 |  | Procedure room 2
[5 empty] | 3.55 | 14.2
1 | 191
| 0.12 | 22.92 |  | 1 | 4 |  | Optitalmology
[5 empty] | 4.8 | 19.2
|  | 73.92 | m2 net area item 6.4
|  |  |  | 1 | 4 |  | Dental
|  |  | 6.5)Approved 9mm thick cearmic floor tile |  | 4.8 | 19.2
1 | 4 |  | ANG/PNC PMTCT ROOM
| 4.67 | 18.68 |  | 2 | 1.4 |  | D1(2Pcs)
[5 empty] | 0.2 | 0.56
1 | 4 |  | Family planning
| 3 | 12 |  | 1 | 1 |  | D5(1Pcs)
[5 empty] | 0.15 | 0.15
1 | 4 |  | Under 5 clinic
| 3 | 12 |  | 4 | 0.8 |  | D7(4Pcs)
[5 empty] | 0.15 | 0.48
1 | 4 |  | EPI/Growth monitoring room
| 4 | 16 |  | 5 | 0.7 |  | D8(5Pcs)
[5 empty] | 0.15 | 0.525
1 | 4 |  | Injection room
| 2.25 | 9 |  | 16 | 0.9 |  | D9(16Pcs)
[5 empty] | 0.15 | 2.16
3 | 4 |  | Examination Room 1,2&3
| 2.85 | 34.2 |  | 1 | 1.2 |  | D11(1Pcs)
[5 empty] | 0.15 | 0.18
1 | 4 |  | Store
| 2.08 | 8.32 |  | 1 | 2.3 |  | Waitting area
[5 empty] | 0.2 | 0.46
2 | 3.85 |  | Toilet
| 1.43 | 11.011 |  | 1 | 1.6
[5 empty] | 0.3 | 0.48
1 | 3.7 |  | Toilet
| 2.7 | 9.99 |  | 1 | 1.6
[5 empty] | 0.2 | 0.32
1 | 34.7 |  | Corridor | 2 | 0.2
| 2.5 | 86.75 |  |  | 0.3 | 0.12
[6 empty] | 357.3655 | m2 net area item 6.5
1 | 2.2 |  | Consuitation
| 2.53 | 5.566
1 | 1.95 |  | Cashier
| 2.53 | 4.9335
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.6)Approved ceramic skirting 10/0.9cm |  |  |  | 6.7)Approved type terrazzo w.sill
1 | 16.34 |  | ANG/PNC PMTCT ROOM | 14 | 1.5 |  | W2
|  | 16.34 | L=3.95*2+4.67*2-0.90=16.34mt |  |  | 21
1 | 13 |  | Family planning | 5 | 1.3 |  | W4
|  | 13 | L=3.95*2+3*2-0.90=13.00mt |  |  | 6.5
1 | 13 |  | Under 5 clinic | 2 | 1 |  | W
|  | 13 | L=3.95*2+3*2-0.90=13.00mt |  |  | 2
1 | 15 |  | EPI/Growth monitoring room |  |  | 29.5 | lm net length item 6.7
|  | 15 | L=3.95*2+4*2-0.90=15.00mt
6.9)10cm thick C-20 RC 1.2mt wide pavement
1 | 11.5 |  | Injection room | 2 | 37.5
|  | 11.5 | L=3.95*2+2.25*2-0.90=11.50mt |  | 1.2 | 90 | L=35.1+1.2x2=37.50mt
3 | 12.7 |  | Examination Room 1,2&3 | 2 | 11.21
|  | 38.1 | L=3.95*2+2.85*2-0.90=12.70mt |  | 1.2 | 26.904 | L=11.21mt
1 | 11.26 |  | Store |  |  | 116.904 | me net area item 6.9
|  | 11.26 | L=3.95*2+2.08*2-0.80=11.26mt
6.10)Half Concrete pipe ditch
2 | 3.56 |  | Toilet | 2 | 38.3 |  | L=35.1+1.2X2+0.4x2=38.30mt
|  | 7.12 | L=1.20*2+1.43*2-0.80-0.90=3.56mt |  |  | 76.6
1 | 56.5 |  | Corridor | 2 | 14.71 |  | L=11.21+1.2X2=13.61mt
|  | 56.5 | L=35.1*2+2.5*4-2.30-15*0.9-3*1.4-2*1.2=56.50mt |  |  | 29.42
1 | 8.56 |  | Consultation | 1 | 1.6 |  | Slab Covered dicth
|  | 8.56 | L=2.20*2+2.53*2-0.9=8.56mt |  |  | -1.6 | L=2.80x2+1.50x2=8.60mt
1 | 8.26 |  | Cashier |  |  | 104.42 | lm net length item 6.10
|  | 8.26 | L=1.95*2+2.53*2-0.7=8.26mt
6.12)Constructe 10/40 cm curb stone
1 | 12.4 |  | Dispensary | 2 | 38.6 |  | L=35.1+1.2X2+0.3x2+0.15x2+0.1x2=38.60mt
|  | 12.4 | L=4*4-0.7-0.8-0.9-1.2=12.40mt |  |  | 77.2
1 | 17.04 |  | Medicine Store | 2 | 14.71 |  | L=11.20+1.2X2+0.15x2+0.3x2=14.50mt
|  | 17.04 | L=4*2+5.37*2-0.8-0.9=17.04mt |  |  | 29.42
1 | 13.3 |  | Waiting area | 1 | 1.6 |  | UnCovered walk way
|  | 13.3 | L=4*2+1.30+0.4+3.60=13.30mt |  |  | -1.6
1 | 16.6 |  | Procedure room 1 |  |  | 105.02 | lm net length item 6.12
|  | 16.6 | L=4*2+4.75*2-0.9=16.60mt
7)Painting
1 | 14.2 |  | Procedure room 2 |  |  |  | 7.1)Int. plastered surface & ext beam & colun
|  | 14.2 | L=4*2+3.55*2-0.9=1420mt
[6 empty] | 1103.5714 | m2 net area item 7.1
1 | 16.7 |  | Ophthalmology
|  | 16.7 | L=4*2+4.80*2-0.9=16.70mt |  |  |  | 7.2)Chip wood ceiling surface
[6 empty] | 339.4875 | m2 net area item 7.2
1 | 16.7 |  | Dental
|  | 16.7 | L=4*2+4.80*2=17.60mt |  |  |  | 7.3)External rendered surface
[6 empty] | 211.6496 | m2 net area item 7.3
|  | 305.58 | lm net length item 6.6
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 9)SANITARY INSTALLATION |  |  |  | 4.)Socket outlet point
|  |  | 9.1)Supplay & install PP-R water pipe |  |  |  | 4.01)Socket outlet point 3x2.5mm2
|  |  | Internal ф 15mm | 32 | 1
1 | 9.65 |  |  |  |  | 32 | pcs net number item 4.01
|  | 9.65 | lm net length item 9.1.a
5)Socket outlets
|  |  | Internal ф 25mm |  |  |  | 5.01)Socket outlets LEGRAND SUNO
1 | 3.8 |  |  | 32 | 1
|  | 3.8 | lm net length item 9.1.b |  |  | 32 | pcs net number item 5.01
|  |  | Internal ф 32mm |  |  |  | 6)Telephone/data point
1 | 8 | [5 empty] | 6.01)Telephone pt feed through cat 5E UTP Cable
|  | 8 | lm net length item 9.1.c | 14 | 1
[6 empty] | 14 | pcs net number item 6.01
50mm dia. Internal
1 | 6.55 |  | Toilet (M) & (F) |  |  |  | 7. Type of light fittings
|  | 6.55 | lm net length item 9.1.d |  |  |  | 7.01)Philips TCS 098/236/2xTL-D 36W
|  |  |  | 30 | 1
|  |  | 9.5)Supply & install waste water pipe |  |  | 30 | pcs net number item 7.01
ф 50mm
1 | 22.31 |  | L=(7x1.4)+(3x0.9)+8.04+1.77=22.31mt |  |  |  | 7.02)Philips TCS 098/136/1xTL-D 36W
|  | 22.31 | lm net length item 9.5.a | 20 | 1
[6 empty] | 20 | pcs net number item 7.02
ф 75mm
1 | 7.9 | [5 empty] | 7.03)RZB 59251.002Q/E27/60W
|  | 7.9 | lm net length item 9.5.b | 7 | 1
[6 empty] | 7 | pcs net number item 7.03
ф 100mm
1 | 11.6 | [5 empty] | 7.04)RZB 59222.002Q/E27/60W
|  | 11.6 | lm net length item 9.5.c | 5 | 1
[6 empty] | 5 | pcs net number item 7.04
9.9)Supply & fix toilet paper holder
1 | 2 | [5 empty] | 8)TV POINTS
|  | 2 | pcs net number item 9.9 |  |  |  | 8.01)TV pt fed through RG6 Coaxial 75ohm Tv cable
|  |  |  | 1 | 1
|  |  | 10. Electrical Installations |  |  | 1 | pcs net number item 8.01
2.00)LIGHT POINT
|  |  | 2.01)points conduti of 16mm 3*2.5mm2 |  |  |  | 10.00. Cable way and Manhole
1 | 60 | [5 empty] | 10.03. Riged pvc Dia. 50mm telephone frame
|  | 60 | pcs net number item 2.01 | 1 | 5.25
[6 empty] | 5.25 | lm net length item 10.3
3.00)SWITCH
3.01)Single Switch legrand
1 | 15
|  | 15 | pcs net number item 3.01
3.02)Double Switch legrand
1 | 19
|  | 19 | pcs net number item 3.02
3.03)Two way Switch legrand
4 | 1
|  | 4 | pcs net number item 3.03

## OPD Bar
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [8 empty] | Date: - | 2016-02-23
CONTRACTOR:-Trust Construction | [9 empty] | Block : OPD
CLIENT:-ANRS Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB-1 ,2 | 14 | 11.88 | 4 | 3 | 12 | - | - | - | - | 142.56
| " | " | 14 | 10.6 | 4 | 3 | 12 | - | - | - | - | 127.2
| " | " | 14 | 7.98 | 4 | 3 | 12 | - | - | - | - | 95.76
| " | " | 14 | 7.17 | 4 | 3 | 12 | - | - | - | - | 86.04
| " | " | 14 | 10.1 | 4 | 3 | 12 | - | - | - | - | 121.2
| " | " | 14 | 10.6 | 4 | 3 | 12 | - | - | - | - | 127.2
| " | " | 14 | 7.37 | 4 | 3 | 12 | - | - | - | - | 88.44
| " | " | 14 | 9.2 | 4 | 3 | 12 | - | - | - | - | 110.4
| " | st | 8 | 1.2 | 4 | 176 | 704 | - | 844.8 | - | - | -
| " | GB-3,4 | 14 | 11.95 | 8 | 3 | 24 | - | - | - | - | 286.8
| " | " | 14 | 11.25 | 8 | 3 | 24 | - | - | - | - | 270
| " | st | 8 | 1.2 | 8 | 62 | 496 | - | 595.2 | - | - | -
TOTAL LENGTH | [8 empty] | 1440 | 0 | 0 | 1455.6
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 568.8 | 0 | 0 | 1761.276
Slab Mesh
1 | (x/01-x/02) & (x/03-x/04) |  | 8 | 3.63 | 2 | 21 | 42 |  | 152.46
| (y/01 - y/02) |  | 8 | 3.87 | 2 | 19 | 38 |  | 147.06
2 | (x/01-x/02) & (x/03-x/04) |  | 8 | 4.67 | 10 | 20 | 200 |  | 934
| (y/02 - y/07) |  | 8 | 3.87 | 10 | 24 | 240 |  | 928.8
3 | (x/01-x/02) & (x/03-x/04) |  | 8 | 5.67 | 2 | 20 | 40 |  | 226.8
| (y/07 - y/08) |  | 8 | 3.87 | 2 | 29 | 58 |  | 224.46
4 | (x/02-x/03) (y/01 - y/02) |  | 8 | 3.57 | 1 | 12 | 12 |  | 42.84
|  |  | 8 | 2.27 | 1 | 19 | 19 |  | 43.13
5 | (x/02-x/03) (y/02 - y/07) |  | 8 | 4.75 | 5 | 21 | 105 |  | 498.75
|  |  | 8 | 2.27 | 5 | 24 | 120 |  | 272.4
6 | (x/02-x/03) (y/07 - y/08) |  | 8 | 5.67 | 1 | 12 | 12 |  | 68.04
|  |  | 8 | 2.27 | 1 | 29 | 29 |  | 65.83
TOTAL LENGTH | [8 empty] | 3604.57 | 0 | 0 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 1423.8052 | 0 | 0 | 0
1 | COLUMN (C1) |  | 12 | 3.63 | 32 | 4 | 128 |  |  |  | 464.64
|  |  | 8 | 0.7 | 32 | 14 | 448 |  | 313.6
2 | TOP TIE BEAM
| TTB1 |  | 12 | 11.78 | 2 | 3 | 6 |  |  |  | 70.68
|  |  | 12 | 10.6 | 2 | 3 | 6 |  |  |  | 63.6
|  |  | 12 | 7.98 | 2 | 3 | 6 |  |  |  | 47.88
|  |  | 12 | 7.07 | 2 | 4 | 8 |  |  |  | 56.56
|  |  | 12 | 10.1 | 2 | 3 | 6 |  |  |  | 60.6
|  |  | 12 | 10.6 | 2 | 3 | 6 |  |  |  | 63.6
|  |  | 12 | 7.37 | 2 | 3 | 6 |  |  |  | 44.22
|  |  | 12 | 9.2 | 2 | 3 | 6 |  |  |  | 55.2
|  |  | 8 | 0.9 | 2 | 175 | 350 |  | 315
| TTB2 |  | 12 | 11.78 | 2 | 3 | 6 |  |  |  | 70.68
|  |  | 12 | 10.6 | 2 | 3 | 6 |  |  |  | 63.6
|  |  | 12 | 7.98 | 2 | 3 | 6 |  |  |  | 47.88
|  |  | 12 | 7.07 | 2 | 4 | 8 |  |  |  | 56.56
|  |  | 12 | 10.1 | 2 | 3 | 6 |  |  |  | 60.6
|  |  | 12 | 10.6 | 2 | 3 | 6 |  |  |  | 63.6
|  |  | 12 | 7.37 | 2 | 3 | 6 |  |  |  | 44.22
|  |  | 12 | 9.2 | 2 | 3 | 6 |  |  |  | 55.2
|  |  | 8 | 0.9 | 2 | 175 | 350 |  | 315
| TTB3 |  | 12 | 11.75 | 2 | 3 | 6 |  |  |  | 70.5
|  |  | 12 | 11.25 | 2 | 3 | 6 |  |  |  | 67.5
|  |  | 8 | 0.9 | 2 | 55 | 110 |  | 99
| TTB4 |  | 12 | 11.75 | 6 | 3 | 18 |  |  |  | 211.5
|  |  | 12 | 11.25 | 6 | 3 | 18 |  |  |  | 202.5
|  |  | 8 | 0.9 | 6 | 55 | 330 |  | 297
TOTAL LENGTH | [8 empty] | 1339.6 | 0 | 1941.32 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 |  | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 529.142 | 0 | 1723.8922 | 0
Lintel
|  |  | 12 | 1.45 | 3 | 2 | 6 |  |  |  | 8.7
| D7 |  | 12 | 1.15 | 3 | 2 | 6 | - | - | - | 6.9 | -
| Stirrups |  | 8 | 0.6 | 3 | 7 | 21 | - | 12.6 | - | - | -
|  |  | 12 | 2.2 | 2 | 2 | 4 |  |  |  | 8.8
| On top of D8 |  | 12 | 1.9 | 2 | 2 | 4 | - | - | - | 7.6 | -
| Stirrups |  | 8 | 0.6 | 2 | 11 | 22 | - | 13.2 | - | - | -
|  |  | 12 | 1.35 | 1 | 2 | 2 | - | - | - | 2.7 | -
| Ditto on D8 |  | 12 | 1.05 | 1 | 2 | 2 | - | - | - | 2.1 | -
| Stirrups |  | 8 | 0.6 | 1 | 5 | 5 | - | 3 | - | - | -
|  |  | 12 | 1.35 | 1 | 2 | 2 |  | - |  | 2.7 | -
| D9 |  | 12 | 1.25 | 1 | 2 | 2 |  | - |  | 2.5 | -
|  |  | 8 | 0.7 | 1 | 7 | 7 |  | 4.9 |  | - | -
|  |  | 12 | 1.95 | 1 | 2 | 2 |  | - |  | 3.9 | -
| W9 |  | 12 | 1.65 | 1 | 2 | 2 |  | - |  | 3.3 | -
|  |  | 8 | 0.5 | 1 | 9 | 9 |  | 4.5 |  | - | -
-
TOTAL LENGTH | [8 empty] | 38.2 | 0 | 49.2 | 0
UINT WEIGHT in KG/ML | [8 empty] | 0.395 | 0.617 | 0.888 | 1.21
TOTAL WEIGHT IN KG | [8 empty] | 15.089 | 0 | 43.6896 | 0

## Staff + SQ Sum
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-Staff Resiedence & Service Quarter
Details of Works executed
Bill No. | Description |  | Sub Total Birr |  | Total Birr
|  |  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  |  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work |  | 167108 | 48734.3916 | 167108 | 48734.3916
2 | Concrete Work |  | 275946 | 175524.8688 | 275946 | 175524.8688
3 | Masonry work |  | 149210 | 77834.9 | 149210 | 77834.9
| sub total A |  | 592264 | 302094.1604 | 592264 | 302094.1604
B. Super Structure
1 | Concrete Work |  | 106795 | 96769.5695 | 106795 | 96769.5695
2 | Block work |  | 166150 | 137962.26 | 166150 | 137962.26
3 | Roofing |  | 101302 | 90833.6 | 101302 | 90833.6
4 | Carpentry & Joinery |  | 61375 | 26291.34 | 61375 | 26291.34
5 | Metal work |  | 78602 | 44325 | 78602 | 44325
6 | Finishing |  | 394550 | 235306.532 | 394550 | 235306.532
7 | Painting |  | 32116 | 10310.2496 | 32116 | 10310.2496
8 | Glazing |  | 10710 | 0 | 10710 | 0
9 | Sanitory Installation |  | 46075 | 4132.64 | 46075 | 4132.64
10 | Electrical Installation |  | 76835.56 | 31680 | 76835.56 | 31680
| sub total B |  | 1074510.56 | 677611.1911 | 1074510.56 | 677611.1911
| Total A+B |  | 1666774.56 | 979705.3515 | 1666774.56 | 979705.3515
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  | Suppervisor :- ______________ |  |  | Consultant:- _____________

## Staff + SQ Measu.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise |  |  |  |  | Block : Staff Residence & SQ
CONTRACTOR:-Trust Construction
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 191 | 8 | 1528 | 266 | 2128
1.2 | Bulk excavation in ordinary | m3 | 206 | 70 | 14420 | 5.554 | 388.78
1.3 | Ditto but exceeding 1.5 m but less than 2 m | m3 | 69 | 70 | 4830 | 79.989 | 5599.23
1.4 | Selected borrowed fill brought from out side | m3 | 275 | 56 | 15400 | 123.8496 | 6935.5776
1.5 | Cart away surplus excavated material to an | m3 | 332.3 | 70 | 23261 | 111.2972 | 7790.804
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 97 | 200 | 19400 | 129.46 | 25892
Total to summary ………Birr |  |  |  |  | 78839 |  | 48734.3916
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 42 | 150 | 6300 | 55.1 | 8265
2.2 | Ditto but under footing pad | m2 | 15 | 150 | 2250 |  | 0
2.2 | 10cm thick reinforced concrete floor slab class c-20 | m2 | 97 | 400 | 38800 | 129.46 | 51784
2.3 | In grade beam & steps | m3 | 11 | 3200 | 35200 | 12.1 | 38720
2.4 | In footing pad | m3 | 3.2 | 3200 | 10240 |  | 0
2.5 | In footing coloumn | m3 | 2.4 | 3200 | 7680 |  | 0
Provide cut and fix in position swan zigba woodform work
2.4 | Grade beam | m2 | 45 | 120 | 5400 | 60.97 | 7316.4
2.7 | In footing pad | m2 | 12 | 120 | 1440 |  | 0
2.8 | In footing coloumn | m2 | 50 | 120 | 6000 |  | 0
2.5 | Steps | m2 | 4 | 150 | 600 |  | 0
price includes cutting, bending, placing in
position and tying wires.
2.6 | Dia 14 mm deformed bar | kg | cp | 36 |  | 920.8584 | 33150.9024
2.6 | Dia. 12mm deformed bar | kg | 435 | 36 | 15660 |  | 0
2.7 | Dia 8 mm deformed bar | kg | 745 | 36 | 26820 | 913.6824 | 32892.5664
2.8 | Dia 6 mm plain bar | kg | 5 | 36 | 180 |  | 0
2.9 | 10/2 cm chip wood expansion joint between | m | 300 | 30 | 9000 | 113.2 | 3396
Total to summary ………Birr |  |  |  |  | 165570 |  | 175524.8688
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 52 | 1250 | 65000 | 29.194 | 36492.5
3.2 | Ditto but well dressed stone above natural ground level | m3 | 26 | 1450 | 37700 | 28.512 | 41342.4
Total to summary ………Birr |  |  |  |  | 102700 |  | 77834.9
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 2.3 | 3200 | 7360 | 2.184 | 6988.8
1.2 | In beams | m3 | 3.6 | 3200 | 11520 | 7.74 | 24768
1.3 | Lintel | m3 | 0.6 | 3200 | 1920 |  | 0
| Provide cut and fix in position swan zigzag wood form work |  |  |  | 0 |  | 0
1.3 | Elevation column | m2 | 38 | 130 | 4940 | 43.68 | 5678.4
1.4 | Beam | m2 | 60 | 130 | 7800 | 92.44 | 12017.2
1.6 | Lintel | m2 | 1.5 | 130 | 195 |  | 0
Reinforcement steel bar according to St.drawing
1.5 | Dia 14mm deformed bar | kg | cp | 36
1.6 | Dia 12mm deformed bar | kg | 714 | 36 | 25704 | 996.9043 | 35888.5555
1.7 | Dia 8mm deformed bar | kg | 250 | 36 | 9000 | 317.4615 | 11428.614
1.8 | Dia 6 mm plain bar | kg
Total to summary ………Birr |  |  |  |  | 68439 |  | 96769.5695
2. BLOCK WORK
2.1 | 20cm thick | m2 | 305 | 350 | 106750 | 267.1068 | 93487.38
2.2 | 15cm thick | m2 | 66 | 400 | 26400 | 111.1872 | 44474.88
Total to summary ………Birr |  |  |  |  | 133150 |  | 137962.26
3.ROOFING
3.1 | G - 28 Roof covering in galvanized corrugated | m2 | 162 | 360 | 58320 | 215.36 | 77529.6
3.2 | G - 28ribbed sheet ceiling under eave | m2 | 16 | 160 | 2560 | 44 | 7040
3.3 | Supply and fix G-28 flat metal sheet gutter | m | 34 | 120 | 4080 | 52.2 | 6264
3.4 | Supply and fix 110 mm diameter PVC down | m | 48 | 110 | 5280 |  | 0
3.5 | Flushing in flat metal sheet fixed as shown | m | 20 |  | 0 | 43.2 | 0
Total to summary ………Birr |  |  |  |  | 70240 |  | 90833.6
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 232 | 23 | 5336 | 364.5 | 8383.5
4.2 | Diagonal & vertical members size-dia. 8 - 10 cm | m | 185 | 16 | 2960 | 298.5 | 4776
4.3 | Purlin zigba size 5/7cm | m | 210 | 33 | 6930 | 229.6 | 7576.8
4.4 | Ziba wooden fascia board price includes three coats | m | 70 | 71 | 4970 | 78.24 | 5555.04
Total to summary ………Birr |  |  |  |  | 20196 |  | 26291.34
5. METAL WORK
Windows
5.1 | Type W2 size - 150/173 cm, | Nº | 4 | 3892.5 | 15570 | 4 | 15570
5.2 | Type W7 size - 180/173 cm, | Nº | 4 | 4671 | 18684 | 3 | 14013
5.3 | Type TW size 90/60 cm | Nº | 4 | 810 | 3240 |  | 0
5.4 | Type W size 100/173 cm |  |  | 2595 | 0 |  | 0
| Doors | Nº | 4 |  |  |  | 0
5.5 | Type D6 size 90/275 cm | Nº | 4 | 3685.5 | 14742 | 4 | 14742
Total to summary ………Birr |  |  |  |  | 52236 |  | 44325
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 105 | 140 | 14700 | 223.448 | 31282.72
6.2 | Apply three coats of plastering to internal walls & | m2 | 610 | 150 | 91500 | 412.1444 | 61821.66
6.4 | Chip wood ceiling nailed on & including | m2 | 97 | 310 | 30070 | 137.2104 | 42535.224
6.6 | Approved type 6mm thick glazed ceramic wall tile | m2 | 45 | 370 | 16650 |  | 0
6.12 | Approv type 9mm thick non slippery ceramic tile floor | m2 | 97 | 320 | 31040 | 137.8904 | 44124.928
6.13 | Approved type Ceramic tile skirting | m | 45 | 100 | 4500 | 121.04 | 12104
6.16 | Approved type Terrazo window cill size 27/3cm | m | 23 | 150 | 3450 | 21.2 | 3180
6.17 | Thread size -30/3cm | m | 5 |  | 0 |  | 0
6.18 | Riser size 15/2cm | m | 5 |  | 0 |  | 0
6.21 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 66 | 550 | 36300 | 62.36 | 34298
6.21 | lay storm water concrete pipes of half diameter 30cm | ml | 64 | 100 | 6400 | 59.6 | 5960
6.21 | Construction of 10x40 cm curb stone | ml | 64 | 265 | 16960 |  | 0
Total to summary ………Birr |  |  |  |  | 251570 |  | 235306.532
7. PAINTING
7.1 | External rendered surface | m2 | 105 | 18.6667 | 1960 | 223.448 | 4171.0293
7.1 | Internal plastered surfaceand external beams& | m2 | 610 | 18.6667 | 11386.6667 | 237.0364 | 4424.6795
7.3 | Chip wood ceiling surface | m2 | 97 | 18.6667 | 1810.6667 | 91.8504 | 1714.5408
Total to summary ………Birr |  |  |  |  | 15157.3333 |  | 10310.2496
9. SANITARY INSTALLATION
9.1 | Supply & install PP-R water pipes for water
| 15mm diameter ;internal | LM | 90 | 40 | 3600 |  | 0
| 20mm diameter ;internal | LM | 20 | 50 | 1000 |  | 0
| 50mm diameter of min. wall thickness=2mm | LM | 15 | 6 | 90 | 9.44 | 56.64
| 75mm diameter of min. wall thickness=3mm | LM | 6 | 95 | 570 | 30.8 | 2926
| 100 mm diameter of min. wall thickness=3.2mm | LM | 10 | 125 | 1250 | 9.2 | 1150
Total to summary ………Birr |  |  |  |  | 6510 |  | 4132.64
10. ELECTRICALL INSTALLATION
4 | Light points
4.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 24 | 400 | 9600 | 36 | 14400
5 | Switches
5.01 | single(774001+774041) | PCs | 12 | 60 | 720 | 8 | 480
5.02 | Two-Way(774006+774041) | " | 16 | 60 | 960 | 16 | 960
5.03 | Intermediate(774007+774041) | " | 4 | 60 | 240 | 4 | 240
6 | Socket outlet points
6.01 | Socket outlet points in regid thermoplastic conduit | PCs | 16 | 260 | 4160 | 4 | 1040
6.02 | Ditto as above but for water Heater points | PCs | 4 | 280 | 1120 |  | 0
6.05 | Ditto as 4.04 above but 3x4mm2 in pvc pipe | PCs | 8 | 750 | 6000 |  | 0
7 | Socket outlets
7.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 16 | 40 | 640 | 24 | 960
7.02 | weather proof socket Legrand Suno 774022+774041 | PCs | 4 | 100 | 400 |  | 0
7.03 | Ditto as above 4.06 but for 25A/1ph for kitchen | PCs | 4 | 220 | 880 |  | 0
8 | Low Voltage Earthing system
8.01 | Copper Earthing rod of 16x2400mm to be driven | PCs | 4 | 3000 | 12000 | 4 | 12000
8.02 | Copper conductor of 1x6.0mm2 for Earthing | Ml | 24 | 80 | 1920 |  | 0
9 | Telephone/Data points
9.01 | Telephone points fed through cat 5E UTP cable | PCs | 4 | 400 | 1600 | 4 | 1600
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 4 | 300 | 1200 |  | 0
8 | TV points |  |  |  | 0 |  | 0
8.01 | TV points fed through RG6 Coaxial 75ohm TV | PCs | 4 | 600 | 2400 |  | 0
8.02 | Flush mounted TV outlets type Legrand Suno | PCs | 4 | 550 | 2200 |  | 0
Total to summary ………Birr |  |  |  |  | 46040 |  | 31680

## Staff TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Staff Residence
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | B-backfill and compaction in side masonary
|  |  | 1) EXCAVATION & EARTH WORK |  |  |  | along x-axis
|  |  | 1.1 Clear off site to remove top soil | 4 | 15 |  | L=17.5-0.25-0.25-0.8-(3*0.4)=15
1 | 19 |  | L=17+1.0+1.0=19 |  | 0.25 |  | W=0.15 ,d=.7
| 9 | 171 | W=7+1.0+1.0=9 |  | 0.7 | 10.5
|  | 171 | m2 Total to item 1.1 | 10 | 5.9 |  | along y-axis
[5 empty] | 0.25 |  | L=7.5-0.25-0.25-0.8-(2*0.15)=5.9
|  |  | 1.2 Bulk Excavation in ordinary soil |  | 0.7 | 10.325 | W=0.15 ,d=.7
1 | 15.7 |  | L=17.5-0.25-0.25-0.4-0.4-0.5=15.7
| 5.7 |  | W=7.5-0.25-0.25-0.4-0.4-0.5=5.7 |  |  | 93.6458 | total insitu fill
0.1
|  | 8.949 |  |  |  |  | 1.4 Cart away excavated material
|  |  |  | 1 | 19
|  |  | DEDUCTION |  | 9
2 | 15.7 |  | along x-axis |  | 0.3 | 51.3 | from item no 1.1
| 0.7 |  | L=17.5-0.25-0.25-0.4-0.4-0.5=15.7
| 0.1 | 2.198 |  |  |  | 5.554 | from item no 1.2
3 | 5.7 |  | along y-axis |  |  | 40.005 | from item no 1.3
| 0.7 |  | W=7.5-0.25-0.25-0.4-0.4-0.5=5.7
| 0.1 | 1.197 |  |  |  | 93.6458 | DEDUCTION
|  | 5.554 | m3 Total to item 1.2 |  |  | 3.2132 | m3 Total to item 1.4
|  |  | 1.3 Ditto to Item 1.2 but Trench |  |  |  | 1.6) 25cm thick basaltic stone hard core
|  |  |  | 4 | 6.3
2 | 17.5 |  | along x-axis |  | 3.95
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=17.5 d=.7 |  |  | 99.54 | m2 Total to item 1.5
| 0.7 | 22.05
2. Concrete Work
2.1-.Lean Concrete, C-7
5 | 5.7 |  | along y-axis |  |  |  | Under masonry grade beam
| 0.9 |  | L=7.5-(2*.9)=5.7 | 2 | 17 |  | axis x01 & x02/Y01-Y05
| 0.7 | 17.955 | W=0.4+0.25+0.25=0.90, d= |  | 0.5 | 17 | L=17.10m W=0.50m
|  | 40.005 | m3 Total to item 1.3 | 5 | 6.2 |  | axis Y01-Y05/X01-X02
[5 empty] | 0.5 | 15.5 | L=6.60m W=0.50m
1.3 Selected Fill
|  |  | A-bulk fill and compaction | 10 | 0.5
1 | 16.2 |  | L=17.5-0.5-0.8=16.2 |  | 0.6 | 3
| 6.2 |  | W=7.5-0.5-0.8=6.2
| 0.78 | 78.3432 |  |  |  | 35.5 | m2 net area item 2.1
3 | 5.9 | [5 empty] | 2.2,10cmthick RC ground slab
| 0.4 |  |  | 4 | 6.3 |  | The same as item No 1.6
| 0.78 | 5.5224 | deduct |  | 3.95
[6 empty] | 99.54 | m2 total area item 2.2
|  | 83.8656 | m3 net volume item 1.3
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.3 (C-25) IN GRADE BEAM | 5 | 6.4 |  | axis y
2 | 17 |  | axis x01 & x02/Y01-Y05 |  | 0.4 |  | L=7.5-.3-.8=6.4
| 0.25 |  | L=17.00m W=0.25 |  | 0.78 | 9.984
| 0.4 | 3.4 | D=0.4
[6 empty] | 20.592 | m3 net volume item 3.1
5 | 6.9 |  | axis Y01 - Y05/X01-X02
| 0.25 |  | L=5.70m W=0.25m D=0.40m |  |  |  | 3.2 masonary work above NGL
| 0.4 | 3.45 |  | 2 | 17 |  | on axis x L=17
0.4
10 | 0.6 |  |  |  | 0.57 | 7.752
0.4
| 0.25 | 0.6 |  |  |  |  | on axis y L=6.4m
|  |  |  | 5 | 6.4
|  | 7.45 | m3 net volume item 2.3 |  | 0.4
[5 empty] | 0.57 | 7.296
Form work
|  |  | 2.4 Grade beam |  |  | 15.048 | m3 net volume item 3.2
2 | 8
| 0.4 | 6.4 |  |  |  |  | B.SUPER STRUCTURE
1.CONCRETE WORK
8 | 6.4 |  |  | 10 | 0.2 |  | 1.1)In elevation column
| 0.4 | 20.48 |  |  | 0.2
2.73
16 | 0.6 |  |  |  |  | 1.092 | m3 net volume item 1.1
| 0.4 | 3.84
1.2)In beam & step
|  |  |  | 2 | 17 |  | TTB1=2Pcs
16 | 4 |  |  |  | 0.3 |  | Axis x/01 & x/02 from (y/01 - y/05)
| 0.4 | 25.6 |  |  | 0.2 | 2.04
|  | 56.32 | m2 net area item 2.4 | 5 | 7 |  | TTB2=5Pcs
[5 empty] | 0.3 |  | Axis Y/01 - Y/05 from ( X/01 - X/02)
|  |  | Reinforcement steel bar |  | 0.2 | 2.1
1 | 536.6592 |  | 2.6. Dia 14mm
|  | 536.6592 | kg net weight item 2.6 |  |  | 4.14 | m3 net volume item 1.2
1 | 628.524 |  | 2.7. Dia 8mm |  |  |  | FORM WORK
|  | 628.524 | kg net weight item 2.7 |  |  |  | 1.3)Elevation column
|  |  |  | 10 | 0.8 |  | C1=20Pcs
|  |  | 2.9)10/2cm expantion joint |  | 2.73
2 | 16.75 |  |  |  |  | 21.84 | m2 net area item 1.3
33.5
1.4)Beam
8 | 5.775 | [5 empty] | TTB1=2Pcs
|  | 46.2 |  | 2 | 16 |  | Axis x/01 & x/02 from (y/01 - y/05)
[5 empty] | 0.8 | 25.6 | Dev.L=0.30*2+0.20=0.80mt
|  | 79.7 | ml net area item 2.9
|  |  |  | 14 | 0.3
|  |  | 3.1 Trychltic stone masonry below NGL |  | 0.2 | 1.2
2 | 17 |  | axis x
| 0.4 |  | L=17 | 5 | 7 |  | TTB2=5Pcs
| 0.78 | 10.608 |  |  | 0.8 | 28 | Axis Y/01 - Y/05 from ( X/01 - X/02)
[6 empty] | 54.8 | m2 net area item 1.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1.6) ф12 mm deformed bars |  |  |  | 3)ROOFING WORK
1 | 584.233 | [5 empty] | 3.1)G-28 CIS Roof covering
|  | 584.233 | kg net weight item 1.6 | 1 | 8.6 |  | W=7.4+0.60X2=8.60mtL=17mt
17
|  |  | 1.7) ф8mm deformed bars |  |  | 146.2 | m2 net area item 3.1
1 | 189.6
|  | 189.6 | kg net weight item 1.7 |  |  |  | 3.2)G-28 Ribbed sheet ceiling
|  |  |  | 2 | 16
|  |  | 2)BLOCK WORK |  | 0.6 | 19.2
2.1)20cm thick HCB wall
5 | 7 |  | Axis Y/01 - Y/05 from (X/01 - X/02) | 2 | 17
| 2.73 | 95.55 |  |  | 0.5 | 17
2 | 16 |  | Axis X/01 - X/02 from (Y/01 - Y/05) |  |  | 36.2 | m2 net area item 3.2
| 2.73 | 87.36
3.3)Supply & fix G-28 gutter dev.
4 | 1.78 |  | W7 | 2 | 17
| 1.68 | -11.9616 |  |  |  | 34 | ml net arae item 3.3
4 | 0.9 |  | W10 |  |  |  | 3.4)Flashing metal sheet.
| 1.12 | -4.032 |  | 4 | 4.4
[6 empty] | 17.6 | ml net arae item 3.4
4 | 0.88 |  | W11
| 1.68 | -5.9136 |  |  |  |  | 4)CARPENTRY
4.1)Uper & lower chord
8 | 0.9 |  | D6 | 15 | 8.8 |  | Upper =2x4.40=8.80mt
| 2.73 | -19.656 |  |  |  | 132
2 | 17 |  | Above top tie beam | 15 | 8.2 |  | Lower =2x4.1=8.20mt
| 0.2 | 6.8 | Axis X/01 & X/02 from (Y/01 - Y/05) |  |  | 123 | TOTAL=255.00ml
2 | 7.4 |  | Axis Y/01 & Y/05 from (X/01 - X/02) |  |  | 255 | ml net arae item 4.1
| 0.9 | 13.32 | Above top tie beam
4.2)Vertical & Diagonal member
|  | 161.4668 | m2 net area item 2.1 | 15 | 5.98 |  | V= 5.98mt
89.7
2.2)15cm thick HCB wall
4 | 4 |  |  | 15 | 8.84 |  | D=8.84
| 3.06 | 48.96 |  |  |  | 132.6
4 | 1 |  | Opening |  |  | 222.3 | ml net arae item 4.2
| 2.73 | -10.92
4.3)Purlin zigba 5/7cm
4 | 3.6 |  |  | 12 | 17
| 3.06 | 44.064 |  |  |  | 204 | ml net arae item 4.3
4 | 0.8 |  | D4 |  |  |  | 4.4)Zigba wooden fascia board
| 2.73 | -8.736 |  | 2 | 17
34
4 | 1.93
| 3.06 | 23.6232 |  | 4 | 4.66 |  | 52.64
[6 empty] | 18.64 | TOTAL=52.64ml
4 | 0.8 |  | D5
| 2.73 | -8.736 |  |  |  | 52.64 | ml net arae item 4.4
|  | 88.2552 | m2 net area item 2.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 5)METAL WORK | 12 | 0.8 |  | D4,D5 & D6
|  |  | 5.1)Type W7 ,Size 178/168 |  | 2.73 | -26.208
4 | 1
|  | 3 | pcs net number item 5.1 | 4 | 0.9
[5 empty] | 2.73 | -9.828
5.5.Type D6 size 90/275 cm
4 | 1 |  |  | 4 | 1 |  | Opening
|  | 4 | pcs net number item 5.2 |  | 2.73 | -10.92
|  |  | 6)FINISHING | 14 | 2.73 |  | Column
|  |  | 6.1)Apply two coats of plastering & one coat rendering |  | 0.2 | 7.644
2 | 7 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
| 2.73 | 38.22 |  | 2 | 7.4 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
[5 empty] | 0.4 | 5.92 | Grade beam
16 | 0.6
| 2.73 | 26.208 |  | 2 | 7.4 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
[5 empty] | 0.3 | 4.44 | Top tie beam
2 | 16 |  | Axis X/01 & X/02 from (Y/01 - Y/05)
| 2.73 | 87.36 |  | 2 | 17 |  | Axis X/01 & X/02 from (Y/01 - Y/05)
[5 empty] | 0.4 | 13.6
4 | 1.8 |  | W7
| 1.68 | -12.096 |  | 2 | 17 |  | Axis X/01 & X/02 from (Y/01 - Y/05)
[5 empty] | 0.3 | 10.2
4 | 0.9 |  | W10
| 0.6 | -2.16 |  | 16 | 0.6 |  | grade beam
[5 empty] | 0.4 | 3.84
4 | 0.9 |  | W11
| 1.73 | -6.228 |  | 10 | 0.4
[5 empty] | 0.2 | 0.8
8 | 0.9 |  | D6
| 2.73 | -19.656 |  | 4 | 0.6
[5 empty] | 0.2 | 0.48
2 | 7.4 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
| 0.7 | 10.36 | Above top tie beam |  |  | 84.35 | DDT Ceramic wall tiles
|  | 122.008 | m2 net area item 6.1 |  |  | 237.0364 | m2 net area item 6.2
|  |  | 6.2)Apply three coats of plastering |  |  |  | 6.4)Chipwood ceiling
|  |  | to internal wall & external beam & colu. | 4 | 1.93 |  | Kitchen
4 | 8.26 |  | Kitchen |  | 2.44 | 18.8368
| 1.43 | 47.2472 | L=1.93X2+2.50X2=8.86mt
|  |  |  | 4 | 1.93 |  | Toilet
4 | 5.16 |  | Toilet |  | 1.18 | 9.1096
| 1.43 | 29.5152 | l=1.93x2+1.35x2=6.56mt
|  |  |  | 4 | 1.93 |  | Corridor
4 | 4.1 |  | Corridor |  | 1 | 7.72
| 3.06 | 50.184 | L=1X2+1.93X2=5.86
|  |  |  | 4 | 1.93 |  | Bed room
4 | 17.7 |  | Bed room |  | 1.1 | 8.492
| 3.06 | 216.648 | L=4.X2+3.55X2+1.10+1.30+0.2=17.70mt
|  |  |  | 4 | 1.93 |  | "
4 | 1.8 |  | W7 |  | 1.1 | 8.492
| 1.68 | -12.096
|  |  |  | 4 | 4 |  | "
4 | 0.9 |  | W10 |  | 2.45 | 39.2
| 1.12 | -4.032
[6 empty] | 91.8504 | m2 net area item 6.4
4 | 0.9 |  | W11
| 1.68 | -6.048
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.12)Approved type 9mm thick |  |  |  | 6.18)10cm thick C-20 RC 1.2mt wide
|  |  | ceramic floor t. |  |  |  | pavement
4 | 1.93 |  | Kitchen | 2 | 19.4 |  | L=17.0X2+1.2X2=19.40
| 2.44 | 18.8368 |  |  | 1.2 | 46.56
L=7.40mt
4 | 1.93 |  | Toilet | 2 | 7.4
| 1.18 | 9.1096 |  |  | 1.2 | 17.76 | 62.36
TOTAL=62.36m2
4 | 1.93 |  | Corridor | 4 | 0.7
| 1 | 7.72 |  |  | 0.7 | -1.96
4 | 1.93 |  | Bed room |  |  | 62.36
| 1.1 | 8.492
6.21)Supply & lay storm water
4 | 1.93 |  | " |  |  |  | concrete pipe of 1/2 ф30cm
| 1.1 | 8.492 |  | 2 | 20 |  | L=19.40+0.3X2=20.00
40
4 | 4 |  | "
| 2.45 | 39.2 |  | 2 | 9.8 |  | L=7.4+1.2X2=9.80
19.6
8 | 0.9 |  | D4,D5 & D6
| 0.2 | 1.44 |  |  |  | 59.6
8 | 0.8 | [5 empty] | 7)Painting
| 0.15 | 0.96 |  |  |  |  | 7.1)External rendered surface
[6 empty] | 122.008 | m2 net area item 7.1
4 | 1 |  | OPENING
| 0.2 | 0.8 |  |  |  |  | 7.2)Int. plastered surface & ext beam & colun
|  | 95.0504 | m2 net area item 6.12 |  |  | 237.0364 | m2 net area item 7.2
|  |  | 6.13)Approved type cearmic skirting 10/0.9cm |  |  |  | 7.3)Chip wood ceiling surface
[6 empty] | 91.8504 | m2 net area item 7.3
4 | 3.26
|  | 13.04 | L=1.93X2+1X2-1-0.8X2=3.26 |  |  |  | 9)SANITARY INSTALLATION
9.6)Supply & install waste water pipe
4 | 14.6 | [5 empty] | made of rigid UPVC
|  | 58.4 | L=4X2+3.25X2+1X2-1-0.9=14.60mt |  |  |  | ф 50mm
|  |  |  | 1 | 9.44
|  | 71.44 | ml net length item 6.13 |  |  | 9.44 | ml net length item 9.6.a
|  |  | 6.16)Approved type terrazzo window cill |  |  |  | ф 75mm
4 | 1.85 |  | W7 | 1 | 30.8
|  | 7.4 |  |  |  | 30.8 | ml net length item 9.6.b
4 | 0.95 |  | W10
|  | 3.8 |  |  |  |  | ф 110mm
4 | 0.95 |  | W11 | 1 | 9.2
|  | 3.8 |  |  |  | 9.2 | ml net length item 9.6.c
|  | 15 | ml net length item 6.16
T | D | S | Item No. and Description | T | D | S | Item No. and Description
10. Electrical Installations
4.01)points conduti of 16mm 3*2.5mm2
28 | 1
|  | 28 | pcs net number item 4.01
5.00)SWITCH
5.01)Single Switch legrand
8 | 1
|  | 8 | pcs net number item 5.01
5.02)Two way Switch legrand
16 | 1
|  | 16 | pcs net number item 5.02
5.03)Intermidate
4 | 1
|  | 4 | pcs net number item 5.03
6.00)Socket outlet point
6.01)Socket outlet point 3x2.5mm2
4 | 1
|  | 4 | pcs net number item 6.01
7.00)Socket outlets
7.01)Socket outlets LEGRAND SUNO
24 | 1
|  | 24 | pcs net number item 7.01
9.00)Telephone/data point
9.01)Telephone point feed through
4 | 1 |  | cat 5E UTP Cable
|  | 4 | pcs net number item 9.01
8)TV POINTS
8.01)TV point fed through RG6
4 | 1 |  | Coaxial 75ohm Tv cable
|  | 4 | pcs net number item 8.01

## SQ TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - SQ
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | 2.2,10cmthick RC ground slab
|  |  | 1) EXCAVATION & EARTH WORK | 4 | 3.4 |  | The same as item No 1.6
|  |  | 1.1 Clear off site to remove top soil |  | 2.2
1 | 19 |  | L=17.00+3=20.00 |  |  | 29.92 | m3Total to item 2.2
| 5 |  | W=3.00+3.00=6.00
|  | 95 | m2 net area item 1.1 |  |  |  | Reinforced concrete class C-25
|  |  |  | 2 | 17 |  | 2.4 In grade beam
|  |  | 1.2 Bulk Excavation in ordinary soil |  | 0.25
4 | 4.2 |  |  |  | 0.4 | 3.4
| 2.8 |  |  | 5 | 2.5
| 0.85 |  |  |  | 0.25
|  | 39.984 | m3Total |  | 0.4 | 1.25
|  |  | Ditto to Item 1.2 but Trench |  |  | 4.65 | m3 net volume item2.4
2 | 17
| 0.9 | [5 empty] | Provide, cut and fix in position
| 1.1 | 33.66 |  |  |  |  | 2.7 In grade beam
|  |  |  | 2 | 17 |  | External
5 | 1.2 |  |  |  | 0.4 | 13.6
| 0.9 |  |  | 2 | 15.75
| 1.1 | 5.94 |  |  | 0.4 | 12.6 | Internal
|  |  |  | 2 | 3
|  | 79.584 | m3 net volume item 1.2 |  | 0.4 | 2.4 | External
|  |  |  | 8 | 2.5
|  |  | 1.4 Selected Borrowed Fill |  | 0.4 | 8
4 | 4.2 |  | On Axis Y/01-Y/05 |  |  | 36.6 | m2 net arae item 2.7
2.8
| 0.85 | [5 empty] | Reinforcement steel bar
|  | 39.984 | m3 net volume item 1.4 | 1 | 384.1992 |  | 2.6. Dia 14mm
[6 empty] | 384.1992 | kg net weight item 2.6
1.5 Cart Away surplus excavated material
1 | 95 |  | From Item 1.1 | 1 | 285.1584 |  | 2.7. Dia 8mm
| 0.3 | 28.5 |  |  |  | 285.1584 | kg net weight item 2.7
2.9)10/2cm expantion joint
1 | 39.984 | 79.584 | From Item 1.2 | 4 | 13.8 |  |  | 2 | 16.75
[6 empty] | 55.2 |  |  |  | 33.5
|  | 108.084 | m3 net area item 1.5
[6 empty] | 33.5 | ml net area item 2.9
|  |  | 1.6 25 cm thick basaltic or equivalent stone hard core |  |  |  | 3. Masonry Work
4 | 3.4 |  |  | 2 | 17 |  | 3.1 Trychltic or equivalent stone masonry below NGL
| 2.2 |  |  |  | 0.4
|  | 29.92 | m3Total to item 1.6 |  | 0.46 | 6.256
|  |  |  | 5 | 2.55
|  |  | 2) CONCRETE WORK |  | 0.4
|  |  | 2.1 5cm thick lean concrete class C-7 |  | 0.46 | 2.346
2 | 17 |  |  |  |  | 8.602 | m3 net volume item 3.1
| 0.4 | 13.6 |  | 2 | 17 |  | 3.2 Ditto but above natural ground level externally left for pointing
0.4
5 | 3 |  |  |  | 0.72 | 9.792
| 0.4 | 6 |  | 5 | 2.55
0.4
|  | 19.6 | m2 net area item 2.1 |  | 0.72 | 3.672
[6 empty] | 13.464 | m3 net volume item 3.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 4 | 1.5 |  | W2
10 | 0.2 |  | 1.1)In elevation column |  | 1.73 | -10.38
0.2
| 2.73 |  |  | 2 | 2.73 |  | Axis Y/01 & Y/05 from ( X/01 - X/02)
|  | 1.092 | m3 net volume item 1.1 |  | 2.8 | 15.288
above top tie beam
|  |  | 1.2)In beam & step | 2 | 2.8 |  | Axis Y/01 & Y/05 from ( X/01 - X/02)
2 | 17 |  | TTB1=2Pcs |  | 0.5 | 2.8
| 0.3 |  | Axis x/01 & x/02 from (y/01 - y/05)
| 0.2 | 2.04 |  | 1 | 17 |  | Axis x/02 from (y/01 - y/05)
[5 empty] | 1.2 | 20.4
5 | 2.8 |  | TTB2=5Pcs
| 0.3 |  | Axis Y/01 - Y/05 from ( X/01 - X/02) |  |  | 105.64 | m2 net area item 2.1
| 0.2 | 0.84
2.2)15cm thick HCB wall
|  | 4.14 | m3 net volume item 1.2 | 3 | 2.8
2.73
|  |  | FORM WORK |  |  | 22.932 | m2 net area item 2.2
1.3)Elevation column
10 | 0.8 |  | C1=10Pcs |  |  |  | 3)ROOFING WORK
| 2.73 | [5 empty] | 3.1)G-28 CIS Roof covering
|  | 21.84 | m2 net area item 1.3 | 1 | 3.8 |  | W=3+0.50=3.50mt
[5 empty] | 18.2 |  | L=17+0.50x2=18.00mt
|  |  | 1.4)Beam |  |  | 69.16 | m2 net area item 3.1
2 | 16 |  | TTB1=2Pcs
| 0.8 | 25.6 | Axis x/01 & x/02 from (y/01 - y/05) |  |  |  | 3.2)G-28 Ribbed sheet ceiling
|  |  | Dev.L=0.30*2+0.20=0.80mt | 1 | 13
14 | 0.3 |  |  |  | 0.6 | 7.8
| 0.2 | 0.84
[6 empty] | 7.8 | m2 net area item 3.2
5 | 2.8 |  | TTB2=5Pcs
| 0.8 | 11.2 | Axis x/02 & x/03 from (y/01 - y/06) |  |  |  | 3.3)Supply & fix G-28 gutter dev.
|  |  | Axis Y/01 - Y/05 from ( X/01 - X/02) | 1 | 18.2
[6 empty] | 18.2 | ml net arae item 3.3
|  | 37.64 | m2 net area item 1.4
3.4)Flashing in metal sheet
|  |  | 1.8) ф12 mm deformed bars | 1 | 18.2
1 | 412.6714 |  |  |  |  | 18.2
|  | 412.6714 | kg net weight item 1.6 | 2 | 3.7
7.4
|  |  | 1.9) ф8mm deformed bars |  |  | 25.6 | ml net arae item 3.4
1 | 127.8615
|  | 127.8615 | kg net weight item 1.7 |  |  |  | 4)CARPENTRY
4.1)Uper & lower chord
|  |  | 2)BLOCK WORK |  |  |  | L=3.3+4.00=7.30ml
|  |  | 2.1)20cm thick HCB wall |  |  |  | No. truss=17.00/1.33+1=14PCS
1 | 16 |  | Axis x/01 from (y/01 - y/05) | 15 | 7.3
| 2.73 | 43.68 |  |  |  | 109.5 | ml net arae item 4.1
1 | 16 |  | Axis x/02 from (y/01 - y/05) |  |  |  | 4.2)Vertical & Diagonal member
| 2.73 | 43.68
|  |  |  | 15 | 2.8
4 | 0.9 |  | D6 |  |  | 42
| 2.73 | -9.828 |  | 15 | 3.5
52.5
[6 empty] | 94.5 | ml net arae item 4.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4.3)Purlin zigba 5/7cm | 2 | 17 |  | Axis X/01 & X/02 from (Y/01 - Y/06)
|  |  | No .pur =3.70/0.9+1=5 |  | 0.4 | 13.6 | beam
5 | 18.2 |  | L=17.00+0.6x2=18.20mt
|  | 91 | ml net arae item 4.3 | 2 | 17 |  | Axis X/01 & X/02 from (Y/01 - Y/06)
[5 empty] | 0.3 | 10.2 | beam
1 | 18.2 |  | 4.4)Zigba wooden fascia board
|  | 18.2 |  | 2 | 3.2 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
2 | 3.7 |  |  |  | 0.4 | 2.56 | beam
7.4
|  |  |  | 2 | 3.2 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
|  | 25.6 | ml net arae item 4.4 |  | 0.3 | 1.92 | Top tie beam
|  |  | 5)METAL WORK | 14 | 2.73 |  | Column
|  |  | 5.1 Window size 150/173cm |  | 0.2 | 7.644
4 | 1
|  | 4 | pcs net number item 5.1 |  |  | 175.108 | m2 net area item 6.2
6.4)Chipwood ceiling
|  |  |  | 4 | 4.05
2.8
[6 empty] | 45.36 | m2 net area item 6.4
|  |  | 6.1)Apply two coats of plastering & |  |  |  | 6.12)approve quality ceramic tiles
|  |  | one coat rendering | 4 | 4.05
1 | 16 |  |  |  | 2.6 | 42.12
| 3.73 | 59.68 | Axis X/01 from (Y/01 - Y/05)
|  |  |  | 4 | 0.9
1 | 16 |  |  |  | 0.2 | 0.72
| 2.73 | 43.68 | Axis X/02 from (Y/01 - Y/05)
[6 empty] | 42.84 | m2 net area item 6.12
4 | 0.9
| 2.73 | -9.828 | D6 |  |  |  | 6.13)approve quality Ceramic skirting
L=4.05X2+2.6X2-0.90=12.40mt
4 | 1.5 |  |  | 4 | 12.4
| 1.73 | -10.38 | W2 |  |  | 49.6 | m2 net area item 6.13
2 | 2.8 |  | Axis Y/01 & Y/05 from (X/01 - X/02) |  |  |  | 6.16)window cill Size, 27/3cm
| 2.73 | 15.288 |  | 4 | 1.55
[6 empty] | 6.2 | m2 net area item 6.16
2 | 3 |  | Axis Y/01 & Y/05 from (X/01 - X/02)
| 0.5 | 3 |  |  |  |  | 7)Painting
7.3)External rendered surface
|  | 101.44 | m2 net area item 6.1 |  |  | 101.44 | m2 net area item 7.3
|  |  | 6.2)Apply three coats of plastering |  |  |  | 10. Electrical Installations
|  |  | to internal wall & external beam & colu. |  |  |  | 4.02. Light point
4 | 13.6 |  | L=4*2+2.8*2=13.60 |  |  |  | 4.01)points conduti of 16mm 3*2.5mm2
| 2.93 | 159.392 |  | 8 | 1
[6 empty] | 8 | pcs net number item 4.01
4 | 0.9 |  | D6
| 2.73 | -9.828
4 | 1.5 |  | W2
| 1.73 | -10.38

## Staff & SQ Reinf
PROJECT:-Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trusr Construction | [9 empty] | Block : Staff residance
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 | 14 | 11.23 | 2 | 3 | 6 | - | - | - | - | 67.38
|  |  | 14 | 7.03 | 2 | 3 | 6 | - | - | - | - | 42.18
|  |  | 14 | 8.58 | 2 | 3 | 6 | - | - | - | - | 51.48
|  |  | 14 | 8.58 | 2 | 3 | 6 | - | - | - | - | 51.48
|  |  | 8 | 1.2 | 2 | 84 | 168 | - | 201.6 | - | - | -
|  | GB2 | 14 | 8.05 | 5 | 3 | 15 | - | - | - | - | 120.75
|  |  | 14 | 7.35 | 5 | 3 | 15 | - | - | - | - | 110.25
|  |  | 8 | 1.2 | 5 | 37 | 185 | - | 222 | - | - | -
| GROUND FLOOR MASH | [5 empty] | 0
| (x/01-x/02) (y/01 - y/05) |  | 8 | 6.3 | 33 | 4 | 132 |  | 831.6
|  |  | 8 | 4 | 21 | 4 | 84 |  | 336
|  |  |  | TOTAL LENGTH |  |  |  |  | 1591.2 | 0 | 0 | 443.52
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 628.524 | 0 | 0 | 536.6592
| CONTRACTOR | [8 empty] | SUPERVISOR
PROJECT:-Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trusr Construction | [9 empty] | Block : Staff residance
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
1 | COLUMN (C1) |  | 12 | 3.68 | 4 | 10 | 40 |  |  |  | 147.2
|  |  | 8 | 0.7 | 15 | 10 | 150 |  | 105
1 | TTB1 |  | 12 | 11.23 | 2 | 3 | 6 |  |  |  | 67.38
|  |  | 12 | 7.03 | 2 | 3 | 6 |  |  |  | 42.18
|  |  | 12 | 8.58 | 2 | 3 | 6 |  |  |  | 51.48
|  |  | 12 | 8.58 | 2 | 3 | 6 |  |  |  | 51.48
|  |  | 8 | 0.9 | 2 | 84 | 168 |  | 151.2
| TTB2 |  | 12 | 8.05 | 5 | 3 | 15 |  |  |  | 120.75
|  |  | 12 | 7.35 | 5 | 3 | 15 |  |  |  | 110.25
|  |  | 8 | 0.9 | 5 | 38 | 190 |  | 171
2 | STAFF RESID. lintel |  | 12 | 1.65 | 4 | 2 | 8 |  |  |  | 13.2
|  | Opening | 12 | 1.35 | 4 | 2 | 8 |  |  |  | 10.8
|  |  | 8 | 0.6 | 4 | 8 | 32 |  | 19.2
|  | D5 | 12 | 1.55 | 4 | 2 | 8 |  |  |  | 12.4
|  |  | 12 | 1.25 | 4 | 2 | 8 |  |  |  | 10
|  |  | 8 | 0.6 | 4 | 7 | 28 |  | 16.8
|  | D4 | 12 | 1.45 | 4 | 2 | 8 |  |  |  | 11.6
|  |  | 12 | 1.15 | 4 | 2 | 8 |  |  |  | 9.2
|  |  | 8 | 0.6 | 4 | 7 | 28 |  | 16.8
|  |  |  | TOTAL LENGTH |  |  |  |  | 480 | 0 | 657.92 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 189.6 | 0 | 584.233 | 0
| CONTRACTOR | [8 empty] | SUPERVISOR
PROJECT:- Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trusr Construction | [9 empty] | Block : S. Quarter
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB-1 | 14 | 11.23 | 2 | 3 | 6 | - | - | - | - | 67.38
|  |  | 14 | 7.03 | 2 | 3 | 6 | - | - | - | - | 42.18
|  |  | 14 | 8.58 | 2 | 3 | 6 | - | - | - | - | 51.48
|  |  | 14 | 8.58 | 2 | 3 | 6 |  |  |  |  | 51.48
|  |  | 8 | 1.2 | 2 | 84 | 168 | - | 201.6 | - | - | -
|  | GB-2 | 14 | 3.85 | 5 | 3 | 15 | - | - | - | - | 57.75
|  |  | 14 | 3.15 | 5 | 3 | 15 | - | - | - | - | 47.25
|  |  | 8 | 1.2 | 5 | 15 | 75 | - | 90 | - | - | -
| GROUND FLOOR MASH | [5 empty] | 0
| (x/01-x/02) (y/01 - y/05) |  | 8 | 3.87 | 4 | 14 | 56 |  | 216.72
|  |  | 8 | 2.67 | 4 | 20 | 80 |  | 213.6
|  |  |  | TOTAL LENGTH |  |  |  |  | 721.92 | 0 | 0 | 317.52
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 285.1584 | 0 | 0 | 384.1992
| CONTRACTOR | [8 empty] | SUPERVISOR
PROJET:-Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trusr Construction | [9 empty] | Block : S. Quarter
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
2 | TOP TIE BEAM
| TTB1 |  | 12 | 11.23 | 2 | 3 | 6 |  |  |  | 67.38
|  |  | 12 | 7.03 | 2 | 3 | 6 |  |  |  | 42.18
|  |  | 12 | 8.58 | 2 | 3 | 6 |  |  |  | 51.48
|  |  | 12 | 8.58 | 2 | 3 | 6 |  |  |  | 51.48
|  |  | 8 | 0.9 | 2 | 84 | 168 |  | 151.2
| TTB2 |  | 12 | 3.85 | 5 | 3 | 15 |  |  |  | 57.75
|  |  | 12 | 3.15 | 5 | 3 | 15 |  |  |  | 47.25
|  |  | 8 | 0.9 | 5 | 15 | 75 |  | 67.5
| COLUMN (C1) |  | 12 | 3.68 | 4 | 10 | 40 |  |  |  | 147.2
|  |  | 8 | 0.7 | 15 | 10 | 150 |  | 105
|  |  |  | TOTAL LENGTH |  |  |  |  | 323.7 |  | 464.72
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 127.8615 | 0 | 412.6714 | 0
| CONTRACTOR | [8 empty] | SUPERVISOR
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15

## OR & Delivery Sum
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-OR & Delivery
Details of Works executed
Bill No. | Description |  | Sub Total Birr |  | Total Birr
|  |  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  |  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work |  | 465036.33 | 191974.3937 | 465036.33 | 191974.3937
2 | Concrete Work |  | 717946 | 619177.3607 | 717946 | 619177.3607
3 | Masonry work |  | 349050 | 61514.48 | 349050 | 61514.48
| sub total A |  | 1532032.33 | 872666.2343 | 1532032.33 | 872666.2343
B. Super Structure
1 | Concrete Work |  | 272040 | 247644.5674 | 272040 | 247644.5674
2 | Block work |  | 282040 | 295896.56 | 282040 | 295896.56
3 | Roofing |  | 397710.4 | 307927.4 | 397710.4 | 307927.4
4 | Carpentary & Joinery |  | 191374.17 | 260458.57 | 191374.17 | 260458.57
5 | Metal work |  | 184915.5 | 148269 | 184915.5 | 148269
6 | Finishing |  | 1044597 | 764489.995 | 1044597 | 764489.995
7 | Painting |  | 82656 | 43825.5197 | 82656 | 43825.5197
8 | Glazing |  | 15730 |  | 15730
9 | Sanitory Installation |  | 95535 | 27385.9 | 95535 | 27385.9
10 | Electrical Installation |  | 266980.43 | 169753.75 | 266980.43 | 169753.75
| sub total B |  | 2833578.5 | 2265651.2622 | 2833578.5 | 2265651.2622
| Total A+B |  | 4365610.83 | 3138317.4965 | 4365610.83 | 3138317.4965
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  | Suppervisor :- ______________ |  |  | Consultant:- _____________

## OR and Delivery
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction |  |  |  |  | Block : OR & Delivery
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 827 | 8 | 6616 | 827.08 | 6616.64
1.2 | Bulk excavation in ordinary | m3 | 776 | 70 | 54320 | 131.6434 | 9215.038
1.3 | Ditto but exceeding 1.5m but less than 2m | m3 | 258.6667 | 70 | 18106.6667 | 213.9615 | 14977.305
1.4 | Selected borrowed fill brought from out side | m3 | 1034.6667 | 56.6 | 58562.1333 | 429.2248 | 24294.1237
1.5 | Cart away surplus excavated material to an | m3 | 1282.7667 | 70 | 89793.6667 | 164.5041 | 11515.287
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 705 | 200 | 141000 | 626.78 | 125356
Total to summary ………Birr |  |  |  |  | 368398.4667 |  | 191974.3937
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 |  | 150 | 0 | 122 | 18300
2.2 | Ditto but under footing pad | m2 |  | 150 | 0 |  | 0
2.3 | 10 cm thick reinforced concrete floor slab class | m2 |  | 400 | 0 | 626.78 | 250712
2.3 | In grade beam & Steps | m3 |  | 3200 | 0 | 31.04 | 99328
2.4 | In footing pad | m3 |  | 3200 | 0 |  | 0
2.5 | In footing coloumn | m3 |  | 3200 | 0 |  | 0
Provide cut and fix in position swan zigzag wood
2.6 | Grade beam | m2 |  | 120 | 0 | 243.32 | 29198.4
Reinforcement steel bar according to St.drawing
2.6 | Dia 14 mm deformed bar | kg |  | 36 | 0 | 2494.8264 | 89813.7504
2.7 | Dia. 12mm deformed bar | kg |  | 36 | 0 |  | 0
2.8 | Dia 8 mm deformed bar | kg |  | 36 | 0 | 3252.9781 | 117107.2103
2.9 | 10/2 cm chip wood expansion joint between | m |  | 30 | 0 | 490.6 | 14718
Total to summary ………Birr |  |  |  |  | 0 |  | 619177.3607
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 1250 | 700 | 875000 | 66.5696 | 46598.72
3.2 | Ditto but above natural ground level externally | m3 | 1450 | 1900 | 2755000 | 7.8504 | 14915.76
Total to summary ………Birr |  |  |  |  | 3630000 |  | 61514.48
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 5 | 3200 | 16000 | 3.9312 | 12579.84
1.2 | In beams& steps | m3 | 23 | 3200 | 73600 | 18.693 | 59817.6
1.3 | Lintel | m3 | 1.2 | 3200 | 3840 | 1.395 | 4464
Provide cut and fix in position swan zigzag wood
1.4 | Elevation column | m2 | 101 | 130 | 13130 | 78.624 | 10221.12
1.5 | Beam | m2 | 313 | 130 | 40690 | 245.04 | 31855.2
1.6 | Lintel | m2 | 10 | 130 | 1300 | 22.55 | 2931.5
Reinforcement steel bar according to St.drawing
1.7 | Dia 14 mm deformed bar | kg | 2614 | 36 | 94104 | 320.6016 | 11541.6576
1.7 | Dia 12 mm deformed bar | kg | 2614 | 36 | 94104 | 2389.2794 | 86014.0598
1.8 | Dia 8 mm deformed bar | kg | 786 | 36 | 28296 | 783.8775 | 28219.59
Total to summary ………Birr |  |  |  |  | 365064 |  | 247644.5674
2. BLOCK WORK
2.1 | 20cm thick | m2 | 561 | 350 | 196350 | 431.592 | 151057.2
2.2 | 15cm thick | m2 | 317 | 320 | 101440 | 452.623 | 144839.36
Total to summary ………Birr |  |  |  |  | 297790 |  | 295896.56
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 987.89 | 360 | 355640.4 | 773.955 | 278623.8
3.2 | G28ribbed sheet ceiling under eave | m2 | 85 | 160 | 13600 | 74.4 | 11904
3.3 | Flashing in flat metal sheet fixed as shown | m | 141 | 110 | 15510 | 61.96 | 6815.6
3.4 | Supply and fix G-28flat metal sheet gutter | m | 108 | 120 | 12960 | 88.2 | 10584
Total to summary ………Birr |  |  |  |  | 397710.4 |  | 307927.4
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 1305.31 | 23 | 30022.13 | 1155.33 | 26572.59
4.2 | Vertical & Diagonal memberes size-diameter 8-10cm | m | 752.4 | 16 | 12038.4 | 1498.86 | 23981.76
4.3 | Purlin zigba size 5/7cm | m | 1013.22 | 33 | 33436.26 | 970.2 | 32016.6
4.4 | Zigba wooden fascia board price includes three coats | m | 112.58 | 71 | 7993.18 | 123.92 | 8798.32
Doors
4.5 | Type D5 size - 100/273cm | Nº | 2 | 5187 | 10374 |  | 0
4.6 | Type D7 size-80/273cm | Nº | 7 | 4149 | 29043 | 4 | 16596
4.7 | Type D8 size-70/273cm | Nº | 6 | 3630 | 21780 | 5 | 18150
4.8 | Type D9 size-90/273cm | Nº | 10 | 4668.3 | 46683 | 15 | 70024.5
| Type D size-130/273cm | Nº |  | 6743.1 | 6743.1 | 2 | 13486.2
| Type D size-140/273cm | Nº |  | 7261.8 | 7261.8 | 7 | 50832.6
Total to summary ………Birr |  |  |  |  | 191369.97 |  | 260458.57
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 26 | 3892.5 | 101205 | 22 | 85635
5.2 | Type W4 size-130/173cm | Nº | 9 | 3373.5 | 30361.5 | 3 | 10120.5
5.3 | Type W14 size-100/173cm | Nº | 2 | 2595 | 5190 | 4 | 10380
5.4 | Type W16 size-150/60cm | Nº | 4 | 1350 | 5400 | 3 | 4050
5.5 | Type W19 size-110/60cm | Nº | 1 | 2200 | 2200 |  | 0
Doors
5.6 | Type D2 size - 140/273cm | Nº | 3 | 5733 | 17199 | 2 | 11466
5.7 | Type D6 size - 90/273cm | Nº | 4 | 3685.5 | 14742 | 4 | 14742
5.8 | Type D10 size - 80/273cm | Nº | 3 | 3276 | 9828 | 2 | 6552
| Type D10 size - 130/273cm | Nº |  | 5323.5 |  | 1 | 5323.5
Total to summary ………Birr |  |  |  |  | 186125.5 |  | 148269
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 416 | 140 | 58240 | 267.301 | 37422.14
6.2 | Apply three coats of plastering to internal walls, | m2 | 1831 | 150 | 274650 | 1516.6472 | 227497.08
6.3 | 8mm thick Chip wood ceiling nailed on & including | m2 | 705 | 310 | 218550 | 563.8475 | 174792.725
6.5 | Approved type 6mm thick glazed ceramic wall tile | m2 | 163 | 370 | 60310 |  | 0
6.7 | 9mm thick non slippery ceramic tile flooring | m2 | 705 | 300 | 211500 | 641.7535 | 192526.05
6.8 | Approved type Ceramic tile skirting | m | 610 | 100 | 61000 | 419.09 | 41909
6.9 | Window sill Size 27/3 cm | m | 73 | 150 | 10950 | 48.25 | 7237.5
6.11 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 148 | 550 | 81400 | 125.46 | 69003
6.12 | lay water concrete pipes of half diameter 30cm | ml | 133 | 100 | 13300 | 62.85 | 6285
| Construction of 10x40 cm curb stone | ml | 133 | 265 | 35245 | 29.5 | 7817.5
Total to summary ………Birr |  |  |  |  | 1025145 |  | 764489.995
7. PAINTING
7.1 | Internal plastered surface and external beams& | m2 | 1831 | 18.6667 | 34178.6667 | 1516.6472 | 28310.7477
7.2 | Chip wood ceiling surface | m2 | 705 | 18.6667 | 13160 | 563.8475 | 10525.1533
7.3 | External rendered surface | m2 | 416 | 18.6667 | 7765.3333 | 267.301 | 4989.6187
Total to summary ………Birr |  |  |  |  | 55104 |  | 43825.5197
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R water pipes for water
| 15mm diameter ;internal | LM | 16 | 70 | 1120 |  | 0
| 20mm diameter ;internal | LM | 50 | 80 | 4000 | 25.6 | 2048
| 25mm diameter ;internal | LM | 26 | 95 | 2470 | 18.7 | 1776.5
| 32mm diameter ;internal | LM | 50 | 125 | 6250 | 4.55 | 568.75
9.3 | Supply and fix bronze gate valves complete
| 15mm diameter | No | 38 | 95 | 3610 | 5 | 475
9.5 | Supply and install waste water pipes made of rigid
| 50mm diameter of min. wall thickness=2mm | LM | 10 | 65 | 650 | 65.79 | 4276.35
| 75mm diameter of min. wall thickness=3mm | LM | 25 | 95 | 2375 | 55.79 | 5300.05
| 100 mm diameter of min. wall thickness=3.2mm | LM | 120 | 125 | 15000 | 38.37 | 4796.25
| 150 mm diameter of min. wall thickness=3.2mm | LM | 50 | 145 | 7250 |  | 0
9.9 | Supply and fix toilet paper holder made of metal | No | 9 | 905 | 8145 | 9 | 8145
Total to summary ………Birr |  |  |  |  | 50870 |  | 27385.9
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 138 | 200 | 27600 | 104 | 20800
3 | Switches
3.01 | single(774001+774041) | PCs | 45 | 81.25 | 3656.25 | 38 | 3087.5
3.02 | Duoble(774005+774042) | " | 20 | 131.25 | 2625 | 23 | 3018.75
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 78 | 200 | 15600 | 64 | 12800
4.02 | Ditto as 4.01 but for water heater points | PCs | 13 | 785 | 10205 | 11 | 8635
4.01 | Ditto as 4.01 above but 3x4mm2 in pvc pipe | PCs | 1 | 220 | 220 | 1 | 220
5 | Socket outlets
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 78 | 90 | 7020 | 64 | 5760
5.02 | weather proof socket Legrand Suno 774022+774041 | PCs | 13 | 281.25 | 3656.25 | 11 | 3093.75
5.03 | Ditto as above 4.06 but for 25A/1ph f | PCs | 8 | 300 | 2400 | 1 | 300
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 13 | 130 | 1690 | 17 | 2210
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 13 | 90 | 1170 |  | 0
7 | Type of Light Fitting With lamp
7.01 | PHILIPS TCS 098/236 IMKwith 2xTLD 36W | PCs | 24 | 1500 | 36000 | 24 | 36000
7.02 | PHILIPS TCS 098/136 IMKwith 1xTLD 36W | PCs | 70 | 1200 | 84000 | 32 | 38400
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 19 | 406.25 | 7718.75 | 21 | 8531.25
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 11 | 406.25 | 4468.75 | 13 | 5281.25
7.05 | MASSIVE 3202/02/67/1XE27/75W | PCs | 14 | 1375 | 19250 | 14 | 19250
8 | TV points
8.01 | TV points fed through RG6 Coaxial 75ohm TV
| accessories | PCs | 1 | 266.25 | 266.25 | 1 | 266.25
10 | Cable way and Manhole
10.01 | Rigid pvc pipe of dia.60mm From CMDB
| to SDB-OPD | mt | 28 | 50 | 1400 |  | 0
10.02 | Rigid pvc pipe of dia.32mm For 4x6mm2 | " | 15 | 40 | 600 |  | 0
10.03 | Rigid pvc pipe of dia.25mm For 4x4mm2 | " | 30 | 60 | 1800 | 35 | 2100
10.04 | Rigid pvc pipe dia. 50mm to |  |  |  | 0 | 13.45 | 0
| telephone Distribution frame | " | 12 | 50 | 600 |  | 0
Total to summary ………Birr |  |  |  |  | 231946.25 |  | 169753.75

## OR Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - OR Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | C- bulk fill under
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 42.15 |  | L=43.45-0.5-0.8=42.15
|  |  | 1.1 Clear off site to remove top soil |  | 15.6 |  | W=16.9-0.5-0.8=15.6
|  |  | L=43.45+1.0+1.0-.5=44.95 |  | 0.46 | 302.4684
1 | 44.95 |  | W=16.9+1.0+1.0-0.5=18.4
| 18.4 | 827.08 |  |  |  |  | DEDUCTION
|  |  |  | 2 | 42.15 |  | along x-axis
|  | 827.08 | m2 Total to item 1.1 |  | 0.4 |  | L=42.15 W=0.4m
[5 empty] | 0.46 | 15.5112
1.2 Bulk Excavation in ordinary soil
1 | 41.65 |  | L=43.45-0.25-0.25-0.4-0.4-0.5=41.65 | 7 | 14.8 |  | along y-axis
| 15.1 |  | W=16.9-0.25-0.25-0.4-0.4-0.5=15.1 |  | 0.4 |  | L=16.9-0.5-0.8-(2*0.4)=14.8
| 0.28 | 176.0962 |  |  | 0.46 | 19.0624
DEDUCTION
[6 empty] | 429.2248 | m3 Total to item 1.4
2 | 41.65 |  | along x-axis
| 0.9 |  | L=43.45-0.25-0.25-0.4-0.4-0.5=41.65 |  |  |  | 1.5 Cart away excavated material to an
| 0.28 | 20.9916 |  | 1 | 44.95
18.4
7 | 13.3 |  | along y-axis |  | 0.3 | 248.124 | from item no 1.1
| 0.9 |  | W=16.9-0.25-0.25-0.4-0.4-0.5-(2*0.9)=13.3
| 0.28 | 23.4612 |  |  |  | 131.6434 | from item no 1.2
|  | 131.6434 | m3 Total to item 1.2 |  |  | 213.9615 | from item no 1.3
|  |  | 1.3 Ditto to Item 1.2 but exceeding 1.5 |  |  | 429.2248 | DEDUCTION
and less than 2m
4 | 43.45 |  | along x-axis |  |  | 164.5041 | m3 Total to item 1.4
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=43.45 d=0.
| 0.81 | 126.7002 |  |  |  |  | 1.6/ 25 cm thick basaltic stone hard core
|  |  |  | 1 | 42.45 |  | L=43.45-0.5-0.5=42.45
9 | 13.3 |  | along y-axis |  | 15.9 | 674.955 | W=16.9-0.5-0.5=15.9
| 0.9 |  | L=16.9-(4*.9)=13.3
| 0.81 | 87.2613 | W=0.4+0.25+0.25=0.90, d= |  |  |  | DEDUCTION
|  |  |  | 2 | 42.45 |  | along x-axis L=42.45 W=0.25
|  | 213.9615 | m3 Total to item 1.3 |  | 0.25 | 21.225
|  |  | 1.4 Selected Fill(insitu source) | 7 | 15.4 |  | along y-axis L=15.4 W=0.25
|  |  | A- fill under masonary |  | 0.25 | 26.95 | L=16.9-0.5-0.5-0.5=15.4
4 | 43.45 |  | for axis x01-x04
| 0.9 |  | L=43.45 |  |  | 626.78 | m2 Total to item 1.6
| 0.55 | 86.031
2) CONCRETE WORK
9 | 13.3 |  | for axis y01-y09 |  |  |  | 2.1 5cm thick lean concrete class C-7
| 0.9 |  | L=13.3 , W=0.9, d=0.3 | 4 | 42.95 |  | L=43.45-0.5=42.95
| 0.55 | 59.2515 |  |  | 0.4 | 68.72
|  |  | B-backfill and compaction in side | 9 | 14.8 |  | L=16.9-0.5-(4*0.4)=14.8
|  |  | masonary along x-axis |  | 0.4 | 53.28
6 | 40.95 |  | L=43.45-0.25-0.25-0.8-(3*0.4)=40.95
| 0.25 |  | W=0.25 ,d= |  |  | 122 | m2Total to item 2.1
| 0.14 | 8.5995
along y-axis
16 | 13.3 |  | L=16.9-0.25-0.25-0.8-(2*0.25)-(2*.9)=13.3
| 0.25 |  | W=0.25 ,d=.
| 0.14 | 7.448
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.3 10cm thick RC floor slab class C-20 |  |  |  | 3. Masonry Work
1 | 42.45 |  | L=43.45-0.25-0.25-0.25-0.25=42.45 |  |  |  | 3.1 Trychltic stone masonry (total)
| 15.9 | 674.955 | W=16.9-0.25-0.25-0.25-0.25=15.9 | 4 | 42.95 |  | axis x01,x02,x03,x04
[5 empty] | 0.4 |  | L=43.45-0.5=42.95
|  |  | DEDUCTION |  | 0.61 | 41.9192
2 | 42.45 |  | along x-axis
| 0.25 | 21.225 | L=43.45-0.25-0.25-0.25-0.25=42.45 | 9 | 14.8 |  | axis y01,y02,y03……y09
[5 empty] | 0.4 |  | L=16.9-0.5-(4*0.4)=14.8
7 | 15.4 |  | along y-axis |  | 0.61 | 32.5008
| 0.25 | 26.95 | L=16.9-0.25-0.25-0.25-0.25-0.5=15.4
[6 empty] | 74.42 | m3 total volume of masonary
|  | 626.78 | m2Total to item 2.3
3.12 masonary work above NGL
|  |  | 2.3 In grade beams | 1 | 33.2 |  | on axis x01 L=33.2m
4 | 42.95 |  | L=43.45-0.25-0.25=42.95 (x-axis) |  | 0.4
| 0.25 |  |  |  | 0.39 | 5.1792
| 0.4 | 17.18
|  |  |  | 1 | 15.9 |  | on axis y01 L=15.9m
9 | 15.4 |  | L=16.9-0.25-0.25-(4*.25)=15.4 |  | 0.4
| 0.25 |  |  |  | 0.42 | 2.6712
| 0.4 | 13.86
[6 empty] | 7.8504 | m3Total to item 3.2
|  | 31.04 | m3 Total to item 2.3
3.13 masonary work below NGL
provide fix in position form work
|  |  | 2.6 In grade beams |  |  | 66.5696 | m3Total to item 3.1
8 | 42.95 |  | L=43.45-0.25-0.25=42.95 (x-axis)
| 0.4 | 137.44
18 | 15.9 |  | L=16.9-0.25-0.25-(2*.25)=15.9
| 0.4 | 114.48
DEDUCTION
86 | 0.4
| 0.25 | 8.6
|  | 243.32 | m2 Total to item 2.6
Reinforcement steel bars
2.6)ф14 mm deformed bars
|  | 2494.8264 | kg net wight item 2.6 |  |  |  |  | #REF!
2.8)ф8 mm deformed bars
|  | 3252.9781 | kg net wight item 2.8
2.9 10/2 cm expansion joint
along x-axis
6 | 40.7 |  | L=43.45-0.25-0.25-0.25-0.25-(.25*7)=40.7
244.2
along y-axis
16 | 15.4 |  | L=16.9-0.25-0.25-0.25-0.25-0.5=15.4
|  | 246.4 | [5 empty] | #REF!
|  | 490.6 | mTotal to item 2.9

## OR Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - OR & Delivery
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 8 | 1.2
|  |  | 1.CONCRETE WORK |  | 0.15 |  | D7(8Pcs)
|  |  | 1.1)In elevation column |  | 0.2
36 | 0.2 |  | C1=36Pcs (0.2x0.2) |  |  | 0.288
| 0.2 |  |  | 12 | 1.1
| 2.73 |  |  |  | 0.1 |  | D8(12Pcs)
|  | 3.9312 | m3 net volume item 1.1 |  | 0.2
0.264
1.2)In beam & step
2 | 42.9 |  | TTB1=2Pcs |  |  | 1.395 | m3 net volume item 1.3
| 0.3 |  | Axis x/01 & x/o4 from (y/01 - y/09)
| 0.2 | [5 empty] | FORM WORK
|  | 5.148 |  |  |  |  | 1.4)Elevation column
|  |  |  | 36 | 0.8 |  | C1=36Pcs (0.2x0.2)
2 | 42.9 |  | TTB2=2Pcs |  | 2.73
| 0.3 |  | Axis x/02,x/03 & x/04 |  |  | 78.624 | m2 net area item 1.4
| 0.2 |  | from ( y/01 - y/09)
|  | 5.148 |  |  |  |  | 1.5)Beam
2 | 15.55 |  | TTB3=2Pcs | 2 | 41.1 |  | TTB1=2Pcs
| 0.3 |  | Axis y/01 & y/09 from ( x/01 - x/04) |  | 0.8 |  | Axis x/01 & x/o4 from (y/01 - y/09)
| 0.2 |  |  |  |  | 65.76 | Dev.L=0.30*2+0.20=0.80mt
1.866
|  |  |  | 18 | 0.3
7 | 15.55 |  | TTB4=7Pcs |  | 0.2
| 0.3 |  | Axis y/02 - y/07 from ( x/01 - x/04) |  |  | 1.2
0.2
|  | 6.531 |  | 2 | 41.1 |  | TTB2=3Pcs
[5 empty] | 0.8 |  | Axis x/02,x/03 & x/04 from ( y/01 - y/09)
|  | 18.693 | m3 net volume item 1.2 |  |  | 65.76 | Dev.L=0.30*2+0.20=0.80mt
|  |  | 1.3)Lintel | 8 | 0.3
2 | 1.6 |  |  |  | 0.2
| 0.15 |  | D9'(1Pc) |  |  | 0.36
0.2
|  | 0.096 |  | 2 | 15.55 |  | TTB3=2Pcs
[5 empty] | 0.8 |  | Axis y/01 & y/09 from ( x/01 - x/04)
5 | 1.3 |  |  |  |  | 24.88 | Dev.L=0.30*2+0.20=0.80mt
| 0.15 |  | D9(5Pcs)
| 0.2 |  |  | 7 | 15.55
|  | 0.195 |  |  | 0.8 |  | TTB4=7Pcs
[6 empty] | 87.08 | Axis y/02 - y/08 from ( x/01 - x/04)
1 | 1.4 | [5 empty] | Dev.L=0.30*2+0.20=0.80mt
| 0.15 |  | D5(1Pcs)
| 0.2 |  |  |  |  | 245.04 | m2 net area item 1.5
0.042
1.6)Lintel
5 | 1.8 |  |  | 1 | 1.6
| 0.15 |  | D2(5Pcs) |  | 0.55 |  | D9'(1Pc)
| 0.2 |  |  |  |  | 0.88
|  | 0.27 |  | 5 | 1.3
[5 empty] | 0.55 |  | D9(5Pcs)
5 | 1.6 |  |  |  |  | 3.575
| 0.15 |  | W9(5Pcs) | 1 | 1.4
| 0.2 |  |  |  | 0.55 |  | D5(1Pcs)
|  | 0.24 |  |  |  | 0.77
T | D | S | Item No. and Description | T | D | S | Item No. and Description
5 | 1.6 |  |  |  | 1.1
| 0.55 |  | W9(5Pcs) | 2 | 1.73 |  | W12(2Pcs)
|  | 4.4 |  |  |  | -3.806
8 | 1.2 |  |  |  | 1
| 0.55 |  | D7(8Pcs) | 2 | 1.73 |  | W14(2Pcs)
|  | 5.28 |  |  |  | -3.46
12 | 1.2 |  |  |  | 15.55
| 0.55 |  | D8(12Pcs) | 2 | 2.73 |  | Axis Y/01 &Y/09 from (X/01 - X/05)
|  | 7.92 |  |  |  | 84.903
5 | 1.8 |  |  |  | 1.15
| 0.55 |  | D2(5Pcs) | 2 | 16.35 |  | Above top tie deam
|  | 4.95 |  |  |  | 37.605
42.9
|  | 22.55 | m2 net area item 1.6 | 2 | 0.2 |  | "
17.16
|  |  | 1.7)ф14 mm deformed bars |  | 1.5
1 | 320.6016 |  |  | 2 | 1.73 |  | W2(2Pcs)
|  | 320.6016 | kg net weight item 1.7 |  |  | -5.19
1.5
|  |  | 1.8)ф12 mm deformed bars | 2 | 0.6 |  | W2(2Pcs)
1 | 2389.2794 |  |  |  |  | -1.8
|  | 2389.2794 | kg net weight item 1.8 |  | 1.1
|  |  |  | 1 | 1.73 |  | W12(1Pc)
|  |  | 1.9)ф8mm deformed bars |  |  | -1.903
1 | 783.8775 |  |  |  | 1.4
|  | 783.8775 | kg net weight item 1.9 | 1 | 2.73 |  | D2(1Pc)
-3.822
|  |  | 2)BLOCK WORK |  | 0.9
|  |  | 2.1)20cm thick HCB wall | 2 | 2.73 |  | D6(2Pcs)
1 | 41.1 |  | Axis X/01 from (Y/01 - Y/09) |  |  | -4.914
| 2.73 |  |  |  | 8.4
|  | 112.203 |  | 1 | 2.73 |  | Axis Y/05 from (X/04 - X/03)
10 | 1.5 |  | W2(10Pcs) |  |  | 22.932
| 1.73 |  |  |  | 5.85
|  | -25.95 |  | 4 | 3.06 |  | Axis Y/05',06',07'&O8'
2 | 1.1 |  | W12(2Pcs) |  |  | 71.604 | from (X/01 - X/02)
| 1.73 |  |  |  | 1.3
|  | -3.806 |  | 2 | 2.73 |  | D
1 | 1.5 |  | W16(1Pc) |  |  | -7.098
| 0.6 |  |  |  | 2.2
|  | -0.9 |  | 1 | 3.06 |  | Axis Y/07
1 | 0.9 |  | D6(1Pc) |  |  | 6.732
| 2.73 |  |  |  | 0.8
|  | -2.457 |  | 1 | 2.73 |  | D7(1Pc)
2 | 0.8 |  | D10(2Pcs) |  |  | -2.184
| 2.73 |  |  |  | 19.8
|  | -4.368 |  | 1 | 2.73 |  | Axis X/02 from (Y/05 - Y/09)
1 | 41.1 |  | Axis X/04 from (Y/01 - Y/09) |  |  | 54.054
| 2.73 |  |  |  | 0.9
|  | 112.203 |  | 4 | 2.73 |  | D9(4Pcs)
10 | 1.5 |  | W2(10Pcs) |  |  | -9.828
| 1.73 |  |  |  | 0.9
|  | -25.95 |  | 1 | 2.73 |  | D14(1Pcs)
1 | 1.3 |  | W4(1Pc) |  |  | -2.457
| 1.73 |  |  |  | 7
|  | -2.249 |  | 1 | 2.93 |  | Axis X/03' from (Y/07 - Y/09)
20.51
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 2.5 |  |  | 1 | 0.8
1 | 3.06 |  | Axis b/n x/02&03 at y/02' |  | 2.73 | -2.184 | D7(1Pc)
7.65
| 1.4 |  |  | 1 | 5.85
1 | 2.73 |  | D2(1Pc) |  | 3.06 | 17.901 | Axis Y/06' from X/03-X/04
-3.822
|  |  |  | 1 | 0.8
|  | 431.592 | m2 net area |  | 2.73 | -2.184 | D7(1Pc)
|  |  | 2.2)15cm thick HCB wall | 1 | 7.25
1 | 5.9 |  | Axis Y/02 from X/03-X/04 |  | 2.73 | 19.7925 | Axis Y/07 from X/01-X/02
| 2.73 | 16.107
|  |  |  | 1 | 2.15
1 | 7.25 |  | Axis Y/02' from X/01-X/02 |  | 3.06 | 6.579 | Axis Y/07' from X/01-X/02
| 3.06 | 22.185
|  |  |  | 1 | 7.25
2 | 0.9 |  | D9(2Pcs) |  | 2.73 | 19.7925 | Axis Y/08 from X/03-X/04
| 2.73 | -4.914
|  |  |  | 1 | 7.25
1 | 7.25 |  | Axis Y/02'' from X/02-X/01 |  | 2.73 | 19.7925 | Axis Y/08' from X/03-X/04
| 3.06 | 22.185
|  |  |  | 1 | 0.9
1 | 5.9 |  | Axis Y/03 from X/03-X/04 |  | 2.73 | -2.457 | D9(1Pc)
| 2.73 | 16.107
|  |  |  | 2 | 0.8
1 | 0.9 |  | D9(1Pc) |  | 2.73 | -4.368 | D7(2Pcs)
| 2.73 | -2.457
|  |  |  | 1 | 3.05
2 | 7.25 |  | Axis Y/03'&Y/03'' from X/01-X/02 |  | 3.06 | 9.333 | Axis b/n y/03 -04 & x/03 -04
| 3.06 | 44.37
|  |  |  | 1 | 0.9
1 | 0.9 |  | D9(1Pc) |  | 2.73 | -2.457 | D9(1Pc)
| 2.73 | -2.457
|  |  |  | 1 | 18.6
1 | 5.9 |  | Axis Y/03''' from X/03-X/04 |  | 2.73 | 50.778 | Axis X/03 from Y/01 - Y/05
| 3.06 | 18.054
|  |  |  | 1 | 3.35
1 | 5.9 |  | Axis Y/04 from X/01-X/02 |  | 2.73 | -9.1455
| 2.73 | 16.107
|  |  |  | 3 | 0.9
2 | 7.25 |  | Axis Y/04'&Y/4'' from X/03-X/04 |  | 2.73 | -7.371 | D9(3Pcs)
| 3.06 | 44.37
|  |  |  | 1 | 1.4
2 | 1.4 |  | D2(1Pc) |  | 2.73 | -3.822 | D2(1Pc)
| 2.73 | -7.644
|  |  |  | 1 | 29.9
1 | 7.25 |  | Axis Y/05' from X/01-X/02 |  | 2.73 | 81.627 | Axis X/02 from Y/01 - Y/09
| 3.06 | 22.185
|  |  |  | 3 | 0.9
1 | 0.8 |  | D7(1Pc) |  | 2.73 | -7.371 | D9(3Pcs)
| 2.73 | -2.184
|  |  |  | 1 | 1.4
1 | 7.25 |  | Axis Y/06 from X/01-X/02 |  | 2.73 | -3.822 | D2(1Pc)
| 2.73 | 19.7925
|  |  |  | 1 | 8.1
1 | 1.25 |  |  |  | 3.06 | 24.786 | Axis X/02' from Y/01 - Y/02'
| 1.73 | -2.1625 | W8(1Pc)
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 1.3 | [5 empty] | 3.4)Supply & fix G-28 gutter dev.
| 2.73 | -3.549 | D9'(1Pc) |  |  |  | length=50cm
|  |  |  | 2 | 44.1
1 | 1.8 |  |  |  |  | 88.2 | m net length item 3.3
| 3.06 | 5.508 | Axis X/02' from Y/03' - Y/03''
4)CARPENTRY
1 | 0.8 |  |  | 33 | 17.86 |  | 4.1)Uper & lower chord size 10-12cm
| 2.73 | -2.184 | D7(1Pc) |  |  | 589.38 | Upper L=8.93x2=17.86
1 | 2.5 |  |  | 33 | 17.15 |  | Lower L=8.85x2=17.70
| 3.06 | 7.65 | Axis X/02'' from Y/04' - Y/04'' |  |  | 565.95
1 | 0.8 |  |  |  |  | 1155.33 | m net length item 4.1
| 2.73 | -2.184 | D7(1Pc)
4.2)Vertical & Diagonal member
2 | 2.5 |  |  | 33 | 20.1 |  | V=20.10mt
| 3.06 | 15.3 | Axis b/n X/01&02 from Y/05' - Y/06 |  |  | 663.3 | D=25.32mt
|  |  |  | 33 | 25.32
1 | 0.8 |  |  |  |  | 835.56
| 2.73 | -2.184 | D7(1Pc)
[6 empty] | 1498.86 | m net length item 4.2
1 | 4.95
| 3.06 | 15.147 | Axis X/02 from Y/07 - Y/08 |  |  |  | 4.3)Purlin zigba 5/7cm
No .pur =8.93/0.9+1=12Pcs
1 | 1.4 |  |  | 22 | 44.1 |  | L=42.90+1.2=44.10mt
| 2.73 | -3.822 | D2(1Pc)
[6 empty] | 970.2 | m net length item 4.3
1 | 1.1 |  | W1
| 1.73 | -1.903 |  |  |  |  | 4.4)Zigba wooden fascia board
|  |  |  | 4 | 8.93
|  | 452.623 | m2 net area item 2.2 |  |  | 35.72
|  |  |  | 2 | 44.1
|  |  | 3)ROOFING WORK |  |  | 88.2
3.1)G-28 CIS Roof covering
1 | 17.55 |  | L=16.35+2x0.60=17.55mt |  |  | 123.92 | m net length item 4.4
| 44.1 |  | L=42.90+2x0.60=44.10mt
|  | 773.955 | m2 net area item 3.1 |  |  |  | WOODEN DOOR
4.6)Type D7 ,Size 80/273
|  |  | 3.2/G28 rebbed sheet | 1 | 4
|  |  | L= 42.9+0.6+0.6=4.10 |  |  | 4 | pcs net number item 4.6
2 | 44.1 |  | W=16.35+0.6+0.6=
| 0.6 | 52.92 | on axis x/01&x/04 |  |  |  | 4.7)Type D8 ,Size 70/273
|  |  |  | 1 | 5
4 | 8.95 |  |  |  |  | 5 | pcs net number item 4.7
| 0.6 | 21.48 | on axis y/01&xy/09
4.8)Type D9 ,Size 90/273
|  | 74.4 | m2 net area item 3.2 | 1 | 15
[6 empty] | 15 | pcs net number item 4.8
3.3)Ridg cover &Flashing in metal sheet
1 | 44.1 |  | Dev. Length 33cm |  |  |  | 4.9)Type D9 ,Size 130/273
|  | 44.1 |  | 1 | 2
| 8.93 |  |  |  |  | 2 | pcs net number item 4.9
4 | 0.5
|  | 17.86 |  |  |  |  | 4.10)Type D9 ,Size 140/273
|  |  |  | 1 | 7
|  | 61.96 | m net length item 3.3 |  |  | 7 | pcs net number item 4.10
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 5)METAL WORK | 1 | 1.3 |  | W4(1Pcs)
|  |  | 5.1)Type W2 ,Size 150/273 |  | 1.73 | -2.249
1 | 22
|  | 22 | pcs net number item 5.1 | 2 | 1.1 |  | W12(2Pcs)
[5 empty] | 1.73 | -3.806
5.2)Type W4 ,Size 130/273
1 | 3 |  |  | 2 | 1 |  | W14(2Pcs)
|  | 3 | pcs net number item 5.2 |  | 1.73 | -3.46
|  |  | 5.3)Type W14 ,Size 100/173 | 1 | 1.4 |  | D1(1Pcs)
2 | 2 |  |  |  | 2.73 | -3.822
|  | 4 | pcs net number item 5.3
|  |  |  | 1 | 1.3 |  | D3(1Pcs)
|  |  | 5.4)Type W16 ,Size 150/60 |  | 2.73 | -3.549
1 | 3
|  | 3 | pcs net number item 5.4 | 2 | 15.55 |  | Axis Y/01 &Y/09 from (X/01 - X/04)
[5 empty] | 2.73 | 84.903
METAL DOOR
|  |  | 5.6)Type D1 ,Size 140/273 | 2 | 1.5 |  | W2(2Pcs)
1 | 2 |  |  |  | 1.73 | -5.19
|  | 2 | pcs net number item 5.6
|  |  |  | 2 | 1.5 |  | W2(2Pcs)
|  |  | 5.7)Type D6 ,Size 90/273 |  | 0.6 | -1.8
1 | 4
|  | 4 | pcs net number item 5.7 | 1 | 1.1 |  | W12(1Pcs)
[5 empty] | 1.73 | -1.903
5.8)Type D10 ,Size 80/273
1 | 2 |  |  | 1 | 1.4 |  | D2(1Pcs)
|  | 2 | pcs net number item 5.8 |  | 2.73 | -3.822
|  |  | 5.9)Type D ,Size 130/273 | 2 | 0.9 |  | D6(2Pcs)
1 | 1 |  |  |  | 2.73 | -4.914
|  | 1 | pcs net number item 5.9
|  |  |  | 2 | 0.5
|  |  | 6)FINISHING WORK |  | 2.73 | 2.73
|  |  |  | 2 | 42.9 |  | Above top tie beam
1 | 41.1 |  | Axis X/01 from (Y/01- Y/09) |  | 0.2 | 17.16
| 2.73 | 112.203
|  |  |  | 2 | 1.15 |  | Above top tie beam
10 | 1.5 |  | W2(10Pcs) |  | 16.35 | 37.605
| 1.73 | -25.95
[6 empty] | 267.301 | m2 net area item 6.1
2 | 1.1 |  | W12(2Pcs)
| 1.73 | -3.806 |  |  |  |  | 6.2)Apply three coats of plastering to
internal wall & external beam & colu.
2 | 0.9 |  | D6(1Pcs) | 1 | 17 |  | Disinfection
| 2.73 | -4.914 |  |  | 3.06 | 52.02 | L=5*2+3.5*2=17.00mt
2 | 0.8 |  | D10(1Pcs) | 2 | 1.5 |  | W2(2Pcs)
| 2.73 | -4.368 |  |  | 1.73 | -5.19
1 | 41.1 |  | Axis X/04 from (Y/01- Y/09) | 1 | 1.3 |  | D9'(1PC)
| 2.73 | 112.203 |  |  | 2.73 | -3.549
10 | 1.5 |  | W2(10Pcs) | 1 | 0.9 |  | D9(1Pc)
| 1.73 | -25.95 |  |  | 2.73 | -2.457
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 17.2 |  | Auto clave | 1 | 10.2 |  | Toilet
| 3.06 | 52.632 | l=5*2+3.6*2=17.20mt |  | 3.06 | 31.212
1 | 1.5 |  | W2(1Pcs) | 1 | 10.8
| 1.73 | -2.595 |  |  | 3.06 | 33.048
1 | 0.9 |  | D9' | 1 | 0.8 |  | D7(2Pcs)
| 2.73 | -2.457 |  |  | 2.73 | -2.184
1 | 0.9 |  | D9(Pcs) | 1 | 1.5 |  | W2(1Pcs)
| 2.73 | -2.457 |  |  | 1.73 | -2.595
1 | 13.2 |  | Sorting | 1 | 25 |  | Laboring
| 3.06 | 40.392 | L=3.1X2+3.5X2=13.20mt |  | 3.06 | 76.5 | L=5.25.2+7.25X2=25.00mt
1 | 0.9 |  | D6(1Pcs) | 1 | 1.4 |  | D2(1Pcs)
| 2.73 | -2.457 |  |  | 2.73 | -3.822
1 | 0.9 |  | D9(Pcs) | 1 | 0.9
| 2.73 | -2.457 |  |  | 2.73 | -2.457
1 | 1.5 |  | W2(1Pcs) | 2 | 1.5 |  | W2(2Pcs)
| 1.73 | -2.595 |  |  | 1.73 | -5.19
1 | 13.4 |  | Clean supply | 1 | 11.2 |  | Utility room
| 3.06 | 41.004 | L=3.1X2+3.6X2=13.40mt |  | 3.06 | 34.272 | L=2.50X2+3.10X2=11.20mt
2 | 0.9 |  | D9(2Pcs) | 2 | 0.8 |  | D10&D7
| 2.73 | -4.914 |  |  | 2.73 | -4.368
1 | 10 |  | Handicupped | 1 | 1.1 |  | W12(1Pcs)
| 3.06 | 30.6 | L=2.95X2+2.05X2=10.00mt |  | 1.73 | -1.903
1 | 1 |  | D5(1Pc) | 1 | 10.8 |  | Utility room Enterance
| 2.73 | -2.73 |  |  | 3.06 | 33.048 | L=2.50+4.15X2=10.80mt
1 | 1.5 |  | W2(1Pcs) | 2 | 1.4 |  | D2(2Pcs)
| 1.73 | -2.595 |  |  | 2.73 | -7.644
1 | 1.1 |  | W9(1Pcs) | 1 | 0.8 |  | D7
| 0.6 | -0.66 |  |  | 2.73 | -2.184
Delivery
2 | 13.2 |  | Toilet |  |  |  | L=3.45x2+7.25x2-0.80-1.40=19.20mt
| 3.06 | 80.784 | L=(2x1.5)+(5.1x2)=13.20mt | 1 | 19.2
[5 empty] | 3.06 | 58.752
1 | 1 |  | D5(1Pc)
| 2.73 | -2.73 |  | 1 | 10.7 |  | Slice
[5 empty] | 3.06 | 32.742 | L=2.50X2+2.85X2=10.70mt
1 | 0.9 |  | D9(1Pcs)
| 2.73 | -2.457 |  | 1 | 0.8 |  | D10(1Pcs)
[5 empty] | 2.63 | -2.104
4 | 0.7 |  | D8(8Pcs)
| 2.73 | -7.644 |  | 2 | 0.8 |  | D7(2Pcs)
[5 empty] | 3.06 | -4.896
8 | 1.4
| 3.06 | 34.272
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 10.4 |  | Sterile | 1 | 0.9
| 3.06 | 31.824 | L=2.50X2+2.70X2=10.40mt |  | 2.73 | -2.457 | D9(1Pcs)
1 | 0.8 |  | D7(1Pcs) | 2 | 8.1 |  | Toilet
| 2.73 | -2.184 |  |  | 3.06 | 49.572 | L=1.50X2+2.55X2=8.10mt
1 | 1.1 |  | W8(1Pcs) | 2 | 1.5 |  | W2(2Pcs)
| 1.73 | -1.903 |  |  | 1.73 | -5.19
1 | 5.6 |  | Scrub up | 1 | 3.31 |  | Opening
| 3.06 | 17.136 | L=2.5+1.55X2=5.60mt |  | 3.06 | -10.1286
1 | 0.8 |  | D7(1Pcs) | 1 | 1.4 |  | D1(1Pcs)
| 2.73 | -2.184 |  |  | 2.73 | -3.822
OR
1 | 22.3 |  | L=5.00x2+7.25x2-0.80-1.40=22.30mt | 1 | 11 |  | Changing room
| 3.06 | 68.238 |  |  | 3.06 | 33.66 | L=3.05X2+2.45X2=11.00mt
1 | 20.1 |  | Recovery | 2 | 0.9 |  | D9(2Pcs)
| 3.06 | 61.506 | L=4.95X2+5.10X2=20.10mt |  | 2.73 | -4.914
2 | 1.5 |  | W2(2Pcs) | 1 | 12.7 |  | Preparation room
| 1.73 | -5.19 |  |  | 3.06 | 38.862 | L=3.05 X2+3.30X2=12.70mt
1 | 1.4 |  | D2(1Pcs) | 2 | 0.9 |  | D9(2Pcs)
| 2.73 | -3.822 |  |  | 2.73 | -4.914
1 | 1.1 |  | W8(1Pcs) | 1 | 1.5 |  | W2(1Pcs)
| 1.73 | -1.903 |  |  | 1.73 | -2.595
1 | 13.4 |  | Nurse station | 1 | 17.2 |  | Nurse station
| 3.06 | 41.004 | L=2.15+4+4.80=13.40mt |  | 3.06 | 52.632 | L=2.70X2+5.95X2=17.20mt
1 | 1.4 |  | D2(1Pcs) | 1 | 1.5 |  | W2(1Pcs)
| 2.73 | -3.822 |  |  | 1.73 | -2.595
1 | 1.1 |  | W8(1Pcs) | 1 | 0.9 |  | D9(1Pcs)
| 1.73 | -1.903 |  |  | 2.73 | -2.457
1 | 16.2 |  | Corridor | 1 | 23.6 |  | Postnatal
| 3.06 | 49.572 | L=1.40+7.40X2=16.20mt |  | 3.06 | 72.216 | L=5.95X2+5.85x2=23.60mt
1 | 0.9 |  | D9(1Pcs) | 1 | 1.4 |  | D2(1Pcs)
| 2.73 | -2.457 |  |  | 2.73 | -3.822
2 | 0.8 |  | D7(2Pcs) | 2 | 1.5 |  | W2(2Pcs)
| 2.73 | -4.368 |  |  | 1.73 | -5.19
1 | 1.1 |  | W12(1Pcs) | 1 | 16.2 |  | Clean supply
| 1.73 | -1.903 |  |  | 3.06 | 49.572 | L=2.25X2+5.85X2=16.20mt
| 9.88 |  | Toilet | 1 | 0.9 |  | D9(1Pcs)
1 | 3.06 | 30.2328 | L=2.95X2+1.98X2=9.88mt |  | 2.73 | -2.457
| 1.5 |  | W12(1Pcs) | 1 | 1 |  | W14(1Pcs)
1 | 1.73 | -2.595 |  |  | 1.73 | -1.73
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 18.6 |  | Anesthesian | 1 | 1.1 |  | W12(1Pcs)
| 3.06 | 56.916 | L=3.45X2+5.85X2=18.60mt |  | 1.73 | -1.903
1 | 1.5 |  | W2(1Pcs) | 1 | 13.2 |  | Instrument room
| 1.73 | -2.595 |  |  | 3.06 | 40.392 | L=3.35X2+3.25X2=13.20mt
1 | 0.9 |  | D9(1Pcs) | 2 | 0.9 |  | D6 & D9
| 2.73 | -2.457 |  |  | 2.73 | -4.914
2 | 19.1 |  | Toilet | 1 | 1.1 |  | W12(1Pcs)
| 3.06 | 116.892 |  |  | 1.73 | -1.903
4 | 5 |  | " | 1 | 11.5 |  | Store
| 3.06 | 61.2 |  |  | 3.06 | 35.19 | L=3.35X2+2.40X2=11.50mt
2 | 0.8 |  | D7(2Pcs) | 1 | 1 |  | W14(1Pcs)
| 2.73 | -4.368 |  |  | 1.73 | -1.73
8 | 0.7 |  | D8(8Pcs) | 1 | 1.3 |  | W4(1Pcs)
| 2.73 | -15.288 |  |  | 1.73 | -2.249
8 | 1.1 |  | W9(1Pcs) | 1 | 0.9 |  | D6(1Pcs)
| 0.6 | -5.28 |  |  | 2.73 | -2.457
1 | 1.5 |  | W2(1Pcs) | 1 | 29.85 |  | Corridor
| 1.73 | -2.595 |  |  | 3.06 | 91.341
1 | 1.1 |  | W12(1Pcs) | 3 | 1.4 |  | D2(3Pcs)
| 1.73 | -1.903 |  |  | 2.73 | -11.466
1 | 1.3 |  | D3(1Pcs) | 4 | 0.9 |  | D9(4Pcs)
| 1.73 | -2.249 |  |  | 2.73 | -9.828
1 | 0.9 |  | D6(1Pcs) | 1 | 5.8 |  | L=3.30+2.50=5.80mt
| 2.73 | -2.457 |  |  | 3.06 | 17.748
1 | 6.9 |  | Toilet enterance | 1 | 37.7 |  | Corridor
| 3.06 | 21.114 | L=1.25X2+2.20X2=6.90mt |  | 3.06 | 115.362
| 0.8 |  | D7(2Pcs) | 3 | 1.4 |  | D2(3Pcs)
2 | 2.73 | -4.368 |  |  | 2.73 | -11.466
| 0.9 |  | D14(1Pcs) | 5 | 0.9 |  | D9(4Pcs)& D14(1Pcs)
1 | 2.73 | -2.457 |  |  | 2.73 | -12.285
1 | 13.8 |  | Changing room | 7 | 2.5
| 3.06 | 42.228 | L=3.65X2+3.25X2=13.20mt |  | 3.06 | 53.55 | Corridor
1 | 0.9 |  | D9(1Pcs) | 1 | 5.2
| 2.73 | -2.457 |  |  | 3.06 | 15.912 | "
1 | 12.1 |  | Preparation admission room | 4 | 7.25 |  | Axisy/02 - y/05 from (x/03-x/04)
| 3.06 | 37.026 | L=3.65X2+2.40X2=12.10mt |  | 3.06 | 88.74
1 | 1.3 |  | D9'(1Pcs) | 1 | 11.5 |  | Axisy/06 - y/08 from (x/01-x/02)
| 2.73 | -3.549 |  |  | 3.06 | 35.19
|  |  |  | 22 | 0.2 |  | External column
[5 empty] | 2.73 | 12.012
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 42.9 |  | X Axis top tie beam | 1 | 2.7 |  | Sterile
| 0.3 | 25.74 |  |  | 2.5 | 6.75
2 | 16.35 |  | Y Axis top tie beam | 1 | 1.4 |  | Scrub up
| 0.3 | 9.81 |  |  | 2.5 | 3.5
2 | 42.9 |  | X Axis top Grade beam | 1 | 4.95 |  | Recovery room
| 0.4 | 34.32 |  |  | 5.1 | 25.245
2 | 16.35 |  | Y Axis top Grade beam | 1 | 2.15 |  | Enterance
| 0.4 | 13.08 |  |  | 2 | 4.3
|  | 1863.0472 | m2 before Deduction | 1 | 2.15 |  | Nurse station
[5 empty] | 2.8 | 6.02
|  | 346.4 | DDT Ceramic wall
|  |  |  | 1 | 7.25 |  | Corridor
|  | 1516.6472 | m2 net area item 6.2 |  | 1.4 | 10.15
|  |  | 6.3)8mm thick chipwood ceiling | 1 | 1.99 |  | Handicapped toilet
1 | 3.5 |  | Disinfection washing |  | 2.95 | 5.8705
| 5 | 17.5
|  |  |  | 1 | 2.5 |  | Toilet
1 | 3.6 |  | Auto clave |  | 1.5 | 3.75
| 5 | 18
|  |  |  | 1 | 2.55
1 | 3.5 |  | Sorting |  | 1.5 | 3.825
| 3.1 | 10.85
|  |  |  | 1 | 2.55
1 | 3.6 |  | Clean supply |  | 1.4 | 3.57
| 3.1 | 11.16
|  |  |  | 1 | 5.9 |  | Doctor's office
1 | 2.05 |  | Handicapped toilet |  | 4.5 | 26.55
| 2.95 | 6.0475
|  |  |  | 1 | 5.9 |  | Wating area
1 | 5.05 |  | Toilet |  | 5.85 | 34.515
| 2.95 | 14.8975
|  |  |  | 1 | 2.45 |  | Changing room
1 | 3.5 |  | " |  | 3.05 | 7.4725
| 1.8 | 6.3
|  |  |  | 1 | 3.3 |  | Preparation room
1 | 3.6 |  | " |  | 3.05 | 10.065
| 1.8 | 6.48
|  |  |  | 1 | 5.9 |  | Nurse station
1 | 7.25 |  | Labouring |  | 2.7 | 15.93
| 5.05 | 36.6125
|  |  |  | 1 | 5.9 |  | Postnatal room
1 | 3.1 |  | Utility room |  | 5.8 | 34.22
| 2.5 | 7.75
|  |  |  | 1 | 5.9 |  | Clean supply
1 | 4.15 |  | " |  | 2.25 | 13.275
| 2.5 | 10.375
|  |  |  | 1 | 5.85 |  | Ansthesian room
1 | 2.85 |  | Slice room |  | 3.45 | 20.1825
| 2.5 | 7.125
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 2.2 |  | Staff ladies | 1 | 2.05 |  | Handicapped toilet
| 2.3 | 5.06 |  |  | 2.95 | 6.0475
1 | 2.5
| 1.68 | 4.2 |  | 1 | 4.9 |  | Toilet
1 | 1.15 |  |  |  | 2.95 | 14.455
| 3.05 | 3.5075
1 | 2.2 |  | Enternce toilet | 1 | 3.5
| 1.25 | 2.75 |  |  | 1.8 | 6.3 | "
1 | 2.2 |  | Gentle man
| 2.4 | 5.28 |  | 1 | 3.6
1 | 2.5 |  |  |  | 1.8 | 6.48 | "
| 1.68 | 4.2
1 | 1.15 |  |  | 1 | 7.25 |  | Labouring
| 3.08 | 3.542 |  |  | 5.25 | 38.0625
2 | 1
| 1.3 | 2.6 |  | 1 | 3.1 |  | Utility room
2 | 1.2 |  |  |  | 2.5 | 7.75
| 1.3 | 3.12
1 | 3.25 |  | Changing room | 1 | 4.15 |  | "
| 3.65 | 11.8625 |  |  | 2.5 | 10.375
1 | 2.4 |  | Preparation/ admission room
| 3.65 | 8.76 |  | 1 | 2.85 |  | Slice room
1 | 3.25 |  | Instrument room |  | 2.5 | 7.125
| 3.35 | 10.8875
1 | 2.4 |  | Store | 1 | 2.7 |  | Sterile
| 3.35 | 8.04 |  |  | 2.5 | 6.75
1 | 2.5 |  | Corridor
| 40.7 | 101.75 |  | 1 | 1.55 |  | Scrub up
|  | 563.8475 | m2 net area item 6.3 |  | 2.5 | 3.875
|  |  |  | 1 | 5.1 |  | Recovery room
[5 empty] | 4.95 | 25.245
|  |  |  | 1 | 2.15 |  | Enterance
[5 empty] | 2 | 4.3
|  |  |  | 1 | 2.15 |  | Nurse station
[5 empty] | 2.8 | 6.02
|  |  |  | 1 | 7.4 |  | Corridor
[5 empty] | 1.4 | 10.36
|  |  |  | 1 | 1.99 |  | Handicapped toilet
[5 empty] | 2.95 | 5.8705
|  |  |  | 1 | 2.5 |  | Toilet
[5 empty] | 1.5 | 3.75
|  |  |  | 1 | 2.55
|  |  | 6.7)Approved type 9mm cearmic Floor |  | 1.5 | 3.825
1 | 3.5 |  | Disinfection washing
| 5 | 17.5 |  | 4 | 1.24
1 | 3.6 |  | Auto clave |  | 1.4 | 6.944
| 5 | 18
1 | 3.5 |  | Sorting | 1 | 5.9 |  | Doctor's office
| 3.1 | 10.85 |  |  | 4.5 | 26.55
1 | 3.6 |  | Clean supply
| 3.1 | 11.16
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 5.9 |  | Wating area | 1 | 2.4 |  | Store
| 5.85 | 34.515 |  |  | 3.35 | 8.04
1 | 3.28 |  | " | 1 | 2.5 |  | Corridor
| 0.15 | 0.492 |  |  | 42.1 | 105.25
1 | 2.45 |  | Changing room | 2 | 1.3 |  | D9'
| 3.05 | 7.4725 |  |  | 0.15 | 0.39
1 | 3.3 |  | Preparation room | 21 | 0.9 |  | D9(17) &D6(4)
| 3.05 | 10.065 |  |  | 0.15 | 2.835
1 | 5.9 |  | Nurse station | 11 | 0.8 |  | D7&D10
| 2.7 | 15.93 |  |  | 0.15 | 1.32
1 | 5.9 |  | Postnatal room | 9 | 1.4 |  | D2(8)&D1(1)
| 5.8 | 34.22 |  |  | 0.15 | 1.89
1 | 5.9 |  | Clean supply | 1 | 1.3 |  | D3
| 2.25 | 13.275 |  |  | 0.2 | 0.26
1 | 5.85 |  | Ansthesian room | 12 | 0.7 |  | D8
| 3.45 | 20.1825 |  |  | 0.1 | 0.84
1 | 2.2 |  | Staff ladies | 1 | 1 |  | D5
| 2.3 | 5.06 |  |  | 0.15 | 0.15
1 | 2.5 |  |  | 1 | 7.25 |  | Delivery room
| 1.68 | 4.2 |  |  | 3.45 | 25.0125
1 | 1.15 |  |  | 1 | 7.25 |  | OR/SURGORY
| 3.05 | 3.5075 |  |  | 5 | 36.25
1 | 2.2 |  | Enternce toilet |  |  | 641.7535 | m2 net area item 6.7
| 1.25 | 2.75
6.8)Approved type 10/0.9mm skirting
1 | 2.2 |  | Gentle man |  | 15.2 |  | Disinfection washing
| 2.4 | 5.28 |  |  |  | 15.2 | L=3.5*2+5*2-1.3-0.9=14.80mt
1 | 2.5 |  |  |  | 15.4 |  | Auto clave
| 1.68 | 4.2 |  |  |  | 15.4 | L=3.6*2+5*2-1.3-0.9=15.00mt
1 | 1.15 |  |  |  | 11.4 |  | Sorting
| 3.08 | 3.542 |  |  |  | 11.4 | L=3.5*2+3.1*2-0.9*2=11.4mt
2 | 1 |  |  |  | 11.6 |  | Clean supply
| 1.3 | 2.6 |  |  |  | 11.6 | L=3.6*2+3.1*2-0.9*2=11.60mt
2 | 1.2 |  |  |  | 8.2 |  | "
| 1.3 | 3.12 |  |  |  | 8.2 | L=3.6*2+1.8*2-0.8-0.9X2=8.20mt
1 | 3.25 |  | Changing room |  | 22.7 |  | Labouring
| 3.65 | 11.8625 |  |  |  | 22.7 | L=7.25*2+5.25*2-0.9-1.4=22.70mt
1 | 2.4 |  | Preparation/ admission room |  | 9.5 |  | Utility room
| 3.65 | 8.76 |  |  |  | 9.5 | L=3.10*2+2.5*2-0.80-0.90=9.5mt
1 | 3.25 |  | Instrument room |  | 8.2 |  | Slice room
| 3.35 | 10.8875 |  |  |  | 8.2 | L=2.5*2+2.85*2-0.8*2-0.90=8.20mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
| 9.6 |  | Sterile |  | 11.4 |  | Instrument room
|  | 9.6 | L=2.5*2+2.70*2-0.80=9.60mt |  |  | 11.4 | L=3.35*2+3.25*2-0.90*2=11.40mt
| 18.4 |  | Recovery room |  | 10.6 |  | Store
|  | 18.4 | L=4.95*4-1.4=18.40mt |  |  | 10.6 | L=3.35*2+2.4*2-0.90=10.60mt
| 4.9 |  | Enterance |  | 23.08 |  | Corridor
|  | 4.9 | L=2.15*2+2-1.4=4.90mt |  |  | 23.08 | L=12+2.5*2+12.28-2.5-.90-1.4*2=23.08ml
| 7.1 |  | Nurse station |  | 28 |  | "
|  | 7.1 | L=2.15*2+2.80=7.10mt |  |  | 28 | L=19.7*2+2.5*2+0.5*2-2.5-2-2.8-
1.4-1.4*3-0.90*5=28.00mt
| 13.8 |  | Corridor
|  | 13.8 | L=7.45*2+1.4-0.8*2-0.9=13.80mt |  |  | 419.09 | ml net length item no 6.80
| 15.84 |  | Corridor Office |  |  |  | 6.9)Terrazzo window cill
|  | 15.84 | L=7.02*2+2,5*2-1.4-.9*2=15.84mt |  |  |  | Size:-27/3cm
|  |  |  | 24 | 1.55 |  | W2(24Pcs)
| 19.9 |  | Doctor's office |  |  | 37.2
|  | 19.9 | L=5.9*2+4.5*2-0.90=19.90mt
|  |  |  | 1 | 1.05 |  | W4(1Pc)
| 20.37 |  | Wating area |  |  | 1.05
|  | 20.37 | L=5.90+6.05+5.85+2.57=20.37mt
|  |  |  | 5 | 1.15 |  | W12(5Pcs)
| 9.2 |  | Changing room |  |  | 5.75
|  | 9.2 | L=3.05*2+2.45*2-0.9*2=9.20mt
|  |  |  | 2 | 1.35 |  | w14(2Pcs)
| 10.9 |  | Preparation room |  |  | 2.7
|  | 10.9 | L=3.05*2+3.3*2-0.9*2=10.90mt
|  |  |  | 1 | 1.55 |  | W16(1Pc)
| 16.3 |  | Nurse station |  |  | 1.55
|  | 16.3 | L=2.7*2+5.9*2-0.90=16.30mt
[6 empty] | 48.25 | ml net length item no 6.90
| 22 |  | Postnatal room
|  | 22 | L=5.90*2+5.80*2-1.40=22.00mt |  |  |  | 6.11)10cm thick concrete pavement
|  |  |  | 2 | 44.1
| 15.3 |  | Clean supply |  | 1.2 | 105.84 | L=42.90+1.20=44.10mt
|  | 15.3 | L=2.25*2+585*2-0.90=15.30mt
|  |  |  | 1 | 16.35
| 14.4 |  |  |  | 1.2 | 19.62 | L=16.35mt
|  | 14.4 | L=5.85*2+2.3*2+.6*2-.7*2-.9-.8=14.40mt
[6 empty] | 125.46 | m2 net area item no 6.11
| 17.7 |  | Ansthesian room
|  | 17.7 | L=3.45*2+5.85*2-0.90=17.70mt |  |  |  | 6.9)Half Concrete pipe ditch
| 4.4 |  |  | 1 | 44.1 |  | L=42.90+1.2X1+0.3=44.40mt
|  | 4.4 | L=1.25*2+2.2*2-0.8*2-0.9=4.40mt |  |  | 44.1
|  |  |  | 1 | 18.75 |  | 16.35+1.2X2=18.75mt
| 12.9 |  | Changing room |  |  | 18.75
|  | 12.9 | L=3.65*2+3.25*2-0.90=12.90mt
[6 empty] | 62.85 | ml net length item no 6.12
| 10.8 |  | Preparation/ admission room
|  | 10.8 | L=3.65*2+2.40*2-1.20=10.90mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.13)Constructe 10/40 cm curbstone | 1 | 55.79 |  | ф 75mm
2 | 0 |  | L=42.90+1.2+0.3+.15+.1=44.65mt |  |  | 55.79 | m net length item 9.5.b
0
|  |  |  | 1 | 38.37 |  | ф 100mm
1 | 29.5 |  | L=16.35+1.2X2+.3X2+0.15x2=19.65mt |  |  | 38.37 | m net length item 9.5.c
29.5
9.9)Supply & fix toilet paper holder
|  | 29.5 | ml net length item no 6.13 | 9 | 1
[6 empty] | 9 | no net number item 9.9
7)Painting
|  |  | 7.1)Int. plastered surface & ext beam & colun |  |  |  | 10. Electrical Installation
2.00)LIGHT POINT
|  | 1516.6472 | m2 net area item 7.1 |  |  |  | 2.01points conduti of 16mm 3*2.5mm2
|  |  |  | 104 | 1
|  |  | 7.2)Chip wood ceiling surface |  |  | 104 | no net number item 2.01
|  | 563.8475 | m2 net area item 7.2
3.00)SWITCH
|  |  | 7.3)External rendered surface |  |  |  | 3.01)Single Switch legrand
|  | 267.301 | m2 net area item 7.3 | 38 | 1
[6 empty] | 38 | no net number item 3.01
9. Sanitary Installation
|  |  | 9.1- Supply & Install PP-R pipes |  |  |  | 3.02)Double Switch legrand
|  |  | 20mm dia. Internal | 23 | 1
1 | 16 |  | Toilet Handi. |  |  | 23 | no net number item 3.02
16
4.00)Socket outlet point
1 | 9.6 |  | Tiolet Gents & Ladies |  |  |  | 4.01)Socket outlet point 3x2.5mm2
|  | 9.6 |  | 64 | 1
[6 empty] | 64 | no net number item 4.01
|  | 25.6 | m net length item 9.1.b
4.02)Ditto 4.01 but water heater
|  |  | 25mm dia. Internal | 11 | 1
1 | 10.5 |  | Toilet Handi. |  |  | 11 | no net number item 4.02
10.5
4.03)Ditto 4.01 but 4x3mm2
1 | 8.2 |  | Tiolet Gents & Ladies | 1 | 1
|  | 8.2 |  |  |  | 1 | no net number item 4.03
|  | 18.7 | m net length item 9.1.c |  |  |  | 5)Socket outlets
5.01)Socket outlets LEGRAND SUNO
|  |  | 32mm dia. Internal | 64 | 1
1 | 4.55 |  | Toilet Handi. |  |  | 64 | no net number item 5.01
|  | 4.55 | m net length item 9.1.d
5.02)Water proof LEGRAND SUNO
|  |  | 40mm dia. Internal | 11 | 1
1 | 1.6 |  | Toilet Handi. |  |  | 11 | no net number item 5.02
|  | 1.6 | m net length item 9.1.e
5.03)Ditto as above 25A/1PH
|  |  | 9.3)Supply & fix bronze gate valve | 1 | 1
1 | 5 |  | 15mm diameter |  |  | 1 | no net number item 5.03
|  | 5 | no pcs number item 9.3
6.00)Telephone/data point
|  |  | 9.5)Supply & install waste water pipe made of rigid UPVC |  |  |  | 6.01)Telephone point feed through cat 5E UTP Cable
1 | 65.79 |  | ф 50mm | 17 | 1
|  | 65.79 | m net length item 9.5.a |  |  | 17 | no net number item 6.01
T | D | S | Item No. and Description | T | D | S | Item No. and Description
7. Type of light fittings
32 | 1 |  | 7.02)Philips TCS 098/236/2xTL-D 36W
|  | 32 | no net number item 7.02
24 | 1 |  | 7.01)Philips TCS 098/136/1xTL-D 36W
|  | 24 | no net number item 7.01
7.03)RZB 59251.002Q/E27/60W
21 | 1
|  | 21 | no net number item 7.03
7.04)RZB 59222.002Q/E27/60W
13 | 1
|  | 13 | no net number item 7.04
7.05)Massive3202/67/10
14 | 1
|  | 14 | no net number item 7.05
8)TV POINTS
8.01)TV point fed through RG6
1 | 1 |  | Coaxial 75ohm Tv cable
|  | 1 | no net number item 8.01
10.0 Cable way and Manhole
10.03 Rigid pvc pipe of dia.25mm For 4x4mm2
1 | 35
|  | 35 | ml net length item 10.03
10.4 Rigid pvc pipe dia. 50mm to
telephone Distribution frame
1 | 13.45
|  | 13.45 | ml net length item 10.04
no | Size | Product | Description | no | Size | Product | Description
|  |  | 6.5)Approved type 6mm thick |  | 4.58 | 0
| 9 |  | Toilet 1 handy cup | 1 | 1.8 | 0 | L=1.4x2+1.24x2-0.7=4.58mt
1 | 1.8 |  | L=2.95X2+2.05X2-1=9.00mt |  |  | 8.244
|  | 16.2 |  |  | 4.62 | 0
| 8.4 | 0 |  | 1 | 1.8 | 0 | L=1.4x2+1.26x2-0.7=4.62mt
1 | 1.8 | 0 | L=5.05X2+1.5X2-1-0.9-0.7X4=8.40mt |  |  | 8.316
|  | 15.12 |  |  | 0.8 | 0 | L=1.5+1.25=2.75mt
| 4.58 | 0 |  | 8 | 0.6 | 0
2 | 1.8 | 0 | L=1.24x2+1.4x2-0.7=4.58mt |  |  | 3.84
|  | 16.488 |  |  | 4.3
| 4.58 | 0 |  | 2 | 1.8 |  | L=1.2x2+1.3x2-0.7=4.30mt
2 | 1.8 | 0 | L=1.24X2+1.4X2-0.7=4.58mt |  |  | 15.48
|  | 16.488 |  |  | 3.9 | 0
| 9.8 | 0 |  | 2 | 1.8 | 0 | L=1x2+1.3x2-0.7=3.90mt
1 | 1.8 | 0 | L=1.8x2+3.5x2-0.8=9.80mt |  |  | 14.04
|  | 17.64 |  |  | 5.26 | 0
| 7.2 | 0 | Front ofUtility room | 2 | 1.8 | 0 | L=1.15+1.4+2.5+0.61-0.7X2=4.26mt
1 | 1.8 | 0 | L=4.15x2+2.5-1.4x2-0.8=7.20mt |  |  | 18.936
|  | 12.96 |  |  | 2.18 | 0
| 4.7 | 0 | Scrub up | 2 | 0.9 | 0
1 | 1.8 | 0 | L=1.50x2+2.5-0.8=4.70mt |  |  | 3.924
8.46
| 19.2 | 0 | Delivery |  |  | 346.3975
1 | 2.93 | 0 | L=3.45x2+7.25x2-0.80-1.40=19.20mt |  |  |  | TOTAL=346.40m2
56.256
| 1.5 | 0
1 | 1.73 | 0 | W2
-2.595
| 22.3 |  | OR
1 | 2.93 |  | L=5.00x2+7.25x2-0.80-1.40=22.30mt
65.339
1.25
1 | 1.73 |  | W8
-2.1625
| 8.98 | 0
1 | 1.8 | 0 | L=2.95x2+1.99x2-0.90=8.98
16.164
| 5.8 | 0
2 | 1.8 | 0 | L=1.5x2+2.5x2-0.7x2-0.8=5.80mt
20.88
| 4.52 | 0
1 | 1.8 | 0 | L=1.4x2+1.21x2-0.7=4.52mt
8.136
| 4.58 | 0
1 | 1.8 | 0 | L=1.4x2+1.24x2-0.7=4.58mt
8.244

## OR-Reinf
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [9 empty] | Block : OR & Delivery
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 & GB2 | 14 | 11.9 | 3 | 4 | 12 | - | - | - | - | 142.8
|  |  | 14 | 11.75 | 3 | 4 | 12 | - | - | - | - | 141
|  |  | 14 | 11.65 | 3 | 4 | 12 | - | - | - | - | 139.8
|  |  | 14 | 10.45 | 3 | 4 | 12 | - | - | - | - | 125.4
|  |  | 14 | 11.6 | 3 | 4 | 12 | - | - | - | - | 139.2
|  |  | 14 | 11.55 | 3 | 4 | 12 | - | - | - | - | 138.6
|  |  | 14 | 11.85 | 3 | 4 | 12 | - | - | - | - | 142.2
|  |  | 14 | 10.7 | 3 | 4 | 12 | - | - | - | - | 128.4
|  |  | 14 | 8.18 | 3 | 9 | 27 | - | - | - | - | 220.86
|  | GB3 & GB4 | 14 | 9.53 | 3 | 9 | 27 | - | - | - | - | 257.31
|  |  | 14 | 9.38 | 3 | 9 | 27 | - | - | - | - | 253.26
|  |  | 14 | 8.63 | 3 | 9 | 27 | - | - | - | - | 233.01
| Strriup | x-axis | 8 | 1.2 | 215 | 4 | 860 | - | 1032 | - | - | -
|  | y-axis | 8 | 1.2 | 82 | 9 | 738 | - | 885.6 | - | - | -
1 | floor mesh |  | 8 | 7.05 | 209.25 | 1 | 209.25 | - | 1475.2125 | - | - | -
|  |  | 8 | 2.35 | 209.25 | 1 | 209.25 | - | 491.7375 | - | - | -
|  |  | 8 | 5.7 | 209.25 | 1 | 209.25 | - | 1192.725 | - | - | -
|  |  | 8 | 5.65 | 237.75 | 1 | 237.75 | - | 1343.2875 | - | - | -
|  |  | 8 | 4.65 | 79.25 | 1 | 79.25 | - | 368.5125 | - | - | -
|  |  | 8 | 4.8 | 79.25 | 1 | 79.25 | - | 380.4 | - | - | -
|  |  | 8 | 4.75 | 79.25 | 1 | 79.25 | - | 376.4375 | - | - | -
|  |  | 8 | 4.35 | 158.5 | 1 | 158.5 | - | 689.475 | - | - | -
[7 empty] | 0 | - | - | - | - | -
|  |  |  | TOTAL LENGTH |  |  |  |  | 8235.3875 | 0 | 0 | 2061.84
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 3252.9781 | 0 | 0 | 2494.8264
1 | COLUMN (C1) |  | 12 | 3.68 | 4 | 18 | 72 |  |  |  | 264.96
|  |  |  | 0.7 | 18 | 15 | 270 |  | 189
| C2 |  | 14 | 3.68 | 4 | 18 | 72 |  |  |  |  | 264.96
|  |  | 8 | 0.7 | 18 | 15 | 270 |  | 189
TOP TIE BEAM
2 | TTB1 |  | 12 | 11.8 | 2 | 3 | 6 |  |  |  | 70.8
|  |  | 12 | 11.75 | 2 | 3 | 6 |  |  |  | 70.5
|  |  | 12 | 11.65 | 2 | 3 | 6 |  |  |  | 69.9
|  |  | 12 | 10.35 | 2 | 3 | 6 |  |  |  | 62.1
|  |  | 12 | 10.7 | 2 | 3 | 6 |  |  |  | 64.2
|  |  | 12 | 11.85 | 2 | 3 | 6 |  |  |  | 71.1
|  |  | 12 | 11.55 | 2 | 3 | 6 |  |  |  | 69.3
|  |  | 12 | 10.65 | 2 | 3 | 6 |  |  |  | 63.9
|  |  | 8 | 0.9 | 2 | 215 | 430 |  | 387
4 | TTB2 |  | 12 | 11.8 | 2 | 3 | 6 |  |  |  | 70.8
|  |  | 12 | 11.75 | 2 | 3 | 6 |  |  |  | 70.5
|  |  | 12 | 11.65 | 2 | 3 | 6 |  |  |  | 69.9
|  |  | 12 | 10.35 | 2 | 3 | 6 |  |  |  | 62.1
|  |  | 12 | 10.7 | 2 | 3 | 6 |  |  |  | 64.2
|  |  | 12 | 11.85 | 2 | 3 | 6 |  |  |  | 71.1
|  |  | 12 | 11.55 | 2 | 3 | 6 |  |  |  | 69.3
|  |  | 12 | 10.65 | 2 | 3 | 6 |  |  |  | 63.9
|  |  | 8 | 0.9 | 2 | 215 | 430 |  | 387
4 | TTB3 |  | 12 | 8.08 | 2 | 4 | 8 |  |  |  | 64.64
|  |  | 12 | 9.43 | 2 | 4 | 8 |  |  |  | 75.44
|  |  | 12 | 9.38 | 2 | 3 | 6 |  |  |  | 56.28
|  |  | 12 | 8.63 | 2 | 3 | 6 |  |  |  | 51.78
|  |  | 8 | 0.9 | 2 | 81 | 162 |  | 145.8
|  |  |  | TOTAL LENGTH |  |  |  |  | 1297.8 | 0 | 1596.7 | 264.96
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 512.631 | 0 | 1417.8696 | 320.6016
6 | TTB4 |  | 12 | 8.08 | 7 | 4 | 28 |  |  |  | 226.24
|  |  | 12 | 9.43 | 7 | 4 | 28 |  |  |  | 264.04
|  |  | 12 | 9.38 | 7 | 3 | 21 |  |  |  | 196.98
|  |  | 12 | 8.63 | 7 | 3 | 21 |  |  |  | 181.23
| LENTEL |  | 8 | 0.9 | 7 | 81 | 567 |  | 510.3
7 | D5 |  | 12 | 1.65 | 1 | 2 | 2 |  |  |  | 3.3
|  |  | 12 | 1.35 | 1 | 2 | 2 |  |  |  | 2.7
|  |  | 8 | 0.6 | 1 | 8 | 8 |  | 4.8
8 | D7 |  | 12 | 1.45 | 8 | 2 | 16 |  |  |  | 23.2
|  |  | 12 | 1.15 | 8 | 2 | 16 |  |  |  | 18.4
|  |  | 8 | 0.6 | 8 | 7 | 56 |  | 33.6
9 | D8 |  | 12 | 1.35 | 12 | 2 | 24 |  |  |  | 32.4
|  |  | 12 | 1.05 | 12 | 2 | 24 |  |  |  | 25.2
|  |  | 8 | 0.5 | 12 | 7 | 84 |  | 42
10 | D9 |  | 12 | 1.55 | 5 | 2 | 10 |  |  |  | 15.5
|  |  | 12 | 1.25 | 5 | 2 | 10 |  |  |  | 12.5
|  |  | 8 | 0.6 | 5 | 7 | 35 |  | 21
11 | D9' |  | 12 | 1.85 | 1 | 2 | 2 |  |  |  | 3.7
|  |  | 12 | 1.55 | 1 | 2 | 2 |  |  |  | 3.1
|  |  | 8 | 0.6 | 1 | 9 | 9 |  | 5.4
12 | D2 |  | 12 | 2.05 | 5 | 2 | 10 |  |  |  | 20.5
|  |  | 12 | 1.75 | 5 | 2 | 10 |  |  |  | 17.5
|  |  | 8 | 0.6 | 5 | 10 | 50 |  | 30
13 | W9 |  | 12 | 1.85 | 5 | 2 | 10 |  |  |  | 18.5
|  |  | 12 | 1.55 | 5 | 2 | 10 |  |  |  | 15.5
|  |  | 8 | 0.6 | 5 | 9 | 45 |  | 27
14 | W8 |  | 12 | 1.83 | 2 | 2 | 4 |  |  |  | 7.32
|  |  | 12 | 1.53 | 2 | 2 | 4 |  |  |  | 6.12
|  |  | 8 | 0.7 | 2 | 9 | 18 |  | 12.6
|  |  |  | TOTAL LENGTH |  |  |  |  | 686.7 |  | 1093.93
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 271.2465 | 0 | 971.4098 | 0
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150

## Emer. Sum
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:- Emergency & Waiting
Details of Works executed
Bill No. | Description | Sub Total Birr |  | Total Birr
|  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work | 267212.38 | 130039.767 | 267212.38 | 130039.767
2 | Concrete Work | 517780 | 416748.2658 | 517780 | 416748.2658
3 | Masonry work | 216850 | 86197.93 | 216850 | 86197.93
| sub total A | 1001842.38 | 632985.9628 | 1001842.38 | 632985.9628
| B. Super Structure |  |  | 0 | 0
1 | Concrete Work | 211086 | 191445.0186 | 211086 | 191445.0186
2 | Block work | 192560 | 148121.959 | 192560 | 148121.959
3 | Roofing | 257176.8 | 171282.5 | 257176.8 | 171282.5
4 | Carpentary & Joinery | 116218.84 | 88012.44 | 116218.84 | 88012.44
5 | Metal work | 167365.75 | 87850.5 | 167365.75 | 87850.5
6 | Finishing | 526925 | 504417.435 | 526925 | 504417.435
7 | Painting | 40992 | 26051.0787 | 40992 | 26051.0787
8 | Glazing | 13525 | 0 | 13525 | 0
9 | Sanitory Installation | 64630 | 11541.55 | 64630 | 11541.55
10 | Electrical Installation | 122834.53 | 121020 | 122834.53 | 121020
| sub total B | 1713313.92 | 1349742.4812 | 1713313.92 | 1349742.4812
| Total A+B | 2715156.3 | 1982728.444 | 2715156.3 | 1982728.444
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  |  |  | Consultant:- _____________

## Emer. & Wait. Meas.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction |  |  |  |  | Block : Emergency
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 594.45 | 8 | 4755.6 | 554.29 | 4434.32
1.2 | Bulk excavation in ordinary | m3 | 467 | 70 | 32690 | 40.8683 | 2860.7845
1.3 | Ditto but exceeding 1.5m less than 2m | m3 | 155.6667 | 70 | 10896.6667 | 155.9916 | 10919.412
1.4 | Selected borrowed fill brought from out side | m3 | 622.6667 | 150 | 93400 | 102.775 | 15416.25
1.5 | Selected borrowed fill brought from insitu | m3 |  | 56 | 0 | 79.949 | 4477.144
1.6 | Cart away surplus excavated material to an | m3 | 801.0017 | 70 | 56070.1167 | 283.198 | 19823.8565
1.7 | 25cm thick basaltic or equivalent stone hard | m2 | 347 | 200 | 69400 | 360.54 | 72108
Total to summary ………Birr |  |  |  |  | 267212.3833 |  | 130039.767
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 195 | 150 | 29250 | 115.3 | 17295
2.2 | Ditto but under footing pad | m2 | 24 | 150 | 3600 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 347 | 400 | 138800 | 360.54 | 144216
2.4 | In grade beam&Steps | m3 | 28 | 3200 | 89600 | 25.62 | 81984
2.6 | In footing pad | m3 | 5 | 3200 | 16000 |  | 0
2.7 | In footing coloumn | m3 | 4 | 3200 | 12800 |  | 0
Provide cut and fix in position swan zigzag wood
2.8 | Grade beam | m2 | 140 | 120 | 16800 | 200.36 | 24043.2
2.9 | In footing pad | m2 | 20 | 120 | 2400 |  | 0
2.1 | In footing coloumn | m2 | 77 | 120 | 9240 |  | 0
2.11 | Steps | m2 | 5 | 150 | 750 |  | 0
Reinforcement steel bar according to St.drawing
2.12 | Dia 14 mm deformed bar | kg | 2000 | 36 | 72000 | 2062.4934 | 74249.7624
2.13 | Dia 8 mm deformed bar | kg | 2490 | 36 | 89640 | 2082.2306 | 74960.3034
2.14 | Dia. 12mm deformed bar | kg | 700 | 36 | 25200 |  | 0
2.15 | 10/2 cm chip wood expansion joint between | m | 390 | 30 | 11700 | 236.3 | 7089
Total to summary ………Birr |  |  |  |  | 517780 |  | 416748.2658
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 141 | 1250 | 176250 | 56.5018 | 70627.25
3.2 | Ditto but above natural ground level externally | m3 | 28 | 1450 | 40600 | 10.7384 | 15570.68
Total to summary ………Birr |  |  |  |  | 216850 |  | 86197.93
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 5.1 | 3200 | 16320 | 4.1496 | 13278.72
1.2 | In beams& steps | m3 | 16.7 | 3200 | 53440 | 14.91 | 47712
1.3 | Lintel | m3 | 1.3 | 3200 | 4160 | 0.298 | 953.6
Provide cut and fix in position swan zigzag wood
1.3 | Elevation column | m2 | 103 | 130 | 13390 | 82.992 | 10788.96
1.4 | Beam | m2 | 224 | 130 | 29120 | 201.2 | 26156
1.6 | Lintel | m2 | 10.8 | 130 | 1404 | 5.29 | 687.7
Reinforcement steel bar according to St.drawing
1.5 | Dia 14mm deformed bar | kg
1.6 | Dia 12mm deformed bar | kg | 1358 | 36 | 48888 | 1935.769 | 69687.6826
1.7 | Dia 8 mm deformed bar | kg | 1227 | 36 | 44172 | 616.121 | 22180.356
| Total to summary ………Birr |  |  |  | 210894 |  | 191445.0186
2. BLOCK WORK
2.1 | 20cm thick | m2 | 360 | 350 | 126000 | 298.9005 | 104615.175
2.2 | 15 cm thick | m2 | 208 | 320 | 66560 | 135.9587 | 43506.784
Total to summary ………Birr |  |  |  |  | 192560 |  | 148121.959
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 596.38 | 300 | 178914 | 492.155 | 147646.5
3.2 | G 28 ribbed sheet ceiling under eave | m2 | 77 | 160 | 12320 | 59 | 9440
3.2 | Flashing in flat metal sheet fixed as shown | m |  | 110 | 0 | 37.2 | 4092
3.3 | Supply and fix G-28 flat metal sheet gutter | m | 134 | 120 | 16080 | 84.2 | 10104
Total to summary ………Birr |  |  |  |  | 207314 |  | 171282.5
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12cm | m | 790 | 23 | 18170 | 845.8 | 19453.4
4.2 | Vertical & diagonal members size-diameter 8 - 10cm | m | 502 | 16 | 8032 | 957.14 | 15314.24 | 4149.6
4.3 | Purlin zigba size 5/7cm | m | 667.74 | 33 | 22035.42 | 631.4 | 20836.2
4.4 | Zigba wooden fascia board price includes three coats | m | 95.42 | 71 | 6774.82 | 120.4 | 8548.4 | 4668.3
4.5 | Type D5 size - 100/273cm | Nº | 2 | 5187 | 10374 | 2 | 10374
4.6 | Type D7 size-80/273cm | Nº | 7 | 4149.6 | 29047.2 | 1 | 4149.6
4.7 | Type D9 size-90/273cm | Nº | 6 | 4668.3 | 28009.8 | 2 | 9336.6
Total to summary ………Birr |  |  |  |  | 122443.24 |  | 88012.44
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 22 | 3892.5 | 85635 | 10 | 38925
5.2 | Type W4 size-130/173cm | Nº | 2 | 3373.5 | 6747 | 2 | 6747
5.3 | Type W8 size-125/173cm | Nº | 1 | 4914 | 4914 |  | 0
5.4 | Type W14 size-100/173cm | Nº | 1 | 4095 | 4095 | 3 | 12285
5.5 | Type W15 size-130/60cm | Nº | 1 | 1170 | 1170 |  | 0
Doors
5.6 | Type D1 size - 160/273cm | Nº | 2 | 3300 | 6600 |  | 0
5.7 | Type D2 size - 140/273cm | Nº | 3 | 5733 | 17199 | 2 | 11466
5.8 | Type D4 size - 120/273cm | Nº | 3 | 2450 | 7350 |  | 0
5.9 | Type D10 size - 80/273cm | Nº | 2 | 3276 | 6552 |  | 0
5.1 | Type D6 size - 90/273cm | Nº | 4 | 3685.5 | 14742 | 5 | 18427.5
Total to summary ………Birr |  |  |  |  | 155004 |  | 87850.5
6. FINISHING
Finishing work shall includes all surface pre
6.1 | Apply two coats of plastering and one coat of ren | m2 | 209 | 140 | 29260 | 185.369 | 25951.66
6.2 | Apply three coats of plastering to internal walls& | m2 | 908 | 150 | 136200 | 839.3045 | 125895.675
6.4 | Chip wood ceiling nailed on & including | m2 | 347 | 310 | 107570 | 370.92 | 114985.2
6.12 | type 9mm thick non slippery ceramic tile flooring | m2 | 347 | 300 | 104100 | 332.7555 | 99826.65
6.13 | Approved type Ceramic tile skirting | m | 378 | 100 | 37800 | 244.25 | 24425
6.17 | window sill Size 27/3 cm | m | 39 | 150 | 5850 | 45.65 | 6847.5
6.21 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 89 | 550 | 48950 | 125.4 | 68970
6.22 | Concrete pipes of half diameter 30cm | ml | 83 | 100 | 8300 | 100.75 | 10075
6.23 | Construction of 10x40 cm curb stone | ml | 83 | 265 | 21995 | 103.55 | 27440.75
Total to summary ………Birr |  |  |  |  | 500025 |  | 504417.435
7. PAINTING
7.1 | Internal plastered surfaceand external beams & | m2 | 990 | 18.6667 | 18480 | 839.3045 | 15667.0173
7.2 | Chip wood ceiling surface | m2 | 347 | 18.6667 | 6477.3333 | 370.92 | 6923.84
7.3 | External rendered surface | m2 | 209 | 18.6667 | 3901.3333 | 185.369 | 3460.2213
Total to summary ………Birr |  |  |  |  | 28858.6667 |  | 26051.0787
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R water pipes for water
| 15mm diameter ;internal | LM | 11 | 70 | 770 | 17.19 | 1203.3
| 20mm diameter ;internal | LM | 10 | 80 | 800 | 0 | 0
| 25mm diameter ;internal | LM | 43 | 95 | 4085 | 3.05 | 289.75
| 32mm diameter ;internal | LM |  | 125 | 0 | 4.2 | 525
9.3 | Supply and fix bronze gate valves complete with unions,
| 15mm diameter | No | 25 | 95 | 2375 | 3 | 285
| 20mm diameter | No | 4 | 105 | 420 |  | 0
| 25mm diameter | No
9.4 | Ditto item 3,but chrome plated 15mm water tap | No
9.5 | Supply and install waste water pipes made of rigid
| 50mm diameter of min. wall thickness=2mm | LM | 50 | 65 | 3250 | 11.4 | 741
| 75mm diameter of min. wall thickness=3mm | LM | 80 | 95 | 7600 | 9 | 855
| 100 mm diameter of min. wall thickness=3.2mm | LM | 127 | 125 | 15875 | 17.7 | 2212.5
9.9 | Supply and fix toilet paper holder made of metal | No | 5 | 905 | 4525 | 6 | 5430
9.16 | Supply & fix 50mm diameter floor drain made of | No | 4 | 90 | 360 |  | 0
9.18 | Supply and fix 100mm 3.2mm thickness down | LM | 102 | 180 | 18360 |  | 0
9.19 | Supply and mount fire extinguishers of class ABC | No | 1 | 3000 | 3000 |  | 0
Total to summary ………Birr |  |  |  |  | 61420 |  | 11541.55
10. ELECTRICAL INSTALLATION
1.02 | Flush mounted Sub distribution board SDB-EMRG | PCs | 1 | 5000 | 5000 |  | 0
2 | Light points
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 62 | 200 | 12400 | 79 | 15800
3 | Switches |  |  |  | 0 |  | 0
3.01 | single(774001+774041) | PCs | 10 | 81.25 | 812.5 | 4 | 325
3.02 | Duoble(774005+774042) | " | 17 | 131.25 | 2231.25 | 19 | 2493.75
3.03 | Two-Way(774006+774041) | " | 4 | 80 | 320 | 6 | 480
4 | Socket outlet points |  |  |  | 0 |  | 0
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 36 | 200 | 7200 | 38 | 7600
4.02 | Ditto as 4.01 but for water heater points | PCs | 1 | 785 | 785 | 1 | 785
5 | Socket outlets |  |  |  | 0 |  | 0
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 36 | 90 | 3240 | 38 | 3420
5.02 | weather proof socket Legrand Suno 774022+774041 | PCs | 1 | 281.25 | 281.25 | 1 | 281.25
6 | Telephone/Data points |  |  |  | 0 |  | 0
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 13 | 130 | 1690 | 11 | 1430
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 13 | 168.75 | 2193.75 | 11 | 1856.25
7 | Type of Light Fitting With lamp |  |  |  | 0 |  | 0
7.01 | PHILIPS TMS 012/236 IMKwith 2xTLD 36W | PCs | 35 | 1500 | 52500 | 29 | 43500
7.02 | PHILIPS TMS 012/136 IMKwith 1xTLD 36W | PCs | 8 | 1200 | 9600 | 27 | 32400
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 11 | 406.25 | 4468.75 | 19 | 7718.75
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 7 | 406.25 | 2843.75 | 4 | 1625
7.05 | MASSIVE 70107/02/11/2XE27/60W | PCs | 5 | 1375 | 6875 |  | 0
8 | TV points |  |  |  | 0 |  | 0
8.01 | TV points fed through RG6 Coaxial 75ohm TV | PCs | 1 | 266.25 | 266.25 | 2 | 532.5
8.02 | Flush mounted TV outlets type Legrand Suno | PCs | 1 | 120 | 120 |  | 0
9 | Power Cables(XLPE 0.6/KV or approved equ.) |  |  |  | 0 |  | 0
9.1 | 4x6mm2 from CMDB- SDB-EMRG | ML | 10 | 90 | 900 |  | 0
10 | Cable way and Manhole |  |  |  | 0 |  | 0
10.02 | Rigid pvc pipe of dia.32mm For 4x6mm2 | " | 9 | 40 | 360 |  | 0
10.02 | Rigid pvc pipe dia. 50mm to |  |  |  | 0 |  | 0
| telephone Distribution frame | " | 12 | 50 | 600 | 15.45 | 772.5
Total to summary ………Birr |  |  |  |  | 114687.5 |  | 121020

## Emer. Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Emergency Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | C-bulk fill (under hard core)
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 22.55 |  | L=23.85-0.5-0.8=22.55
|  |  | 1.1 Clear off site to remove top soil |  | 10.6 |  | W=11.9-0.5-0.8=10.6
|  |  | L=23.35+1.0+1.0=25.35 |  | 0.5 | 119.515
1 | 25.35 |  | W=11.4+1.0+1.0=13.4
| 13.4 | 339.69 |  |  |  |  | DEDUCTION
|  |  |  | 2 | 22.25 |  | along x-axis
|  | 339.69 | m2 Total to item 1.1 |  | 0.4 |  | L=22.25 W=0.4m
[5 empty] | 0.5 | 8.9
1.2 Bulk Excavation in ordinary soil
1 | 22.05 |  | L=23.85-0.25-0.25-0.4-0.4-0.5=22.05 | 4 | 9.8 |  | along y-axis
| 10.1 |  | W=11.9-0.25-0.25-0.4-0.4-0.5=10.1 |  | 0.4 |  | L=11.9-0.5-0.8-(2*0.4)=9.8
| 0.21 | 46.7681 |  |  | 0.5 | 7.84
|  |  | DEDUCTION |  |  | 102.775 | m3 Total to item 1.4( borrowed)
2 | 22.05 |  | along x-axis
| 0.9 |  | L=23.85-0.25-0.25-0.4-0.4-0.5=22.05 |  |  |  | 1.5 Cart away excavated material to an
| 0.21 | 8.3349 |  | 1 | 25.35 |  | approprate trip
13.4
4 | 8.3 |  | along y-axis |  | 0.3 | 101.907 | from item no 1.1
| 0.9 |  | W=11.9-0.25-0.25-0.4-0.4-0.5-(2*0.9)
| 0.21 | 6.2748 | W=8.3 |  |  | 32.1583 | from item no 1.2
|  | 32.1583 | m3 Total to item 1.2 |  |  | 145.0656 | from item no 1.3
|  |  | 1.3 Ditto to Item 1.2 but exceeding 1.5 |  |  | 79.949 | DEDUCTION
and less than 2m
4 | 23.85 |  | along x-axis |  |  | 199.182 | m3 Total to item 1.5
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=23.85 d=0.
| 0.92 | 78.9912 |  |  |  |  | 1.6/ 25 cm thick basaltic stone hard core
|  |  |  | 1 | 22.85 |  | L=23.85-0.5-0.5=22.85
6 | 13.3 |  | along y-axis |  | 10.9 | 249.065 | W=11.9-0.5-0.5=10.9
| 0.9 |  | L=11.9-(4*.9)=8.3
| 0.92 | 66.0744 | W=0.4+0.25+0.25=0.90, d= |  |  |  | DEDUCTION
|  |  |  | 2 | 22.85 |  | along x-axis L=22.85 W=0.25
|  | 145.0656 | m3 Total to item 1.3 |  | 0.25 | 11.425
|  |  | 1.4 Selected Fill | 4 | 10.4 |  | along y-axis L=10.4 W=0.25
|  |  | A- fill under masonary(insitu material) |  | 0.25 | 10.4 | L=11.9-0.5-0.5-0.5=10.4
4 | 23.85 |  | for axis x01-x04
| 0.9 |  | L=23.85 |  |  | 227.24 | m2 Total to item 1.6
| 0.5 | 42.93
2) CONCRETE WORK
6 | 8.3 |  | for axis y01-y05 |  |  |  | 2.1 5cm thick lean concrete class C-7
| 0.9 |  | L=8.3 , W=0.9, d=0.3 | 4 | 23.35 |  | L=23.85-0.5=23.35
| 0.5 | 22.41 | 8.3 |  | 0.5 | 46.7
|  |  | B-backfill anin side masonary | 6 | 9.8 |  | L=11.9-0.5-(4*0.4)=9.8
|  |  | along x-axis(insitu material) |  | 0.5 | 29.4
6 | 20.95 |  | L=23.85-0.25-0.25-0.8-(4*0.4)=20.95
| 0.25 |  | W=0.25 ,d= |  |  | 76.1 | m2 Total to item 2.1
| 0.28 | 8.799
along y-axis
10 | 8.3 |  | L=11.9-0.25-0.25-0.8-(2*0.25)-(2*.9)=8.3
| 0.25 |  | W=0.25 ,d=.
| 0.28 | 5.81
|  | 79.949 | m3 Total item 1.4(insitu material)
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.3 10cm thick RC floor slab class C-25 |  |  |  | 3. Masonry Work
1 | 22.85 |  | L=23.85-0.25-0.25-0.25-0.25=22.85 |  |  |  | 3.1 Trychltic stone masonry (Total)
| 10.9 | 249.065 | W=11.9-0.25-0.25-0.25-0.25=10.9 | 4 | 23.35 |  | axis x01,x02,x03,x04
[5 empty] | 0.4 |  | L=23.85-0.5=23.35
|  |  | DEDUCTION |  | 0.74 | 27.6464
along x-axis
2 | 22.85 |  | L=23.85-0.25-0.25-0.25-0.25=22.85 | 6 | 9.8 |  | axis y01,y02,y03……y09
| 0.25 | 11.425 |  |  | 0.4 |  | L=11.9-0.5-(4*0.4)=9.8
|  |  | along y-axis |  | 0.74 | 17.4048
4 | 10.4 |  | L=11.9-0.25-0.25-0.25-0.25-0.5=10.4 |  |  | 45.0512 | m3 Total Volume of masonary
| 0.25 | 10.4
3.12 masonary work above NGL
|  | 227.24 | m2 Total to item 2.3 | 1 | 7.95 |  | on axis x01 L=4.45+3.75-.25=7.95
0.4
|  |  | 2.4 In grade beams and steps |  | 0.43 | 1.3674
4 | 23.35 |  | L=23.85-0.25-0.25=23.35
| 0.25 |  |  | 1 | 11.4 |  | on axis y08L=4.2+2.6+4.35+.25=11.4
| 0.4 | 9.34 |  |  | 0.4
[5 empty] | 0.46 | 2.0976
6 | 10.4 |  | L=11.9-0.25-0.25-(4*.25)=10.4
| 0.25 |  |  | 1 | 3.75 |  | on axis x04 L=3.75-.25=5
| 0.4 | 6.24 |  |  | 0.4
[5 empty] | 0.2 | 0.3
|  | 15.58 | m3Total to item 2.4
[6 empty] | 3.765 | m3Total to item 3.2
provide fix in position form work
|  |  | 2.7 In grade beams |  |  |  | 3.13 masonary work below NGL
8 | 23.35 |  | L=23.85-0.25-0.25=23.35 (x-axis)
| 0.4 | 74.72 |  |  |  | 41.2862 | m3Total to item 3.1
12 | 10.9 |  | L=11.9-0.25-0.25-(2*.25)=10.9
| 0.4 | 52.32
56 | 0.4 |  | DEDUCTION
| 0.25 | 5.6
|  | 121.44 | m2 Total to item 2.7
Reinforcement steel bars
|  |  | 2.12)ф14 mm deformed bars |  |  |  |  | #REF!
|  | 1263.4578 | kg net wight item 2.12
2.13)ф8 mm deformed bars
|  | 1289.1101 | kg net wight item 2.13
2.15 10/2 cm chipwood expansion joint
along x-axis
6 | 22.05 |  | L=23.85-0.25-0.25-0.25-0.25-(.25*4)=22.05
132.3
along y-axis
10 | 10.4 |  | L=11.9-0.25-0.25-0.25-0.25-0.5=10.4
|  | 104 | [5 empty] | #REF!
|  | 236.3 | mTotal to item 2.15

## Wait. Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Waiting Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | C-bulk fill and compaction
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 15.7 |  | L=17-0.5-0.8=15.7
|  |  | 1.1 Clear off site to remove top soil |  | 8.8 |  | W=10.1-0.5-0.8=8.8
|  |  | L=16.5+1.0+1.0=18.5 |  | 0 | 0
1 | 18.5 |  | W=9.6+1.0+1.0=11.6
| 11.6 | 214.6 |  |  |  |  | DEDUCTION
|  |  |  | 2 | 15.7 |  | along x-axis
|  | 214.6 | m2 Total to item 1.1 |  | 0.4 |  | L=15.7 W=0.4m
[5 empty] | 0 | 0
1.2 Bulk Excavation in ordinary soil
1 | 15.2 |  | L=17-0.25-0.25-0.4-0.4-0.5=15.2 | 2 | 8 |  | along y-axis
| 8.3 |  | W=10.1-0.25-0.25-0.4-0.4-0.5=8.3 |  | 0.4 |  | L=10.1-0.5-0.8-(2*0.4)=8
| 0.1 | 12.616 |  |  | 0 | 0
|  |  | DEDUCTION |  |  | 58.0145 | m3 Total to item 1.4
2 | 15.2 |  | along x-axis |  |  |  | 1.5 Cart away excavated material to an
| 0.9 |  | L=17-0.25-0.25-0.4-0.4-0.5=15.2 |  |  |  | approprate trip
| 0.1 | 2.736 |  | 1 | 18.5
11.6
2 | 6.5 |  | along y-axis |  | 0.3 | 64.38 | from item no 1.1
| 0.9 |  | W=10.1-0.25-0.25-0.4-0.4-0.5-(2*0.9)
| 0.1 | 1.17 | W=6.5 |  |  | 8.71 | from item no 1.2
|  | 8.71 | m3 Total to item 1.2 |  |  | 10.926 | from item no 1.3
|  |  | 1.3 Ditto to Item 1.2 but exceeding 1.5 |  |  | 84.016 | m3 Total to item 1.5
and less than 2m
4 | 23.85 |  | along x-axis |  |  |  | 1.6/ 25 cm thick hard core
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=17 d=0.10 |  |  |  | L=17-0.5-0.5=16
| 0.1 | 8.586 |  | 1 | 16 |  | W=10.1-0.5-0.5=9.1
[5 empty] | 9.1 | 145.6
4 | 6.5 |  | along y-axis
| 0.9 |  | L=11.9-(4*.9)=6.5 |  |  |  | DEDUCTION
| 0.1 | 2.34 | W=0.4+0.25+0.25=0.90, d= | 2 | 16 |  | along x-axis L=16 W=0.25
[5 empty] | 0.25 | 8
|  | 10.926 | m3 Total to item 1.3
|  |  |  | 2 | 8.6 |  | along y-axis L=10.4 W=0.25
|  |  | 1.4 Selected borrowed Fill |  | 0.25 | 4.3 | L=10.1-0.5-0.5-0.5=8.6
A- fill under masonary
4 | 16.5 |  | for axis x01-x04 |  |  | 133.3 | m2 Total to item 1.6
| 0.9 |  | L=23.85
| 0.5 | 29.7 |  |  |  |  | 2) CONCRETE WORK
2.1 5cm thick lean concrete class C-7
4 | 6.5 |  | for axis y01-y05 | 4 | 16.5 |  | L=17-0.5=16.5
| 0.9 |  | L=6.5 , W=0.9, d=0.00 |  | 0.4 | 26.4
| 0.5 | 11.7
|  |  |  | 4 | 8 |  | L=10.1-0.5-(4*0.4)=8
|  |  | B-backfill and compaction in side |  | 0.4 | 12.8
masonary along x-axis
6 | 14.9 |  | L=17-0.25-0.25-0.8-(2*0.4)=14.9 |  |  | 39.2 | m2Total to item 2.1
| 0.25 |  | W=0.25 ,d=0.00
| 0.47 | 10.5045 |  |  |  |  | 2.3 10cm thick RC floor slab class C-25
|  |  |  | 1 | 16 |  | L=17-0.25-0.25-0.25-0.25=16
|  |  | along y-axis |  | 9.1 | 145.6 | W=10.1-0.25-0.25-0.25-0.25=9.1
8 | 6.5 |  | L=11.9-0.25-0.25-0.8-(2*0.25)-(2*.9)
| 0.25 |  | L=8.3 W=0.25 ,d=.0
| 0.47 | 6.11
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | DEDUCTION |  |  |  | 3. Masonry Work
|  |  | along x-axis |  |  |  | 3.1 Trychltic or equivalent stone masonry (total)
2 | 16 |  | L=17-0.25-0.25-0.25-0.25=16 | 4 | 16.5 |  | axis x01,x02,x03,x04
| 0.25 | 8 |  |  | 0.4 |  | L=17-0.5=16.5
[5 empty] | 0.47 | 12.408
along y-axis
2 | 8.6 |  | L=10.1-0.25-0.25-0.25-0.25-0.5=8.6 | 4 | 8 |  | axis y01,y02,y03……y09
| 0.25 | 4.3 |  |  | 0.4 |  | L=10.1-0.5-(4*0.4)=8
[5 empty] | 0.47 | 6.016
|  | 133.3 | m2Total to item 2.3
[6 empty] | 18.424 | m3 Total Volume of masonary
2.4 In grade beams and steps
4 | 16.5 |  | L=17-0.25-0.25=16.5 |  |  |  | 3.12 masonary work above NGL
| 0.25 |  |  | 1 | 9.65 |  | on axis x01 L=3.1+2.7+3.6+.25=9.65
| 0.4 | 6.6 |  |  | 0.4
[5 empty] | 0.67 | 2.5862
4 | 8.6 |  | L=10.1-0.25-0.25-(4*.25)=8.6
| 0.25 |  |  | 1 | 16.05 |  | on axis y01L=6+6.2+4.1-.25=16.05
| 0.4 | 3.44 |  |  | 0.4
[5 empty] | 0.46 | 2.9532
|  | 10.04 | m3Total to item 2.4
|  |  |  | 1 | 11.95 |  | on axis y04 L=6+6.2-.25=11.95
|  |  | provide cut form work |  | 0.4
|  |  | 2.8 In grade beams |  | 0.3 | 1.434
8 | 16.5 |  | L=17-0.25-0.25=16.5(x-axis)
| 0.4 | 52.8 |  |  |  | 6.9734 | m3Total to item 3.2
8 | 9.1 |  | L=10.1-0.25-0.25-(2*.25)=9.1 |  |  | 11.4506 | 3.13 masonary work below NGL
| 0.4 | 29.12
[6 empty] | 11.4506 | m3Total to item 3.1
30 | 0.4 |  | DEDUCTION
| 0.25 | 3
|  | 78.92 | m2 Total to item 2.8
Reinforcement steel bars
2.12)ф14 mm deformed bars
|  | 799.0356 | kg net wight item 2.12
|  |  | 2.13)ф8 mm deformed bars |  |  |  |  | #REF!
|  | 793.1205 | kg net wight item 2.13
2.14 10/2 cm expansion joint
along x-axis
6 | 15 |  | L=17-0.25-0.25-0.25-0.25-(.25*4)=15
| 0 | 0
along y-axis
6 | 8.6 |  | L=10.1-0.25-0.25-0.25-0.25-0.5=8.6
| 0 | 0
|  | 0 | mTotal to item 2.14 |  |  |  |  | #REF!

## Emer. Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Emergency
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 2 | 10.55 |  | TTB3=2Pcs
|  |  | 1.CONCRETE WORK |  | 0.8 | 16.88 | Axis y/01 & y/06 from ( x/01 - x/04)
24 | 0.2 |  | 1.1)In elevation column
| 0.2 |  | C1=20Pcs & C2=4Pcs (0.2x0.2) | 4 | 10.55 |  | TTB4=4Pcs
| 2.73 |  |  |  | 0.8 | 33.76 | Axis y/02 - y/05 from ( x/01 - x/04)
|  | 2.6208 | m3 net volume item 1.1
[6 empty] | 126.4 | m3 net volume item 1.5
|  |  | 1.2)In beam & step |  |  |  | 1.6)Lintel
2 | 23.3 |  | TTB1=2Pcs | 1 | 1.3 |  | D9(1Pcs)
| 0.3 |  | Axis x/01 & x/o4 from (y/01 - y/06) |  | 0.6 | 0.78
| 0.2 | 2.796 |  | 3 | 1.2 |  | D7(3Pcs)
[5 empty] | 0.55 | 1.98
2 | 23.3 |  | TTB2=2Pcs | 3 | 1.1 |  | D8(3Pcs)
| 0.3 |  | Axis x/02 & x/03 from ( y/01-y/06) |  | 0.55 | 1.815
| 0.2 | 2.796 |  |  |  | 4.575 | m3 net volume item 1.6
1.6)ф12 mm deformed bars
2 | 10.55 |  | TTB3=2Pcs | 1 | 1224.4632
| 0.3 |  | Axis y/01 & y/06 from ( x/01-x/04) |  |  | 1224.4632 | kg net weight item 1.8
| 0.2 | 1.266 |  |  |  |  | 1.7)ф8mm deformed bars
|  |  |  | 1 | 388.838
4 | 10.55 |  | TTB4=4Pcs |  |  | 388.838 | kg net weight item 1.9
| 0.3 |  | Axis y/02 - y/05 from ( x/01 - x/04) |  |  |  | 2)BLOCK WORK
| 0.2 | 2.532 |  |  |  |  | 2.1) 20cm thick HCB wall
|  |  |  | 1 | 22.1 |  | Axis X/01 from (Y/01 - Y/04)
|  | 9.39 | m3 net volume item 1.2 |  | 2.73 | 60.333
|  |  |  | 1 | 1.75 |  | Opening
|  |  | 1.3)Lintel |  | 1.65 | -2.8875
1 | 1.3 |  | D9(1Pcs)
| 0.2 |  |  | 3 | 1.5 |  | W2
| 0.2 | 0.052 |  |  | 1.73 | -7.785
3 | 1.2 |  | D7(3Pcs) | 1 | 1.3 |  | W4
| 0.15 |  |  |  | 1.73 | -2.249
| 0.2 | 0.108
|  |  |  | 1 | 1 |  | W14
3 | 1.1 |  | D8(3Pcs) |  | 1.73 | -1.73
0.15
| 0.2 | 0.099 |  | 5 | 0.9 |  | D6
[5 empty] | 2.73 | -12.285
|  | 0.259 | m3 net volume item 1.3
|  |  |  | 1 | 1.2 |  | D4
|  |  | FORM WORK |  | 2.73 | -3.276
1.4)Elevation column
24 | 0.8 |  |  | 1 | 19.15 |  | Axis X/02 from (Y/01 - Y/04)
| 2.73 |  |  |  | 2.73 | 52.2795
|  | 52.416 | m3 net volume item 1.4
|  |  |  | 2 | 0.9 |  | D9
|  |  | 1.5)Beam |  | 2.73 | -4.914
2 | 23.3 |  | TTB1=2Pcs
| 0.8 | 37.28 | Axis x/01 & x/o4 from (y/01-y/06) | 1 | 22.1 |  | Axis X/04 from (Y/01 - Y/04)
|  |  | Dev.L=0.30*2+0.20=0.80mt |  | 2.63 | 58.123
20 | 0.3
| 0.2 | 1.2 |  | 6 | 1.5 |  | W2
[5 empty] | 1.73 | -15.57
2 | 23.3 |  | TTB2=2Pcs
| 0.8 | 37.28 | Axis x/02 & x/03 from (y/01 - y/06) | 1 | 1.3 |  | W4
[5 empty] | 0.6 | -0.78
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 4.25 |  | W6 | 1 | 2.7 |  | D8(1Pc)
| 0.6 | -2.55 |  |  | 3.03 | 8.181
1 | 1.25 |  | W9 | 1 | 1.16 |  | W9(1Pc)
| 0.6 | -0.75 |  |  | 0.6 | -0.696
2 | 6.4 |  | Axis Y/07 from (X/02 - X/04) | 1 | 1.4 |  | D8(1Pc)
| 2.73 | 34.944 |  |  | 3.03 | -4.242
1 | 4 |  |  | 1 | 0.8 |  | D7(1Pc)
| 1 | 4 | Axis Y/01 (X/01 - X/02) |  | 2.73 | -2.184
2 | 1.4 |  |  | 2 | 1.4 |  | Axis b/n y/04' - y/06'(x/03 - x/04)
| 2.73 | -7.644 | D1 |  | 3.03 | 8.484
5 | 4 |  |  | 1 | 0.7 |  | D8(1Pc)
| 2.73 | 54.6 | Axis Y/01 - Y/5 from (X/01 - X/02) |  | 2.73 | -1.911
1 | 0.9 |  |  | 1 | 0.8 |  | D7(1Pc)
| 2.73 | -2.457 | D9 |  | 2.73 | -2.184
2 | 1.05 |  | Above top tie beam x/01 & x/04 |  |  | 126.1052 | m2 net arae item 2.2
| 11.35 | 23.835
3)ROOFING WORK
2 | 23.3 |  | Above top tie beam y/01 & y/06 |  |  |  | 3.1)G-28 CIS Roof covering
| 0.2 | 9.32 |  |  |  |  | W=11.35+0.60X2=12.55mt
|  |  |  | 1 | 12.55 |  | L=23.30+0.60X2=24.50mt
|  | 232.557 | m2 net arae item 2.1 |  | 24.5
[6 empty] | 307.475 | m2 net area item no 3.1
2.2)15cm thick HCB wall
1 | 22.1 |  | Axis X/03 from (Y/01 -Y/06) |  |  |  | 3.2)G-28 Ribbed sheet ceiling
| 2.73 | 60.333 |  | 2 | 23.3
[5 empty] | 0.5 | 23.3
2 | 1.2 |  | D4
| 2.73 | -6.552 |  | 4 | 6.47
[5 empty] | 0.5 | 12.94
4 | 1 |  | D5
| 2.73 | -10.92 |  |  |  | 36.24 | m2 net area item no 3.2
3 | 4.2 |  | Axis Y/02,Y/04 & Y/07 from (X/03 - X/04) |  |  |  | 3.3)Flashing in metal sheet
| 2.73 | 34.398 |  | 4 | 6.47 |  | Ridge cover
[6 empty] | 25.88 | ml net length item 3.3
2 | 4.2 |  | Axis Y/03' & Y/06' from (X/03 - X/04)
| 3.03 | 25.452 |  |  |  |  | 3.4)Supply & fix G-28 gutter dev.
|  |  |  | 2 | 24.5 |  | L=23.30+0.60X2=24.50mt
1 | 0.7 |  | D7(1Pc) |  |  | 49 | ml net length item 3.4
| 2.73 | 1.911
|  |  | Toilet |  |  |  | 4)CARPENTRY
1 | 2.02 |  | Axis b/n y/04 - Y/06 from (X/03-x/04) |  |  |  | 4.1)Uper & lower chord size 10-12cm
| 3.03 | 6.1206 |  | 19 | 12.94 |  | Upper =6.47x2=12.94mt
245.86
1 | 2.02 |  | "
| 2.73 | 5.5146 |  | 19 | 12.16 |  | Lower =6.08x2=12.16mt
231.04
1 | 2 |  | D7(1Pc)
| 2.2 | 4.4 |  |  |  | 476.9 | ml net length item 4.1
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4.2)Vertical & Diagonal member |  |  |  | 6.1)Apply two coats of plastering &
19 | 12.9 |  | V =12.90mt |  |  |  | one coat rendering
|  | 245.1 |  | 1 | 22.1 |  | Axis X/01 from (Y/01 - Y/07)
[5 empty] | 2.73 | 60.333
19 | 16.02 |  | D =16.02mt
|  | 304.38 |  | 3 | 1.5 |  | W2
[5 empty] | 1.73 | -7.785
|  | 549.48 | ml net length item 4.2
|  |  |  | 1 | 1.3 |  | W4
|  |  | 4.3)Purlin zigba 5/7cm |  | 1.73 | -2.249
No .pur =6.47/0.9+1=8Pcs
16 | 24.5 |  | L=23.30+0.60X2=24.50mt | 1 | 1 |  | W14
|  | 392 | ml net length item 4.3 |  | 1.73 | -1.73
|  |  | 4.4)Zigba wooden fascia board | 5 | 0.9 |  | D6
4 | 6.47 |  |  |  | 2.73 | -12.285
25.88
|  |  |  | 1 | 1.2 |  | D4
2 | 24.5 |  |  |  | 2.73 | -3.276
49
|  |  |  | 1 | 1.63 |  | Opening
|  | 74.88 | ml net length item 4.4 |  | 1.75 | -2.8525
|  |  | 4.5)Type D5 ,Size 100/273 | 1 | 22.1 |  | Axis X/04 from (Y/01 - Y/07)
2 | 1 |  |  |  | 2.73 | 60.333
|  | 2 | pcs net number 4.5
|  |  |  | 6 | 1.5 |  | W2
|  |  | 4.6)Type D7 ,Size 80/273 |  | 1.73 | -15.57
1 | 1
|  | 1 | pcs net number 4.6 | 1 | 1.3 |  | W4
[5 empty] | 1.73 | -2.249
4.8)Type D ,Size 90/273
2 | 1 |  |  | 1 | 4.25 |  | W6
|  | 2 | pcs net number 4.8 |  | 0.6 | -2.55
|  |  |  | 1 | 1.25 |  | W9
[5 empty] | 0.6 | -0.75
|  |  | 5)METAL WORK | 1 | 10.55 |  | Axis Y/07 from (X/02 - X/04)
|  |  | 5.1)Type W2 ,Size 150/173 |  | 2.73 | 28.8015
9 | 1
|  | 9 | pcs net number 5.1 | 1 | 6.35 |  | Axis Y/01 from (X/01 - X/02)
[5 empty] | 2.73 | 17.3355
5.2)Type W4 ,Size 130/173
2 | 1 |  |  | 1 | 4 |  | Axis Y/01 from (X/01 - X/02)
|  | 2 | pcs net number 5.2 |  | 1 | 4
|  |  | 5.4)Type W14, Size 100/173 | 2 | 1.4 |  | D1
1 | 1 |  |  |  | 2.73 | -7.644
|  | 1 | pcs net number 5.4
|  |  |  | 2 | 11.35 |  | Above top tie beam
|  |  | 5.7)Type D1= D2, Size 140/273 |  | 1.05 | 23.835
2 | 1
|  | 2 | pcs net number 5.7 |  |  | 135.6975 | m2 net area item 6.1
5.10)Type D6, Size 90/273
5 | 1
|  | 5 | pcs net number 5.10
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.2)Apply three coats of plastering | 2 | 1.4 |  | D1
|  |  | to internal wall &external beam & colu. |  | 2.73 | -7.644
1 | 6.15 |  | Emerg. waiting/
| 1 | 6.15 | L=1.95+4.20=6.15mt | 2 | 1.2 |  | D4
[5 empty] | 2.73 | -6.552
1 | 4.4 |  | "
| 3.06 | 13.464 |  | 4 | 1 |  | D5
[5 empty] | 2.73 | -10.92
1 | 13.9 |  | Archive
| 3.06 | 42.534 | L=4X2+2.95X2=13.90mt | 2 | 0.9 |  | D9
[5 empty] | 2.73 | -4.914
1 | 0.9 |  | D6
| 2.73 | -2.457 |  | 1 | 2.95 |  | Opening
[5 empty] | 2.73 | -8.0535
1 | 1.5 |  | W2
| 1.73 | -2.595 |  | 1 | 20 |  | Emergence triage examination
[5 empty] | 3.06 | 61.2 | L=4.20x2+5.80x2=20.00mt
1 | 13.9 |  | Hmis
| 3.06 | 42.534 | L=4X2+2.95X2=13.90mt | 2 | 1.5 |  | W2
[5 empty] | 1.73 | -5.19
2 | 0.9 |  | D6 & D9
| 2.73 | -4.914 |  | 1 | 1.2 |  | D4
[5 empty] | 2.73 | -3.276
1 | 1.3 |  | W14
| 1.73 | -2.249 |  | 1 | 22.9 |  | Observation room
[5 empty] | 3.06 | 70.074 | L=4.20x2+7.25x2=22.90mt
1 | 13.9 |  | Medical recording
| 3.06 | 42.534 | L=4X2+2.95X2=13.90mt | 3 | 1.5 |  | W2
[5 empty] | 1.73 | -7.785
2 | 0.9 |  | D6 & D9
| 2.73 | -4.914 |  | 1 | 1.2 |  | D4
[5 empty] | 2.73 | -3.276
1 | 1 |  | W14
| 1.73 | -1.73 |  | 1 | 12.8 |  | Duty room
|  |  | Procedure room |  | 3.06 | 39.168 | L=2.20X2+4.20X2=12.80mt
1 | 18.1 |  | L=4X2+5.05X2=18.10mt
| 3.06 | 55.386 |  | 1 | 0.8 |  | D7 (1Pc)
[5 empty] | 2.73 | -2.184
2 | 0.9 |  | D6 & D9
| 2.73 | -4.914 |  | 1 | 1.5 |  | W2
[5 empty] | 1.73 | -2.595
1 | 1.5 |  | W2 |  |  |  | Toilet M & F
| 1.73 | -2.595 |  | 1 | 5.2 |  | L=1.20X2+1.4X2=5.20mt
[5 empty] | 3.06 | 15.912
1 | 18.1 |  | Staff room
| 3.06 | 55.386 | L=4x2+5.05x2=18.10mt | 1 | 1 |  | D5(1Pc)
[5 empty] | 2.73 | -2.73
2 | 0.9 |  | D6 & D9
| 2.73 | -4.914 |  | 1 | 0.8 |  | D7(1Pc)
[5 empty] | 2.73 | -2.184
1 | 1.5 |  | W2
| 1.73 | -2.595 |  |  |  |  | Toilet M & F
|  |  |  | 2 | 8.5 |  | L=1.40X2+2.85X2=8.50mt
1 | 50.6 |  | Corridor |  | 3.06 | 52.02
| 3.06 | 154.836 | L=22.9X2+2.4X2=50.60mt
|  |  |  | 2 | 0.8 |  | D7(1Pc)
[5 empty] | 2.73 | -4.368 | W6=6x0.6=3.6
T | D | S | Item No. and Description | T | D | S | Item No. and Description
4 | 0.7 |  | D8(2Pcs) | 1 | 4.2 |  | Axis Y/03 (x/03 -x/04)
| 1.73 | -4.844 |  |  | 0.8 | 3.36
1 | 1.3 |  | W4(1Pc) |  |  | 79.45 | DDT ceramic wall
| 0.6 | -0.78
|  |  | Handicapped |  |  | 646.2775 | m2 net area item 6.2
1 | 9.5 |  | L=2.05x2+2.70X2=9.50mt
| 3.06 | 29.07 |  |  |  |  | 6.3)Chipwood ceiling
|  |  |  | 1 | 4 |  | Emerg. Waiting
1 | 1 |  | D5(1Pc) |  | 2.95 | 11.8
| 2.73 | -2.73
|  |  |  | 1 | 4 |  | Archive
1 | 1.2 |  | W9(1Pc) |  | 2.95 | 11.8
| 0.6 | -0.72
|  |  | W.C | 1 | 4 |  | Hmis
4 | 4.2 |  | L=1.00x2+1.10X2=4.20mt |  | 2.95 | 11.8
| 3.06 | 51.408
|  |  |  | 1 | 4 |  | Medical recording
4 | 0.7 |  | D8(2Pcs) |  | 2.75 | 11
| 2.73 | -7.644
|  |  | Shower enterance | 1 | 4 |  | Procedure room
1 | 6.4 |  | L=1.75X2+1.45X2=6.40mt |  | 4.85 | 19.4
| 3.06 | 19.584
|  |  |  | 1 | 4 |  | Staff room
1 | 1 |  | D5(1Pc) |  | 4.85 | 19.4
| 2.73 | -2.73
|  |  |  | 1 | 22.9 |  | Corridor
1 | 0.8 |  | D7(1Pc) |  | 2.4 | 54.96
| 2.73 | -2.184
|  |  |  | 1 | 4.2 |  | Emergence triage examination
1 | 0.7 |  | D8(1Pc) |  | 5.8 | 24.36
| 2.73 | -1.911
|  |  | Shower enterance | 1 | 4.2 |  | Observation room
1 | 7.5 |  | L=2.30X2+1.45X2=7.50mt |  | 7.05 | 29.61
| 3.06 | 22.95
|  |  |  | 2 | 1.4 |  | Toilet
1 | 0.7 |  | D8(1Pc) |  | 4.05 | 11.34
| 2.73 | -1.911
|  |  |  | 1 | 2.7 |  | Toilet
1 | 1.25 |  | W9(1Pc) |  | 3.95 | 10.665
| 0.6 | -0.75
|  |  |  | 1 | 1.45 |  | Toilet
20 | 0.2 |  | Column |  | 4.05 | 5.8725
| 2.73 | 10.92
|  |  |  | 1 | 2.2 |  | Duty room
2 | 23.3 |  | Grade beam at x axis |  | 4.2 | 9.24
| 0.4 | 18.64
[6 empty] | 231.2475 | m2 net area item 6.3
2 | 11.35 |  | Grade beam at x axis
| 0.4 | 9.08 |  |  |  |  | 6.5)Approved type 9mm thick
non slipery cearmic floor tile
2 | 23.3 |  | Top tie beam at x axis | 1 | 4.2 |  | Emerg. Waiting
| 0.3 | 13.98 |  |  | 2.95
12.39
2 | 11.35 |  | Top tie beam at x axis | 1 | 4 |  | Archive
| 0.3 | 6.81 |  |  | 2.95
11.8
4 | 6.4 |  | Exposed beam
| 0.8 | 20.48 | Axis Y/02,03,04&06 (x/01 -x/03)
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 4 |  | Hmis |  |  |  | 6.6)Approved type cearmic skirting 10/0.9cm
| 2.95 | 11.8 |  | 1 | 12.1 |  | Emerg. Waiting
[6 empty] | 12.1 | L=4.40*2+1.55+1.75=12.10
1 | 4 |  | Medical recording | 1 | 13 |  | Archive
| 2.95 | 11.8 |  |  |  | 13 | L=4X2+2.95X2-0.9=13.00mt
|  |  |  | 1 | 12.1 |  | Hmis
1 | 4 |  | Procedure room |  |  | 12.1 | L=4X2+2.95X2-0.9X2=12.10mt
| 5.05 | 20.2 |  | 1 | 12.1 |  | Medical recording
[6 empty] | 12.1 | L=4X2+2.95X2-0.9X2=12.10mt
1 | 4 |  | Staff room | 1 | 16.3 |  | Procedure room
| 5.05 | 20.2 |  |  |  | 16.3 | L=4X2+5.05X2-0.9X2=16.10mt
|  |  |  | 1 | 16.5 |  | Staff room
1 | 23.1 |  | Corridor |  |  | 16.5 | L=4x2+5.05x2-0.9X2=16.30mt
| 2.4 | 55.44 |  | 1 | 36.65 |  | Corridor
[6 empty] | 36.65 | L=22.9*2+2.4*2-2.95-1.4*2-
1 | 4.2 |  | Emergence triage examination |  |  |  | 1.2*2-1*4-0.9*2=36.65mt
| 5.8 | 24.36 |  | 1 | 18.8 |  | Emergence triage examination
[6 empty] | 18.8 | L=4.20x2+5.80x2-1.2=18.80mt
1 | 4.2 |  | Observation room | 1 | 21.7 |  | Observation room
| 7.25 | 30.45 |  |  |  | 21.7 | L=4.20x2+7.25x2-1.2=21.70mt
|  |  |  | 2 | 3.4 |  | Toilet
2 | 1.4 |  | Toilet |  |  | 6.8 | L=1.4x2+1.2x2-1-0.8=3.40mt
| 4.05 | 11.34 |  | 1 | 3.7 |  | Toilet
[6 empty] | 3.7 | L=1.45x2+1.20x2-1-0.7-0.8=2.804mt
1 | 2.7 |  | Toilet | 1 | 12 |  | Duty room
| 2.05 | 5.535 |  |  |  | 12 | L=2.2x2+4.2x2-0.80=12mt
|  |  |  | 4 | 0.15 |  | D1
4 | 0.98 |  | Toilet |  |  | 0.6
| 1.4 | 5.488 |  | 4 | 0.15 |  | 182.95
0.6
1 | 1.45 |  | "
| 4.05 | 5.8725 |  |  |  | 182.95 | ml net area item 6.6
1 | 2.2 |  | Duty room |  |  |  | 6.7)Approved type terrazzo Cill
| 4.2 | 9.24 |  | 9 | 1.55 |  | W2(9Pcs)
13.95
2 | 1.4 |  | D1 | 2 | 1.35 |  | W4(2Pcs)
| 0.2 | 0.56 |  |  |  | 2.7
|  |  |  | 1 | 4.3 |  | W6(1Pc)
2 | 1.2 |  | D4(3Pcs) |  |  | 4.3
| 0.15 | 0.36 |  | 2 | 1.3 |  | W9(2Pcs)
2.6
4 | 1 |  | D5(4Pcs) | 1 | 1.05 |  | W14(1Pcs)
| 0.2 | 0.8 |  |  |  | 1.05
|  |  |  | 1 | 1.25 |  | W21(1Pc)
5 | 0.9 |  | D6(5Pcs) |  |  | 1.25
| 0.2 | 0.9
[6 empty] | 25.85 | ml net length item 6.7
3 | 0.8 |  | D7(3Pcs)
| 0.15 | 0.36
5 | 0.7 |  | D8(5Pcs)
| 0.1 | 0.35
3 | 0.9 |  | D9(3Pcs)
| 0.15 | 0.405
|  | 239.6505 | m2 net area item 6.5
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.9)10cm thick C-20 RC 1.2mt wide |  |  |  | 9.5)Supply & install waste water pipe
2 | 25.7 |  | pavement |  |  |  | made of rigid UPVC ф 50mm
| 1.2 | 61.68 |  |  |  |  | ф 50mm of min. wall thickness=3mm
|  |  | L=23.30+1.20X2=25.70mt | 1 | 11.4
2 | 11.35 |  |  |  |  | 11.4 | m net length item 9.5.a
| 1.2 | 27.24 | L=11.35mt
ф 75mm of min. wall thickness=3mm
|  | 88.92 | m2 net area item 6.9 | 1 | 9
[6 empty] | 9 | m net length item 9.5.b
6.21. concrete pipe of 1/2 ф30cm
2 | 26.3 |  | L=23.30+1.20X2+0.3X2=26.30mt |  |  |  | ф 100mm of min. wall thickness=3.2mm
|  | 52.6 |  | 1 | 17.7
[6 empty] | 17.7 | m net length item 9.5.c
1 | 14.15 |  | L=11.35+1.20X2=13.75mt
|  | 14.15 | L=2.50+5.00=7.50mt |  |  |  | 9.9)Supply & fix toilet paper holder
|  |  |  | 6 | 1
|  | 66.75 | m2 net area item 6.21 |  |  | 6 | m net length item 9.9
|  |  | 6.19)Consrutcte 10/40 cm curb stone |  |  |  | 10. Electrical Installations
2 | 26.8 |  | L=23.30+1.20X2+0.3X2+0.15X2+0.1X2=26.8mt |  |  |  | 2)LIGHT POINT
|  | 53.6 |  |  |  |  | 2.1points conduti of 16mm 3*2.5mm2
|  |  |  | 56 | 1
1 | 14.95 |  | L=11.35+1.20X2+0.3X2+0.15X2=14.95mt |  |  | 56 | no net number item 2.01
14.95
3.01)Single Switch legrand
|  | 68.55 | ml net length item 6.19 | 4 | 1
[6 empty] | 4 | no net number item 3.01
7)Painting
|  |  | 7.1)Int. plastered surface & ext beam & colun |  |  |  | 3.02)Double Switch legrand
|  |  |  | 14 | 1
|  | 646.2775 | m2 net area item 7.1 |  |  | 14 | no net number item 3.02
|  |  | 7.2)Chip wood ceiling surface |  |  |  | 3.03)Two way Switch legrand
|  | 231.2475 | m2 net area item 7.2 | 6 | 1
[6 empty] | 6 | no net number item 3.03
7.3)External rendered surface
|  | 135.6975 | m2 net area item 7.3 |  |  |  | 4.)Socket outlet point
4.01)Socket outlet point 3x2.5mm2
|  |  | 9)SANITARY INSTALLATION | 30 | 1
|  |  | 9.10)Supplay & install PP-R water pipe |  |  | 30 | no net number item 4.01
Internal ф 15mm
1 | 17.19 | [5 empty] | 4.02)Ditto 4.01 but water heater
|  | 17.19 | m net length item 9.1.a | 1 | 1
[6 empty] | 1 | no net number item 4.02
Internal ф 25mm
1 | 3.05 | [5 empty] | 5)Socket outlets
|  | 3.05 | m net length item 9.1.b |  |  |  | 5.01)Socket outlets LEGRAND SUNO
|  |  |  | 30 | 1
|  |  | Internal ф 32mm |  |  | 30 | no net number item 5.01
1 | 4.2
|  | 4.2 | m net length item 9.1.c |  |  |  | 5.02)Water proof LEGRAND SUNO
|  |  |  | 1 | 1
|  |  | 9.3)Supply & fix bronze gate valve |  |  | 1 | no net number item 5.02
20mm diameter
3 | 1
|  | 3 | m net length item 9.3
T | D | S | Item No. and Description | T | D | S | Item No. and Description
6)Telephone/data point
6.01)Telephone point feed through
8 | 1 |  | cat 5E UTP Cable
|  | 8 | no net number item 6.01
6.03)Flush mounted Telephone
8 | 1 |  | outlets RJ11 type
|  | 8 | no net number item 6.03
7. Type of light fittings
7.01)Philips TCS 098/1/1xTL-D 36W
27 | 1
|  | 27 | no net number item 7.01
7.02)Philips TCS 098/1/2xTL-D 36W
6 | 1
|  | 6 | no net number item 7.02
7.03)RZB 59251.002
19 | 1
|  | 19 | no net number item 7.03
7.04)RZB 59222.002Q/E27/60W
4 | 1
|  | 4 | no net number item 7.04
8)TV POINTS
8.01)TV point fed through RG6
1 | 1 |  | Coaxial 75ohm Tv cable
|  | 1 | no net number item 8.01
10.0 Cable way and Manhole
10.4 Rigid pvc pipe dia. 50mm to
telephone Distribution frame
1 | 15.45
|  | 15.45 | no net number item 10.04

## Wait Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Waiting
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE |  |  |  | 1.6)ф12 mm deformed bars
|  |  | 1.CONCRETE WORK | 1 | 711.3058
|  |  | 1.1)In elevation column |  |  | 711.3058 | kg net weight item 1.8
14 | 0.2 |  | C1=20Pcs & C2=4Pcs (0.2x0.2)
| 0.2 | [5 empty] | 1.7)ф8mm deformed bars
| 2.73 |  |  | 1 | 227.283
|  | 1.5288 |  |  |  | 227.283 | kg net weight item 1.9
|  |  | 1.2)In beam & step |  |  |  | 2)BLOCK WORK
3 | 8.8 |  | TTB1=3Pcs |  |  |  | 2.1)20cm HCB wall
| 0.3 |  |  | 2 | 3.9 |  | Axis y/01 & y/04 from (x/03 - x/04)
| 0.2 | 1.584 |  |  | 2.73 | 21.294
2 | 16.4 |  | TTB2=2Pcs | 1 | 1.5 |  | W2
| 0.3 |  |  |  | 1.73 | -2.595
| 0.2 | 1.968
|  |  |  | 1 | 1.15 |  | W21
2 | 16.4 |  | TTB3=2Pcs |  | 1.73 | -1.9895
| 0.3 |  | Axis y/01 & y/06 from ( x/01-x/04)
| 0.2 | 1.968 |  | 1 | 1 |  | W14
[5 empty] | 1.73 | -1.73
5.52
|  |  |  | 2 | 0.8 |  | D10
|  |  | 1.3)Lintel |  | 2.73 | -4.368
1 | 1.3 |  | chasier
| 0.2 |  |  | 1 | 13.9 |  | Half wall
| 0.15 |  |  |  | 1 | 13.9 | L=3.8+2.90+3.40+3.80=13.90mt
0.039
|  |  |  | 1 | 7.3 |  | Central triage
|  |  | FORM WORK |  | 2.73 | 19.929 | L=3.90+3.40=7.30mt
1.4)Elevation column
14 | 0.8 |  | C1=14Pcs | 1 | 0.9 |  | D9
| 2.73 |  |  |  | 2.73 | -2.457
|  | 30.576 |  |  |  |  | Above top tie beam x/01 & x/04
|  |  |  | 2 | 1.05
|  |  | 1.5)Beam |  | 9.6 | 20.16
3 | 8.8 |  | TTB1=2Pcs |  |  |  | Above top tie beam Y axis
| 0.8 | 21.12 | Axis x/01 & x/o4 from (y/01 - y/06) | 2 | 10.5
|  |  | Dev.L=0.30*2+0.20=0.80mt |  | 0.2 | 4.2
10 | 0.3
| 0.2 | 1.2 | TTB2=2Pcs |  |  | 66.3435
Axis x/02 & x/03 from (y/01 - y/06)
2 | 16.4 | [5 empty] | 2.2)15cm thick HCB wall
| 0.8 | 26.24 |  |  | 2.95
|  |  |  | 1 | 2.73
2 | 16.4 |  | TTB3=2Pcs |  |  | 8.0535
| 0.8 | 26.24 | Axis y/01 & y/06 from ( x/01 - x/04) |  | 1.8
|  |  |  | 1 | 2.73
|  | 74.8 |  |  |  | 4.914
0.9
|  |  | 1.6)Lintel | 2 | 1.73
1 | 1.3 |  | chaser |  |  | -3.114
0.55
|  | 0.715 |  |  |  | 9.8535
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 3)ROOFING WORK |  |  |  | 5)METAL WORK
|  |  | 3.1)G-28 CIS Roof covering |  |  |  | 5.1)Type W2 ,Size 150/173
|  |  | W=10.50+6+0.60=17.10mt | 1 | 1
| 17.1 |  | L=9.60+0.60x2=10.80mt |  |  | 1
10.8
|  | 184.68 |  |  |  |  | 5.2)Type W14 ,Size 100/173
|  |  |  | 2 | 1
2 | 5.66 |  | 3.2)G-28 Ribbed sheet ceiling |  |  | 2
0.5
|  | 5.66 |  |  |  |  | 6.1)Apply two coats of plastering &
2 | 17.1 | [5 empty] | one coat rendering
| 0.5 |  |  | 2 | 3.9 |  | Axis y/01 &y/04 from (x/01 - x/04)
|  | 17.1 |  |  | 2.73 | 21.294
|  | 22.76 |  | 1 | 1.5 |  | W2
[5 empty] | 1.73 | -2.595
|  |  | 3.3)Flashing in metal sheet | 1 | 1 |  | W14
2 | 5.66 |  | Dev. Length 33cm |  | 1.73 | -1.73
11.32
|  |  |  | 1 | 1.15 |  | W21
[5 empty] | 1.73 | -1.9895
2 | 17.6 |  | 3.4)Supply & fix G-28 gutter dev.
|  | 35.2 |  | 2 | 0.8 |  | D10
[5 empty] | 2.73 | -4.368
|  |  | 4)CARPENTRY | 1 | 14.7 |  | Half wall
17 | 11.5 |  | 4.1)Uper & lower chord |  | 1 | 14.7
195.5
|  |  |  | 2 | 1.05 |  | Above top tie beam y/01 &y/06
17 | 10.2 | 0 |  |  | 9.6 | 20.16
173.4
|  |  |  | 2 | 10.5 |  | Above top tie beam Y axis
|  | 368.9 |  |  | 0.2 | 4.2
49.6715
17 | 10.82 |  | 4.2)Vertical & Diagonal member
|  | 183.94 |  |  |  |  | 6.2)Apply three coats of plastering
|  |  |  | 1 | 9.5 |  | Casier9
17 | 13.16 |  |  |  | 2.93 | 27.835 | L=1.8x2+2.95x2=9.50mt
223.72
|  |  |  | 1 | 0.9 |  | D10
|  | 407.66 |  |  | 2.73 | -2.457
|  |  |  | 1 | 1 |  | W14
14 | 17.1 |  | 4.3)Purlin zigba 5/7cm |  | 1.73 | -1.73
239.4
|  |  |  | 2 | 1 |  | W8
[5 empty] | 1.73 | -3.46
2 | 5.66 |  | 4.4)Zigba wooden fascia board
|  | 11.32 |  | 1 | 5.25 |  | Rec/Reg.
[5 empty] | 2.93 | 15.3825 | L=2.15+3.1=5.25mt
2 | 17.1
|  | 34.2 |  | 1 | 0.9 |  | D10
[5 empty] | 2.63 | -2.367
45.52
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 1 |  | W21 |  |  |  | 6.3)Chipwood ceiling
| 1.73 | -1.73 |  | 1 | 1.8 |  | Cashier
[5 empty] | 2.95 | 5.31
1 | 1 |  | W8
| 1.73 | -1.73 |  | 1 | 1.95 |  | Rec/Reg.
[5 empty] | 2.95 | 5.7525
1 | 10.45 |  | Corridor
| 2.93 | 30.6185 | L=4.3+2.15+3.80+0.2=10.45mt | 1 | 2.5 |  | Corridor
[5 empty] | 3.9 | 9.75
1 | 0.9 |  | D9
| 2.63 | -2.367 |  | 1 | 3.9 |  | Central triage
[5 empty] | 3.4 | 13.26
1 | 1 |  | W8
| 1.73 | -1.73 |  | 2 | 6 |  | Main waiting area
[5 empty] | 2.9 | 34.8
1 | 14.6 |  | Central triage
| 2.93 | 42.778 | L=3.40x2+3.90x2=14.60mt | 2 | 6 |  | "
[5 empty] | 3.4 | 40.8
1 | 0.9 |  | D9
| 2.73 | -2.457 |  | 2 | 6 |  | Corridor
[5 empty] | 2.5 | 30
1 | 1.5 |  | W2
| 1.73 | -2.595 |  |  |  | 139.6725
1 | 15.2 |  | Half wall |  |  |  | 6.5)Approved type 9mm thick ceramic floor t.
| 1 | 15.2 | L=3.8X2+4+3.6=15.2mt | 1 | 1.8 |  | waitting
[5 empty] | 2.95 | 5.31
24 | 0.2 |  | Columns |  |  |  | Cashier
| 2.73 | 13.104 |  | 1 | 2.15
[5 empty] | 3.1 | 6.665 | Rec/Reg.
4 | 0.8 |  | "
| 2.63 | 8.416 |  | 1 | 2.5
[5 empty] | 3.9 | 9.75 | Corridor
4 | 0.8 |  | Half wall column
| 1.63 | 5.216 |  | 1 | 3.9
[5 empty] | 3.4 | 13.26 | Central triage
2 | 10.5 |  | top tie beam
| 0.3 | 6.3 |  | 1 | 6
[5 empty] | 9.2 | 55.2 | Main waiting area
2 | 9.6 |  | top tie beam
| 0.3 | 5.76 |  | 2 | 2.2
[5 empty] | 0.2 | 0.88 | Axis y/01 & y/04 from (x/02' - x/03)
4 | 1
| 6 | 24 |  | 3 | 2.5
[5 empty] | 0.2 | 1.5 | Axis x/02, x/03 & x/04 from (y/02 - y/03)
1 | 1
| 8.8 | 8.8 |  | 3 | 0.9
[5 empty] | 0.2 | 0.54 | D10(2Pcs) & D9(1Pc)
2 | 10.5 |  | Grade beam
| 0.4 | 8.4 |  |  |  | 93.105
1 | 9.6
| 0.4 | 3.84
193.027
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.6) Cearmic skirting 10/0.9cm |  |  |  | 6.19)Consrutcte curb stone
1 | 8.7 |  | Cashier | 2 | 20 |  | L=16.5+1.2X2+.3X2+.15x2+0.1x2 = 20.00mt
|  | 8.7 | L=1.8x2+3.00x2-0.9=8.7mt |  |  | 40
1 | 4.15 |  | Rec/Reg.
|  | 4.15 | L=2.05+3.00-0.90=4.15mt | 2 | 2.5 |  | covered slab
1 | 9.35 |  | Corridor |  |  | -5
|  | 9.35 | L=4.3+2.15+3.80-0.90=9.35mt
1 | 13.7 |  | Central triage |  |  | 35
|  | 13.7 | L=3.4X2+3.90X2-0.9=13.70mt
1 | 22.2 |  | Main waiting area |  |  |  | 7.1)Int. plastered surface & ext beam & colun
|  | 22.2 | L=4X2+3.30+3.80+3.3+3.8=22.20mt
4 | 0.8 |  | Column |  |  | 193.027 | m2 net area item 7.1
3.2
7.2)Chip wood ceiling surface
|  | 61.3 |  |  |  | 139.6725 | m2 net area item 7.2
|  |  | 6.7) Terrazzo window cill Size |  |  |  | 7.3)External rendered surface
[6 empty] | 49.6715 | m2 net area item 7.3
1 | 1.55
|  | 1.55 | W2(1Pcs) |  |  |  | 11. Electrical Installation
2)LIGHT POINT
1 | 1.05 | [5 empty] | 2.1points conduti of 16mm 3*2.5mm2
|  | 1.05 | W14(1Pcs) | 23 | 1
23
1 | 1.2
|  | 1.2 | W21(1Pcs) |  |  |  | 3)SWITCH
3.02)Double Switch legrand
2 | 1.05 |  |  | 5 | 1
|  | 2.1 | W8(2Pcs) |  |  | 5
1 | 13.9 | [5 empty] | 4.)Socket outlet point
|  | 13.9 | Main watting area | 8 | 1 |  | 4.01)Socket outlet point 3x2.5mm2
8
19.8
5)Socket outlets
|  |  | 6.9) 1.2mt wide pavement |  |  |  | 5.01)Socket outlets LEGRAND SUNO
|  |  |  | 8 | 1
2 | 17.7 |  | L=16.50+1.2=17.70mt |  |  | 8
| 1.2 | 42.48
6)Telephone/data point
2 | 2.5 | [5 empty] | 6.01)Telephone point feed through
| 1.2 | -6 |  | 3 | 1 |  | cat 5E UTP Cable
3
36.48
6.03)Flush mounted Telephone
|  |  | 6.19) Concrete pipe of 1/2 ф30cm |  |  |  | outlets RJ11 type
|  |  |  | 3 | 1
2 | 19.5 |  | L=16.5+1.20X2+0.3X2=19.50mt |  |  | 3
39
7. Type of light fittings
2 | 2.5 |  | covered slab |  |  |  | 7.01)Philips TCS 098/1/2xTL-D 36W
|  | -5 |  | 23 | 1
23
34
8)TV POINTS
8.01)TV point fed through RG6
|  |  |  | 1 | 1 |  | Coaxial 75ohm Tv cable
1

## EMG &Waitng Reinf
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Emergency
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Mem. | b/mem. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade Beam | axis x01 up to x04 | 14 | 11.95 | 4 | 3 | 12 | - | - | - | - | 143.4
|  | " | 14 | 8.4 | 4 | 3 | 12 | - | - | - | - | 100.8
|  | " | 14 | 4.95 | 4 | 3 | 12 | - | - | - | - | 59.4
|  | " | 14 | 11.35 | 4 | 3 | 12 | - | - | - | - | 136.2
|  | " | 14 | 7.5 | 4 | 3 | 12 | - | - | - | - | 90
|  | " | 14 | 6.7 | 4 | 3 | 12 | - | - | - | - | 80.4
|  | st | 8 | 1.2 | 4 | 119 | 476 | - | 571.2 | - | - | -
|  | axis y01 up to y06 | 14 | 6.13 | 6 | 3 | 18 | - | - | - | - | 110.34
|  |  | 14 | 6.58 | 6 | 3 | 18 | - | - | - | - | 118.44
|  |  | 14 | 11.4 | 6 | 3 | 18 | - | - | - | - | 205.2
|  | st | 8 | 1.2 | 58 | 6 | 348 | - | 417.6 | - | - | -
|  |  |  | TOTAL LENGTH |  |  |  |  | 988.8 | 0 | 0 | 1044.18
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 390.576 | 0 | 0 | 1263.4578
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Emergency
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
1 | (x/01-x/02) (y/01-y/02) |  | 8 | 5.67 | 1 | 21 | 21 |  | 119.07
|  |  | 8 | 4.02 | 1 | 29 | 29 |  | 116.58
| (x/01-x/02) (y/02-y/03) |  | 8 | 4.42 | 1 | 21 | 21 |  | 92.82
|  |  | 8 | 4.02 | 1 | 23 | 23 |  | 92.46
| (x/01-x/02) (y/03-y/04) |  | 8 | 3.82 | 1 | 21 | 21 |  | 80.22
|  |  | 8 | 4.02 | 1 | 20 | 20 |  | 80.4
| (x/01-x/02) (y/04-y/05) |  | 8 | 4.12 | 1 | 21 | 21 |  | 86.52
|  |  | 8 | 4.02 | 1 | 22 | 22 |  | 88.44
| (x/01-x/02) (y/05-y/06) |  | 8 | 3.42 | 1 | 21 | 21 |  | 71.82
|  |  | 8 | 4.02 | 1 | 18 | 18 |  | 72.36
2 | (x/02-x/03) (y/01-y/02) |  | 8 | 5.67 | 1 | 12 | 12 |  | 68.04
|  |  | 8 | 2.27 | 1 | 29 | 29 |  | 65.83
| (x/02-x/03) (y/02-y/03) |  | 8 | 4.42 | 1 | 12 | 12 |  | 53.04
|  |  | 8 | 2.27 | 1 | 23 | 23 |  | 52.21
| (x/02-x/03) (y/03-y/04) |  | 8 | 3.82 | 1 | 12 | 12 |  | 45.84
|  |  | 8 | 2.27 | 1 | 20 | 20 |  | 45.4
| (x/02-x/03) (y/04-y/05) |  | 8 | 4.12 | 1 | 12 | 12 |  | 49.44
|  |  | 8 | 2.27 | 1 | 22 | 22 |  | 49.94
| (x/02-x/03) (y/05-y/06) |  | 8 | 3.42 | 1 | 12 | 12 |  | 41.04
|  |  | 8 | 2.27 | 1 | 18 | 18 |  | 40.86
3 | (x/03-x/04) (y/01-y/02) |  | 8 | 5.67 | 1 | 20 | 20 |  | 113.4
|  |  | 8 | 3.87 | 1 | 29 | 29 |  | 112.23
| (x/03-x/04) (y/02-y/03) |  | 8 | 4.42 | 1 | 20 | 20 |  | 88.4
|  |  | 8 | 3.87 | 1 | 23 | 23 |  | 89.01
| (x/03-x/04) (y/03-y/04) |  | 8 | 3.82 | 1 | 20 | 20 |  | 76.4
|  |  | 8 | 3.87 | 1 | 20 | 20 |  | 77.4
| (x/03-x/04) (y/04-y/05) |  | 8 | 4.12 | 1 | 20 | 20 |  | 82.4
|  |  | 8 | 3.87 | 1 | 22 | 22 |  | 85.14
| (x/03-x/04) (y/05-y/06) |  | 8 | 3.42 | 1 | 20 | 20 |  | 68.4
|  |  | 8 | 3.87 | 1 | 18 | 18 |  | 69.66
|  |  |  | TOTAL LENGTH |  |  |  |  | 2274.77 | 0 | 0 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 898.5342 | 0 | 0 | 0
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Emergency
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Summary
Sub structure
6
|  |  | 8 | [5 empty] | #REF!
|  |  | 10 | [6 empty] | 0
|  |  | 12 | [7 empty] | 0
|  |  | 14 | [8 empty] | 1044.18
|  |  |  | TOTAL LENGTH |  |  |  |  | #REF! | 0 | 0 | 1044.18
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | #REF! | 0 | 0 | 1263.4578
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Emergency
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
1 | COLUMN (C1) |  | 12 | 3.58 | 20 | 4 | 80 |  |  |  | 286.4
|  |  | 8 | 0.7 | 20 | 14 | 280 |  | 196
|  |  | 14 | 3.58 | 4 | 4 | 16 |  |  |  |  | 57.28
|  |  | 8 | 0.7 | 4 | 14 | 56 |  | 39.2
2 | TTB1 |  | 12 | 11.85 | 2 | 4 | 8 |  |  |  | 94.8
|  |  | 12 | 8.4 | 2 | 3 | 6 |  |  |  | 50.4
|  |  | 12 | 4.85 | 2 | 3 | 6 |  |  |  | 29.1
|  |  | 12 | 11.35 | 2 | 3 | 6 |  |  |  | 68.1
|  |  | 12 | 7.5 | 2 | 3 | 6 |  |  |  | 45
|  |  | 12 | 6.7 | 2 | 3 | 6 |  |  |  | 40.2
|  |  | 8 | 0.9 | 2 | 117 | 234 |  | 210.6
3 | TTB2 |  | 12 | 11.85 | 2 | 3 | 6 |  |  |  | 71.1
|  |  | 12 | 8.4 | 2 | 3 | 6 |  |  |  | 50.4
|  |  | 12 | 4.85 | 2 | 3 | 6 |  |  |  | 29.1
|  |  | 12 | 11.35 | 2 | 3 | 6 |  |  |  | 68.1
|  |  | 12 | 7.5 | 2 | 3 | 6 |  |  |  | 45
|  |  | 12 | 6.7 | 2 | 3 | 6 |  |  |  | 40.2
|  |  | 8 | 0.9 | 2 | 117 | 234 |  | 210.6
4 | TTB3 |  | 12 | 11.8 | 2 | 3 | 6 |  |  |  | 70.8
|  |  | 12 | 11.4 | 2 | 3 | 6 |  |  |  | 68.4
|  |  | 8 | 0.9 | 2 | 55 | 110 |  | 99
5 | TTB4 |  | 12 | 11.8 | 4 | 3 | 12 |  |  |  | 141.6
|  |  | 12 | 11.4 | 4 | 3 | 12 |  |  |  | 136.8
|  |  | 8 | 0.9 | 4 | 55 | 220 |  | 198
8 | D7/LENTEL/ |  | 12 | 1.45 | 3 | 2 | 6 |  |  |  | 8.7
|  |  | 12 | 1.15 | 3 | 2 | 6 |  |  |  | 6.9
|  |  | 8 | 0.6 | 3 | 7 | 21 |  | 12.6
9 | D8 |  | 12 | 2.15 | 2 | 2 | 4 |  |  |  | 8.6
|  |  | 12 | 1.85 | 2 | 2 | 4 |  |  |  | 7.4
|  |  | 8 | 0.5 | 2 | 10 | 20 |  | 10
10 | D8 |  | 12 | 1.35 | 1 | 2 | 2 |  |  |  | 2.7
|  |  | 12 | 1.05 | 1 | 2 | 2 |  |  |  | 2.1
|  |  | 8 | 0.6 | 1 | 6 | 6 |  | 3.6
10 | W9 |  | 12 | 1.9 | 1 | 2 | 2 |  |  |  | 3.8
|  |  | 12 | 1.6 | 1 | 2 | 2 |  |  |  | 3.2
|  |  | 8 | 0.6 | 1 | 8 | 8 |  | 4.8
|  |  |  | TOTAL LENGTH |  |  |  |  | 984.4 | 0 | 1378.9 | 57.28
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 388.838 | 0 | 1224.4632 | 69.3088
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : waiting
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade Beam | X/01,02,03&04 |  |  |  |  | 0 | - | - | - | - | -
|  |  | 14 | 10.28 | 3 | 4 | 12 | - | - | - | - | 123.36
|  |  | 14 | 9.58 | 3 | 4 | 12 |  |  |  | - | 114.96
[7 empty] | 0 |  |  |  | - | -
|  | Y/01,02,03,04 |  |  |  |  | 0 | - | - | - | - | -
|  |  | 14 | 6.93 | 3 | 4 | 12 | - | - | - | - | 83.16
|  |  | 14 | 11.3 | 3 | 4 | 12 | - | - | - | - | 135.6
|  |  | 14 | 8.47 | 3 | 4 | 12 | - | - | - | - | 101.64
|  |  | 14 | 8.47 | 3 | 4 | 12 | - | - | - | - | 101.64
| stirupps | x- xis | 8 | 1.2 | 49 | 4 | 196 | - | 235.2 | - | - | -
|  | y-axis | 8 | 1.2 | 84 | 4 | 336 | - | 403.2 | - | - | -
[7 empty] | 0 | - | - | - | - | -
[7 empty] | 0 | - | - | - | - | -
| floor mesh | [5 empty] | 0 | - | - | - | - | -
|  |  | 8 | 5.65 | 46 | 1 | 46 | - | 259.9 | - | - | -
|  |  | 8 | 5.85 | 46 | 1 | 46 | - | 269.1 | - | - | -
|  |  | 8 | 3.75 | 46 | 1 | 46 | - | 172.5 | - | - | -
|  |  | 8 | 2.75 | 80 | 1 | 80 | - | 220 | - | - | -
|  |  | 8 | 2.35 | 80 | 1 | 80 | - | 188 | - | - | -
|  |  | 8 | 3.25 | 80 | 1 | 80 | - | 260 | - | - | -
[7 empty] | 0 | - | - | - | - | -
[7 empty] | 0 | - | - | - | - | -
[7 empty] | 0 | - | - | - | - | -
|  |  |  | TOTAL LENGTH |  |  |  |  | 2007.9 | 0 | 0 | 660.36
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 793.1205 | 0 | 0 | 799.0356
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : waiting
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
Summary
Sub structure
6
|  |  | 8 | [5 empty] | #REF!
|  |  | 10 | [6 empty] | #REF!
|  |  | 12 | [7 empty] | #REF!
|  |  | 14 | [8 empty] | 660.36
|  |  |  | TOTAL LENGTH |  |  |  |  | #REF! | #REF! | #REF! | 660.36
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | #REF! | #REF! | #REF! | 799.0356
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : waiting
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
1 | COLUMN |  | 12 | 3.58 | 14 | 4 | 56 |  |  |  | 200.48
|  |  | 8 | 0.7 | 15 | 14 | 210 |  | 147
2 | TTB3 |  | 12 | 6.93 | 4 | 3 | 12 |  |  |  | 83.16
|  |  | 12 | 11.3 | 4 | 3 | 12 |  |  |  | 135.6
|  |  | 12 | 8.46 | 4 | 3 | 12 |  |  |  | 101.52
|  |  | 12 | 8.46 | 4 | 3 | 12 |  |  |  | 101.52
|  |  | 8 | 0.9 | 4 | 83 | 332 |  | 298.8
4 | TTB4 |  | 12 | 10.28 | 3 | 3 | 9 |  |  |  | 92.52
|  |  | 12 | 9.58 | 3 | 3 | 9 |  |  |  | 86.22
|  |  | 8 | 0.9 | 3 | 48 | 144 |  | 129.6
|  |  |  | TOTAL LENGTH |  |  |  |  | 575.4 | 0 | 801.02 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 227.283 | 0 | 711.3058 | 0
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0.15
0.40
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15

## Admin. Sum
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-Administration
Details of Works executed
Bill No. | Description | Sub Total Birr |  | Total Birr
|  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work | 239171.33 | 83451.9569 | 239171.33 | 83451.9569
2 | Concrete Work | 346586 | 277861.4908 | 346586 | 277861.4908
3 | Masonry work | 164250 | 57631.2 | 164250 | 57631.2
| sub total A | 750007.33 | 418944.6477 | 750007.33 | 418944.6477
| B. Super Structure |  |  | 0 | 0
1 | Concrete Work | 113712 | 117117.6294 | 113712 | 117117.6294
2 | Block work | 117300 | 123243.5 | 117300 | 123243.5
3 | Roofinig | 143225.6 | 139410.6 | 143225.6 | 139410.6
4 | Carpentary & Joinery | 52632.08 | 84638.36 | 52632.08 | 84638.36
5 | Metal work | 246757.5 | 67191.5 | 246757.5 | 67191.5
6 | Finishing | 603125 | 391985.065 | 603125 | 391985.065
7 | Painting | 35672 | 20424.236 | 35672 | 20424.236
8 | Glazing | 12345 |  | 12345
9 | Sanitory Installation | 18305 | 2408.5 | 18305 | 2408.5
10 | Electrical Installation | 57266.86 | 49242.5 | 57266.86 | 49242.5
| sub total B | 1400341.04 | 995661.8904 | 1400341.04 | 995661.8904
| Total A+B | 2150348.37 | 1414606.5381 | 2150348.37 | 1414606.5381
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  |  |  | Consultant:- _____________

## Admin. Meas.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [5 empty] | Block : Adminstration
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 342 | 8 | 2736 | 375.4975 | 3003.98
1.2 | Bulk excavation in ordinary | m3 | 446 | 70 | 31220 | 164.8104 | 11536.7262
1.3 | Ditto but exceeing 1.50m less than 2m | m3 | 148.6667 | 70 | 10406.6667 |  | 0
1.4 | Selected borrowed fill brought from out side | m3 | 594.6667 | 56.6 | 33658.1333 | 209.5465 | 11860.3319
1.5 | Cart away surplus excavated material to an | m3 | 697.2667 | 70 | 48808.6667 | 67.9131 | 4753.9187
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 284 | 200 | 56800 | 261.485 | 52297
Total to summary ………Birr |  |  |  |  | 183629.4667 |  | 83451.9569
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 77 | 150 | 11550 | 59.62 | 8943
2.2 | Ditto but under footing pad | m2 | 20 | 150 | 3000 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 284 | 400 | 113600 | 261.485 | 104594
2.4 | In grade beam&Steps | m3 | 15 | 3200 | 48000 | 15.205 | 48656
2.5 | In footing pad | m3 | 4 | 3200 | 12800 |  | 0
2.6 | In footing coloumn | m3 | 3.5 | 3200 | 11200 |  | 0
| Provide cut and fix in position swan zigzag wood |  |  |  | 0 |  | 0
2.7 | Grade beam | m2 | 77 | 120 | 9240 | 119.04 | 14284.8
2.8 | In footing pad | m2 | 16 | 120 | 1920 |  | 0
2.9 | In footing coloumn | m2 | 65 | 120 | 7800 |  | 0
2.1 | Steps | m2 | 5 | 150 | 750 |  | 0
Reinforcement steel bar according to St.drawing
2.12 | Dia 14 mm deformed bar | kg | 1121 | 36 | 40356 | 1213.146 | 43673.256
2.13 | Dia. 12mm deformed bar | kg | 580 | 36 | 20880 |  | 0
2.14 | Dia 8 mm deformed bar | kg | 1635 | 36 | 58860 | 1414.2343 | 50912.4348
2.15 | 10/2 cm chip wood expansion joint between | m | 221 | 30 | 6630 | 226.6 | 6798
Total to summary ………Birr |  |  |  |  | 346586 |  | 277861.4908
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 114 | 1250 | 142500 | 40.3502 | 50437.75
3.2 | Ditto but above natural ground level externally | m3 | 15 | 1450 | 21750 | 4.961 | 7193.45
Total to summary ………Birr |  |  |  |  | 164250 |  | 57631.2
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 2.4 | 3200 | 7680 | 2.184 | 6988.8
1.2 | In beams& steps | m3 | 9.3 | 3200 | 29760 | 9.156 | 29299.2
1.3 | Lintel | m3 | 0.75 | 3200 | 2400 |  | 0
Provide cut and fix in position swan zigzag wood
1.4 | Elevation column | m2 | 48 | 130 | 6240 | 43.68 | 5678.4
1.5 | Beam | m2 | 124 | 130 | 16120 | 119.96 | 15594.8
1.6 | Lintel | m2 | 8 | 130 | 1040 |  | 0
Reinforcement steel bar according to St.drawing
1.7 | Dia 12mm deformed bar | kg | 1077 | 36 | 38772 | 1288.0618 | 46370.2234
1.8 | Dia 8 mm deformed bar | kg | 325 | 36 | 11700 | 366.2835 | 13186.206
1.9 | Dia 6 mm deformed bar | kg | 0 | 36 | 0 |  | 0
Total to summary ………Birr |  |  |  |  | 113712 |  | 117117.6294
2. BLOCK WORK
2.1 | 20cm thick | m2 | 230 | 350 | 80500 | 170.986 | 59845.1
2.2 | 15cm thick | m2 | 115 | 320 | 36800 | 198.12 | 63398.4
Total to summary ………Birr |  |  |  |  | 117300 |  | 123243.5
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 342.46 | 360 | 123285.6 | 342.22 | 123199.2
3.2 | G28ribbed sheet ceiling under eave | m2 | 42 | 160 | 6720 | 38.62 | 6179.2
3.3 | Flashing in flat metal sheet fixed as shown | m | 70 | 110 | 7700 | 38.62 | 4248.2
3.4 | Supply and fix G-28 flat metal sheet gutter | m | 46 | 120 | 5520 | 48.2 | 5784
Total to summary ………Birr |  |  |  |  | 143225.6 |  | 139410.6
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12cm | m | 446.56 | 23 | 10270.88 | 509.76 | 11724.48
4.2 | Vertical & diagonal members size-diameter 8 - 10cm | m | 276.8 | 16 | 4428.8 | 598.68 | 9578.88
4.3 | Purlin zigba size 5/7cm | m | 385.6 | 33 | 12724.8 | 433.8 | 14315.4
4.4 | Zigba wooden fascia board price includes | m | 48.2 | 70 | 3374 | 48.2 | 3374
Doors
4.5 | Type D9 size - 90/273 | № | 2 | 4668.3 | 9336.6 | 2 | 9336.6
4.6 | Type D2 size 140/273 cm | № | 0 | 7261.8 | 0 | 5 | 36309
Total to summary ………Birr |  |  |  |  | 40135.08 |  | 84638.36
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 16 | 3892.5 | 62280 | 3 | 11677.5
5.3 | Type W17 size-120/173cm | Nº | 2 |  |  |  | 0
5.4 | Type W14 size-150/173cm | Nº | 20 | 3892.5 | 77850 |  | 0
5.5 | Type W26 size-120/173cm | Nº | 1 |  |  |  | 0
* | Type W size-160/173cm | Nº |  | 3114 |  | 16 | 49824
* | Type W size-120/90cm | Nº |  | 1620 |  | 2 | 3240
| Doors |  |  |  | 0 |  | 0
5.7 | Type D4 size - 120/273cm | Nº | 3 | 2450 | 7350 | 1 | 2450
Total to summary ………Birr |  |  |  |  | 147480 |  | 67191.5
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 213 | 140 | 29820 | 158.946 | 22252.44
6.2 | Apply three coats of plastering to internal walls& | m2 | 790 | 150 | 118500 | 668.547 | 100282.05
6.3 | Chip wood ceiling nailed on & including | m2 | 284 | 310 | 88040 | 266.6625 | 82665.375
6.5 | 9mm thick non slippery ceramic tile floor | m2 | 790 | 320 | 252800 | 261.135 | 83563.2
6.6 | Approved type Ceramic tile skirting | m | 221 | 150 | 33150 | 189.6 | 28440
6.7 | Approved type Terrazo window cill size 27/3cm | m | 77.1 | 100 | 7710 | 278.7 | 27870
6.9 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 92 | 550 | 50600 | 73.44 | 40392
6.12 | Concrete pipes of half diameter 30cm | ml | 86 | 100 | 8600 | 65.2 | 6520
| Construction of 10x40 cm curb stone | ml | 86 | 265 | 22790 |  | 0
Total to summary ………Birr |  |  |  |  | 612010 |  | 391985.065
7. PAINTING
7.1 | Internal plastered surfaceand external beams & | m2 | 790 | 18.6667 | 14746.6667 | 668.547 | 12479.544
7.2 | Chip wood ceiling surface | m2 | 284 | 18.6667 | 5301.3333 | 266.6625 | 4977.7
7.3 | External rendered surface | m2 | 200 | 18.6667 | 3733.3333 | 158.946 | 2966.992
Total to summary ………Birr |  |  |  |  | 23781.3333 |  | 20424.236
9. SANITARY INSTALLATION
| 50mm diameter of min. wall thickness=2mm | LM | 5 | 60 | 300 | 13 | 780
| 75mm diameter of min. wall thickness=3mm | LM | 8 | 65 | 520 | 8.62 | 560.3
| 100 mm diameter of min. wall thickness=3.2mm | LM | 9 | 70 | 630 | 15.26 | 1068.2
| 150 mm diameter of min. wall thickness=3.2mm | LM | 5 | 80 | 400 |  | 0
Total to summary ………Birr |  |  |  |  | 1850 |  | 2408.5
10. ELECTRICAL INSTALLATION
1.02 | Flush mounted Sub distribution board SDB-ADM | PCs | 1 | 7000 | 7000 |  | 0
2 | Light points |  |  |  | 0 |  | 0
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 21 | 250 | 5250 | 29 | 7250
3 | Switches |  |  |  | 0 |  | 0
3.01 | single(774001+774041) | PCs | 6 | 81.25 | 487.5 | 8 | 650
3.02 | Duoble(774005+774042) | " | 5 | 131.25 | 656.25 | 4 | 525
4 | Socket outlet points |  |  |  | 0 |  | 0
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 24 | 200 | 4800 | 19 | 3800
4.02 | Ditto as above but for water Heater points | PCs | 1 | 785 | 785 |  | 0
4.05 | Ditto as 4.04 above but 3x4mm2 in pvc pipe | PCs | 3 |  | 0 |  | 0
5 | Socket outlets |  |  |  | 0 |  | 0
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 24 | 90 | 2160 | 19 | 1710
5.03 | weather proof socket Legrand Suno 774022+774041 | PCs | 1 | 281.25 | 281.25 |  | 0
5.06 | Ditto as above 4.06 but for 25A/1ph for kitchen | PCs | 3 |  | 0 |  | 0
6 | Telephone/Data points | [5 empty] | 0
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 6 | 266.25 | 1597.5 | 7 | 1863.75
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 6 | 90 | 540 |  | 0
7 | Type of Light Fitting With lamp |  |  |  | 0 |  | 0
7.01 | PHILIPS TCS 098/236 IMKwith 2xTLD 36W | PCs | 6 | 1500 | 1500 | 12 | 18000
7.02 | PHILIPS TCS 098/136 IMKwith 1xTLD 36W | PCs | 8 | 1200 | 1200 | 10 | 12000
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 5 | 406.25 | 406.25 | 5 | 2031.25
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 2 | 406.25 | 406.25 | 2 | 812.5
8 | TV points | [5 empty] | 0
8.01 | TV points fed through RG6 Coaxial 75ohm TV | PCs | 2 | 600 | 1200 | 1 | 600
8.02 | Flush mounted TV outlets type Legrand Suno | PCs | 2 | 250 | 500 |  | 0
9 | Power Cables(XLPE 0.6/KV or approved equ.) |  |  |  | 0 |  | 0
9.01 | 5x10mm2 | ML | 17 | 200 | 3400 |  | 0
10 | Cable way and Manhole |  |  |  | 0 |  | 0
10.01 | Rigid pvc pipe of dia.40mm From CMDB |  |  |  | 0 |  | 0
| to SDB-ADM | mt | 15 | 40 | 600 |  | 0
10.02 | Rigid pvc pipe dia. 50mm to telephone | " | 12 | 50 | 600 |  | 0
11 | Low Voltage Earthing system |  |  |  | 0 |  | 0
11.01 | Copper Earthing rod of 16x2400mm to be driven | PCs | 1 | 3000 | 3000 |  | 0
11.02 | Copper conductor of 1x10mm2 for Earthing | Ml | 19 | 100 | 1900 |  | 0
Total to summary ………Birr |  |  |  |  | 38270 |  | 49242.5

## Admin. Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Adminstrator Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | C-bulk fill and compaction (under hard core)
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 22.15 |  | L=23.45-0.5-0.8=22.15
|  |  | 1.1 Clear off site to remove top soil |  | 12.25 |  | W=13.55-0.5-0.8=12.25
|  |  | L=22.95+1.0+1.0=24.95 |  | 0.54 | 146.5222
1 | 24.95 |  | W=13.05+1.0+1.0=15.05
| 15.05 | 375.4975 |  |  |  |  | DEDUCTION
|  |  |  | 2 | 22.15 |  | along x-axis
|  | 375.4975 | m2 Total to item 1.1 |  | 0.4 |  | L=22.15 W=0.4m
[5 empty] | 0.54 | 9.5688
1.2 Bulk Excavation in ordinary soil
1 | 21.65 |  | L=23.45-0.25-0.25-0.4-0.4-0.5=21.65 | 3 | 11.45 |  | along x-axis
| 11.75 |  | W=13.55-0.25-0.25-0.4-0.4-0.5=11.75 |  | 0.4 |  | L=13.55-0.5-0.8-(2*0.4)=11.45
| 0.23 | 58.5091 |  |  | 0.54 | 7.4196
|  |  | DEDUCTION |  |  | 209.5465 | m3 Total to item 1.4
2 | 21.65 |  | along x-axis
| 0.9 |  | L=23.45-0.25-0.25-0.4-0.4-0.5=21.65 |  |  |  | 1.5 Cart away excavated material to an
| 0.23 | 8.9631 |  | 1 | 24.95
15.05
3 | 9.95 |  | along y-axis |  | 0.3 | 112.6492 | from item no 1.1
| 0.9 |  | W=13.55-0.25-0.25-0.4-0.4-0.5-(2*0.9)=8.15
| 0.23 | 6.1789 |  |  |  | 43.3671 | from item no 1.2
|  | 43.3671 | m3 Total to item 1.2 |  |  | 121.4433 | from item no 1.3
|  |  | 1.3 Ditto to Item 1.2 but exceeding 1.5 |  |  | 209.5465 | DEDUCTION
and less than 2m
4 | 23.45 |  | along x-axis |  |  | 67.9131 | m3 Total to item 1.4
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=23.45 d=0.92
| 0.94 | 79.3548 |  |  |  |  | 1.6/ 25 cm thick basaltic or equivalent stone hard core
|  |  |  | 1 | 22.45 |  | L=23.45-0.5-0.5=22.45W=13.55-0.5-0.5=12.55
5 | 9.95 |  | along y-axis |  | 12.55 | 281.7475
| 0.9 |  | L=13.55-(4*.9)=9.95
| 0.94 | 42.0885 | W=0.4+0.25+0.25=0.90, d= |  |  |  | DEDUCTION
|  |  |  | 2 | 22.45 |  | along x-axis L=22.45 W=0.25
|  | 121.4433 | m3 Total to item 1.3 |  | 0.25 | 11.225
|  |  | 1.4 Selected Fill( insitu material ) | 3 | 12.05 |  | along y-axis L=12.05 W=0.25
|  |  | A- fill under masonary |  | 0.25 | 9.0375 | L=13.55-0.5-0.5-0.5=12.05
4 | 23.45 |  | for axis x01-x04
| 0.9 |  |  |  |  | 261.485 | m2 Total to item 1.6
| 0.52 | 43.8984
2) CONCRETE WORK
5 | 9.95 |  | for axis y01-y05 |  |  |  | 2.1 5cm thick lean concrete class C-7
| 0.9 |  | L=9.95 , W=0.9, d=0.3 | 4 | 22.95 |  | L=23.45-0.5=22.95
| 0.52 | 23.283 | 9.95 |  | 0.4 | 36.72
|  |  | B-backfill and compaction in side masonary | 5 | 11.45 |  | L=13.55-0.5-(4*0.4)=11.45
|  |  | along x-axis |  | 0.4 | 22.9
6 | 20.95 |  | L=23.45-0.25-0.25-0.8-(3*0.4)=20.95
| 0.25 |  | W=0.25 ,d= |  |  | 59.62 | m2 Total to item 2.1
| 0.25 | 7.8562
2.3 10cm thick RC floor slab class C-25
|  |  | along y-axis |  |  |  | L=23.45-0.25-0.25-0.25-0.25=22.45
8 | 9.95 |  | L=13.55-0.25-0.25-0.8-(2*0.25)-(2*.9)=9.95 | 1 | 22.45 |  | W=13.55-0.25-0.25-0.25-0.25=12.55
| 0.25 |  | W=0.25 ,d=. |  | 12.55 | 281.7475
| 0.25 | 4.975
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | DEDUCTION |  |  |  | 3. Masonry Work
|  |  | along x-axis |  |  |  | 3.1 Trychltic stone masonry (total)
2 | 22.45 |  | L=23.45-0.25-0.25-0.25-0.25=22.45 | 4 | 22.95 |  | axis x01,x02,x03,x04
| 0.25 | 11.225 |  |  | 0.4 |  | L=23.45-0.5=22.95
[5 empty] | 0.76 | 27.9072
along y-axis
3 | 12.05 |  | L=13.55-0.25-0.25-0.25-0.25-0.5=12.05 | 5 | 11.45 |  | axis y01,y02,y03……y09
| 0.25 | 9.0375 |  |  | 0.4 |  | L=13.55-0.5-(4*0.4)=11.45
[5 empty] | 0.76 | 17.404
|  | 261.485 | m2 Total to item 2.3
[6 empty] | 45.3112 | m3 Total volume of masonary
2.4 In grade beams and steps
4 | 22.95 |  | L=23.45-0.25-0.25=22.95 |  |  |  | 3.12 masonary work above NGL
| 0.25 |  |  | 1 | 17.8 |  | on axis x01 L=5.2+5.1+7.25+.25=17.8
| 0.4 | 9.18 |  |  | 0.4
[5 empty] | 0.45 | 3.204
5 | 12.05 |  | L=13.55-0.25-0.25-(4*.25)=12.05
| 0.25 | [5 empty] | on axis y01L=5.3+2.2+5.3-0.25=12.55
| 0.4 | 6.025 |  | 1 | 12.55
0.4
|  | 15.205 | m3 Total to item 2.4 |  | 0.35 | 1.757
|  |  | provide cut fix form work or panel |  |  | 4.961 | m3 Total to item 3.2
2.7 In grade beams
8 | 22.95 |  | L=23.45-0.25-0.25=22.95 (x-axis) |  |  | 40.3502 | 3.13 masonary work below NGL
| 0.4 | 73.44
[6 empty] | 40.3502 | m3 Total to item 3.1
10 | 12.55 |  | L=13.55-0.25-0.25-(2*.25)=12.55
| 0.4 | 50.2
46 | 0.4 |  | DEDUCTION
| 0.25 | 4.6
|  | 119.04 | m2 Total to item 2.7
Reinforcement steel bars
2.12)ф14 mm deformed bars
|  | 1213.146 | kg net wight item 2.12
|  |  | 2.14)ф8 mm deformed bars |  |  |  |  | #REF!
|  | 1414.2343 | kg net wight item 2.14
2.15 10/2 cm expansion joint b/n
along x-axis
6 | 21.7 |  | L=23.45-0.25-0.25-0.25-0.25-(.25*3)=21.7
130.2
along y-axis
8 | 12.05 |  | L=13.55-0.25-0.25-0.25-0.25-0.5=12.05
96.4
|  | 226.6 | mTotal to item 2.15
#REF!

## Admin Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Adminstrator
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE |  |  |  | 1.7)ф12 mm deformed bars
1.CONCRETE WORK
20 | 0.2 |  | 1.1)In elevation column |  |  | 1288.0618 | kg net weight item 1.7
| 0.2 |  | C1=20Pcs & C2=4Pcs (0.2x0.2)
| 2.73 | [5 empty] | 1.8)ф8 mm deformed bars
|  | 2.184 | m3 net volume item 1.1
[6 empty] | 366.2835 | kg net weight item 1.8
1.2)In beam & step
2 | 22.9 |  | TTB1=2Pcs |  |  |  | 2)BLOCK WORK
| 0.3 |  | Axis x/01 & x/o4 from (y/01 - y/06) |  | 21.9 |  | 2.1)20cm thick HCB wall
| 0.2 |  |  | 1 | 2.73 |  | Axis X/01 from (Y/01 - Y/05)
|  | 2.748 |  |  |  | 59.787
2 | 22.9 |  | TTB2=2Pcs |  | 1.6
| 0.3 |  | Axis x/02 & x/03 from ( y/01 - y/06) | 1 | 1.63 |  | W1(1Pc)
| 0.2 |  |  |  |  | -2.608
|  | 2.748 |  |  | 1.5
2 | 12.2 |  | TTB3=2Pcs | 6 | 1.63 |  | W2(6Pcs)
| 0.3 |  | Axis y/01 & y/06 from ( x/01 - x/04) |  |  | -14.67
| 0.2 |  |  |  | 1.2
|  | 1.464 |  | 2 | 0.6 |  | W20(2PCS)
3 | 12.2 |  | TTB4=3Pcs |  |  | -1.44
| 0.3 |  | Axis y/02 - y/05 from ( x/01 - x/04) |  | 21.9
| 0.2 |  |  | 1 | 2.73 |  | Axis X/04 from (Y/01 - Y/05)
|  | 2.196 | 9.156 |  |  | 59.787
1.6
|  | 9.156 | m3 net volume item 1.2 | 2 | 1.63 |  | W1(2Pcs)
-5.216
|  |  | FORM WORK |  | 1.5
20 | 0.8 |  | 1.4)Elevation column | 7 | 1.63 |  | W2(6Pcs)
| 2.73 |  | C1=20Pcs |  |  | -17.115
|  | 43.68 | m2 net area item 1.4 |  | 12.2
|  |  |  | 2 | 2.73 |  | Axis Y/01 & Y/05 from (X/01 - X/04)
|  |  | 1.5)Beam |  |  | 66.612
2 | 21.9 |  | TTB1=2Pcs |  | 1.2
| 0.8 |  | Axis x/01 & x/o4 from (y/01 - y/05) | 1 | 2.73 |  | D13
|  | 35.04 | Dev.L=0.30*2+0.20=0.80mt |  |  | -3.276
1.5
18 | 0.3 |  |  | 3 | 1.63 |  | W2(3Pcs)
| 0.2 |  |  |  |  | -7.335
|  | 1.08 |  |  | 1.05
|  |  |  | 2 | 13 |  | Above top tie beam X/01 & X/06
2 | 21.9 |  | TTB2=2Pcs |  |  | 27.3
| 0.8 |  | Axis x/02 & x/03 from (y/01 - y/06) |  | 22.9
|  | 35.04 | Dev.L=0.30*2+0.20=0.80mt | 2 | 0.2 |  | Above top tie beam Y/01 &x/05
9.16
2 | 12.2 |  | TTB3=2Pcs
| 0.8 |  | Axis y/01 & y/06 from ( x/01 - x/04) |  |  | 170.986 | m2 net area item 2.1
|  | 19.52 | Dev.L=0.30*2+0.20=0.80mt
2.2)15cm thick HCB wall
3 | 12.2 |  | TTB4=3Pcs | 2 | 21.9 |  | Axis X/02 & X/03 from (Y/01 - Y/05)
| 0.8 |  | Axis y/02 - y/05 from ( x/01 - x/04) |  | 2.73
|  | 29.28 | Dev.L=0.30*2+0.20=0.80mt |  |  | 119.574
|  |  |  | 5 | 1.4 |  | D2(5Pcs)
|  | 119.96 | m2 net area item 1.5 |  | 2.73
-19.11
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 0.9 |  | D9(2Pcs) |  |  |  | 4)CARPENTRY
| 2.73 | -4.914 |  | 18 | 14.52 |  | 4.1)Uper & lower chord size 10-12cm
[6 empty] | 261.36 | Upper =7.26x2=14.52mt
1 | 1.15 |  | OPENING | 18 | 13.8 | 0 | L0wer =6.90x2=13.80mt
| 2.73 | -3.1395 |  |  |  | 248.4
1 | 10.2 |  | Axis Y/03 from (X/01 - X/04) |  |  | 509.76 | m net length item 4.1
| 2.73 | 27.846
4.2)Vertical & Diagonal member
3 | 5.15 |  | Axis Y/03' & Y/04' from (X/01 - X/04)
| 2.93 | 45.2685 |  | 18 | 14.62 |  | V =14.62mt
263.16
1 | 5.1 |  |  | 18 | 18.64 | 0 | D= 18.64mt
| 2.73 | 13.923 |  |  |  | 335.52
2 | 2.55 |  | TOILET |  |  | 598.68 | m net length item 4.2
| 3.06 | 15.606
4.3)Purlin zigba 5/7cm
1 | 3.5 | [5 empty] | No .pur =7.26/0.9+1=9X2=18
| 3.06 | 10.71 |  | 18 | 24.1 |  | L=22.90+1.2=24.10mt
[6 empty] | 433.8 | m net length item 4.3
4 | 0.7 |  | D4
| 2.73 | -7.644 |  | 4 | 7.26 |  | 4.4)Zigba wooden fascia board
29.04
|  | 198.12 | m2 net area item 2.2
|  |  |  | 2 | 24.1 |  | 77.24
|  |  | 3)ROOFING WORK |  |  | 48.2
3.1)G-28 CIS Roof covering
1 | 14.2 |  | W=13.00+0.60X2=14.20mt |  |  | 48.2 | m net length item 4.4
| 24.1 |  | L=22.90+1.20=24.10mt
|  | 342.22 | m2 net area item 3.1 |  |  |  | WOODEN DOOR
4.8)Type D9 ,Size 90/273
|  |  | 3.2)G-28 Ribbed sheet ceiling | 1 | 2
| 24.1 |  | L =22.90+0.60*2 =24.10 |  |  | 2 | pcs net number item 4.8
2 | 0.5
|  | 24.1 |  |  |  |  | 4.9)Type D ,Size 140/273
| 7.26 |  |  | 1 | 5
4 | 0.5 |  |  |  |  | 5 | pcs net number item 4.9
14.52
5)METAL WORK
|  | 38.62 | m2 net area item 3.2 |  |  |  | Windows
5.1)Type W2 ,Size 150/173
|  |  | 3.3)Flashing in metal sheet | 1 | 3
1 | 24.1 |  |  |  |  | 3 | pcs net number item 5.1
24.1
| 7.26 | [5 empty] | 5.2)Type W2 ,Size 160/73
4 | 0.5 |  |  | 1 | 16
|  | 14.52 |  |  |  | 16 | pcs net number item 5.1
|  | 38.62 | m2 net area item 3.3 |  |  |  | 5.6)Type W2 ,Size 120/90
|  |  |  | 1 | 2
|  |  | 3.4)Supply & fix G-28 gutter dev. |  |  | 2 | pcs net number item 5.1
2 | 24.1
|  | 48.2 | m2 net area item 3.4 |  |  |  | Doors
5.7)Type D4=13 ,Size 120/273
|  |  |  | 1 | 1
[6 empty] | 1 | pcs net number item 5.7
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.1)Apply two coats of plastering & | 1 | 7.9 |  | Toilet
|  |  | one coat rendering |  | 3.06 | 24.174 | L=1.4x2+2.55x2=7.90mt
1 | 21.9 |  | Axis X/01 from (Y/01 - Y/07)
| 2.73 | 59.787 |  | 1 | 1.15 |  | Opening
[5 empty] | 2.73 | -3.1395
1 | 1.6 |  | W1(1Pc)
| 1.73 | -2.768 |  | 2 | 0.7 |  | D8(2Pcs)
[5 empty] | 2.73 | -3.822
6 | 1.5 |  | W2(6Pcs)
| 1.73 | -15.57 |  | 1 | 23.6 |  | L=3.5x4+2.4x4=23.60
[5 empty] | 2.73 | 64.428
2 | 1.2 |  | W20(2PCS)
| 0.6 | -1.44 |  | 2 | 1.2 |  | W20(2Pcs)
[5 empty] | 0.6 | -1.44
1 | 21.9 |  | Axis X/04 from (Y/01 - Y/05)
| 2.73 | 59.787 |  | 6 | 0.7
[5 empty] | 2.73 | -11.466
2 | 1.6 |  | W1(1Pc)
| 1.73 | -5.536 |  | 1 | 20.3 |  | Accountant &Purchaser
[5 empty] | 3.06 | 62.118 | L=5x2+5.15x2=203.30mt
7 | 1.5 |  | W2(7Pcs)
| 1.73 | -18.165 |  | 2 | 1.5 |  | W2(2Pcs)
[5 empty] | 1.73 | -5.19
2 | 12.2 |  | Axis Y/01 & Y/06 from (X/01 - X/04)
| 2.73 | 66.612 |  | 1 | 1.4 |  | D2(1Pc)
[5 empty] | 2.73 | -3.822
1 | 1.2 |  | D13
| 2.73 | -3.276 |  | 1 | 49 |  | Corridor
[5 empty] | 3.06 | 149.94 | L=22.50x2+2x2=49.00
3 | 1.5 |  | W2(3Pcs)
| 1.73 | -7.785 |  | 1 | 1.15 |  | Opening
[5 empty] | 2.73 | -3.1395
2 | 1.05 |  | Above top tie beam X/01 & X/06
| 13 | 27.3 |  | 1 | 1.5 |  | W2(1Pcs)
[5 empty] | 1.73 | -2.595
|  | 158.946 | m2 net area itm 6.1
|  |  |  | 5 | 1.4 |  | D2(5Pcs)
|  |  | 6.2)Apply three coats of plastering |  | 2.73 | -19.11
to internal wall & external beam & colu.
1 | 30.6 |  | Meeting hall | 2 | 0.9 |  | D9(2Pcs)
| 3.06 | 93.636 | L=10.15x2+5.15x2=30.60mt |  | 2.73 | -4.914
5 | 1.5 |  | W2(5Pcs) | 1 | 1.2 |  | D13(1Pcs)
| 1.73 | -12.975 |  |  | 2.73 | -3.276
1 | 1.4 |  | D2(1Pc) | 1 | 30.6 |  | Library
| 2.73 | -3.822 |  |  | 3.06 | 93.636 | L=10.15x2+5.15x2=30.60mt
1 | 19 |  | Personnel | 5 | 1.5 |  | W2(5Pcs)
| 3.06 | 58.14 | L=4.35x2+5.15x2=19.00mt |  | 1.73 | -12.975
1 | 1.6 |  | W1(5Pcs) | 1 | 1.4 |  | D2(1Pc)
| 1.73 | -2.768 |  |  | 2.73 | -3.822
1 | 1.4 |  | D2(1Pc) | 1 | 20.2 |  | Office for CEO
| 2.73 | -3.822 |  |  | 3.06 | 61.812 | L=4.95x2+5.15x2=20.20mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 1.5 |  | W2(2Pcs) | 1 | 4.35 |  | Personnel
| 1.73 | -5.19 |  |  | 5.15 | 22.4025
1 | 1.4 |  | D2(1Pc) | 1 | 5 |  | Accountant &Purchaser
| 2.73 | -3.822 |  |  | 5.15 | 25.75
1 | 15.9 |  | Secretary | 1 | 21.9 |  | Corridor
| 3.06 | 48.654 | L=2.80x2+5.15x2=15.90mt |  | 2 | 43.8
1 | 1.5 |  |  | 1 | 9.95 |  | Library
| 1.73 | -2.595 | W2(1Pc) |  | 5.15 | 51.2425
1 | 0.9 |  |  | 1 | 4.95 |  | Office for CEO
| 2.73 | -2.457 | D9(1Pcs) |  | 5.15 | 25.4925
1 | 18.6 |  |  | 1 | 2.6 |  | Secretary
| 3.06 | 56.916 | Office for CCO |  | 5.15 | 13.39
L=4.15x2+5.15x2=18.60mt
2 | 1.6 |  |  | 1 | 4.15 |  | Office for CCO
| 1.73 | -5.536 | W1(2Pcs) |  | 5.15 | 21.3725
1 | 0.9 |  |  | 1 | 2.55 |  | Toilet
| 2.73 | -2.457 | D9(1Pcs) |  | 1.4 | 3.57
18 | 0.2 |  |  | 2 | 1.2
| 2.73 | 9.828 | Column |  | 2.1 | 5.04
2 | 22.9 |  |  | 2 | 1.2
| 0.4 | 18.32 | Grade beam |  | 1.4 | 3.36
2 | 22.9 |  |  |  |  | 266.6625 | m2 net area item 6.3
| 0.3 | 13.74 | Top tie beam
6.5)Approved type 9mm thick ceramic floor t.
2 | 13 |  |  | 1 | 10.15 |  | Meeting hall
| 0.4 | 10.4 | Grade beam |  | 5.15 | 52.2725
2 | 13 |  |  | 1 | 4.35 |  | Personnel
| 0.3 | 7.8 | Top tie beam |  | 5.15 | 22.4025
1 | 12.3 |  | Axis Y/03 from X/01 - X/04 | 1 | 5 |  | Accountant &Purchaser
| 0.8 | 9.84 | exposed beam |  | 5.15 | 25.75
2 | 2 |  |  | 1 | 22.5 |  | Corridor
| 0.8 | 3.2 | Corridor beam exposed beam |  | 2 | 45
2 | 2 |  |  | 1 | 10.15 |  | Library
| 0.5 | 2 | Corridor beam exposed beam |  | 5.15 | 52.2725
1 | 5.15 |  |  | 1 | 4.95 |  | Office for CEO
| 0.8 | 4.12 | Axis Y/04 from X/03 - X/04 |  | 5.15 | 25.4925
|  | 668.547 | m2 net area item 6.2 | 1 | 2.8 |  | Secretary
[5 empty] | 5.15 | 14.42
6.3)Chipwood ceiling
1 | 9.95 |  | Meeting hall | 1 | 4.15 |  | Office for CCO
| 5.15 | 51.2425 |  |  | 5.15 | 21.3725
T | D | S | Item No. and Description | T | D | S | Item No. and Description
5 | 1.4 |  | D2(5Pcs) |  |  |  | 6.9)10cm thick C-20 RC 1.2mt wide
| 0.15 | 1.05 |  |  |  |  | pavement
|  |  |  | 2 | 24.1
4 | 0.7 |  | D8(4Pcs) |  | 1.2 | 57.84 | L=22.90+1.20=24.10mt
| 0.15 | 0.42
|  |  |  | 1 | 13
2 | 0.9 |  | D9(2Pcs) |  | 1.2 | 15.6
| 0.15 | 0.27
[6 empty] | 73.44 | m2 net area item 6.9
1 | 1.15 |  | Opening
| 0.15 | 0.1725 |  |  |  |  | 6.12)Supply & lay storm water
concrete pipe of 1/2 ф30cm
1 | 1.2 |  | D13(1Pc)
| 0.2 | 0.24 |  | 2 | 24.9 |  | L=24.10+0.40X2=24.40mt
49.8
|  | 261.135 | m2 net area item 6.5
|  |  |  | 1 | 15.4 |  | L=13+1.2X2=15.40mt
|  |  | 6.6)Approved type cearmic skirting 10/0.9cm |  |  | 15.4
1 | 29.2 |  | Meeting hall
|  | 29.2 | L=10.15x2+5.15x2-1.4=29.20mt |  |  | 65.2 | m net length item 6.12
1 | 17.6 |  | Personnel |  |  |  | 7)Painting
|  | 17.6 | L=4.35x2+5.15x2-1.4=17.60mt |  |  |  | 7.1)Int. plastered surface & ext beam & colun
1 | 18.9 |  | Accountant &Purchaser |  |  | 668.547 | m2 net area item 7.1
|  | 18.9 | L=5.00x2+5.15x2-1.4=18.90mt
7.2)Chip wood ceiling surface
1 | 37.85 |  | Corridor |  |  | 266.6625 | m2 net area item 7.2
|  | 37.85 | L=22.50x2+2x2-1.4x5-1.15-.9x2-1.2=37.85mt
7.3)External rendered surface
1 | 29.2 |  | Library |  |  | 158.946 | m2 net area item 7.3
|  | 29.2 | L=10.15x2+5.15x2-1.4=29.20mt
9.5)Supply & install waste water pipe
1 | 18.8 |  | Office for CEO |  |  |  | ф 50mm of min. wall thickness=2mm
|  | 18.8 | L=4.95x2+5.15x2-1.4=18.80mt | 1 | 13
[6 empty] | 13 | m net length item 9.5.a
1 | 15 |  | Secretary
|  | 15 | L=2.8x2+5.15x2-0.90=15.00mt |  |  |  | ф 75mm of min. wall thickness=3mm
|  |  |  | 1 | 8.62
1 | 17.7 |  | Office for CCO |  |  | 8.62 | m net length item 9.5.b
|  | 17.7 | L=4.15x2+5.15x2-0.90=17.70mt
ф 100mm of min. wall thickness=3.2mm
1 | 5.35 |  | Toilet corridor | 1 | 15.26
|  | 5.35 | L=2.55x2+1.40x2-0.70x2-1.15=5.35mt |  |  | 15.26 | m net length item 9.5.c
|  | 189.6 | m net length item 6.6 |  |  |  | 10.00. Electrical Installations
2.00)LIGHT POINT
|  |  | 6.7)Approved type terrazzo |  |  |  | 2.01points conduti of 16mm 3*2.5mm2
|  |  | window cill Size, 27/3cm | 29 | 1
3 | 1.65 |  |  |  |  | 29 | no net number item 2.01
|  | 4.95 | W1(3Pcs)
3.00)SWITCH
16 | 1.55 | [5 empty] | 3.01)Single Switch legrand
|  | 24.8 | W2(16Pcs) | 8 | 1
[6 empty] | 8 | no net number item 3.01
2 | 1.25
|  | 2.5 | W20(2Pcs) |  |  |  | 3.02)Double Switch legrand
|  |  |  | 4 | 1
|  | 278.7 | m net length item 6.7 |  |  | 4 | no net number item 3.02
T | D | S | Item No. and Description | T | D | S | Item No. and Description
4.)Socket outlet point
4.01)Socket outlet point 3x2.5mm2
19 | 1
|  | 19 | no net number item 4.01
5)Socket outlets
5.01)Socket outlets LEGRAND SUNO
19 | 1
|  | 19 | no net number item 5.01
6)Telephone/data point
6.01)Telephone point feed through cat 5E UTP Cable
7 | 1
|  | 7 | no net number item 6.01
7. Type of light fittings
7.01)Philips TCS 098/236/2xTL-D 36W
12 | 1
|  | 12 | no net number item 7.01
7.02)Philips TCS 098/136/1xTL-D 36W
10 | 1
|  | 10 | no net number item 7.02
7.03)RZB 59251.002Q/E27/60W
5 | 1
|  | 5 | no net number item 7.03
7.04)RZB 59222.002Q/E27/60W
2 | 1
|  | 2 | no net number item 7.04
8)TV POINTS
8.01)TV point fed through RG6
1 | 1 |  | Coaxial 75ohm Tv cable
|  | 1 | no net number item 8.01

## Admin. Reinf
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [9 empty] | Block : Administration
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| grade beam | axis x01 - x04 | 14 | 8.22 | 4 | 3 | 12 |  | - |  |  | 98.64
| " | " | 14 | 7.38 | 4 | 3 | 12 |  | - |  |  | 88.56
| " | " | 14 | 9.25 | 4 | 3 | 12 |  | - |  |  | 111
| " | " | 14 | 11.7 | 4 | 3 | 12 |  | - |  |  | 140.4
| " | " | 14 | 11.85 | 4 | 3 | 12 |  | - |  |  | 142.2
| " | st | 8 | 1.2 | 115 | 4 | 460 |  | 552 |  |  | -
| " | axis y01- y05 | 14 | 7.16 | 5 | 3 | 15 |  | - |  |  | 107.4
| " | " | 14 | 7.2 | 5 | 3 | 15 |  | - |  |  | 108
| " | " | 14 | 7.91 | 5 | 3 | 15 |  | - |  |  | 118.65
| " | " | 14 | 5.85 | 5 | 3 | 15 |  | - |  |  | 87.75
| " | st | 8 | 1.2 | 5 | 65 | 325 |  | 390
| TOTAL LENGTH | [7 empty] | 942 | 0 | 0 | 1002.6
| UINT WEIGHT in KG/ML | [7 empty] | 0.395 | 0.617 | 0.888 | 1.21
| TOTAL WEIGHT IN KG | [7 empty] | 372.09 | 0 | 0 | 1213.146
GROUND FLOOR MESH
| (x/01-x/02) & (x/03-x/04) |  | 8 | 4.87 | 2 | 26 | 52 |  | 253.24
| (y/01 - y/02) |  | 8 | 4.97 | 2 | 25 | 50 |  | 248.5
| (x/01-x/02) & (x/03-x/04) |  | 8 | 4.77 | 2 | 26 | 52 |  | 248.04
| (y/02 - y/03) |  | 8 | 4.97 | 2 | 25 | 50 |  | 248.5
| (x/01-x/02) & (x/03-x/04) |  | 8 | 6.92 | 2 | 26 | 52 |  | 359.84
| (y/03 - y/04) |  | 8 | 4.97 | 2 | 36 | 72 |  | 357.84
| (x/01-x/02) & (x/03-x/04) |  | 8 | 4.82 | 2 | 26 | 52 |  | 250.64
| (y/04 - y/05) |  | 8 | 4.97 | 2 | 25 | 50 |  | 248.5
| (x/02-x/03) (y/01 - y/02) |  | 8 | 4.87 | 1 | 10 | 10 |  | 48.7
|  |  | 8 | 1.87 | 1 | 26 | 26 |  | 48.62
| (x/02-x/03) (y/02 - y/03) |  | 8 | 4.77 | 1 | 10 | 10 |  | 47.7
|  |  | 8 | 1.87 | 1 | 25 | 25 |  | 46.75
| (x/02-x/03) (y/03 - y/04) |  | 8 | 6.92 | 1 | 10 | 10 |  | 69.2
|  |  | 8 | 1.87 | 1 | 36 | 36 |  | 67.32
| (x/02-x/03) (y/04 - y/05) |  | 8 | 4.82 | 1 | 10 | 10 |  | 48.2
|  |  | 8 | 1.87 | 1 | 25 | 25 |  | 46.75
|  |  |  | TOTAL LENGTH |  |  |  |  | 2638.34 | 0 | 0 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 1042.1443 | 0 | 0 | 0
1 | COLUMN (C1) |  | 12 | 3.68 | 4 | 20 | 80 |  |  |  | 294.4
|  |  | 8 | 0.7 | 15 | 20 | 300 |  | 210
TOP TIE BEAM
2 | TTB1 |  | 12 | 8.22 | 2 | 3 | 6 |  |  |  | 49.32
|  |  | 12 | 7.38 | 2 | 4 | 8 |  |  |  | 59.04
|  |  | 12 | 9.25 | 2 | 4 | 8 |  |  |  | 74
|  |  | 12 | 11.7 | 2 | 3 | 6 |  |  |  | 70.2
|  |  | 12 | 11.85 | 2 | 3 | 6 |  |  |  | 71.1
|  |  | 8 | 0.9 | 2 | 114 | 228 |  | 205.2
3 | TTB2 |  | 12 | 8.22 | 2 | 3 | 6 |  |  |  | 49.32
|  |  | 12 | 7.38 | 2 | 4 | 8 |  |  |  | 59.04
|  |  | 12 | 9.25 | 2 | 4 | 8 |  |  |  | 74
|  |  | 12 | 11.7 | 2 | 3 | 6 |  |  |  | 70.2
|  |  | 12 | 11.85 | 2 | 3 | 6 |  |  |  | 71.1
|  |  | 8 | 0.9 | 2 | 114 | 228 |  | 205.2
4 | TTB3 |  | 12 | 7.06 | 2 | 4 | 8 |  |  |  | 56.48
|  |  | 12 | 7.1 | 2 | 4 | 8 |  |  |  | 56.8
|  |  | 12 | 7.91 | 2 | 3 | 6 |  |  |  | 47.46
|  |  | 12 | 5.85 | 2 | 3 | 6 |  |  |  | 35.1
|  |  | 8 | 0.9 | 2 | 65 | 130 |  | 117
5 | TTB4 |  | 12 | 7.06 | 3 | 4 | 12 |  |  |  | 84.72
|  |  | 12 | 7.1 | 3 | 4 | 12 |  |  |  | 85.2
|  |  | 12 | 7.91 | 3 | 3 | 9 |  |  |  | 71.19
|  |  | 12 | 5.85 | 3 | 3 | 9 |  |  |  | 52.65
|  |  | 8 | 0.9 | 3 | 65 | 195 |  | 175.5
6 | D8 LENTEL |  | 12 | 1.35 | 4 | 2 | 8 |  |  |  | 10.8
|  |  | 12 | 1.05 | 4 | 2 | 8 |  |  |  | 8.4
|  |  | 8 | 0.6 | 4 | 6 | 24 |  | 14.4
|  |  |  | TOTAL LENGTH |  |  |  |  | 927.3 | 0 | 1450.52 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 366.2835 | 0 | 1288.0618 | 0

## Diagno. Sum
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-Diagnostic
Details of Works executed
Bill No. | Description | Sub Total Birr |  | Total Birr
|  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work | 187493.67 | 72095.6075 | 187493.67 | 72095.6075
2 | Concrete Work | 324434 | 229221.859 | 324434 | 229221.859
3 | Masonry work | 107800 | 36827.03 | 107800 | 36827.03
| sub total A | 619727.67 | 338144.4965 | 619727.67 | 338144.4965
B. Super Structure
1 | Concrete Work | 100282 | 110243.0284 | 100282 | 110243.0284
2 | Block work | 110900 | 136260.465 | 110900 | 136260.465
3 | Roofinig | 135547.6 | 130242.2 | 135547.6 | 130242.2
4 | Carpentary & Joinery | 123031.61 | 75757.62 | 123031.61 | 75757.62
5 | Metal work | 87105 | 52202.5 | 87105 | 52202.5
6 | Finishing | 362075 | 294949.06 | 362075 | 294949.06
7 | Painting | 24696 | 28404.5524 | 24696 | 28404.5524
8 | Glazing | 10545 |  | 10545 | 0
9 | Sanitory Installation | 43195 | 12249.85 | 43195 | 12249.85
10 | Electrical Installation | 85890.18 | 72954.75 | 85890.18 | 72954.75
| sub total B | 1083267.39 | 913264.0258 | 1083267.39 | 913264.0258
| Total A+B | 1702995.06 | 1251408.5223 | 1702995.06 | 1251408.5223
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  |  |  | Consultant:- _____________

## Diagno. Meas
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [5 empty] | Block : Diagnostic
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 343 | 8 | 2744 | 301.725 | 2413.8
1.2 | Bulk excavation in ordinary | m3 | 349 | 70 | 24430 | 62.55 | 4378.5
1.3 | Ditto but exceeding 1.5m less than 2m | m3 | 116.3333 | 70 | 8143.3333 |  | 0
1.4 | Selected borrowed fill brought from out side | m3 | 465.3333 | 150 | 69800 | 93.7406 | 14061.0825
1.5 | Cart away surplus excavated material to an | m3 | 568.2333 | 70 | 39776.3333 | 153.0675 | 10714.725
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 213 | 200 | 42600 | 202.6375 | 40527.5
Total to summary ………Birr |  |  |  |  | 187493.6667 |  | 72095.6075
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 70 | 150 | 10500 | 49.14 | 7371
2.2 | Ditto but under footing pad | m2 | 18 | 150 | 2700 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 213 | 400 | 85200 | 202.6375 | 81055
2.4 | In grade beam&Steps | m3 | 22 | 3200 | 70400 | 12.555 | 40176
Provide cut and fix in position swan zigzag wood
2.7 | Grade beam | m2 | 70 | 120 | 8400 | 98.24 | 11788.8
2.1 | Steps | m2 | 5 | 150 | 750 |  | 0
Reinforcement steel bar according to St.drawing
2.11 | Dia 14 mm deformed bar | kg | 1008 | 36 | 36288 | 1054.2609 | 37953.3924
2.12 | Dia. 12mm deformed bar | kg | 555 | 36 | 19980 |  | 0
2.13 | Dia 8 mm deformed bar | kg | 1496 | 36 | 53856 | 1260.8519 | 45390.6666
2.14 | 10/2 cm chip wood expansion joint between | m | 208 | 30 | 6240 | 182.9 | 5487
Total to summary ………Birr |  |  |  |  | 294314 |  | 229221.859
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 70 | 1250 | 87500 | 22.6044 | 28255.5
3.2 | Ditto but above natural ground level externally | m3 | 14 | 1450 | 20300 | 5.9114 | 8571.53
Total to summary ………Birr |  |  |  |  | 107800 |  | 36827.03
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 2 | 3200 | 6400 | 1.9656 | 6289.92
1.2 | In beams& steps | m3 | 8 | 3200 | 25600 | 8.589 | 27484.8
1.3 | Lintel | m3 | 0.8 | 3200 | 2560 | 0.897 | 2870.4
| Provide cut and fix in position swan zigzag wood |  |  |  | 0 |  | 0
1.4 | Elevation column | m2 | 47 | 130 | 6110 | 39.312 | 5110.56
1.5 | Beam | m2 | 111 | 130 | 14430 | 113.52 | 14757.6
1.6 | Lintel | m2 | 9 | 130 | 1170 | 14.482 | 1882.66
Reinforcement steel bar according to St.drawing
1.7 | Dia 14mm deformed bar | kg | 0
1.8 | Dia 12mm deformed bar | kg | 1028 | 36 | 37008 | 1084.7364 | 39050.5104
1.9 | Dia 8 mm deformed bar | kg | 294 | 36 | 10584 | 355.4605 | 12796.578
1.1 | Dia 6 mm deformed bar | kg | 0 | 36 | 0 |  | 0
Total to summary ………Birr |  |  |  |  | 103862 |  | 110243.0284
2. BLOCK WORK
Concrete block wall class "C" bedded in cement
2.1 | 20cm thick | m2 | 134 | 350 | 46900 | 148.4475 | 51956.625
2.2 | 15cm thick | m2 | 200 | 320 | 64000 | 263.4495 | 84303.84
Total to summary ………Birr |  |  |  |  | 110900 |  | 136260.465
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 319.41 | 360 | 114987.6 | 313.6825 | 112925.7
3.2 | G28 ribbed sheet ceiling under eave | m2 | 43 | 160 | 6880 | 37.05 | 5928
3.3 | Flashing in flat metal sheet fixed as shown | m | 72 | 110 | 7920 | 50.95 | 5604.5
3.4 | Supply and fix G-28 flat metal sheet gutter | m | 48 | 120 | 5760 | 48.2 | 5784
Total to summary ………Birr |  |  |  |  | 135547.6 |  | 130242.2
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12cm | m | 425.17 | 23 | 9778.91 | 487.08 | 11202.84
4.2 | Vertical & Diagonal memberes size-dia. 8 - 10 cm | m | 268.6 | 16 | 4297.6 | 544.68 | 8714.88
4.3 | Purlin zigba size 5/7cm | m | 238 | 33 | 7854 | 416.7 | 13751.1
4.4 | Zigba wooden fascia board price includes three coats | m | 50.5 | 71 | 3585.5 | 74.1 | 5261.1
| Doors |  |  |  | 0 |  | 0
4.5 | Type D7 size-80/273cm | Nº | 7 | 4149.6 | 29047.2 | 6 | 24897.6
4.6 | Type D8 size-70/273cm | Nº | 6 | 3630.9 | 21785.4 | 2 | 7261.8
4.7 | Type D9 size-90/273cm | Nº | 10 | 4668.3 |  | 1 | 4668.3
Total to summary ………Birr |  |  |  |  | 76348.61 |  | 75757.62
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 6 | 3892.5 | 23355 | 13 | 50602.5
5.2 | Type W3 size-50/50cm | Nº | 2 | 200 | 400 |  | 0
5.3 | Type W4 size-130/173cm | Nº | 2 | 1800 | 3600 |  | 0
5.4 | Type W7 size-480/60cm | Nº | 1 | 2200 | 2200 |  | 0
5.5 | Type W8 size-125/173cm | Nº | 1 | 2200 | 2200 |  | 0
5.6 | Type W9 size-120/173cm | Nº | 1 | 1600 | 1600 | 1 | 1600
5.7 | Type W12 size-110/173cm | Nº | 1 | 1400 | 1400 |  | 0
5.8 | Type W13 size-105/173cm | Nº | 1 | 1400 | 1400 |  | 0
5.9 | Type W15 size-130/60cm | Nº | 2 | 600 | 1200 |  | 0
5.1 | Type W21 size-370/60cm | Nº | 1 | 1700 | 1700 |  | 0
5.11 | Type W22 size-265/60cm | Nº | 1 | 1600 | 1600 |  | 0
| Doors |  |  |  | 0 |  | 0
5.12 | Type D2 size - 140/273cm | Nº | 3 | 4000 | 12000 |  | 0
5.13 | Type D6 size - 90/273cm | Nº | 4 | 2000 | 8000 |  | 0
Total to summary ………Birr |  |  |  |  | 60655 |  | 52202.5
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 184 | 140 | 25760 | 164.3835 | 23013.69
6.2 | Apply three coats of plastering to internal walls& | m2 | 545 | 150 | 81750 | 850.0648 | 127509.72
6.3 | Chip wood ceiling nailed on & including | m2 | 213 | 310 | 66030 |  | 0
6.4 | Approved type 6mm thick glazed ceramic wall tile | m2 | 93 | 370 | 34410 |  | 0
6.5 | 9mm thick non slippery ceramic tile floor | m2 | 213 | 300 | 63900 | 238.9895 | 71696.85
6.6 | Approved type Ceramic tile skirting | m | 208 | 100 | 20800 | 212.77 | 21277
6.7 | Approved type Terrazo window cillsize 27/3 cm | m | 31 | 150 | 4650 | 23.1 | 3465
6.8 | 30/30/3mm angle iron corner protection | m | 6 | 70 | 420 |  | 0
6.9 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 82 | 530 | 43460 | 76.56 | 40576.8
6.1 | storm water concrete pipes of half diameter 30cm | ml | 77 | 100 | 7700 | 74.1 | 7410
| Construction of 10x40 cm curb stone | ml | 77 | 265 | 20405 |  | 0
Total to summary ………Birr |  |  |  |  | 369285 |  | 294949.06
7. PAINTING
7.1 | Internal plastered surfaceand external beams& | m2 | 545 | 28 | 15260 | 850.0648 | 23801.8144
7.2 | Chip wood ceiling surface | m2 | 213 | 28 | 5964 |  | 0
7.3 | External rendered surface | m2 | 169 | 28 | 4732 | 164.3835 | 4602.738
Total to summary ………Birr |  |  |  |  | 25956 |  | 28404.5524
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R water pipes for water
| 15mm diameter ;internal | LM | 26 | 70 | 1820 | 24.59 | 1721.3
| 20mm diameter ;internal | LM | 20 | 80 | 1600 | 22.58 | 1806.4
| 25mm diameter ;internal | LM | 20 | 95 | 1900 | 25.43 | 2415.85
| 32mm diameter ;internal | LM | 30 | 125 | 3750 |  | 0
9.3 | Supply and fix bronze gate valves complete with unions,
| 15mm diameter | No | 95 | 95 | 9025 | 3 | 285
| 20mm diameter | No | 155 | 155 | 24025 |  | 0
9.5 | Supply and install waste water pipes made of rigid
| 50mm diameter of min. wall thickness=2mm | LM | 10 | 65 | 650 | 32.48 | 2111.2
| 75mm diameter of min. wall thickness=3mm | LM | 10 | 95 | 950 | 7.83 | 743.85
| 100 mm diameter of min. wall thickness=3.2mm | LM | 48 | 125 | 6000 | 16.93 | 2116.25
9.9 | Supply and fix toilet paper holder made of metal | No | 6 | 150 | 905 | 7 | 1050
Total to summary ………Birr |  |  |  |  | 50625 |  | 12249.85
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 41 | 200 | 8200 | 43 | 8600
3 | Switches |  |  |  | 0 |  | 0
3.01 | single(774001+774041) | PCs | 9 | 81.25 | 731.25 | 19 | 1543.75
3.02 | Duoble(774005+774042) | " | 11 | 131.25 | 1443.75 | 7 | 918.75
3.03 | Two-Way(774006+774041) | " | 4 | 80 | 320 | 4 | 320
4 | Socket outlet points |  |  |  | 0 |  | 0
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 30 | 200 | 6000 | 29 | 5800
5 | Socket outlets |  |  |  | 0 |  | 0
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 30 | 281.25 | 8437.5 | 29 | 8156.25
6 | Telephone/Data points |  |  |  | 0 |  | 0
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 8 | 600 | 4800 | 9 | 5400
6.03 | Flush mounted Telephone outlets RJ11 type | PCs | 8 | 200 | 1600 | 9 | 1800
7 | Type of Light Fitting With lamp |  |  |  | 0 |  | 0
7.01 | PHILIPS TMS 012/236 IMKwith 2xTLD 36W | PCs | 19 | 1500 | 28500 | 9 | 13500
7.02 | PHILIPS TMS 012/136 IMKwith 1xTLD 36W | PCs | 8 | 1200 | 9600 | 14 | 16800
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 7 | 406.25 | 2843.75 | 13 | 5281.25
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 6 | 406.25 | 2437.5 | 6 | 2437.5
7.05 | MASSIVE 70107/02/11/2XE27/60W | PCs | 1 | 1375 | 1375 | 1 | 1375
8 | TV points |  |  |  | 0 |  | 0
8.01 | TV points fed through RG6 Coaxial 75ohm TV | PCs | 1 | 266.25 | 266.25 | 1 | 266.25
8.02 | Flush mounted TV outlets type Legrand Suno |  |  |  | 0 |  | 0
| (TV-R-SAT) | PCs | 1 | 200 | 200 |  | 0
10 | Cable way and Manhole |  |  |  | 0 |  | 0
10.01 | Rigid pvc pipe of dia.40mm From CMDB | mt | 18 | 70 | 1260 |  | 0
10.02 | Rigid pvc pipe of dia.32mm For 4x6mm2 | " | 15 | 40 | 600 |  | 0
10.03 | Rigid pvc pipe dia. 50mm to telephone | " | 12 | 60 | 720 | 12.6 | 756
Total to summary ………Birr |  |  |  |  | 79335 |  | 72954.75

## Diagno. Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Diagnostic Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE | 9.3 |  |  | C-bulk fill and compaction
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 19.55 |  | L=20.85-0.5-0.8=19.55
|  |  | 1.1 Clear off site to remove top soil |  | 10.7 |  | W=12-0.5-0.8=10.7
|  |  | L=20.85+1.0+1.0-0.5=22.35 |  | 0.51 | 106.6844
1 | 22.35 |  | W=12+1.0+1.0-0.5=13.5 |  |  |  | DEDUCTION
| 13.5 | 301.725 |  | 1 | 22.25 |  | along x-axis
[5 empty] | 0.4 |  | L=19.55 W=0.4m
|  | 301.725 | m2 Total to item 1.1 |  | 0.51 | 4.539
|  |  | 1.2 Bulk Excavation in ordinary soil | 4 | 10.3 |  | along y-axis
1 | 19.05 |  | L=20.85-0.25-0.25-0.4-0.4-0.5=19.05 |  | 0.4 |  | L=12-0.5-0.8-(1*0.4)=10.3
| 10.2 |  | W=12-0.25-0.25-0.4-0.4-0.5=10.2 |  | 0.51 | 8.4048
| 0.25 | 48.5775
|  |  | DEDUCTION |  |  | 93.7406 | m3 Total to item 1.4
1 | 19.05 |  | along x-axis
| 0.9 |  | L=20.85-0.25-0.25-0.4-0.4-0.5=19.05
| 0.25 | 4.2862
4 | 9.3 |  | along y-axis
| 0.9 |  | W=12-0.25-0.25-0.4-0.4-0.5-(1*0.9)=13.3
| 0.25 | 8.37
|  | 35.9213 | m3 Total to item 1.2
1.3 Ditto to Item 1.2 but exceeding 1.5
and less than 2m
3 | 20.85 |  | along x-axis | 1 | 22.35 |  | 1.5 Cart away excavated material
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=20.85 d=0.25 |  | 13.5
| 0.25 | 14.0738 |  |  | 0.3 | 90.5175 | from item no 1.1
[6 empty] | 35.9213 | from item no 1.2
6 | 9.3 |  | along y-axis |  |  | 26.6288 | from item no 1.3
| 0.9 |  | L=12-(3*.9)=9.3
| 0.25 | 12.555 | W=0.4+0.25+0.25=0.90, d= |  |  | 153.0675 | m3 Total to item 1.5
|  | 26.6288 | m3 Total to item 1.3 |  |  |  | 1.6/ 25cm thick basaltic hard core
|  |  | 1.4 Selected Borrowed Fill | 1 | 19.85 |  | L=20.85-0.5-0.5=19.85
|  |  | A- fill under masonary |  | 11 | 218.35 | W=12-0.5-0.5=11
4 | 23.45 |  | for axis x01-x04
| 0.9 |  | L=23.85 |  |  |  | DEDUCTION
| 0 | 0 |  | 1 | 19.85 |  | along x-axis L=19.85 W=0.25
[5 empty] | 0.25 | 4.9625
5 | 9.95 |  | for axis y01-y05
| 0.9 |  | L=8.4 , W=0.9, d=0.3 | 4 | 10.75 |  | along y-axis L=10.75 W=0.25
| 0 | 0 | 8.4 |  | 0.25 | 10.75 | L=12-0.5-0.5-0.25=10.75
|  |  | B-backfill and compaction in side masonary |  |  | 202.6375 | m2 Total to item 1.6
along x-axis
4 | 17.95 |  | L=20.85-0.25-0.25-0.8-(4*0.4)=17.95 |  |  |  | 2) CONCRETE WORK
| 0.25 |  | W=0.25 ,d= |  |  |  | 2.1 5cm thick lean concrete class C-7
| 0 | 0 |  | 3 | 20.35 |  | L=20.85-0.5=20.35
[5 empty] | 0.4 | 24.42
along y-axis
10 | 8.4 |  | L=12-0.25-0.25-0.8-(2*0.25)-(2*.9)=8.4 | 6 | 10.3 |  | L=12-0.5-(3*0.4)=10.3
| 0.25 |  | W=0.25 ,d=. |  | 0.4 | 24.72
| 0 | 0
[6 empty] | 49.14 | m2Total to item 2.1
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.3 10cm thick RC floor slab class C-25 |  |  |  | 3. Masonry Work
1 | 19.85 |  | L=20.85-0.25-0.25-0.25-0.25=19.85 |  |  |  | 3.1 Trychltic or equivalent stone masonry (total)
| 11 | 218.35 | W=12-0.25-0.25-0.25-0.25=11 | 3 | 20.35 |  | axis x01,x02,x03,x04
[5 empty] | 0.4 |  | L=20.85-0.5=20.35
|  |  | DEDUCTION |  | 0.46 | 11.2332
along x-axis
1 | 19.85 |  | L=20.85-0.25-0.25-0.25-0.25=19.85 | 6 | 10.3 |  | axis y01,y02,y03……y09
| 0.25 | 4.9625 |  |  | 0.4 |  | L=12-0.5-(3*0.4)=10.3
|  |  | along y-axis |  | 0.46 | 11.3712
4 | 10.75 |  | L=12-0.25-0.25-0.25-0.25-0.25=10.75
| 0.25 | 10.75 |  |  |  | 22.6044 | m3Total VOLUME MASONARY
|  | 202.6375 | m2 Total to item 2.3 |  |  |  | 3.2 masonary work above NGL
|  |  |  | 1 | 20.35 |  | on axis x01 L=5.2+5.1+7.25+.25=17.8
|  |  | 2.4 In grade beams |  | 0.4
3 | 20.35 |  |  |  | 0.51 | 4.1514
0.25
| 0.4 | 6.105 |  |  |  |  | on axis y01L=5.3+2.2+5.3-0.25=12.55
|  |  |  | 1 | 11
6 | 10.75 |  |  |  | 0.4
| 0.25 |  |  |  | 0.4 | 1.76
| 0.4 | 6.45
[6 empty] | 5.9114 | m3 Total to item 3.2
|  | 12.555 | m3 net volume item 2.4
[6 empty] | 16.693 | 3.13 masonary work below NGL
provide cut form work
|  |  | 2.7 In grade beams |  |  | 16.693 | m3 Total to item 3.1
6 | 20.35 |  | L=20.85-0.25-0.25=20.35 (x-axis)
| 0.4 | 48.84
12 | 11 |  | L=12-0.25-0.25-(2*.25)=11
| 0.4 | 52.8
34 | 0.4 |  | DEDUCTION
| 0.25 | 3.4
|  | 98.24 | m2Total to item 2.
Reinforcement steel bars
2.11)ф14 mm deformed bars
|  | 1054.2609 | kg net wight item 2.12 |  |  |  |  | #REF!
2.13)ф8 mm deformed bars
|  | 1260.8519 | kg net wight item 2.13
2.14 10/2 cm chip wood expansion joint
along x-axis
4 | 18.85 |  | L=20.85-0.25-0.25-0.25-0.25-(.25*4)=18.85
75.4
along y-axis
10 | 10.75 |  | L=12-0.25-0.25-0.25-0.25-0.25=10.75
107.5
#REF!
|  | 182.9 | mTotal to item 2.14

## Diagno Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Diagnostic
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE |  |  |  | FORM WORK
|  |  | 1.CONCRETE WORK |  |  |  | 1.4)Elevation column
|  |  | 1.1)In elevation column | 18 | 0.8 |  | C1=20Pcs
18 | 0.2 |  | C1=18Pcs |  | 2.73
| 0.2 |  |  |  |  | 39.312 | m2 net area item 1.4
2.73
|  | 1.9656 | m3 net volume item 1.1 |  |  |  | 1.5)Beam
|  |  |  | 2 | 20.75 |  | TTB1=2Pcs
|  |  | 1.2)In beam & step |  | 0.8 | 33.2 | Axis x/01 & x/o4 from (y/01 - y/05)
2 | 21.95 |  | TTB1=2Pcs |  |  |  | Dev.L=0.30*2+0.20=0.80mt
| 0.3 |  | Axis x/01 & x/03 from (y/01 - y/06) | 20 | 0.3
| 0.2 | 2.634 |  |  | 0.2 | 1.2
1 | 21.95 |  | TTB2=1Pcs | 1 | 20.75 |  | TTB2=1Pcs
| 0.3 |  | Axis x/02 & x/03 from ( y/01 - y/06) |  | 0.8 | 16.6 | Axis x/02 & x/03 from (y/01 - y/06)
| 0.2 | 1.317 |  |  |  |  | Dev.L=0.30*2+0.20=0.80mt
2 | 11.75 |  | TTB3=2Pcs | 2 | 11.75 |  | TTB3=2Pcs
| 0.3 |  | Axis y/01 & y/06 from ( x/01 - x/03) |  | 0.8 | 18.8 | Axis y/01 & y/06 from ( x/01 - x/04)
| 0.2 | 1.41 |  |  |  |  | Dev.L=0.30*2+0.20=0.80mt
4 | 11.75 |  | TTB4=4Pcs | 4 | 11.75 |  | TTB4=4Pcs
| 0.3 |  | Axis y/02 - y/05 from ( x/01 - x/03) |  | 0.8 | 37.6 | Axis y/02 - y/05 from ( x/01 - x/04)
| 0.2 | 2.82 |  |  |  |  | Dev.L=0.30*2+0.20=0.80mt
1 | 10.2 |  | T- Beam | 1 | 10.2 |  | T- Beam
| 0.4 |  |  |  | 0.6 | 6.12
| 0.1 | 0.408
[6 empty] | 113.52 | m2 net area item 1.5
|  | 8.589 | m3 net volume item 1.2
1.6)Lintel
|  |  | 1.3)Lintel | 5 | 1.2 |  | D7(5Pcs)
5 | 1.2 |  | D7(5Pcs) |  | 0.55 | 3.3
0.15
| 0.2 | 0.18 |  | 12 | 1.1 |  | D8(12Pcs)
[5 empty] | 0.55 | 7.26
12 | 1.1 |  | D8(12Pcs)
| 0.15 |  |  | 1 | 1.1 |  | D16(1Pcs)
| 0.2 | 0.396 |  |  | 0.78 | 0.858
1 | 1.1 |  | D16(1Pcs) | 1 | 1.2 |  | W3(1Pcs)
| 0.35 |  |  |  | 0.78 | 0.936
| 0.2 | 0.077
|  |  |  | 1 | 1.6 |  | W19(1Pcs)
1 | 1.2 |  | W3(1Pcs) |  | 0.78 | 1.248
0.35
| 0.2 | 0.084 |  | 1 | 1.6 |  | W20(1Pcs)
[5 empty] | 0.55 | 0.88
1 | 1.6 |  | W19(1Pcs)
| 0.35 |  |  |  |  | 14.482 | m2 net area item 1.6
| 0.2 | 0.112
1.8)ф12 mm deformed bars
1 | 1.6 |  | W20(1Pcs)
| 0.15 |  |  |  |  | 1084.7364 | kg net weight item 1.8
| 0.2 | 0.048
1.9)ф8 mm deformed bars
|  | 0.897 | m3 net volume item 1.3
[6 empty] | 355.4605 | kg net weight item 1.9
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2) Block work | 1 | 1.2 |  | W20(1Pc)
|  |  | 2.1) 20cm thick |  | 0.6 | -0.72
2 | 21.95
| 2.73 | 119.847 |  | 3 | 2.55 |  | Axis x/01',X/01'' & X/02' from (Y/04 - Y/04')
[5 empty] | 3.03 | 23.1795
1 | 12.35
| 2.73 | 33.7155 |  | 1 | 1.5 |  | Axis x/02'' from (Y/04' - Y/05)
[5 empty] | 3.03 | 4.545
1 | 3.25
| 2.73 | 8.8725 |  | 1 | 4.6 |  | Axis x/01' from (Y/05' - Y/05)
[5 empty] | 3.03 | 13.938
1 | 3
| 2.732 | 8.196 |  | 3 | 0.7 |  | D8(3Pcs)
[5 empty] | 2.73 | -5.733
2 | 6.17
| 1.8 | 22.212 |  | 1 | 11.75 |  | Axis Y/02 from (X/01 - X/03)
|  | 192.843 |  |  | 2.73 | 32.0775
-1 | 1.5 |  | Deduction | 1 | 0.7 |  | D7(1Pcs)
| 1.73 | -2.595 |  |  | 2.73 | -1.911
-1 | 0.6 |  |  | 2 | 2.05 |  | Axis b/n Y/02 & Y/03, b/n(x/02 &x/03)
| 4.1 | -2.46 |  |  | 3.03 | 12.423
-6 | 1.5 |  |  | 1 | 2.75 |  | Axis b/n Y/02 & Y/03, b/n(x/02 &x/03)
| 1.73 | -15.57 |  |  | 3.03 | 8.3325
-4 | 1.2 |  |  | 1 | 2.8 |  | Axis b/n Y/02 & Y/03, b/n(x/01 &x/02)
| 1.73 | -8.304 |  |  | 3.03 | 8.484
-1 | 1.05 |  |  | 1 | 6.5 |  | Axis Y/03 from (X/01 -X/02)
| 1.73 | -1.8165 |  |  | 2.73 | 17.745
-2 | 2.5 |  | Opening | 1 | 10.15 |  | Axis Y/04 from (X/01 -X/03)
| 2.73 | -13.65 |  |  | 2.73 | 27.7095
|  | 148.4475 | m2 net area item 2.1 | 2 | 0.8 |  | D7(2Pcs)
[5 empty] | 2.73 | -4.368
2.2)15cm thick HCB wall
3 | 4.2 |  | Axis x/01',X/01'' & X/02' from (Y/01 - Y/02) | 1 | 10.15 |  | Axis Y/04' from (X/01 -X/03)
| 3.03 | 38.178 |  |  | 3.03 | 30.7545
3 | 0.8 |  |  | 1 | 0.8 |  | D7(1Pcs)
| 2.73 | -6.552 | D7(3Pcs) |  | 2.73 | -2.184
1 | 3.15 |  |  | 1 | 0.7 |  | D8(1Pcs)
| 3.03 | 9.5445 | Axis x/01' from (Y/02' - Y/03) |  | 2.73 | -1.911
1 | 4.37 |  |  | 1 | 2.55 |  | Axis Y/05 from (X/01 -X/02)
| 3.03 | 13.2411 | Axis x/02' from (Y/02 - Y/03) |  | 2.73 | 6.9615
3 | 0.7 |  |  | 1 | 0.7 |  | D8(1Pcs)
| 2.73 | -5.733 | D8(3Pcs) |  | 2.73 | -1.911
1 | 2.23 |  |  | 1 | 3.25 |  | Axis Y/05 from (X/02 -X/03)
| 3.03 | 6.7569 | Axis x/02'' from (Y/02 - Y/03) |  | 2.73 | 8.8725
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 0.8 |  | D7(1Pcs) |  |  |  | 4)CARPENTRY
| 2.73 | -2.184 |  |  |  |  | 4.1)Uper & lower chord size 10-12cm
|  |  |  | 18 | 13.9 |  | Upper =6.95X2=13.90ml
2 | 1.45 |  | Axis b/n Y/05 - Y/06 from (x/01 &x/02) |  |  | 250.2 | Lower =6.58X2=13.16ml
| 3.03 | 8.787
|  |  |  | 18 | 13.16
1 | 2.7 |  | Axis b/n Y/05 - Y/06 from (x/01 &x/02) |  |  | 236.88
| 3.03 | 8.181
[6 empty] | 487.08 | m net length item 4.1
1 | 0.8 |  | D7(1Pcs)
| 2.73 | -2.184 |  |  |  |  | 4.2)Vertical & Diagonal member
V= 13.78mt
1 | 3.25 |  | Axis b/n Y/05 - Y/06 from (x/02 &x/03) | 18 | 13.78 |  | D= 16.48mt
| 3.03 | 9.8475 |  |  |  | 248.04
1 | 0.8 |  | D7(1Pcs) | 18 | 16.48
| 2.73 | -2.184 |  |  |  | 296.64
4 | 1 |  |  |  |  | 544.68 | m net length item 4.2
| 2.73 | 10.92
4.3)Purlin zigba 5/7cm
2 | 1.5 | [5 empty] | No .pur =6.95/0.9+1=9x2=18
| 2.73 | 8.19 |  | 18 | 23.15 |  | L=22+1.20=23.15mt
[6 empty] | 416.7 | m net length item 4.3
4 | 0.7
| 2.73 | -7.644 |  |  |  |  | 4.4)Zigba wooden fascia board
|  |  |  | 4 | 6.95
|  | 263.4495 | m2 net area item 2.2 |  |  | 27.8
|  |  | 3)ROOFING WORK | 2 | 23.15
|  |  | 3.1)G-28 CIS Roof covering |  |  | 46.3
1 | 13.55 |  | L=12.35+0.60x2=13.55mt
| 23.15 |  | L=21.95+0.60X2=23.15mt |  |  | 74.1 | m net length item 4.4
|  | 313.6825 | m net length item 3.1
WOODEN DOOR
|  |  | 3.2)G-28 Ribbed sheet ceiling |  |  |  | 4.5)Type D7 ,Size 80/273
2 | 23.15 |  | length=33cm | 1 | 6
| 0.5 | 23.15 |  |  |  | 6 | pcs net number item 4.5
4 | 6.95 | [5 empty] | 4.6)Type D8 ,Size 70/273
| 0.5 | 13.9 |  | 1 | 2
[6 empty] | 2 | pcs net number item 4.6
|  | 37.05 | m net length item 3.2
4.7)Type D9 ,Size 90/273
|  |  | 3.3)Flashing in metal sheet | 1 | 1
1 | 23.15 |  | Dev. Length 33cm |  |  | 1 | pcs net number item 4.7
23.15
5)METAL WORK
4 | 6.95 | [5 empty] | 5.1)Type W2 ,Size 150/273
| 1 | 27.8 |  | 1 | 13
[6 empty] | 13 | pcs net number item 5.1
|  | 50.95 | m net length item 3.3
5.6)Type W13,Size 120/173
|  |  | 3.4- Gutter | 1 | 1
2 | 24.1 |  | Left & Right side |  |  | 1 | pcs net number item 5.6
48.2
|  | 48.2 | m net length item 3.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.1)Apply two coats of plastering & | 1 | 24.45 |  | Corridor
|  |  | one coat rendering |  | 3.06 | 74.817 | L=6.85+4.20+1.50+3.00+2.95+
2 | 18.25 |  | Axis X/01 & X/03 from (Y/01 - Y/06) |  |  |  | 2.80+3.15=24.45mt
| 2.73 | 99.645 |  | 1 | 0.8 |  | D7(1Pcs)
[5 empty] | 2.73 | -2.184
3 | 1.5 |  | W2(3Pcs)
| 1.73 | -7.785 |  | 3 | 0.7 |  | D8(3Pcs)
[5 empty] | 2.73 | -5.733
1 | 1.05 |  | W13(1Pcs)
| 1.73 | -1.8165 |  | 1 | 0.8 |  | W3 (1Pcs)
[5 empty] | 1.73 | -1.384
1 | 1.5 |  | W14(1Pcs)
| 1.73 | -2.595 |  | 1 | 18.9 |  | Corridor
[5 empty] | 3.06 | 57.834 | L=6.75+12.15=18.90mt
3 | 1.2 |  | W20(3PCS)
| 0.6 | -2.16 |  | 2 | 0.8 |  | D7(2Pcs)
[5 empty] | 2.73 | -4.368
1 | 4.15 |  | W26(1Pc)
| 0.6 | -2.49 |  | 1 | 1.6
[5 empty] | 2.73 | -4.368
2 | 11.75 |  | Axis Y/01& Y/06 from (X/01 - X/03)
| 2.73 | 64.155 |  | 1 | 7.96 |  | Toilet handi
[5 empty] | 2.73 | 21.7308 | L=1.93X2+2.05X2=7.96mt
3 | 1.5 |  | W2(3Pcs)
| 1.73 | -7.785 |  | 1 | 1.2 |  | W20 (1Pcs)
[5 empty] | 0.6 | -0.72
1 | 1.2 |  | W20(1PCS)
| 0.6 | -0.72 |  | 1 | 0.7 |  | D8(1Pcs)
[5 empty] | 2.73 | -1.911
2 | 1.05 |  | Axis Y/06 & Y/03 from (X/01 - X/03)
| 12.35 | 25.935 |  | 2 | 21.1 |  | Toilet for male & female
[5 empty] | 2.73 | 115.206
|  | 164.3835 | m2 net area item 2.2
|  |  |  | 10 | 0.7 |  | D8(10Pcs)
|  |  | 6.2)Apply three coats of plastering |  | 2.73 | -19.11
to internal wall & external beam & colu.
3 | 14.4 |  | Bacteriology/Hematology AFB room | 1 | 1.2 |  | W20 (1Pcs)
| 3.06 | 132.192 | Parasitology |  | 0.6 | -0.72
L=4.2X2+3X2=14.40mt
3 | 1.5 |  | W2(3Pcs) | 1 | 4.15 |  | W26(1Pcs)
| 1.73 | -7.785 |  |  | 0.6 | -2.49
W14(1Pcs)
1 | 1.5 |  |  | 1 | 12.1 |  | Duty room
| 1.73 | -2.595 |  |  | 3.06 | 37.026 | L=3.50X2+2.55X2=12.10mt
5 | 0.8 |  | D7(5Pcs) | 1 | 1.5 |  | W2(1Pcs)
| 2.73 | -10.92 |  |  | 1.73 | -2.595
1 | 13.4 |  | Specimen | 1 | 0.8 |  | D7(1Pc)
| 3.06 | 41.004 | L=4.2X2+2.50X2=13.40mt |  | 2.63 | -2.104
1 | 1.5 |  | W2(1Pcs) | 1 | 0.7 |  | D8(1Pcs)
| 1.73 | -2.595 |  |  | 2.73 | -1.911
2 | 0.8 |  | D7(2Pcs) | 1 | 11.7 |  | Store
| 2.73 | -4.368 |  |  | 3.06 | 35.802 | L=3.30X2+2.55X2=11.70mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 0.8 |  | D7(1Pcs) | 1 | 0.7 |  | W19 (1Pcs)
| 2.73 | -2.184 |  |  | 0.7 | -0.49
1 | 11.3 |  | Archive | 1 | 0.4 |  | W3(1Pcs)
| 3.06 | 34.578 | L=3.10X2+2.55X2=11.30mt |  | 0.4 | -0.16
1 | 0.8 |  | D7(1Pcs) | 1 | 11.4 |  | corridor
| 2.73 | -2.184 |  |  | 3.06 | 34.884 | L=1.10X2+4.6X2=11.40mt
1 | 26.5 |  | Corridor | 5 | 0.7 |  | D8(5Pcs)
| 3.06 | 81.09 | L=4.35+9.70+1.50+8.1+2.85=26.50mt |  | 2.73 | -9.555
1 | 0.7 |  | D8(1Pc) | 1 | 0.8 |  | D16(1Pc)
| 2.73 | -1.911 |  |  | 2.73 | -2.184
2 | 0.8 |  | D7(2Pcs) | 2 | 5.6 |  | Change room
| 2.73 | -4.368 |  |  | 3.06 | 34.272 | L=1.35X2+1.45X2=5.60
1 | 1.4 |  | Lead door | 1 | 6.1 |  | Barium kitchen
| 2.73 | -3.822 |  |  | 3.06 | 18.666 | L=1.60X2+1.45X2=6.10
Toilet
1 | 7.2 |  | L=1.5X2+2.1X2=7.20mt | 3 | 0.7 |  | D8(3Pcs)
| 2.73 | 19.656 |  |  | 2.73 | -5.733
1 | 0.7 |  | D8(1Pcs) | 2 | 1.2 |  | W20(2Pcs)
| 2.73 | -1.911 |  |  | 0.6 | -1.44
1 | 1.2 |  | W20 (1Pcs) | 1 | 1.5 |  | W2(1Pc)
| 0.6 | -0.72 |  |  | 1.73 | -2.595
1 | 13.2 |  | Control room | 1 | 7.6 |  | Toilet
| 3.06 | 40.392 | L=3.35X2+3.25X2=13.20mt |  | 2.73 | 20.748 | L=1.1X2+2.7X2=7.60mt
2 | 0.8 |  | D7(2Pcs) | 1 | 0.7 |  | D8(1Pcs)
| 2.73 | -4.368 |  |  | 2.73 | -1.911
1 | 0.4 |  | W19 (1Pcs) | 1 | 1.2
| 0.4 | -0.16 |  |  | 0.6 | -0.72
1 | 11.2 |  | Dark room | 20 | 2.73 |  | Column
| 3.06 | 34.272 | L=2.35X2+3.25X2=11.20mt |  | 0.2 | 10.92
1 | 0.8 | 0 | D7(1Pcs) | 2 | 21.95 |  | At axis x/01 & x/03
| 2.73 | -2.184 |  |  | 0.3 | 13.17
1 | 0.7 |  | W3(1Pcs) | 2 | 12.35 |  | At axis y/01 & y/06
| 0.7 | -0.49 |  |  | 0.3 | 7.41
1 | 21.2 |  | X - RAY room | 2 | 21.95 |  | At axis x grade beams
| 3.06 | 64.872 | L=5.20X2+5.40X2=21.20mt |  | 0.4 | 17.56
1 | 1.4 |  | Lead door | 2 | 12.35 |  | At axis y grade beams
| 2.73 | -3.822 |  |  | 0.4 | 9.88
Exposed beams
1 | 0.8 |  | D16(1Pc) | 1 | 20.75 |  | Axis X2 (y/01 - y/06)
| 2.73 | -2.184 |  |  | 0.8 | 16.6
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 2.5 |  | Axis X1 & x3 (y/01 - y/06) | 1 | 8.1 |  | Corridor
| 0.6 | 3 |  |  | 1.5 | 12.15
Axis y/03 (x1 - x2)& axis y/04
1 | 6.8 | 5.44 | L=5.20+1.6=6.80mt | 1 | 2.1 |  | Toilet
| 0.8 |  |  |  | 1.5 | 3.15 | L=1.5X2+2.1X2=7.20mt
|  | 850.0648 | m2 net area item 6.2 | 1 | 3.25 |  | Control room
|  |  | 6.4)Approved 6mm thick ceramic wall |  | 3.35 | 10.8875 | L=3.35X2+3.25X2=13.20mt
1 | 203 |  | staff gents
| 0.06 | 12.18 |  | 1 | 5.2 |  | X - RAY room
[5 empty] | 5.4 | 28.08
1 | 150 |  | staff ladies
| 0.06 | 9 |  | 1 | 1.1 |  | corridor
[5 empty] | 4.6 | 5.06
1 | 610 |  | toilet, handi., shower
| 0.06 | 36.6 |  | 1 | 1.35 |  | Chang room
[5 empty] | 1.45 | 1.9575
| 0.06 | 0
|  |  |  | 1 | 1.35 |  | Chang room
| 0.06 | 0 |  |  | 1.45 | 1.9575
| 0.06 | 0 |  | 1 | 1.6 |  | Barium kitchen
[5 empty] | 1.45 | 2.32
|  | 57.78 | m2 net area item 6.4
|  |  | 6.5)Approved type 9mm thick ceramic floor t. | 1 | 1.1 |  | Toilet
|  |  | Bacteriology/Hematology AFB room |  | 2.7 | 2.97
3 | 3 |  | Parasitology
| 4.2 | 37.8 |  | 9 | 0.8 |  | D7(9Pcs)
1 | 2.5 |  | Specimen |  | 0.15 | 1.08
| 4.2 | 10.5
1 | 1.5 |  | Cooridor | 13 | 0.7 |  | D8(13Pcs)
| 4.15 | 6.225 |  |  | 0.15 | 1.365
1 | 2.95 |  | "
| 1.2 | 3.54 |  | 1 | 0.9 |  | D16(1Pc)
1 | 1.14 |  | Toilet |  | 0.35 | 0.315
| 2.2 | 2.508
1 | 1 |  | " | 1 | 1.4 |  | LEAD DOOR
| 2.2 | 2.2 |  |  | 0.35 | 0.49
2 | 2.05 |  | "
| 1.2 | 4.92 |  | 1 | 2.35 |  | Dark room
4 | 1 |  | " |  | 3.25 | 7.6375
| 1.5 | 6
1 | 1.93 |  | Handicup |  |  | 238.9895 | m2 net area item 6.5
| 2.05 | 3.9565
1 | 2.8 |  | Rec/Recording /Reporting |  |  |  | 6.6)Approved type cearmic skirting 10/0.9cm
| 3 | 8.4 |  |  |  |  | Bacteriology/Hematology AFB room
1 | 2.4 |  | Cooridor | 3 | 13.6 |  | Parasitology
| 4.35 | 10.44 |  |  |  | 40.8 | L=4.2X2+3X2-0.8=13.60mt
1 | 12.35
| 2.5 | 30.875 |  | 1 | 11.8 |  | Specimen
1 | 3.5 |  | Duty room |  |  | 11.8 | L=4.2X2+2.50X2-0.8x2=11.80mt
| 2.55 | 8.925
1 | 3.3 |  | Store | 1 | 26.07 |  | Corridor
| 2.55 | 8.415 |  |  |  | 26.07 | L=4.35+6.85+4.15+1.50+3+2.95+0.15
1 | 3.1 |  | Archive |  |  |  | 2.80+3.00-0.8-0.7x3=26.07mt
| 2.55 | 7.905 |  | 1 | 16.1 |  | Corridor
1 | 1.6 |  | Corridor |  |  | 16.1 | L=6.95+12.35-0.8x2-1.6=16.10mt
| 4.35 | 6.96
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 10.6 |  | Duty room |  |  |  | 6.9)10cm thick C-20 RC 1.2mt wide
|  | 10.6 | L=3.50X2+2.55X2-0.7-0.8=10.60mt | 1 | 24.35 |  | pavement
[5 empty] | 1.2 |  | L=21.95+1.2x2=24.35mt
1 | 10.9 |  | Store |  |  | 29.22
|  | 10.9 | L=3.30X2+2.55X2-0.8=10.90mt | 1 | 14.75
1.2
1 | 10.5 |  | Archive |  |  | 17.7
|  | 10.5 | L=3.10X2+2.55X2-0.8=10.50mt | 2 | 12.35 | 0
[5 empty] | 1.2 | 0
1 | 22.8 |  | Corridor |  |  | 29.64
|  | 22.8 | L=9.7x2+1.5+4.35+2.85-1.6-1.6-.7-1.4=22.8mt
[6 empty] | 76.56 | m2 net area item 6.9
1 | 11.6 |  | Control room
|  | 11.6 | L=3.35X2+3.25X2-0.8=11.60mt |  |  |  | 6.12- Half Ditch
|  |  |  | 2 | 15.35 |  | Left & Right Side
1 | 10.4 |  | Dark room |  |  | 30.7
|  | 10.4 | L=2.35X2+3.25X2-0.8=10.40mt
|  |  |  | 2 | 24.35 |  | Front & Rare side
1 | 18.9 |  | X - RAY room |  |  | 48.7
|  | 18.9 | L=5.20X2+5.40X2-1.4-0.9=18.90mt
[6 empty] | 79.4 | m before deduction
1 | 7.1 |  | corridor
|  | 7.1 | L=1.10X2+4.6X2-0.7x5-0.8=7.10mt |  |  |  | Deduction
|  |  |  | 1 | 2.8 |  | Ramp
2 | 4.9 |  | Change room |  |  | 2.8
|  | 9.8 | L=1.35X2+1.45X2-0.70=4.90mt
|  |  |  | 1 | 2.5
1 | 5.4 |  | Barium kitchen |  |  | 2.5
|  | 5.4 | L=1.60X2+1.45X2-0.7=5.40mt
[6 empty] | 5.3 | m total Deduction
|  | 212.77 | m net length item 6.6
[6 empty] | 74.1 | m net length item 6.10
6.7)Approved type terrazzo
|  |  | window cill Size, 27/3cm |  |  |  | 7) Painting
7 | 1.55 |  | W2(7Pcs) |  |  |  | 7.1)Int. plastered surface & ext beam & colun
10.85
[6 empty] | 850.0648 | m2 net area item 7.1
1 | 1.1 |  | W13(1Pcs)
|  | 1.1 |  |  |  |  | 7.3)External rendered surface
[6 empty] | 164.3835 | m2 net area item 7.3
1 | 1.1 |  | W14(1Pcs)
|  | 1.1 |  |  |  |  | 9)SANITARY INSTALLATION
9.1)Supplay & install PP-R water pipe
4 | 1.25 |  | W20(5Pcs) |  |  |  | Internal ф 15mm
|  | 5 |  | 1 | 24.59
[6 empty] | 24.59 | m net length item 9.1.a
1 | 4.2 |  | W26(1Pcs)
|  | 4.2 |  |  |  |  | Internal ф 20mm
|  |  |  | 1 | 22.58
1 | 0.85 |  |  |  |  | 22.58 | m net length item 9.1.b
0.85
|  | 23.1 | m net length item 6.7 |  |  |  | Internal ф 25mm
|  |  |  | 1 | 25.43
[6 empty] | 25.43 | m net length item 9.1.c
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 9.3)Supply & fix bronze gate valve |  |  |  | 6.03)Flush mounted Telephone
1 | 3 |  | 15mm diameter | 9 | 1 |  | outlets RJ11 type
|  | 3 |  |  |  | 9 | pcs net number item 6.03
|  |  | 9.5)Supply & install waste water pipe |  |  |  | 7. Type of light fittings
|  |  | made of rigid UPVC |  |  |  | 7.01)Philips TMS012/236/2xTL-D 36W
|  |  | ф 50mm | 9 | 1
1 | 32.48 |  |  |  |  | 9 | pcs net number item 7.01
|  | 32.48 | m net length item 9.5.a
7.02)Philips TMS 012/136/1xTL-D 36W
|  |  | ф 75mm | 14 | 1
1 | 7.83 |  |  |  |  | 14 | pcs net number item 7.02
|  | 7.83 | m net length item 9.5.b
7.03)RZB 59251.002Q/E27/60W
|  |  | ф 100mm | 13 | 1
1 | 16.93 |  |  |  |  | 13 | pcs net number item 7.03
|  | 16.93 | m net length item 9.5.c
7.04)RZB 59222.002Q/E27/60W
|  |  | 9.9)Supply & fix toilet paper holder made | 6 | 1
|  |  | of metal roller of size 150x150x25mm |  |  | 6 | pcs net number item 7.04
7 | 1
|  | 7 | pcs net number item 9.9 |  |  |  | 7.05)Massive3202/67/10
|  |  |  | 1 | 1
|  |  | 10. Electrical Installations |  |  | 1 | pcs net number item 7.05
2)LIGHT POINT
|  |  | 2.1points conduti of 16mm 3*2.5mm2 |  |  |  | 8)TV POINTS
43 | 1 | [5 empty] | 8.01)TV point fed through RG6
|  | 43 | pcs net number |  |  |  | Coaxial 75ohm Tv cable
|  |  |  | 1 | 1
|  |  | 3)SWITCH |  |  | 1 | pcs net number item 8.01
3.01)Single Switch legrand
19 | 1 | [5 empty] | 10.00. Cable way & manhole
|  | 19 | pcs net number item 3.01 |  |  |  | 10.03. riged pvc pipe dia.50mm To telephone
|  |  |  | 1 | 12.6
|  |  | 3.02)Double Switch legrand |  |  | 12.6 | pcs net number item 10.03
7 | 1
|  | 7 | pcs net number item 3.02
3.03)Two way Switch legrand
4 | 1
|  | 4 | pcs net number item 3.03
4.)Socket outlet point
4.01)Socket outlet point 3x2.5mm2
29 | 1
|  | 29 | pcs net number item 4.01
5)Socket outlets
5.01)Socket outlets LEGRAND SUNO
29 | 1
|  | 29 | pcs net number item 5.01
6)Telephone/data point
6.01)Telephone point feed through
9 | 1 |  | cat 5E UTP Cable
|  | 9 | pcs net number item 6.01

## Daigon Reinf
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Diagnostcs
CLIENT:-ANRS Health Bureau
Take off sheet for Steel reinforsment
No | Location | Shape | Dia | Length | No.of member . | No.of bar. | Total No. of bar | Total Length in D I A M E T E R
|  |  |  | Length | member |  |  | 6 | 8 | 10 | 12 | 14
| Grade beam | axis x1-x3 | 14 | 11.75 | 3 | 3 | 9 | - | - | - | - | 105.75
|  |  | 14 | 11.55 | 3 | 3 | 9 | - | - | - | - | 103.95
|  |  | 14 | 11.65 | 3 | 3 | 9 | - | - | - | - | 104.85
|  |  | 14 | 11.2 | 3 | 3 | 9 | - | - | - | - | 100.8
|  | st | 8 | 1.2 | 111 | 3 | 333 | - | 399.6 | - | - | -
|  | axis y1-y6 | 14 | 6.78 | 6 | 3 | 18 | - | - | - | - | 122.04
|  |  | 14 | 7.05 | 6 | 3 | 18 | - | - | - | - | 126.9
|  |  | 14 | 11.5 | 6 | 3 | 18 | - | - | - | - | 207
|  | st | 8 | 1.2 | 63 | 6 | 378 | - | 453.6 | - | - | -
|  |  |  | TOTAL LENGTH |  |  |  | 0 | 853.2 | 0 | 0 | 871.29
|  |  |  | UINT WEIGHT in KG/ML |  |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  | 0 | 337.014 | 0 | 0 | 1054.2609
No | Location | Shape | Dia | Length | No.of member . | No.of bar. | Total No. of bar | Total Length in D I A M E T E R
|  |  |  | Length | member |  |  | 6 | 8 | 10 | 12 | 14
| GROUND FLOOR MESH | [8 empty] | - | - | -
1 | (x/01-x/02) (y/01-y/02) |  | 8 | 4.02 | 1 | 29 | 29 | - | 116.58 | - | - | -
|  |  | 8 | 5.67 | 1 | 21 | 21 |  | 119.07 | - | - | -
| (x/01-x/02) (y/02-y/03) |  | 8 | 4.02 | 1 | 29 | 29 |  | 116.58 | - | - | -
|  |  | 8 | 5.67 | 1 | 21 | 21 |  | 119.07 | - | - | -
| (x/01-x/02) (y/03-y/04) |  | 8 | 2.37 | 1 | 29 | 29 |  | 68.73 | - | - | -
|  |  | 8 | 5.67 | 1 | 13 | 13 |  | 73.71 | - | - | -
| (x/01-x/02) (y/04-y/05) |  | 8 | 4.02 | 1 | 29 | 29 |  | 116.58 |  |  | -
|  |  | 8 | 5.67 | 1 | 21 | 21 |  | 119.07 |  |  | -
| (x/01-x/02) (y/05-y/06) |  | 8 | 5.67 | 1 | 29 | 29 |  | 164.43 |  |  | -
|  |  | 8 | 5.67 | 1 | 29 | 29 |  | 164.43 |  |  | -
2 | (x/02-x/03) (y/01-y/02) |  | 8 | 4.02 | 1 | 29 | 29 | - | 116.58
|  |  | 8 | 5.82 | 1 | 21 | 21 | - | 122.22
| (x/02-x/03) (y/02-y/03) |  | 8 | 4.02 | 1 | 30 | 30 | - | 120.6
|  |  | 8 | 5.82 | 1 | 21 | 21 | - | 122.22
| (x/02-x/03) (y/03-y/04) |  | 8 | 2.37 | 1 | 30 | 30 | - | 71.1
|  |  | 8 | 5.82 | 1 | 13 | 13 | - | 75.66
| (x/02-x/03) (y/04-y/05) |  | 8 | 2.37 | 1 | 30 | 30 |  | 71.1
|  |  | 8 | 5.82 | 1 | 21 | 21 |  | 122.22
| (x/02-x/03) (y/05-y/06) |  | 8 | 5.67 | 1 | 30 | 30 |  | 170.1
|  |  | 8 | 5.82 | 1 | 29 | 29 |  | 168.78 | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - | - | -
[8 empty] | - | - | - |  | -
|  |  |  | TOTAL LENGTH |  |  |  | 0 | 2338.83 | 0 | 0 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  | 0 | 923.8379 | 0 | 0 | 0
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
1 | COLUMN (C1) |  | 12 | 3.63 | 16 | 4 | 64 |  | - | - | 232.32
|  |  | 8 | 0.7 | 16 | 14 | 224 |  | 156.8 | -
|  |  | 14 | 3.63 | 2 | 4 | 8 |  | - | - |  | 29.04
|  |  | 8 | 0.7 | 2 | 14 | 28 |  | 19.6 | -
2 | TOP TIE BEAM | [5 empty] | 0 |  | - | -
| TTB1 |  | 12 | 11.65 | 2 | 3 | 6 |  | - | - | 69.9
|  |  | 12 | 11.45 | 2 | 3 | 6 |  | - | - | 68.7
|  |  | 12 | 11.65 | 2 | 3 | 6 |  | - | - | 69.9
|  |  | 12 | 11.2 | 2 | 3 | 6 |  | - | - | 67.2
|  |  | 8 | 0.9 | 2 | 110 | 220 |  | 198 | -
[7 empty] | 0 |  | - | -
| TTB2 |  | 12 | 11.65 | 1 | 3 | 3 |  | - | - | 34.95
|  |  | 12 | 11.45 | 1 | 3 | 3 |  | - | - | 34.35
|  |  | 12 | 11.65 | 1 | 3 | 3 |  | - | - | 34.95
|  |  | 12 | 11.2 | 1 | 3 | 3 |  | - | - | 33.6
|  |  | 8 | 0.9 | 1 | 110 | 110 |  | 99 | -
| TTB3 |  | 12 | 6.68 | 2 | 4
|  |  | 12 | 6.95 | 2 | 4 | 8 |  | - | -
|  |  | 12 | 11.5 | 2 | 3 | 6 |  | - | -
|  |  | 8 | 0.9 | 2 | 61 | 122 |  | 109.8 | - | 109.8
[7 empty] | 0 |  | - | - | 0
[7 empty] | 0 |  | - | - | 0
[7 empty] | 0 |  | - | -
| TTB4 |  | 12 | 6.68 | 4 | 4 | 16 |  | - | - | 106.88
|  |  | 12 | 6.95 | 4 | 4 | 16 |  | - | - | 111.2
|  |  | 12 | 11.5 | 4 | 3 | 12 |  | - | - | 138
|  |  | 8 | 0.9 | 4 | 61 | 244 |  | 219.6 | -
|  |  |  | TOTAL LENGTH |  |  |  |  | 802.8 | 0 | 1111.75 | 29.04
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 317.106 | 0 | 987.234 | 35.1384
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
LENTEL
| D7 |  | 12 | 1.45 | 5 | 2 | 10 |  |  |  | 14.5
|  |  | 12 | 1.15 | 5 | 2 | 10 |  |  |  | 11.5
|  |  | 8 | 0.6 | 5 | 7 | 35 |  | 21
| D8 |  | 12 | 1.35 | 4 | 2 | 8 |  |  |  | 10.8
|  |  | 12 | 1.05 | 4 | 2 | 8 |  |  |  | 8.4
|  |  | 8 | 0.6 | 4 | 6 | 24 |  | 14.4
| D16 |  | 12 | 1.75 | 1 | 2 | 2 |  |  |  | 3.5
|  |  | 12 | 1.45 | 1 | 2 | 2 |  |  |  | 2.9
|  |  | 8 | 1 | 1 | 8 | 8 |  | 8
| D8 |  | 12 | 2.2 | 4 | 2 | 8 |  |  |  | 17.6
|  |  | 12 | 1.9 | 4 | 2 | 8 |  |  |  | 15.2
|  |  | 8 | 0.6 | 4 | 11 | 44 |  | 26.4
| W3 |  | 12 | 1.45 | 1 | 2 | 2 |  |  |  | 2.9
|  |  | 12 | 1.05 | 1 | 2 | 2 |  |  |  | 2.1
|  |  | 8 | 1.1 | 1 | 6 | 6 |  | 6.6
| W9 |  | 12 | 1.85 | 1 | 2 | 2 |  |  |  | 3.7
|  |  | 12 | 1.55 | 1 | 2 | 2 |  |  |  | 3.1
|  |  | 8 | 1.1 | 1 | 9 | 9 |  | 9.9
| W10&W20 |  | 12 | 1.85 | 2 | 2 | 4 |  |  |  | 7.4
|  |  | 12 | 1.55 | 2 | 2 | 4 |  |  |  | 6.2
|  |  | 8 | 0.6 | 2 | 9 | 18 |  | 10.8
|  |  |  | TOTAL LENGTH |  |  |  |  | 97.1 | 0 | 109.8 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 38.3545 | 0 | 97.5024 | 0

## Gen + Pump Summary
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-Generator + Pump House
Details of Works executed
Details of Works executed
Bill No. | Description | Sub Total Birr |  | Total Birr
|  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work | 119019 | 20695.59 | 119019 | 20695.59
2 | Concrete Work | 170313 | 69433.4082 | 170313 | 69433.4082
3 | Masonry work | 51340 | 18121.1 | 51340 | 18121.1
| sub total A | 340672 | 108250.0982 | 340672 | 108250.0982
B. Super Structure
1 | Concrete Work | 111182.2 | 29967.6738 | 111182.2 | 29967.6738
2 | Block work | 78932 | 33292.7 | 78932 | 33292.7
3 | Roofinig | 109600 | 33289.08 | 109600 | 33289.08
4 | Carpentary & Joinery | 15706 | 18356.7 | 15706 | 9059.08
5 | Metal work | 30870 | 0 | 30870 | 0
6 | Finishing | 124620 | 26586.98 | 124620 | 26586.98
7 | Painting | 15621 | 964.866 | 15621 | 964.866
8 | Glazing |  |  | 0 | 0
9 | Sanitory Installation | 0 | 0 | 0 | 0
10 | Electrical Installation | 15200 | 7690 | 15200 | 7690
| sub total B | 501731.2 | 150147.9998 | 501731.2 | 140850.3798
| Total A+B | 842403.2 | 258398.098 | 842403.2 | 249100.478
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  |  |  | Consultant:- _____________

## Generator+Pump house
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction |  |  |  |  | Block : Generator + Pump House
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract Qty |  |  | executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 92 | 8 | 736 | 67.43 | 539.44
1.2 | Bulk excavation in ordinary | m3 | 138 | 70 | 9660 |  | 0
1.3 | Ditto but exceeding 1.5 m but less than 2 m | m3 | 46 | 70 | 3220 | 13.041 | 912.87
1.4 | Selected borrowed fill brought from out side | m3 | 184 | 150 | 27600 | 20.985 | 3147.75
1.5 | Cart away surplus excavated material to an | m3 | 211.6 | 70 | 14812 | 34.039 | 2382.73
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 88 | 200 | 17600 | 27.09 | 5418
Total to summary ………Birr |  |  |  |  | 73628 |  | 12400.79
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 21 | 150 | 3150 | 9.92 | 1488
2.2 | Ditto but under footing pad | m2 | 10 | 150 | 1500 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 88 | 400 | 35200 | 29.505 | 11802
2.4 | In grade beam & steps | m3 | 6 | 3200 | 19200 | 4.71 | 15072
2.5 | In footing pad | m3 | 0.5 | 3200 | 1600 |  | 0
2.6 | In footing coloumn | m3 | 1.8 | 3200 | 5760 |  | 0
| Provide cut and fix in position swan zigba wood |  |  |  | 0 |  | 0
2.7 | Grade beam | m2 | 35 | 120 | 4200 | 24.98 | 2997.6
2.8 | In footing pad | m2 | 8 | 120 | 960 |  | 0
2.9 | In footing coloumn | m2 | 27 | 120 | 3240 |  | 0
2.1 | Steps | m2 | 2 | 150 | 300 |  | 0
| Reinforcement steel bar according to St.drawing |  |  |  | 0 |  | 0
2.11 | Dia. 14mm deformed bar | kg | 542 | 36 | 19512 | 143.022 | 5148.792
2.12 | Dia 8 mm deformed bar | kg | 447 | 36 | 16092 | 201.1379 | 7240.9662
2.13 | 10/2 cm chip wood expansion joint between | m | 120 | 36 | 4320 | 31.9 | 1148.4
Total to summary ………Birr |  |  |  |  | 115034 |  | 44897.7582
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 20 | 1250 | 25000 | 4.676 | 5845
3.2 | Ditto but well dressed stone above natural ground level | m3 | 6 | 1450 | 8700 | 2.338 | 3390.1
Total to summary ………Birr |  |  |  |  | 33700 |  | 9235.1
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 2.2 | 3200 | 7040 | 0.4368 | 1397.76
1.2 | In beams | m3 | 2 | 3200 | 6400 | 1.074 | 3436.8
Provide cut and fix in position swan zigzag wood
1.3 | Elevation column | m2 | 24 | 130 | 3120 | 8.736 | 1135.68
1.4 | Beam | m2 | 24 | 130 | 3120 | 14.16 | 1840.8
| Reinforcement steel bar according to St.drawing |  |  |  | 0 |  | 0
1.5 | Dia 12mm deformed bar | kg | 534 | 36 | 19224 | 183.3898 | 6602.0314
1.6 | Dia 8mm deformed bar | kg | 150 | 36 | 5400 | 58.539 | 2107.404
Total to summary ………Birr |  |  |  |  | 44304 |  | 16520.4754
2. BLOCK WORK
2.1 | 20cm thick | m2 | 163 | 350 | 57050 | 46.36 | 16226
Total to summary ………Birr |  |  |  |  | 57050 |  | 16226
3.ROOFING
3.1 | G - 28 Roof covering in galvanized corrugated | m2 | 114 | 360 | 41040 | 33.99 | 12236.4
3.2 | G - 28 ribbed sheet ceiling under eave | m2 | 42 | 160 | 6720 | 25.488 | 4078.08
3.3 | Supply and fix G-28 flat metal sheet gutter | m | 40 | 110 | 4400 | 12.8 | 1408
3.4 | Flushing in flat metal sheet fixed as shown | m | 22 | 120 | 2640 | 29.68 | 3561.6
| Total to summary ………Birr |  |  |  | 257508 |  | 21284.08
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 180 | 23 | 4140 | 62.94 | 1447.62
4.2 | Diagonal & vertical members size-diameter 8 - 10 cm | m | 100 | 16 | 1600 | 37.5 | 600
4.3 | Purlin zigba size 5/7cm | m | 160 | 33 | 5280 | 52.8 | 1742.4
4.4 | Zigba wooden fascia board price includes three coats | m | 66 | 71 | 4686 | 36.08 | 2561.68
| Total to summary ………Birr |  |  |  | 15706 |  | 6351.7
5. METAL WORK
Windows
5.1 | Type W1 size-90/90cm | Nº | 2 | 6200 | 12400 |  | 0
Doors
5.4 | Type D3 size - 200/280 cm | Nº | 1 | 1 | 1 |  | 0
| Total to summary ………Birr |  |  |  | 12401
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 147 | 140 | 20580 | 34.4595 | 4824.33
6.2 | Apply three coats of plastering to internal walls & | m2 | 154 | 150 | 23100 | 46.983 | 7047.45
6.4 | Chip wood ceiling nailed on & including | m2 | 0 | 360 | 360 |  | 0
6.1 | Cement screed floor120 mm thickness | m2 | 88 | 180 | 15840 |  | 0
6.11 | Approved type10/2cm terrazzo tile skirting | m | 45 | 200 | 9000 |  | 0
| Approved type Terrazo window cill | m | 4 | 260 | 1040 |  | 0
6.21 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 46 | 530 | 24380 | 21.84 | 11575.2
6.1 | storm water concrete pipes of half diameter 30cm | ml | 77 | 100 | 7700 | 31.4 | 3140
| Construction of 10x40 cm curb stone | ml | 77 | 265 | 20405 |  | 0
| Total to summary ………Birr |  |  |  | 94300 |  | 26586.98
7. PAINTING
7.1 | External rendered surface | m2 | 147 | 28 | 4116 | 34.4595 | 964.866
7.2 | Internal plastered surfaceand external beams& | m2 | 154 | 28 | 4312 |  | 0
7.3 | Chip wood ceiling surface | m2 | 60 | 28 | 1680 |  | 0
| Total to summary ………Birr |  |  |  | 10108 |  | 964.866
Transformer house/Pump house/
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 68.25 | 8 | 546 | 36.85 | 294.8
1.2 | Bulk excavation in ordinary | m3 | 102.38 | 70 | 7166.6 | 18.72 | 1310.4
1.3 | Ditto but exceeding 1.5 m but less than 2 m | m3 | 34.13 | 70 | 2389.1 |  | 0
1.4 | Selected borrowed fill brought from out side | m3 | 136.5 | 150 | 20475 | 13.9 | 2085
1.5 | Cart away surplus excavated material to an | m3 | 136.5 | 70 | 9555 | 29.78 | 2084.6
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 26.3 | 200 | 5260 | 12.6 | 2520
| Total to summary ………Birr |  |  |  | 45391.7 |  | 8294.8
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 11 | 150 | 1650 | 12.24 | 1836
2.2 | Base of Man hole | m2 | 26.3 | 150 | 3945 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 38 | 360 | 13680 | 12.6 | 4536
2.4 | In grade beam & steps | m3 | 2.44 | 2400 | 5856 | 2.53 | 6072
| Provide cut and fix in position swan zigba wood | [5 empty] | 0
2.6 | Grade beam | m2 | 6.8 | 80 | 544 | 12.32 | 985.6
2.7 | In man hole concrete wall | m2 | 22 | 150 | 3300 |  | 0
| Reinforcement steel bar according to St.drawing | [5 empty] | 0
2.8 | Dia. 12mm deformed bar | kg | 125 | 35 | 4375 | 184.95 | 6473.25
2.9 | Dia 8 mm deformed bar | kg | 58 | 40 | 2320 | 97.82 | 3912.8
2.1 | Dia 6 mm plain bar | kg | 51 | 45 | 2295 |  | 0
2.11 | 10/2 cm chip wood expansion joint between | m | 26 | 50 | 1300 | 14.4 | 720
| Total to summary ………Birr |  |  |  | 39265 |  | 24535.65
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 10.4 | 1200 | 12480 | 5.18 | 6216
3.2 | Ditto but well dressed stone above natural ground level | m3 | 3.2 | 1500 | 4800 | 1.78 | 2670
| Total to summary ………Birr |  |  |  | 17280 |  | 8886
B. SUPER - STRUCTURE
1.CONCRETE WORK
1.1 | In elevation column | m3 | 1 | 2400 | 2400 | 0.4368 | 1048.32
1.2 | In top tie beams | m3 | 1.22 | 2400 | 2928 | 0.924 | 2217.6
1.3 | In concrete roof slab (12 cm thick) | m3 | 5.57 | 2400 | 13368 |  | 0
1.4 | Lintels | m3 | 0.8 | 2400 | 1920 |  | 0
| Provide cut and fix in position swan zigzag wood |  |  |  | 0 |  | 0
1.5 | In elevation column and beams | m2 | 57.13 | 160 | 9140.8 | 20.896 | 3343.36
1.6 | In concrete roof slab (12 cm thick) | m2 | 50 | 220 | 11000 |  | 0
1.7 | Lintels | m2 | 3.41 | 150 | 511.5 |  | 0
| Reinforcement steel bar according to St.drawing |  |  |  | 0 |  | 0
1.8 | Dia 12mm deformed bar | kg | 217 | 35 | 7595 | 145.1702 | 5080.9584
1.9 | Dia 8mm deformed bar | kg | 330 | 40 | 13200 | 43.924 | 1756.96
1.1 | Dia 6 mm plain bar | kg | 217 | 45 | 9765 |  | 0
| Total to summary ………Birr |  |  |  | 71828.3 |  | 13447.1984
2. BLOCK WORK
2.1 | 20cm thick | m2 | 75.52 | 350 | 26432 | 48.762 | 17066.7
| Total to summary ………Birr |  |  |  | 26432 |  | 17066.7
3.ROOFING
3.1 | G - 28 Roof covering in galvanized corrugated | m2 | 114 | 300 | 34200 | 19.27 | 5781
3.2 | G - 28 ribbed sheet ceiling under eave | m2 | 42 | 350 | 14700 | 5.64 | 1974
3.3 | Supply and fix G-28 flat metal sheet gutter | m | 40 | 250 | 10000 | 12.8 | 3200
3.4 | Flushing in flat metal sheet fixed as shown | m | 22 | 150 | 3300 | 7 | 1050
| Total to summary ………Birr |  |  |  | 58900 |  | 12005
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 180 | 23 | 4140 | 60.3 | 1386.9
4.2 | Diagonal & vertical members size-diameter 8 - 10 cm | m | 100 | 16 | 1600 | 37.68 | 602.88
4.3 | Purlin zigba size 5/7cm | m | 160 | 33 | 5280 | 6.9 | 227.7
4.4 | Zigba wooden fascia board price includes three coats | m | 66 | 71 | 4686 | 6.9 | 489.9
| Total to summary ………Birr |  |  |  | 15706 |  | 2707.38
5. METAL WORK
Windows
5.1 | Type W1 size-80/90cm | Nº | 6 | 650 | 3900 |  | 0
| Doors |  |  |  | 0 |  | 0
5.2 | Type D3 size - 300/300 cm | Nº | 1 | 8000 | 8000 |  | 0
| Total to summary ………Birr |  |  |  | 11900
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 100 | 180 | 18000 |  | 0
6.2 | Apply three coats of plastering to internal walls | m2 | 147 | 220 | 32340 |  | 0
6.3 | Cement screed floor 120mm thickness | m2 | 32 | 180 | 5760 |  | 0
6.4 | Approved type10/2cm terrazzo tile skirting | m | 24 | 150 | 3600 |  | 0
6.5 | Approved type Terrazo window cill . | ml | 12 | 200 | 2400 |  | 0
| Total to summary ………Birr |  |  |  | 62100 |  | 0
7. PAINTING
7.1 | External rendered surface | m2 | 75.5 | 30 | 2265 |  | 0
7.2 | Internal plastered surfaceand external beams& | m2 | 100 | 25 | 2500 |  | 0
7.3 | Concrete ceiling surface | m2 | 46.41 | 27 | 1253.07 |  | 0
| Total to summary ………Birr |  |  |  | 6018.07 |  | 0
8 | Electrical Installations
8.1 | Light Points
8.1.1 | Light points feed through PVC insulated cooper conductor of | No | 2 | 300 | 600 |  | 0
8.1.2 | Extra over light points flush/surface mounted legrand |  |  |  | 0 |  | 0
| a) Single pole switch | No | 1 | 40 | 40 |  | 0
8.2 | Socket Out Lets( Siements Shuko type) legrand mosaic plate |  |  |  | 0 |  | 0
| with frame and boxes |  |  |  | 0 |  | 0
8.2.1 | Flush mounted socket out let of 10/16 A ( 1- ph ) | No | 1 | 300 | 300 |  | 0
8.2.2 | Three phase socket out let with earthing terminal fed through | No | 1 | 60 | 60 |  | 0
8.2.3 | Light Fittings and Lamps (Optional). |  |  |  | 0 |  | 0
| As specified or equivalent |  |  |  | 0 |  | 0
| Phillips TCS 020/136 IC M2 + 1*36 w fl lamp | No | 2 | 250 | 500 |  | 0
| Total Carried Summary |  |  |  | 1500 |  | 0

## Gen. Sub TOS
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Guenerator House Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | 1.5 Cart away excavated material
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 7.4
|  |  | 1.1 Clear off site to remove top soil |  | 5.95
|  |  | L=5.4+1.0+1.0=7.4 |  | 0.3 | 13.209 | from item no 1.1
1 | 7.4 |  | W=3.95+1.0+1.0=5.95
| 5.95 | 44.03 |  |  |  | 7.8 | from item no 1.2
|  | 44.03 | m2 Total to item 1.1 |  |  | 13.03 | from item no 1.3
|  |  | 1.2 Bulk Excavation in ordinary soil |  |  | 34.039 | m3 Total to item 1.5
1 | 5
| 3.75 | [5 empty] | 1.6/ 25 cm thick basaltic or equivalent stone hard core
| 0.6 | 11.25 | m3 Total to item 1.2 | 1 | 4.6
[5 empty] | 3.15 | 14.49 | m2 Total to item 1.6
2 | 5.9 |  | 1.3 Ditto but Trench excavation
| 0.9 | [5 empty] | 2) CONCRETE WORK
| 0.7 | 7.434 |  |  |  |  | 2.1 5cm thick lean concrete class C-7
|  |  |  | 2 | 5.4
2 | 4.45 |  |  |  | 0.4 | 4.32
0.9
| 0.7 | 5.607 |  | 2 | 3.15 |  | L=12-0.5-(3*0.4)=10.3
[5 empty] | 0.4 | 2.52
|  | 13.041 | m3 Total to item 1.3
[6 empty] | 6.84 | m2Total to item 2.1
1.4 Selected Borrowed Fill
|  |  | A- fill under masonary |  |  |  | 2.3 10cm thick RC floor slab class C-25
1 | 5.7 |  |  | 1 | 4.9 |  | L=20.85-0.25-0.25-0.25-0.25=19.85
| 0.9 |  |  |  | 3.45 | 16.905 | W=12-0.25-0.25-0.25-0.25=11
| 0.5 | 2.565
[6 empty] | 16.905 | m2 Total to item 2.3
2 | 3.95
0.9
| 0.5 | 3.555
6.12
B- Fill around Masonary
4 | 5.2
0.25
| 0.6 | 3.12
4 | 3.95
0.25
| 0.6 | 2.37
5.49
C- Under hardcore
1 | 5
3.75
| 0.5 | 9.375
|  | 20.985 | m3 net volume item 1.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.4 In grade beams |  |  |  | 3. Masonry Work
2 | 5.4 | [5 empty] | 3.1 Trychltic or equivalent stone masonry (total)
| 0.25 |  |  | 2 | 5.2 |  | BGL
| 0.4 | 1.08 |  |  | 0.4
[5 empty] | 0.7 | 2.912
2 | 3.95
| 0.25 |  |  | 2 | 3.15
| 0.4 | 0.79 |  |  | 0.4
[5 empty] | 0.7 | 1.764
|  | 1.87 | m2Total to item 2.4
[6 empty] | 4.676 | m3 Total to item 3.1
provide fix in position form work or panel
|  |  | 2.7 To grade beam |  |  |  | 3.12 masonary work above AGL
4 | 5.4 |  |  | 2 | 5.2
| 0.4 | 8.64 |  |  | 0.4
[5 empty] | 0.35 | 1.456
4 | 3.95
| 0.4 | 6.32 |  | 2 | 3.15
0.4
-4 | 0.25 |  | deduction |  | 0.35 | 0.882
| 0.4 | -0.4
[6 empty] | 2.338 | m3Total to item 3.12
|  | 14.56 | m2 Total to item 2.7
2.15 10/2 cm chip wood expansion joint
along x-axis
2 | 5 |  | L=20.85-0.25-0.25-0.25-0.25-(.25*4)=18.85
10
along y-axis
2 | 3.75 |  | L=12-0.25-0.25-0.25-0.25-0.25=10.75
7.5
|  | 17.5 | mTotal to item 2.15
#REF!

## Genera Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Generator House
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 5 | 0.8
|  |  | 1.CONCRETE WORK |  | 0.9 | -3.6 | W7(5Pcs)
4 | 2.73 |  | 1.1)In elevation column
| 0.2 |  |  | 1 | 1.5
| 0.2 |  | C1=20Pcs & C2=4Pcs (0.2x0.2) |  | 2.73 | -4.095 | D3(1Pcs)
|  | 0.4368 | m3 net volume item 1.1
[6 empty] | 46.36 | m2 net area item 2.1
1.2)In beam
2 | 5.4 |  | TTB1=2Pcs |  |  |  | 3)ROOFING WORK
| 0.3 |  | Axis x/01 & x/02 from (y/01 - y/02) |  |  |  | 3.1)G-28 CIS Roof covering
| 0.2 | 0.648 |  | 1 | 6.6 |  | W=5.40+0.60X2=6.60mt
[5 empty] | 5.15 |  | L=3.95+0.60X2=5.15mt
2 | 3.55 |  | TTB2=2Pcs |  |  | 33.99 | m2 net area item 3.1
| 0.3 |  | Axis y/01 & y/02 from ( y/01 - y/02)
| 0.2 | 0.426
3.2 - Ribbed Sheet
|  | 1.074 | m3 net volume item 1.2 | 2 | 6.4 |  | Left & Right side
[5 empty] | 0.6 | 7.68
FORM WORK
4 | 2.73 |  | 1.3)Elevation column | 4 | 7.42 |  | Gable side
| 0.8 |  | C1 =4PCS |  | 0.6 | 17.808 | l = (0.95^2+7.35^2)^0.5 =7.41m
|  | 8.736 | m2 net area item 1.3
[6 empty] | 25.488 | m2 net area item 3.2
1.4) beam
2 | 5 |  | TTB1=2Pcs |  |  |  | 3.3- Flashing
| 0.8 | 8 | Axis x/01 & x/02 from (y/01 - y/06) | 4 | 7.42
[6 empty] | 29.68 | m net length item 3.3
2 | 3.55 |  | TTB2=2Pcs
| 0.8 | 5.68 | Axis x/02 & x/03 from ( y/01 - y/06) |  |  |  | 3.4- Gutter
|  |  |  | 2 | 6.4
8 | 0.2 |  |  |  |  | 12.8 | m net length item 3.4
| 0.3 | 0.48
4)CARPENTRY
|  | 14.16 | m2 net area item 1.4 |  |  |  | 4.1)Uper & lower chord size 10-12cm
|  |  |  | 6 | 10.49
|  |  | 1.5)ф12mm deformed bar |  |  | 62.94 | m net length item 4.2
|  | 183.3898 | kg net weight item 1.5
4.2)Vertical & Diagonal member
|  |  | 1.6)ф8mm deformed bar | 5 | 7.5
|  | 58.539 | kg net weight item 1.6 |  |  | 37.5 | m net length item 4.2
|  |  | 2)BLOCK WORK |  |  |  | 4.3)Purlin zigba 5/7cm
|  |  | 2.1)20cm thick HCB wall |  |  |  | No .pur =2.75/0.9+1=4X2=8
2 | 5 |  |  | 8 | 6.6 |  | L=5.4+1.2=6.60mt
| 2.73 | 27.3 | Axis x/01 from (y/01 - y/02) |  |  | 52.8 | m net length item 4.3
2 | 3.55 | [5 empty] | 4.4- Fasia Board
| 2.73 | 19.383 | Axis x/02 from (y/01 - y/02) | 1 | 6.4 |  | Left & Right Side
6.4
2 | 0.68
| 3.95 | 5.372 | TOP TIE BEAM | 4 | 7.42 |  | Gable
29.68
2 | 5
| 0.2 | 2 | Diitto as above |  |  | 36.08 | m net length item 4.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.1)Apply two coats of plastering & |  |  | 46.983 | m2 net area item 6.2
one coat rendering
2 | 5 |  | Axis x/01 from (y/01 - y/02) |  |  |  | 6.9- Pavment
| 2.73 | 27.3 |  | 2 | 7.6 |  | Left & Right Side
1.2
2 | 3.55 |  | Axis x/02 from (y/01 - y/02) |  |  | 18.24
| 2.73 | 19.383
|  |  |  | 2 | 2.7 |  | Front & Rare Side
1 | 0.83 |  | Axis y/01 & y/02 from ( y/01 - y/02) |  | 1.2
| 3.55 | 2.9465 | Top tie beam |  |  | 6.48
1 | 5 |  | " |  |  | 24.72 | m2 before deduction
| 0.2 | 1
Deduction
5 | 1.5 |  | W1(4Pcs) | 1 | 2.4 |  | Ramp
| 1.63 | -12.225 |  |  | 1.2
1 | 1.5 |  |  |  |  | 2.88 | m2 total deduction
| 2.63 |  | D1(1Pcs)
|  | -3.945 |  |  |  | 21.84 | m2 net area item 6.21
|  | 34.4595 | m2 net area item 6.1 |  |  |  | 6.1- Half Ditch
|  |  |  | 2 | 8.2 |  | Left & Right Side
|  |  | 6.2)Apply three coats of plastering |  |  | 16.4
to internal wall & external beam & colu.
1 | 15.5 |  | L=3.515X2+4.6X2=17.10mt | 2 | 5.1 |  | Front & Rare Side
| 3.03 | 46.965 |  |  |  | 10.2
5 | 1.5 |  | W1(5Pcs) |  |  |  | Around ramp
| 1.63 | -12.225 |  | 2 | 3.6
7.2
1 | 1.5 |  | D1(1Pcs)
| 2.73 | -4.095 |  |  |  | 33.8 | m before deduction
2 | 5 |  | GRADE BEAM | 1 | 2.4 |  | Deduction
| 0.4 | 4
[6 empty] | 2.4 | m total deduction
2 | 3.55
| 0.4 | 2.84 |  |  |  | 31.4 | m net length item 6.22
2 | 5 |  | TOP TIE BEAM |  |  |  | 7)Painting
| 0.3 | 3 |  |  |  |  | 7.3)External rendered surface
[6 empty] | 34.4595 | m2 net area item 7.3
2 | 3.55 |  | TOP TIE BEAM
| 0.3 | 2.13
8 | 2.73 |  | COLUMNS
| 0.2 | 4.368

## Tran. Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Transformer Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | SUB STRUCTURE |  |  |  | 1.6)Hard core
|  |  | 1.1)Site clearing |  | 4.2
1 | 4.5 |  |  |  | 3
| 5.2 |  |  |  |  | 12.6
|  | 23.4 |  |  |  |  | 12.6
|  |  | 23.4 |  |  |  | TOTAL=12.60m2
|  |  | TOTAL=23.40m3 |  |  |  | 2)CONCRETE WORK
|  |  | 1.2)Bulk excavation |  |  |  | 2.1)Lean concrete
1 | 0.9 |  |  |  | 4.7
| 4.5 |  |  | 2 | 0.4
| 5.2 |  |  |  |  | 1.88
|  | 21.06 |  |  | 3 | 0
|  |  | 21.06 | 2 | 0.4 | 0
|  |  | TOTAL=21.06m3 |  |  | 1.2
|  |  | 1.3)Ditto but exceeding 1.50mt |  |  |  | 3.08
TOTAL=3.08m2
4 | 0.45
1.5
1.5
4.05
4.05
TOTAL=4.05m3
|  |  | 1.4)selected borrowed fill |  |  |  | 2.3)10cm thick concrete slab
| 23.4 |  |  |  | 4.2
| 0.3 | 7.02 | item 1.1 |  | 3
12.6
|  | 21.06 | item 1.2 |  |  |  | 12.6
TOTAL=12.60m2
|  | 4.05 | item 1.03 |  |  |  | 2.4)in grade beam
4.7
|  |  |  | 2 | 0.4
0.25
[6 empty] | 0.94 | beam
3
|  |  |  | 2 | 0.4
|  |  | 32.13 |  | 0.25
|  |  | TOTAL=31.01m3 |  |  | 0.6
|  |  | 1.5)Cart away |  | 4.7
|  | 7.02 | item 1.1 | 2 | 0.4
[5 empty] | 0.25 |  | beam
|  | 21.06 | item 1.2 |  |  | 0.94
3
|  | 4.05 | item 1.3 | 2 | 0.4 |  | beam
|  |  | 32.13 |  | 0.15 |  | 2.84
|  |  | TOTAL=32.13m3 |  |  | 0.36 | TOTAL=2.84m3
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2.11 Reinforcement steel bar
[6 empty] | #REF! | Dia 14mm
[6 empty] | #REF! | Dia 12mm
[6 empty] | #REF! | Dia 10mm
[6 empty] | #REF! | Dia 8mm
2.14)10/2cm chipwoodexpantion
joint
|  |  |  | 2 | 4.2
8.4
|  |  |  | 2 | 3 | 0
|  |  | FORM WORK |  |  | 6
| 4.25 | 0 | 2.7)Grade beam |  |  |  | 14.4
4 | 0.15 | 0 | beam |  |  |  | TOTAL=14.40ml
|  | 2.55 |  |  |  |  | 3)MASONRY
| 3.05 | 0 |  |  |  |  | 3.1)Masonry below NGL
4 | 0.15 | 0 | " |  | 4.7
|  | 1.83 |  | 2 | 0.7
| 4.5 | 0 |  |  | 0.4
2 | 0.4 | 0 | g.beam |  |  | 2.632
|  | 3.6 |  |  | 3 | 0
| 3.05 | 0 |  | 2 | 0.7 | 0
2 | 0.4 | 0 | " |  | 0.4 | 0
|  | 2.44 |  |  |  | 1.68
|  |  | 10.42 |  |  |  | 4.312
|  |  | TOTAL=10.42m3 |  |  |  | TOTAL=4.31m3
#REF!

## Trans Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Transformer House
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 1 | 4.7
|  |  | 1.CONCRETE WORK |  | 0.2 | 0.94 | "
4 | 2.73 |  | 1.1)In elevation column
| 0.2 |  | C1=20Pcs & C2=4Pcs (0.2x0.2) | 1 | 4.7
| 0.2 |  |  |  | 1.25 | 5.875
|  | 0.4368 | m3 net volume item 1.1
|  |  |  | 1 | 0.9 |  | D1
[5 empty] | 2.73 | -2.457
|  |  | 1.2)In beam |  |  |  | W1
2 | 4.7 |  | TTB1=2Pcs | 2 | 1.8
| 0.3 |  | Axis x/01 & x/02 from (y/01 - y/02) |  | 0.6 | -2.16
| 0.2 | 0.564
[6 empty] | 48.762 | me net area item 2.1
2 | 3 |  | TTB2=2Pcs
| 0.3 |  | Axis y/01 & y/02 from ( y/01 - y/02) |  |  |  | 3)ROOFING WORK
| 0.2 | 0.36 |  |  |  |  | 3.1)G-28 CIS Roof covering
W=4.70mt
|  | 0.924 | m3 net volume item 1.2 | 1 | 4.7 |  | L=3.50+0.6=4.10mt
4.1
|  |  | FORM WORK |  |  | 19.27 | m2 net area item 3.1
1.3)Elevation column & beam
4 | 2.73 |  | C1 =4PCS | 2 | 4.7 |  | 3.2- Ribbed Sheet
| 0.8 |  |  |  | 0.6 |  | Front Side
|  | 8.736 | m2 net area item 1.3 |  |  | 5.64 | m2 net area item 3.2
|  |  | 1.4) beam | 2 | 6.4 |  | 3.3- Gutter
2 | 4.3 |  | TTB1=2Pcs
| 0.8 | 6.88 | Axis x/01 & x/02 from (y/01 - y/06) |  |  | 12.8 | m net length item 3.3
2 | 3 |  | TTB2=2Pcs |  |  |  | 4- Crpentary & Joinery
| 0.8 | 4.8 | Axis x/02 & x/03 from ( y/01 - y/06)
4.1)Uper & lower chord size 10-12cm
8 | 0.2 | [5 empty] | L=2.75X2+4.55=10.05ml
| 0.3 | 0.48 |  | 6 | 10.05 |  | No. truss=5.40/1.33+1=5pcs
[6 empty] | 60.3 | m net length item 4.2
|  | 12.16 | m2 net area item 1.4
4.2)Vertical & Diagonal member
|  |  | 1.5)ф12mm deformed bar | 6 | 6.28
|  | 145.1702 | kg net weight item 1.5 |  |  | 37.68 | m net length item 4.2
|  |  | 1.6)ф8mm deformed bar |  |  |  | 4.3)Purlin zigba 5/7cm
|  | 43.924 | kg net weight item 1.6 |  |  |  | No .pur =4.17/0.9+1=4X2=8
|  |  |  | 6 | 5.9 |  | L=5.4+1.2=6.60mt
|  |  | 2)BLOCK WORK |  |  | 35.4 | m net length item 4.3
2.1)20cm thick HCB wall
2 | 4.3 | [5 empty] | 4.4)Zigba wooden fascia board
| 2.73 | 23.478 | Axis x/01 from (y/01 - y/02) | 1 | 5.9
[6 empty] | 5.9 | L=2.75X4+6.6x2=24.20mt
2 | 3.1
| 2.73 | 16.926 | Axis x/02 from (y/01 - y/02) | 2 | 0.5
1
2 | 3.5
| 0.88 | 6.16 | TOP TIE BEAM |  |  | 6.9 | m net length item 4.4

## Gen Reinf
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Generator
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 | 14 | 6.05 | 2 | 3 | 6 |  |  |  |  | 36.3
|  |  | 14 | 5.35 | 2 | 3 | 6 |  |  |  |  | 32.1
|  |  | 8 | 1.2 | 2 | 26 | 52 |  | 62.4
|  | GB2 | 14 | 4.4 | 2 | 3 | 6 |  |  |  |  | 26.4
|  |  | 14 | 3.9 | 2 | 3 | 6 |  |  |  |  | 23.4
|  |  | 8 | 1.2 | 2 | 19 | 38 |  | 45.6
| MEUSH |  | 8 | 3.42 | 1 | 25 | 25 |  | 85.5
|  |  | 8 | 4.87 | 1 | 18 | 18 |  | 87.66
0
|  |  |  | TOTAL LENGTH |  |  |  |  | 281.16 | 0 | 0 | 118.2
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 111.0582 | 0 | 0 | 143.022
| COLUMN (C1) |  | 12 | 3.68 | 4 | 6 | 24 |  |  |  | 88.32
|  |  | 8 | 0.7 | 16 | 6 | 96 |  | 67.2
| TTB1 |  | 12 | 6.05 | 2 | 3 | 6 |  |  |  | 36.3
|  |  | 12 | 5.35 | 2 | 3 | 6 |  |  |  | 32.1
|  |  | 8 | 0.9 | 2 | 26 | 52 |  | 46.8
| TTB2 |  | 12 | 4.4 | 2 | 3 | 6 |  |  |  | 26.4
|  |  | 12 | 3.9 | 2 | 3 | 6 |  |  |  | 23.4
|  |  | 8 | 0.9 | 2 | 19 | 38 |  | 34.2
0
0
0
0
0
0
|  |  |  | TOTAL LENGTH |  |  |  |  | 148.2 | 0 | 206.52 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 58.539 | 0 | 183.3898 | 0

## Re-bar pump house
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [9 empty] | Block : pump house
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 | 12 | 5.4 | 2 | 3 | 6 |  |  |  | 32.4
|  |  | 12 | 4.65 | 2 | 3 | 6 |  |  |  | 27.9
|  |  | 8 | 1.2 | 2 | 23 | 46 |  | 55.2
|  | GB2 | 12 | 4.2 | 2 | 3 | 6 |  |  |  | 25.2
|  |  | 12 | 3.45 | 2 | 3 | 6 |  |  |  | 20.7
|  |  | 8 | 1.2 | 2 | 17 | 34 |  | 40.8
| mesh |  | 8 | 3.05 | 1 | 21 | 21 |  | 64.05
|  |  | 8 | 4.25 | 1 | 16 | 16 |  | 68
|  |  |  | TOTAL LENGTH |  |  |  |  | 228.05 | 0 | 106.2 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 90.0798 | 0 | 94.3056 | 0
| COLUMN (C1) |  | 12 | 3.58 | 4 | 4 | 16 |  |  |  | 57.28
|  |  | 8 | 0.7 | 4 | 14 | 56 |  | 39.2
| TTB1 |  | 12 | 5.4 | 2 | 3 | 6 |  |  |  | 32.4
|  |  | 12 | 4.65 | 2 | 3 | 6 |  |  |  | 27.9
|  |  | 8 | 0.9 | 2 | 23 | 46 |  | 41.4
| TTB2 |  | 12 | 4.2 | 2 | 3 | 6 |  |  |  | 25.2
|  |  | 12 | 3.45 | 2 | 3 | 6 |  |  |  | 20.7
|  |  | 8 | 0.9 | 2 | 17 | 34 |  | 30.6
0
0
|  |  |  | TOTAL LENGTH |  |  |  |  | 111.2 | 0 | 163.48 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 43.924 | 0 | 145.1702 | 0

## Kitchen Summary
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau
Location : Wegeda
Contractor :- Trust Construction
Block:-kitchen
Details of Works executed
Details of Works executed
Bill No. | Description | Sub Total Birr |  | Total Birr
|  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work | 215998 | 119402.6901 | 215998 | 119402.6901
2 | Concrete Work | 404278 | 348993.5756 | 404278 | 348993.5756
3 | Masonry work | 202550 | 53102.74 | 202550 | 53102.74
| sub total A | 822826 | 521499.0057 | 822826 | 521499.0057
B. Super Structure
1 | Concrete Work | 140629 | 145195.1887 | 140629 | 145195.1887
2 | Block work | 144930 | 173822.8 | 144930 | 173822.8
3 | Roofing | 173531.2 | 171470.64 | 173531.2 | 171470.64
4 | Carpentary & Joinery | 135889.7 | 99798.32 | 135889.7 | 99798.32
5 | Metal work | 134211 | 50385 | 134211 | 50385
6 | Finishing | 445235 | 455573.715 | 445235 | 455573.715
7 | Painting | 32200 | 26890.444 | 32200 | 26890.444
8 | Glazing | 13075 |  | 13075
9 | Sanitory Installation | 30150 | 6495.65 | 30150 | 6495.65
10 | Electrical Installation | 99408.75 | 49881.5 | 99408.75 | 49881.5
| sub total B | 1349259.65 | 1179513.2577 | 1349259.65 | 1179513.2577
| Total A+B | 2172085.65 | 1701012.2635 | 2172085.65 | 1701012.2635
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  |  |  | Consultant:- _____________

## Kit. Meas
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [5 empty] | Block : kitchen
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 462 | 8 | 3696 | 462.035 | 3696.28
1.2 | Bulk excavation in ordinary | m3 | 375 | 70 | 26250 | 40.2577 | 2818.039
1.3 | Ditto but exceeding 1.5m less than 2m | m3 | 125 | 70 | 8750 | 122.3145 | 8562.015
1.4 | Selected borrowed fill brought from out side | m3 | 500 | 150 | 75000 | 126.4767 | 18971.505
1.5 | Selected borrowed fill brought from insitu | m3 | 56.6 | 56.6 | 3203.56 | 95.5178 | 5406.3047
1.5 | Cart away surplus excavated material to an | m3 | 638.6 | 70 | 44702 | 205.665 | 14396.5465
1.6 | 25cm thick basaltic or equivalent stone hard | m2 | 288 | 200 | 57600 | 327.76 | 65552
Total to summary ………Birr |  |  |  |  | 219201.56 |  | 119402.6901
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 95 | 150 | 14250 | 73.4 | 11010
2.2 | Ditto but under footing pad | m2 | 24 | 150 | 3600 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 288 | 400 | 115200 | 327.76 | 131104
2.4 | In grade beam & Steps | m3 | 19 | 3200 | 60800 | 18.71 | 59872
Provide cut and fix in position swan zigzag wood
2.7 | Grade beam | m2 | 153 | 120 | 18360 | 146.48 | 17577.6
2.1 | Steps | m2 | 5 | 150 | 750 |  | 0
Reinforcement steel bar according to St.drawing
2.11 | Dia 14mm deformed bar | kg | 1381 | 36 | 49716 | 1505.5788 | 54200.8368
2.12 | Dia. 12mm deformed bar | kg | 696 | 36 | 25056 |  | 0
2.13 | Dia 8 mm deformed bar | kg | 1891 | 36 | 68076 | 1853.9483 | 66742.1388
2.14 | 10/2 cm chip wood expansion joint between | m | 277 | 30 | 8310 | 282.9 | 8487
Total to summary ………Birr |  |  |  |  | 364118 |  | 348993.5756
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 140 | 1250 | 175000 | 37.8118 | 47264.75
3.2 | Ditto but above natural ground level externally | m3 | 19 | 1450 | 27550 | 4.0262 | 5837.99
Total to summary ………Birr |  |  |  |  | 202550 |  | 53102.74
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 2.9 | 3200 | 9280 | 2.6208 | 8386.56
1.2 | In beams& steps | m3 | 12 | 3200 | 38400 | 11.268 | 36057.6
1.3 | Lintel | m3 | 0.9 | 3200 | 2880 | 0.388 | 1241.6
Provide cut and fix in position swan zigzag wood
form work or metal panel. To:-
1.4 | Elevation column | m2 | 58 | 130 | 7540 | 52.416 | 6814.08
1.5 | Beam | m2 | 152 | 130 | 19760 | 147.6 | 19188
1.6 | Lintel | m2 | 9.3 | 130 | 1209 | 7.18 | 933.4
| Reinforcement steel bar according to St.drawing |  |  | 36
1.7 | Dia 14mm deformed bar | kg | cp | 36 | 35 | 35.6224 | 1282.4064
1.8 | Dia 12mm deformed bar | kg | 1314 | 36 | 47304 | 1494.2731 | 53793.8323
1.9 | Dia 8 mm deformed bar | kg | 396 | 36 | 14256 | 486.0475 | 17497.71
Total to summary ………Birr |  |  |  |  | 140664 |  | 145195.1887
2. BLOCK WORK
2.1 | 20cm thick | m2 | 287 | 350 | 100450 | 435.272 | 152345.2
2.2 | 15 cm thick | m2 | 139 | 320 | 44480 | 67.1175 | 21477.6
Total to summary ………Birr |  |  |  |  | 144930 |  | 173822.8
3.ROOFING
3.1 | G-28 CIS Roof covering in galvanized corrugated | m2 | 424.17 | 360 | 152701.2 | 423.87 | 152593.2
3.2 | G28ribbed sheet ceiling under eave | m2 | 50 | 160 | 8000 | 53.244 | 8519.04
3.3 | Flashing in flat metal sheet fixed as shown | m | 85 | 110 | 9350 | 29.04 | 3194.4
3.4 | Supply and fix G-28flat metal sheet gutter | m | 29 | 120 | 3480 | 59.7 | 7164
Total to summary ………Birr |  |  |  |  | 173531.2 |  | 171470.64
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 558.2 | 23 | 12838.6 | 664.7 | 15288.1
4.2 | Vertical & diagonal members size-diameter 8 - 10cm | m | 346 | 16 | 5536 | 764.98 | 12239.68
4.3 | Purlin zigba size 5/7cm | m | 477.6 | 33 | 15760.8 | 537.3 | 17730.9
4.4 | Zigba wooden fascia board price includes three coats | m | 59.7 | 71 | 4238.7 | 88.74 | 6300.54
Doors
4.5 | Type D7 size-80/273cm | Nº | 7 | 4149.6 | 29047.2 | 5 | 20748
4.5 | Type D8 size 70/273 cm | № | 6 | 3630.9 | 21785.4 | 5 | 18154.5
4.7 | Type D9 size-90/273cm | Nº | 10 | 4668.3 | 46683 | 2 | 9336.6
Total to summary ………Birr |  |  |  |  | 135889.7 |  | 99798.32
5. METAL WORK
Windows
5.1 | Type W2 size-150/173cm | Nº | 12 | 2000 | 24000 | 12 | 24000
5.2 | Type W4 size-130/173cm | Nº | 4 | 1700 | 6800 | 4 | 6800
5.3 | Type W15 size-130/60cm | Nº | 2 | 1500 | 3000 | 2 | 3000
5.5 | Type W5 size-460/60cm | Nº | 0 | 2500 | 0 |  | 0
Doors
5.6 | Type D2 size - 140/273cm | Nº | 3 | 3892.5 | 11677.5 | 2 | 7785
5.7 | Type D3 size - 130/273cm | Nº | 6 | 1700 | 10200 | 4 | 6800
5.8 | Type D6 size - 90/273cm | Nº | 4 | 2000 | 8000 | 1 | 2000
Total to summary ………Birr |  |  |  |  | 63677.5 |  | 50385
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 198 | 140 | 27720 | 180.116 | 25216.24
6.2 | Apply three coats of plastering to internal walls& | m2 | 664 | 150 | 99600 | 932.651 | 139897.65
6.3 | Chip wood ceiling nailed on & including | m2 | 288 | 310 | 89280 | 327.7925 | 101615.675
6.5 | 9mm thick non slippery ceramic tile floor | m2 | 288 | 300 | 86400 | 338.8405 | 101652.15
6.6 | Approved type Ceramic tile skirting | m | 277 | 100 | 27700 | 278.8 | 27880
6.7 | Terrazo window cill | m | 30 | 150 | 4500 | 25.8 | 3870
6.9 | 10 cm thick C-20 RC 1.2 m wide pavement | M | 106 | 550 | 58300 | 87.24 | 47982
6.12 | Concrete pipes of half diameter 30cm | ml | 97 | 100 | 9700 | 74.6 | 7460
| Construction of 10x40 cm curb stone | ml | 97 | 265 | 25705 |  | 0
Total to summary ………Birr |  |  |  |  | 428905 |  | 455573.715
7. PAINTING
7.1 | Internal plastered surfaceand external beams& | m2 | 664 | 18.6667 | 12394.6667 | 932.651 | 17409.4853
7.2 | Chip wood ceiling surface | m2 | 288 | 18.6667 | 5376 | 327.7925 | 6118.7933
7.3 | External rendered surface | m2 | 198 | 18.6667 | 3696 | 180.116 | 3362.1653
Total to summary ………Birr |  |  |  |  | 21466.6667 |  | 26890.444
9. SANITARY INSTALLATION
9.1 | Supply and install PP-R water pipes for water
| 15mm diameter ;internal | LM | 20 | 40 | 800 | 31.56 | 1262.4
| 20mm diameter ;internal | LM | 15 | 45 | 675 |  | 0
9.3 | Supply and fix bronze gate valves complete with unions,
| 15mm diameter | No | 10 | 120 | 1200 | 5 | 600
| 20mm diameter | No | 4 | 150 | 600 |  | 0
9.5 | Supply and install waste water pipes made of rigid
| 50mm diameter of min. wall thickness=2mm | LM | 16 | 50 | 800 | 53.21 | 2660.5
| 75mm diameter of min. wall thickness=3mm | LM | 10 | 55 | 550 | 13.45 | 739.75
| 100 mm diameter of min. wall thickness=3.2mm | LM | 14 | 60 | 840 | 20.55 | 1233
Total to summary ………Birr |  |  |  |  | 5465 |  | 6495.65
10. ELECTRICAL INSTALLATION
2 | Light points
2.01 | light points in rigid thermoplastic conduit of 16mm | PCs | 39 | 200 | 7800 | 45 | 9000
3 | Switches
3.01 | single(774001+774041) | PCs | 6 | 81.25 | 487.5 | 10 | 812.5
3.02 | Duoble(774005+774042) | " | 11 | 131.25 | 1443.75 | 9 | 1181.25
4 | Socket outlet points
4.01 | Socket outlet points in regid thermoplastic conduit | PCs | 23 | 200 | 4600 | 26 | 5200
4.02 | Ditto as above but for water Heater points | PCs | 5 | 785 | 3925 | 3 | 2355
4.03 | Ditto as 4.01 but for 3 phase points in 4x2.5 | PCs | 2 | 350 | 700 | 2 | 700
4.04 | power cable of 3x6mm2 in rigid pvc conduit of | PCs | 2 | 70 | 140 | 2 | 140
4.05 | Ditto as 4.04 above but for 3 phase in 4x4mm2 | PCs | 2 | 80 | 160 | 3 | 240
5 | Socket outlets
5.01 | Socket outlet LEGRAND SUNO 774023 16 1ph | PCs | 23 | 90 | 2070 | 26 | 2340
5.02 | Ditto as above 5.01 but 3 phase socket 16A/1P | PCs | 2 | 281.25 | 562.5 | 3 | 843.75
5.03 | weather proof socket Legrand Suno 774022+7740 41 | PCs | 5 | 80 | 400 | 2 | 160
5.06 | Ditto as above 4.06 but for 25A/1ph for kitchen | PCs | 2 | 80 | 160 | 3 | 240
5.07 | Ditto as above 4.06 but for 20A/3ph for kitchen | PCs | 2 | 80 | 160 | 2 | 160
6 | Telephone/Data points
6.01 | Telephone points fed through cat 5E UTP cable | PCs | 5 | 600 | 3000 | 6 | 3600
6.03 | Flush mounted Telephone outlets RJ11 type
| Legrand Suno774038+774041 | PCs | 5 | 200 | 1000 |  | 0
7 | Type of Light Fitting With lamp
7.01 | PHILIPS TCS 098/236 IMKwith 2xTLD 36W | PCs | 15 | 800 | 12000 | 10 | 8000
7.02 | PHILIPS TCS 098/136 IMKwith 1xTLD 36W | PCs | 10 | 600 | 6000 | 16 | 9600
7.03 | RZB 59251.002 with RZB 05-56150Q50W lamp or | PCs | 4 | 200 | 800 | 6 | 1200
7.04 | RZB 59222.002 with RZB 05-56150Q50W lamp or | PCs | 2 | 200 | 400 | 2 | 400
7.05 | PHILIPS TMW 065/236 IMKwith 2xTLD 36W | PCs | 8 | 300 | 2400 | 8 | 2400
10 | Cable way and Manhole |  |  |  | 0 |  | 0
10.04 | Rigid pvc pipe of dia.25mm For 4x4mm2 | " | 34 | 35 | 1190 | 37.4 | 1309
Total to summary ………Birr |  |  |  |  | 49398.75 |  | 49881.5
X

## Kit. Sub TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Kitchen Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | C-bulk fill and compaction
|  |  | 1) EXCAVATION & EARTH WORK | 1 | 27.9 |  | L=29.2-0.5-0.8=27.9
|  |  | 1.1 Clear off site to remove top soil |  | 12.25 |  | W=13.55-0.5-0.8=12.25
|  |  | L=29.2+1.0+1.0-.5=30.7 |  | 0.42 | 143.5455
1 | 30.7 |  | W=13.55+1.0+1.0-.5=15.05
| 15.05 | 462.035 | m2 Total to item 1.1 |  |  |  | DEDUCTION
|  |  |  | 2 | 27.9 |  | along x-axis
|  |  | 1.2 Bulk Excavation in ordinary soil |  | 0.4 |  | L=27.9 W=0.4m
1 | 27.4 |  | L=29.2-0.25-0.25-0.4-0.4-0.5=27.4 |  | 0.42 | 9.3744
| 11.75 |  | W=13.55-0.25-0.25-0.4-0.4-0.5=11.75
| 0.17 | 54.7315 |  | 4 | 11.45 |  | along y-axis
[5 empty] | 0.4 |  | L=13.55-0.5-0.8-(2*0.4)=11.45
|  |  | DEDUCTION |  | 0.42 | 7.6944
2 | 27.4 |  | along x-axis
| 0.9 |  | L=29.2-0.25-0.25-0.4-0.4-0.5=27.4 |  |  | 126.4767 | m3 Total to item 1.49 ( borrowed)
| 0.17 | 8.3844
1.5 Cart away excavated material to an
4 | 9.95 |  | along y-axis | 1 | 30.7
| 0.9 |  | W=13.55-0.25-0.25-0.4-0.4-0.5-(2*0.9)=9.95 |  | 15.05
| 0.17 | 6.0894 |  |  | 0.3 | 138.6105 | from item no 1.1
[6 empty] | 40.2577 | from item no 1.2
|  | 40.2577 | m3 Total to item 1.2 |  |  | 122.3145 | from item no 1.3
[6 empty] | 95.5178 | DEDUCTION
|  |  | 1.3 Ditto to Item 1.2 but Trench |  |  | 205.665 | m3 Total to item 1.4
4 | 29.2 |  | along x-axis
| 0.9 |  | W=0.4+0.25+0.25=0.90 L=29.2 d=0.92 |  |  |  | 1.6/ 25 cm thick basaltic or equivalent stone hard core
| 0.77 | 80.9424
|  |  |  | 1 | 28.2 |  | L=29.2-0.5-0.5=28.2W=13.55-0.5-0.5=12.55
6 | 9.95 |  | along y-axis |  | 12.55 | 353.91
| 0.9 |  | L=13.55-(4*.9)=9.95
| 0.77 | 41.3721 | W=0.4+0.25+0.25=0.90, d= |  |  |  | DEDUCTION
|  |  |  | 2 | 28.2 |  | along x-axis L=28.2 W=0.25
|  | 122.3145 | m3 Total to item 1.3 |  | 0.25 | 14.1
|  |  | 1.4 Selected Fill | 4 | 12.05 |  | along y-axis L=12.05 W=0.25
|  |  | A- fill under masonary |  | 0.25 | 12.05 | L=13.55-0.5-0.5-0.5=12.05
4 | 29.2 |  | for axis x01-x04
| 0.9 |  | L=29.2 |  |  | 327.76 | m2 Total to item 1.6
| 0.54 | 56.7648
2) CONCRETE WORK
6 | 9.95 |  | for axis y01-y05 |  |  |  | 2.1 5cm thick lean concrete class C-7
| 0.9 |  | L=9.95 , W=0.9, d=0.3 | 4 | 28.7 |  | L=29.2-0.5=28.7
| 0.54 | 29.0142 | 9.95 |  | 0.4 | 45.92
|  |  | B-backfill and compaction in side masonary | 6 | 11.45 |  | L=13.55-0.5-(4*0.4)=11.45
|  |  | along x-axis |  | 0.4 | 27.48
6 | 26.7 |  | L=29.2-0.25-0.25-0.8-(3*0.4)=26.70
| 0.25 |  | W=0.25 ,d= |  |  | 73.4 | m2Total to item 2.1
| 0.15 | 6.0075
along y-axis
10 | 9.95 |  | L=13.55-0.25-0.25-0.8-(2*0.25)-(2*.9)=9.95
| 0.25 |  | W=0.25 ,d=.
| 0.15 | 3.7312
|  | 95.5178 | m3 Total to item 1.4( insitu materal)
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 2.3 10cm thick RC floor slab class C-25 |  |  |  | 2.14 10/2 cm chip wood expansion joint
1 | 28.2 |  | L=29.2-0.25-0.25-0.25-0.25=28.2 |  |  |  | along x-axis
| 12.55 | 353.91 | W=13.55-0.25-0.25-0.25-0.25=12.55 | 6 | 27.2 |  | L=29.2-0.25-0.25-0.25-0.25-(.25*4)=27.2
163.2
|  |  | DEDUCTION |  |  |  | along y-axis
|  |  | along x-axis | 8 | 12.05 |  | L=13.55-0.25-0.25-0.25-0.25-0.5=12.05
2 | 28.2 |  | L=29.2-0.25-0.25-0.25-0.25=28.2 |  |  | 96.4
| 0.25 | 14.1
|  |  | along y-axis |  |  | 259.6 | mTotal to item 2.14
4 | 12.05 |  | L=13.55-0.25-0.25-0.25-0.25-0.5=12.05
| 0.25 | 12.05 |  |  |  |  | 3. Masonry Work
3.1 Trychltic stone masonry (total)
|  | 327.76 | m2Total to item 2.3 | 4 | 28.7 |  | axis x01,x02,x03,x04
[5 empty] | 0.4 |  | L=29.2-0.5=28.7
[5 empty] | 0.57 | 26.1744
2.4 In grade beams and steps
4 | 28.7 |  | L=29.2-0.25-0.25=28.7 | 6 | 11.45 |  | axis y01,y02,y03……y09
| 0.25 |  |  |  | 0.4 |  | L=13.55-0.5-(4*0.4)=11.45
| 0.4 | 11.48 |  |  | 0.57 | 15.6636
[6 empty] | 41.838 | m3Total Volume Masonary
6 | 12.05 |  | L=13.55-0.25-0.25-(4*.25)=12.05 |  |  |  | 3.12 masonary work above NGL
| 0.25 |  |  | 1 | 24.35 |  | on axis x01 L=20.35
| 0.4 | 7.23 |  |  | 0.4
[5 empty] | 0.33 | 3.2142
|  | 18.71 | m3Total to item 2.4
on axis y01 L=7.25m
|  |  | provide fix in form work | 1 | 7.25
|  |  | 2.7 In grade beams |  | 0.4
8 | 28.7 |  | L=29.2-0.25-0.25=28.7 (x-axis) |  | 0.28 | 0.812
| 0.4 | 91.84 |  |  |  | 4.0262 | m3Total to item 3.2
12 | 12.55 |  | L=13.55-0.25-0.25-(2*.25)=12.55 |  |  |  | 3.13 masonary work below NGL
| 0.4 | 60.24
[6 empty] | 37.8118 | m3Total to item 3.1
56 | 0.4 |  | DEDUCTION
| 0.25 | 5.6
|  | 146.48 | m2Total to item 2.7
Reinforcement steel bars
|  |  | 2.11)ф14 mm deformed bars |  |  |  |  | #REF!
|  | 1505.5788 | kg net wight item 2.11
2.13)ф8 mm deformed bars
|  | 1853.9483 | kg net wight item 2.13

## Kit Super TOS
Project: - Wogeda Primary Hospital
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: -Kitchen
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 2 | 12.2 |  | TTB3=2Pcs
|  |  | 1.CONCRETE WORK |  | 0.8 | 19.52 | Axis y/01 & y/06 from ( x/01 - x/04)
|  |  | 1.1)In elevation column |  |  |  | Dev.L=0.30*2+0.20=0.80mt
24 | 2.73 |  | C1=20Pcs & C2=4Pcs (0.2x0.2) | 4 | 12.2 |  | TTB4=4Pcs
| 0.2 |  |  |  | 0.8 | 39.04 | Axis y/02-y/05 from ( x/01 - x/04)
0.2
|  | 2.6208 | m3 net volume item 1.1 |  |  | 147.6 | m2 net area item 1.5
|  |  | 1.2)In beam & step |  |  |  | 1.6)Lintel
2 | 28.65 |  | TTB1=2Pcs | 4 | 1.2 |  | D7(4Pcs)
| 0.3 |  | Axis x/01 & x/o4 from (y/01 - y/06) |  | 0.55 | 2.64
| 0.2 | 3.438
|  |  |  | 4 | 1.1 |  | D8(4Pcs)
2 | 28.65 |  | TTB2=2Pcs |  | 0.5 | 2.2
| 0.3 |  | Axis x/02 & x/03 from ( y/01 - y/06)
| 0.2 | 3.438 |  | 3 | 1.3 |  | D9(3Pcs)
[5 empty] | 0.6 | 2.34
2 | 12.2 |  | TTB3=2Pcs
| 0.3 |  | Axis y/01 & y/06 from ( x/01 - x/04) |  |  | 7.18 | m2 net area item 1.6
| 0.2 | 1.464
1.7)ф14mm deformed bar
4 | 12.2 |  | TTB4=4Pcs |  |  | 35.6224 | kg net weight item 1.7
| 0.3 |  | Axis y/02 - y/05 from ( x/01 - x/04)
| 0.2 | 2.928 |  |  |  |  | 1.8)ф12mm deformed bar
[6 empty] | 1494.2731 | kg net weight item 1.8
|  | 11.268 | m3 net volume item 1.2
2.0)ф8mm deformed bar
|  |  | 1.3)Lintel |  |  | 486.0475 | kg net weight item 1.9
4 | 1.2 |  | D7(4Pcs)
| 0.2 | [5 empty] | 2)BLOCK WORK
| 0.15 | 0.144 |  |  |  |  | 2.1)20cm thick HCB wall
|  |  |  | 4 | 27.45 |  | Axis X/01 - X/04 from (Y/01 - Y/06)
4 | 1.1 |  | D8(4Pcs) |  | 2.73 | 299.754
0.1
| 0.2 | 0.088 |  | 12 | 1.5 |  | W2(12Pcs)
[5 empty] | 1.63 | -29.34
3 | 1.3 |  | D9(3Pcs)
| 0.2 |  |  | 4 | 1.3 |  | W4(4Pcs)
| 0.2 | 0.156 |  |  | 1.63 | -8.476
|  | 0.388 | m2 net area item 1.3 | 4 | 1.3 |  | D3(4PCS)
[5 empty] | 2.73 | -14.196
FORM WORK
|  |  | 1.4)Elevation column | 1 | 0.9 |  | D6(1Pc)
24 | 2.73 |  | C1=22Pcs +C2 2Pcs =24Pcs |  | 2.73 | -2.457
0.8
|  | 52.416 | m2 net area item 1.4 | 2 | 0.9 |  | D9(2Pc)
[5 empty] | 2.73 | -4.914
|  |  | 1.5)Beam |  |  |  | Opening
2 | 27.45 |  | TTB1=2Pcs | 1 | 1.3
| 0.8 | 43.92 | Axis x/01 & x/o4 from (y/01 - y/05) |  | 2.73 | -3.549
Dev.L=0.30*2+0.20=0.80mt
20 | 0.3 |  |  | 2 | 1.3 |  | D11(2Pc)
| 0.2 | 1.2 |  |  | 2.73 | -7.098
2 | 27.45 |  | TTB2=2Pcs | 2 | 12.7 |  | Axis Y/01 & Y/06 from (X/01 - X/04)
| 0.8 | 43.92 | Axis x/02& x/03 from (y/01- y/06) |  | 2.73 | 69.342
Dev.L=0.30*2+0.20=0.80mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
2 | 1.3 |  | D2(2Pc) |  |  |  | 3.3)Flashing in metal sheet
| 2.73 | -7.098 |  | 4 | 7.26 |  | Dev. Length 33cm
[6 empty] | 29.04 | m2 net area item 3.3
2 | 1.3 |  | W15(2Pc)
| 0.6 | -1.56 |  |  |  |  | 3.4)Supply & fix G-28 gutter dev.
|  |  |  | 2 | 29.85 |  | length=50cm
3 | 5.5 |  | Axis Y/01' y/02'' & y/03' from (X/02 - X/04) |  |  | 59.7 | m2 net area item 3.4
| 3.03 | 49.995
4)CARPENTRY
3 | 0.9 |  | D9(3Pcs) | 23 | 14.7 |  | 4.1)Uper & lower chord size 10-12cm
| 2.73 | -7.371 |  |  |  | 338.1 | L=7.35*2=14.70ml
2 | 5.5 |  | Axis Y/02 from (X/01 - X/02)& y/04(x/03-x/04) | 23 | 14.2 |  | No. truss=28.65/1.33+1=23pcs
| 2.73 | 30.03 |  |  |  | 326.6
2 | 5.5 |  | Axis y/03'& Y/04' from (X/01 - X/02) |  |  | 664.7 | m net length item 4.1
| 3.03 | 33.33
4.2)Vertical & Diagonal member
2 | 1.05 |  | Above top tie beam X/01 & X/04
| 13 | 27.3 |  | 23 | 14.62 |  | V = 14.62mt
[6 empty] | 336.26 | D = 18.64mt
2 | 28.95 |  | Above top tie beam Y/01 &x/06
| 0.2 | 11.58 |  | 23 | 18.64
428.72
|  | 435.272 | m2 net arae item 2.1
[6 empty] | 764.98 | m net length item 4.2
2.2)15cm thick HCB wall
3 | 5.1 |  | Axis X/02 & X/03 from (Y/01 - Y/05) |  |  |  | 4.3)Purlin zigba 5/7cm
| 3.03 | 46.359 |  |  |  |  | No .pur =7.26/0.9+1=9x2=18
|  |  |  | 18 | 29.85 |  | L=28.65+1.2=29.85mt
4 | 0.8 |  | D7(4Pcs) |  |  | 537.3 | m net length item 4.3
| 2.73 | -8.736
4.4) Zigba wooden fascia board
1 | 5.1 |  | Axis Y/05 from (X/01 - X/02) | 4 | 7.26
| 2.73 | 13.923 |  |  |  | 29.04
1 | 0.9 |  | D9(1Pcs) | 2 | 29.85
| 2.73 | -2.457 |  |  |  | 59.7
1 | 5.95 |  | Axis b/n x/03 &x/04 from (y/04' - y/06) |  |  | 88.74 | m net length item 4.4
| 3.03 | 18.0285
WOODEN DOOR
|  | 67.1175 | m2 net arae item 2.2 |  |  |  | 4.5)Type D7 ,Size 80/273
|  |  |  | 1 | 5
|  |  | 3)ROOFING WORK |  |  | 5 | pcs net number item 4.5
3.1)G-28 CIS Roof covering
1 | 14.2 |  | W=13.00+0.60X2=14.20mt |  |  |  | 4.6)Type D8 ,Size 70/273
| 29.85 |  | L=28.65+0.6X2=29.85mt | 1 | 5
|  | 423.87 | m2 net area item 3.1 |  |  | 5 | pcs net number item 4.6
|  |  | 3.2)G-28 Ribbed sheet ceiling |  |  |  | 4.7)Type D9 ,Size 90/273
2 | 29.85 |  |  | 1 | 2
| 0.6 | 35.82 |  |  |  | 2 | pcs net number item 4.7
4 | 7.26 | [5 empty] | 5)METAL WORK
| 0.6 | 17.424 |  | 12 | 1 |  | 5.1)Type W2 ,Size 150/273
[6 empty] | 12 | pcs net number item 5.1
|  | 53.244 | m2 net area item 3.2
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 5.2)Type W4 ,Size 130/273 | 2 | 0.9 |  | D9(2Pc)
4 | 1 |  |  |  | 2.73 | -4.914
|  | 4 | pcs net number item 5.1
|  |  |  | 1 | 26.2 |  | WASHING /FOOD PREPARATION
|  |  | 5.3)Type W15,Size 130/60 |  | 3.06 | 80.172 | L=5.10X2+8X2=26.20mt
2 | 1
|  | 2 | pcs net number item 5.3 | 3 | 1.5 |  | W2(3Pcs)
[5 empty] | 1.73 | -7.785
5.6)Type D2 ,Size 140/273
2 | 1 |  |  | 2 | 0.9 |  | D9(2Pc)
|  | 2 | pcs net number item 5.1 |  | 2.73 | -4.914
|  |  | 5.7)Type D3 ,Size 130/273 | 2 | 1.3 |  | D11(2Pcs)
4 | 1 |  |  |  | 2.73 | -7.098
|  | 4 | pcs net number item 5.1
|  |  |  | 2 | 16.6 |  | STORE 1 & 2
|  |  | 5.8)Type D6 ,Size 90/273 |  | 3.06 | 101.592 | L=5.10X2+3.20X2=16.60mt
1 | 1
|  | 1 | pcs net number item 5.1 | 2 | 1.5 |  | W2(2Pcs)
[5 empty] | 1.73 | -5.19
6.1)Apply two coats of plastering &
2 | 27.45 |  | one coat rendering | 2 | 0.9 |  | D9(2Pcs)
| 2.73 | 149.877 | Axis X/01 & x/04 from (Y/01 - Y/06) |  | 2.73 | -4.914
12 | 1.5 |  |  | 1 | 15.2 |  | OFFICE
| 1.63 | -29.34 | W2(12Pcs) |  | 3.06 | 46.512 | L=5.10X2+2.50X2=15.20mt
4 | 1.3 |  |  | 1 | 1.3 |  | W4(1Pcs)
| 1.63 | -8.476 | W4(4Pcs) |  | 1.73 | -2.249
4 | 1.3 |  |  | 1 | 0.9 |  | D9(1Pc)
| 2.73 | -14.196 | D3(4PCS) |  | 2.73 | -2.457
1 | 0.9 |  |  | 1 | 11.9 |  | Corridor
| 2.73 | -2.457 | D6(1Pc) |  | 3.06 | 36.414 | L=5.3x2+1.30=11.90mt
2 | 12.2 |  |  | 2 | 0.8 |  | D7(2Pc)
| 2.73 | 66.612 | Axis Y/01 & Y/06 from (X/01 - X/04) |  | 2.73 | -4.368
2 | 1.4 |  |  | 1 | 21.9 |  | CHANGING F. & M.
| 2.73 | -7.644 | D2(2Pc) |  | 3.06 | 67.014 | L=4.95X2+3X4=21.90mt
2 | 1.3 |  |  | 4 | 0.8 |  | D7(4Pc)
| 0.6 | -1.56 | W15(2Pc) |  | 2.73 | -8.736
2 | 1.05 |  | Above top tie beam X/01 & X/04 | 1 | 1.5 |  | W2(1Pcs)
| 13 | 27.3 |  |  | 1.73 | -2.595
|  | 180.116 | m2 net area item 6.1 | 1 | 42.8 |  | TOILET
[5 empty] | 2.73 | 116.844 | L=4.95X4+2.95X4+1.40X8=42.80mt
6.2)Apply three coats of plastering
|  |  | to internal wall & external beam & colu. | 2 | 0.8 |  | D7(2Pc)
1 | 16.2 |  | SERVER |  | 2.73 | -4.368
| 3.06 | 49.572 | L=5.10X2+3X2=16.20mt
|  |  |  | 4 | 1.55
1 | 1.3 |  | W4(1Pc) |  | 2.73 | 16.926
| 1.73 | -2.249
T | D | S | Item No. and Description | T | D | S | Item No. and Description
8 | 0.7 |  | D8(8Pc) | 1 | 0.9 |  | D9(1Pc)
| 2.73 | -15.288 |  |  | 2.73 | -2.457
2 | 1.3 |  | W15(2Pcs) | 1 | 18.8 |  | RECEIVING/ STORING
| 0.6 | -1.56 |  |  | 3.06 | 57.528 | L=5.10X2+4.30X2=18.80mt
1 | 60.5 |  | Corridor | 1 | 1.3 |  | D3(1PCS)
| 3.06 | 185.13 | L=28.25X2+2X2=60.50mt |  | 2.73 | -3.549
1 | 1.3 |  | OPENING | 1 | 0.9 |  | D9(1Pc)
| 2.73 | -3.549 |  |  | 2.73 | -2.457
2 | 1.4 |  |  | 1 | 1.3
| 2.73 | -7.644 | D2(2Pc) |  | 1.73 | -2.249 | W4
2 | 0.9 |  | D9(2Pcs) | 2 | 28.65
| 2.73 | -4.914 |  |  | 0.4 | 22.92 | GRADE BEAM
2 | 1.3 |  | D11(2Pcs) | 2 | 13
| 2.73 | -7.098 |  |  | 0.4 | 10.4 | GRADE BEAM
1 | 22 |  | CAFTRERIA | 20 | 2.63
| 3.06 | 67.32 | L=5.10X2+5.90X2=22.00mt |  | 0.2 | 10.52 | COLUMN
2 | 1.5 |  | W2(2Pcs) | 2 | 28.65
| 1.73 | -5.19 |  |  | 0.3 | 17.19 | TOP TIE BEAM
1 | 1.3 |  | D3(1PCS) | 2 | 13
| 2.73 | -3.549 |  |  | 0.3 | 7.8 | TOP TIE BEAM
1 | 25.4 |  | GENERAL STORE | 3 | 5.1 |  | EXPOSED BEAM
| 3.06 | 77.724 | L=5.10X2+7.60X2=25.40mt |  | 0.8 | 12.24 | Axis Y/02,Y/03 & Y/05 from (x/02 - X/04)
2 | 1.5 |  | W2(2Pcs) | 2 | 5.1 |  | Axis Y/03 & Y/04 from (x/01 - X/02)
| 1.73 | -5.19 |  |  | 0.8 | 8.16
1 | 1.3 |  | D3(1PCS) | 4 | 2 | 6.4 | CORRIDOR
| 2.73 | -3.549 |  |  | 0.8
1 | 22.2 |  | PHARMACY STORE | 1 | 1.3
| 3.06 | 67.932 | L=5.10X2+6.00X2=22.20mt |  | 0.5 | 0.65
2 | 1.5 |  | W2(2Pcs) |  |  | 44.64 | DDT Ceramic wall tiles
| 1.73 | -5.19
[6 empty] | 932.651 | m2 net area item 6.2
1 | 1.3 |  | D3(1PCS)
| 2.73 | -3.549 |  |  |  |  | 6.3)Chipwood ceiling
|  |  |  | 1 | 5.1 |  | SERVER
1 | 17.6 |  | LUNDARY |  | 3 | 15.3
| 3.06 | 53.856 | L=5.10X2+3.70X2=17.60mt
|  |  |  | 1 | 5.1 |  | WASHING /FOOD PREPARATION
1 | 0.9 |  | D6(1Pc) |  | 7.8 | 39.78
| 2.73 | -2.457
|  |  |  | 2 | 5.1 |  | STORE 1 & 2
1 | 1.3 |  | W4(1Pc) |  | 3.1 | 31.62
| 1.73 | -2.249
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 5.1 |  | OFFICE | 1 | 28.25 |  | Corridor
| 2.5 | 12.75 |  |  | 2 | 56.5
1 | 5.1 |  | Corridor | 1 | 5.1
| 1.3 | 6.63 |  |  | 5.9 | 30.09 | CAFTRERIA
1 | 5 |  | CHANGING F. & M. | 1 | 5.1
| 2.8 | 14 |  |  | 7.6 | 38.76 | GENERAL STORE
1 | 4.95 |  | TOILET | 1 | 5.1
| 2.95 | 14.6025 |  |  | 6 | 30.6 | PHARMACY STORE
1 | 27.45 |  | Corridor | 1 | 5.1
| 2 | 54.9 |  |  | 3.7 | 18.87 | LUNDARY
1 | 5.1 |  | CAFTRERIA | 1 | 5.1
| 5.9 | 30.09 |  |  | 4.3 | 21.93 | RECEIVING/ STORING
1 | 5.1 |  | GENERAL STORE | 2 | 1.4
| 7.4 | 37.74 |  |  | 0.2 | 0.56 | D2(2Pcs)
1 | 5.1 |  | PHARMACY STORE | 6 | 1.3
| 5.8 | 29.58 |  |  | 0.2 | 1.56 | D3(6Pcs)
1 | 5.1 |  | LUNDARY | 1 | 0.9
| 3.7 | 18.87 |  |  | 0.2 | 0.18 | D6(1Pc)
1 | 5.1 |  | RECEIVING/ STORING | 4 | 0.8
| 4.3 | 21.93 |  |  | 0.15 | 0.48 | D7(4Pcs)
|  | 327.7925 | m2 net area item 6.3 | 4 | 0.7
[5 empty] | 0.1 | 0.28 | D8(4Pcs)
6.5)Approved type 9mm thick ceramic floor t.
1 | 5.1 |  | SERVER | 4 | 0.9
| 3 | 15.3 |  |  | 0.2 | 0.72 | D9(6Pcs)
1 | 5.1 |  | WASHING /FOOD PREPARATION | 2 | 1.3
| 8 | 40.8 |  |  | 0.2 | 0.52 | D11(2Pcs)
2 | 5.1 |  | STORE 1 & 2 |  |  | 338.8405 | m2 net area item 6.5
| 3.2 | 32.64
6.6)Approved type 9mm thick ceramic Skirting
1 | 5.1 |  | OFFICE
| 2.5 | 12.75 |  | 1 | 14.4 |  | SERVER
[6 empty] | 14.4 | L=5.10X2+3X2-0.9x2=14.40mt
1 | 5.3 |  | Corridor
| 1.3 | 6.89 |  | 1 | 21.8 |  | WASHING /FOOD PREPARATION
[6 empty] | 21.8 | L=5.10X2+8X2-1.3x2-0.9x2=21.80mt
1 | 4.95 |  | CHANGING F. & M.
| 3 | 14.85 |  | 1 | 14.8 |  | STORE 1
[6 empty] | 14.8 | L=5.10X2+3.20X2-0.9x2=14.80mt
1 | 4.95 |  | TOILET
| 1.55 | 7.6725 |  | 1 | 15.7 |  | STORE 2
[6 empty] | 15.7 | L=5.10X2+3.20X2-0.9=15.70mt
4 | 1.4
| 1.23 | 6.888 |  | 1 | 14.3 |  | OFFICE
[6 empty] | 14.3 | L=5.10X2+2.50X2-0.9=14.30mt
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 10.3 |  | Corridor |  |  |  | Deduction
|  | 10.3 | L=5.3x2+1.30-0.8x2=10.30mt | 3 | 1.7 |  | Ramp
5.1
2 | 18.7 |  | CHANGING F. & M.
|  | 37.4 | L=4.95X2+3X4-0.8x4=18.70mt |  |  | 5.1 | m total deduction
1 | 52 |  | Corridor |  |  | 74.6 | m net length item 6.12
|  | 52 | L=28.25X2+2X2-1.3-1.3x2-1.4x2-0.9x2=52.00mt
7)PAINTING
1 | 20.7 |  | CAFTRERIA |  |  |  | 7.1)Internal plastered surface & external beam & column
|  | 20.7 | L=5.10X2+5.90X2-1.3=20.70mt
|  |  |  | 1 | 932.651 |  | Ditto Item no 6.2
1 | 24.1 |  | GENERAL STORE |  |  | 932.651 | m2 net area item 7.1
|  | 24.1 | L=5.10X2+7.60X2-1.3=24.10mt
7.2)Chip wood ceiling surface
1 | 20.9 |  | PHARMACY STORE | 1 | 327.7925 |  | Ditto Item no 6.3
|  | 20.9 | L=5.10X2+6.00X2-1.3=20.90mt |  |  | 327.7925 | m2 net area item 7.2
1 | 15.8 |  | LUNDARY |  |  |  | 7.3)External rendered surface
|  | 15.8 | L=5.10X2+3.70X2-0.9x2=15.80mt | 1 | 180.116 |  | Ditto Item no 6.1
[6 empty] | 180.116 | m2 net area item 7.3
1 | 16.6 |  | RECEIVING/ STORING
|  | 16.6 | L=5.10X2+4.30X2-0.9-1.3=16.60mt |  |  |  | 9)SANITARY INSTALLATION
9.10)Supplay & install PP-R water pipe
|  | 278.8 | m net length item 6.6 | 1 | 31.56 |  | Internal ф 15mm
[6 empty] | 31.56 | m net length item 9.1.a
6.7- Terrazo window cill
Internal ф 25mm
6 | 1.3 |  | W4 & W15 | 1 | 33.03
|  | 7.8 |  |  |  | 33.03 | m net length item 9.1.c
12 | 1.5 | [5 empty] | 9.3)Supply & fix bronze gate valve
|  | 18 |  | 1 | 5 |  | 15mm diameter
[6 empty] | 5 | no net number item 9.3
|  | 25.8 | m net length item 6.7
9.5)Supply & install waste water pipe
|  |  | 6.9)10cm thick C-20 RC 1.2mt wide |  |  |  | made of rigid UPVC
|  |  | pavement |  |  |  | ф 50mm
2 | 29.85 |  | L=28.65+1.20=29.85mt | 1 | 53.21
| 1.2 | 71.64 |  |  |  | 53.21 | m net length item 9.5.a
1 | 13 |  |  | 1 | 13.45 |  | ф 75mm
| 1.2 | 15.6 |  |  |  | 13.45 | m net length item 9.5.b
|  | 87.24 | m2 net area item 6.9 | 1 | 20.55 |  | ф 100mm
[6 empty] | 20.55 | m net length item 9.5.c
6.12- Half Ditch
2 | 31.85 |  | Left & Right Side
63.7
1 | 16 |  | Rare side
16
|  | 79.7 | m before deduction
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 10. ELECTRICAL INSTALLATION |  |  |  | 6)Telephone/data point
|  |  | 2)LIGHT POINT |  |  |  | 6.01)Telephone point feed through
|  |  | 2.1points conduti of 16mm 3*2.5mm2 | 6 | 1 |  | cat 5E UTP Cable
45 | 1 |  |  |  |  | 6 | no net number item 6.01
|  | 45 | no net number item 2.01
|  |  |  | 6 | 1 |  | 6.3. outlets RJ11 type
|  |  | 3)SWITCH |  |  | 6 | no net number item 6.03
3.01)Single Switch legrand
10 | 1 | [5 empty] | 7. Type of light fittings
|  | 10 | no net number item 3.01 | 10 | 1 |  | 7.01)Philips TCS 098/236/2xTL-D 36W
[6 empty] | 10 | no net number item 7.01
3.02)Double Switch legrand
9 | 1 | [5 empty] | 7.02)Philips TCS 098/136/1xTL-D 36W
|  | 9 | no net number item 3.02 | 16 | 1
[6 empty] | 16 | no net number item 7.02
4.)Socket outlet point
|  |  | 4.01)Socket outlet point 3x2.5mm2 |  |  |  | 7.03)RZB 59251.002Q/E27/60W
26 | 1 |  |  | 6 | 1
|  | 26 | no net number item 4.01 |  |  | 6 | no net number item 7.03
|  |  | 4.02)Socket outlet water heater |  |  |  | 7.04)RZB 59222.002Q/E27/60W
3 | 1 |  |  | 2 | 1
|  | 3 | no net number item 4.02 |  |  | 2 | no net number item 7.04
|  |  | 4.03)Socket outlet 3ph point 4x2.5mm2 |  |  |  | 7.05)Philips TMW 065/236 1 IMK
2 | 1 |  |  | 8 | 1
|  | 2 | no net number item 4.03 |  |  | 8 | no net number item 7.05
|  |  | 4.04)Socket outlet 3ph point 4x4mm2 |  |  |  | 8)TV POINTS
3 | 1 | [5 empty] | 8.01)TV point fed through RG6
|  | 3 | no net number item 4.04 | 1 | 1 |  | Coaxial 75ohm Tv cable
[6 empty] | 1 | no net number item 8.01
4.05)Socket outlet 3ph point3x6mm2
2 | 1 | [5 empty] | 10.04 Cable way & manhole
|  | 2 | no net number item 4.05 |  |  |  | riged pvc pipe dia.50mm To telephone
|  |  |  | 1 | 37.4
|  |  | 5)Socket outlets |  |  | 37.4 | m net length item 10.04
5.01)Socket outlets LEGRAND SUNO
26 | 1
|  | 26 | no net number item 5.01
5.02 ditto as above but 3 phase socket in 4x4mm2
3 | 1
|  | 3 | no net number item 5.02
5.03 weather proof socket Legrand suno
2 | 1
|  | 2 | no net number item 5.03
5.06 Ditto as above but for 25A/1ph for kithcen
3 | 1
|  | 3 | no net number item 5.04
5.07 Ditto as above but for 20A/3ph for kithcen
2 | 1
|  | 2 | no net number item 5.05

## Kit. Rein.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction | [9 empty] | Block : Kitchen
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 & GB2 | 14 | 9.88 | 4 | 3 | 12 |  |  |  |  | 118.56
|  |  | 14 | 11.48 | 4 | 3 | 12 |  |  |  |  | 137.76
|  |  | 14 | 9.25 | 4 | 3 | 12 |  |  |  |  | 111
|  |  | 14 | 10.1 | 4 | 3 | 12 |  |  |  |  | 121.2
|  |  | 14 | 9.45 | 4 | 3 | 12 |  |  |  |  | 113.4
|  |  | 14 | 11.35 | 4 | 3 | 12 |  |  |  |  | 136.2
|  |  | 8 | 1.2 | 144 | 4 | 576 |  | 691.2
|  | GB3 & GB4 | 14 | 7.16 | 6 | 3 | 18 |  |  |  |  | 128.88
|  |  | 14 | 7.2 | 6 | 3 | 18 |  |  |  |  | 129.6
|  |  | 14 | 7.91 | 6 | 3 | 18 |  |  |  |  | 142.38
|  |  | 14 | 5.85 | 6 | 3 | 18 |  |  |  |  | 105.3
|  |  | 8 | 1.2 | 66 | 6 | 396 |  | 475.2
|  |  |  | TOTAL LENGTH |  |  |  |  | 1166.4 | 0 | 0 | 1244.28
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 460.728 | 0 | 0 | 1505.5788
| CONTRACTOR | [8 empty] | SUPERVISOR
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
GROUND FLOOR MESH
| (x/01-x/02) & (x/03-x/04) |  | 8 | 5.85 | 2 | 26 | 52 |  | 304.2
| (y/01 - y/02) |  | 8 | 5.05 | 2 | 30 | 60 |  | 303
| (x/01-x/02) & (x/03-x/04) |  | 8 | 5.75 | 6 | 26 | 156 |  | 897
| (y/02 - y/05) |  | 8 | 5.05 | 6 | 30 | 180 |  | 909
| (x/01-x/02) & (x/03-x/04) |  | 8 | 4.02 | 2 | 26 | 52 |  | 209.04
| (y/05 - y/06) |  | 8 | 4.97 | 2 | 21 | 42 |  | 208.74
| (x/02-x/03) (y/01 - y/02) |  | 8 | 5.77 | 1 | 10 | 10 |  | 57.7
|  |  | 8 | 1.87 | 1 | 30 | 30 |  | 56.1
| (x/02-x/03) (y/02 - y/05) |  | 8 | 5.67 | 3 | 20 | 60 |  | 340.2
|  |  | 8 | 1.87 | 3 | 29 | 87 |  | 162.69
| (x/02-x/03) (y/05 - y/06) |  | 8 | 4.02 | 1 | 10 | 10 |  | 40.2
|  |  | 8 | 1.87 | 1 | 21 | 21 |  | 39.27
|  |  |  | TOTAL LENGTH |  |  |  |  | 3527.14 | 0 | 0 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 1393.2203 | 0 | 0 | 0
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| COLUMN (C1) |  | 12 | 3.68 | 4 | 22 | 88 |  |  |  | 323.84
|  |  | 8 | 0.9 | 15 | 22 | 330 |  | 297
|  |  | 14 | 3.68 | 4 | 2 | 8 |  |  |  |  | 29.44
|  |  | 8 | 0.7 | 15 | 2 | 30 |  | 21
| TTB1 |  | 12 | 9.78 | 2 | 4 | 8 |  |  |  | 78.24
|  |  | 12 | 11.48 | 2 | 4 | 8 |  |  |  | 91.84
|  |  | 12 | 9.15 | 2 | 4 | 8 |  |  |  | 73.2
|  |  | 12 | 10.1 | 2 | 3 | 6 |  |  |  | 60.6
|  |  | 12 | 9.45 | 2 | 3 | 6 |  |  |  | 56.7
|  |  | 12 | 11.35 | 2 | 3 | 6 |  |  |  | 68.1
|  |  | 8 | 0.9 | 2 | 143 | 286 |  | 257.4
| TTB2 |  | 12 | 9.78 | 2 | 3 | 6 |  |  |  | 58.68
|  |  | 12 | 11.48 | 2 | 3 | 6 |  |  |  | 68.88
|  |  | 12 | 9.15 | 2 | 3 | 6 |  |  |  | 54.9
|  |  | 12 | 10.1 | 2 | 3 | 6 |  |  |  | 60.6
|  |  | 12 | 9.45 | 2 | 3 | 6 |  |  |  | 56.7
|  |  | 12 | 11.35 | 2 | 3 | 6 |  |  |  | 68.1
|  |  | 8 | 0.9 | 2 | 143 | 286 |  | 257.4
| TTB3&TTB4 |  | 12 | 7.06 | 6 | 3 | 18 |  |  |  | 127.08
|  |  | 12 | 7.1 | 6 | 3 | 18 |  |  |  | 127.8
|  |  | 12 | 7.91 | 6 | 3 | 18 |  |  |  | 142.38
|  |  | 12 | 5.85 | 6 | 3 | 18 |  |  |  | 105.3
|  |  | 8 | 0.9 | 6 | 65 | 390 |  | 351
| D7 |  | 12 | 1.45 | 2 | 2 | 4 |  |  |  | 5.8
|  |  | 12 | 1.15 | 2 | 2 | 4 |  |  |  | 4.6
|  |  | 8 | 0.6 | 2 | 7 | 14 |  | 8.4
| D8 |  | 12 | 1.35 | 2 | 2 | 4 |  |  |  | 5.4
|  |  | 12 | 1.05 | 2 | 2 | 4 |  |  |  | 4.2
|  |  | 8 | 0.5 | 2 | 6 | 12 |  | 6
| D9 |  | 12 | 1.55 | 4 | 2 | 8 |  |  |  | 12.4
|  |  | 12 | 1.25 | 4 | 2 | 8 |  |  |  | 10
|  |  | 8 | 0.7 | 4 | 7 | 28 |  | 19.6
| D7 |  | 12 | 2.45 | 1 | 2 | 2 |  |  |  | 4.9
|  |  | 12 | 2.15 | 1 | 2 | 2 |  |  |  | 4.3
|  |  | 8 | 0.6 | 1 | 12 | 12 |  | 7.2
| D8 |  | 12 | 2.2 | 1 | 2 | 2 |  |  |  | 4.4
|  |  | 12 | 1.9 | 1 | 2 | 2 |  |  |  | 3.8
|  |  | 8 | 0.5 | 1 | 11 | 11 |  | 5.5
|  |  |  | TOTAL LENGTH |  |  |  |  | 1230.5 |  | 1682.74 | 29.44
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 486.0475 | 0 | 1494.2731 | 35.6224
| CONTRACTOR | [8 empty] | SUPERVISOR
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15

## Gua. Sum.
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau |  |  |  |  | Page - ___
Location : Wegeda
Contractor :- Trust Consteraction
Block:-Guard House
Details of Works executed
Bill No. | Description |  | Sub Total Birr |  | Total Birr
|  |  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  |  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work |  | 25732 | 2112.5 | 25732 | 2112.5
2 | Concrete Work |  | 24492 | 18301.6 | 24492 | 18301.6
3 | Masonry work |  | 11300 | 6510 | 11300 | 6510
| sub total A |  | 61524 | 26924.1 | 61524 | 26924.1
| B. Super Structure |  |  |  | 0 | 0
1 | Concrete Work |  | 12384 | 15075.7704 | 12384 | 15075.7704
2 | Block work |  | 22330 | 18294.6 | 22330 | 18294.6
3 | Roofing |  | 17850 | 10063.5 | 17850 | 10063.5
4 | Carpentary & Joinery |  | 3776 | 3194 | 3776 | 3194
5 | Metal work |  | 19615.5 | 0 | 19615.5 | 0
6 | Finishing |  | 45210 | 33598.7 | 45210 | 33598.7
7 | Painting |  | 2548 | 3950.68 | 2548 | 3950.68
8 | Glazing |  | 4500 | 0 | 4500 | 0
9 | Sanitory Installation |  | 0 |  | 0
10 | Electrical Installation |  | 9450 | 1800 | 9450 | 1800
| sub total B |  | 137663.5 | 85977.2504 | 137663.5 | 85977.2504
| Total A+B |  | 199187.5 | 112901.3504 | 199187.5 | 112901.3504
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  | Suppervisor :- ______________ |  |  | Consultant:- _____________

## Gua. Meas.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise
CONTRACTOR:-Trust Construction |  |  |  |  | Block : Guard House
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | Qty | Rate | Amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 39 | 50 | 1950 | 42.25 | 2112.5
1.2 | Bulk excavation in ordinary | m3 | 58.5 | 50 | 2925 | 20.01 | 1000.5
1.3 | Ditto but exceeding 1.5 m but less than 2 m | m3 | 19.5 | 40 | 780 |  | 0
1.3 | Selected borrowed fill brought from out side | m3 | 78 | 40 | 3120 | 15.52 | 620.8
1.4 | Cart away surplus excavated material to an | m3 | 78 | 15 | 1170 | 32.68 | 490.2
1.5 | 25cm thick basaltic or equivalent stone hard | m2 | 14 | 280 | 3920 | 16.25 | 4550
| Total to summary ………Birr |  |  |  | 13865 |  | 8774
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 8 | 180 | 1440 | 7.2 | 1296
2.2 | 10cm thick reinforced concrete floor slab class | m2 | 14 | 350 | 4900 | 12.6 | 4410
2.3 | In grade beam & steps | m3 | 2 | 2400 | 4800 | 2.04 | 4896
Provide cut and fix in position swan zigba wood
form work or metal panel. To:-
2.4 | Grade beam | m2 | 15 | 150 | 2250 | 12.32 | 1848
2.5 | Steps | m2 | 2 | 150 | 300 | 2.7 | 405
Reinforcement steel bar according to St.drawing
price includes cutting, bending, placing in
position and tying wires.
2.6 | Dia 16 mm deformed bar | kg | 122 | 32 | 3904 |  | 0
2.6 | Dia. 12mm deformed bar | kg |  |  | 0 | 105.49 | 0
2.7 | Dia 8 mm deformed bar | kg | 115 | 35 | 4025 | 139.16 | 4870.6
2.8 | Dia 6 mm plain bar | kg | 0 |  | 0 |  | 0
2.9 | 10/2 cm chip wood expansion joint between | m | 22 | 40 | 880 | 14.4 | 576
| Total to summary ………Birr |  |  |  | 22499 |  | 18301.6
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 8 | 1000 | 8000 | 3.9 | 3900
3.2 | Ditto but well dressed stone above natural grou. | m3 | 3 | 1500 | 4500 | 1.74 | 2610
| Total to summary ………Birr |  |  |  | 12500 |  | 6510
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 0.54 | 2400 | 1296 | 0.4368 | 1048.32
1.2 | In beams | m3 | 1 | 2400 | 2400 | 1.068 | 2563.2
| Provide cut and fix in position swan zigzag wood |  |  |  | 0 |  | 0
1.3 | Elevation column | m2 | 8.72 | 150 | 1308 | 8.736 | 1310.4
1.4 | Beam | m2 | 16 | 150 | 2400 | 14.08 | 2112
Reinforcement steel bar according to St.drawing
position and tying wires.
1.5 | Dia 14mm deformed bar | kg
1.6 | Dia 12mm deformed bar | kg | 66 | 35 | 2310 | 169.5014 | 5932.5504
1.7 | Dia 8mm deformed bar | kg | 55 | 40 | 2200 | 52.7325 | 2109.3
1.8 | Dia 6 mm plain bar | kg | 3 |  | 0 |  | 0
| Total to summary ………Birr |  |  |  | 11914 |  | 15075.7704
2. BLOCK WORK
2.1 | 20cm thick | m2 | 56 | 300 | 16800 | 60.982 | 18294.6
2.2 | 10 cm thick | m2 | 16 | 300 | 4800 |  | 0
| Total to summary ………Birr |  |  |  | 21600 |  | 18294.6
3.ROOFING
3.1 | Roof covering in galvanized corrugated | m2 | 30 | 300 | 9000 | 23.78 | 7134
3.2 | G - 28 ribbed sheet ceiling under eave | m2 | 20 | 320 | 6400 | 2.9 | 928
3.3 | Supply and fix G-28 flat metal sheet gutter | m | 11 | 200 | 2200 | 5.8 | 1160
3.4 | Flushing in flat metal sheet fixed as shown | m | 22 | 90 | 1980 | 9.35 | 841.5
| Total to summary ………Birr |  |  |  | 19580 |  | 10063.5
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 44 | 25 | 1100 | 40 | 1000
4.2 | Diagonal & vertical members size-dia. 8 - 10 cm | m | 27 | 20 | 540 | 31.2 | 624
4.3 | Purlin zigba size 5/7cm | m | 47 | 30 | 1410 | 36 | 1080
4.4 | Ziba wooden fascia board price includes three coats | m | 11 | 70 | 770 | 7 | 490
| Total to summary ………Birr |  |  |  | 3820 |  | 3194
5. METAL WORK
Windows
5.1 | Type W1 size-78/163cm | Nº | 3 | 1100 | 3300 |  | 0
| Type D3 size - 78/33 cm | Nº | 2 | 2500 | 5000 |  | 0
| Doors |  |  |  | 0 |  | 0
5.4 | Type D1 size - 78/243 cm | Nº | 2 | 1500 | 3000 |  | 0
| Type D2 size 68/243 cm | Nº | 3 | 1400 | 4200 |  | 0
| Total to summary ………Birr |  |  |  | 15500 |  | 0
6. FINISHING
6.1 | Apply two coats of plastering and one coat of rendering | m2 | 33 | 150 | 4950 | 39.426 | 5913.9
6.2 | Apply three coats of plastering to internal walls & external | m2 | 52 | 150 | 7800 | 93.112 | 13966.8
6.4 | Chip wood ceiling nailed on & including | m2 | 14 | 200 | 2800 | 16.3 | 3260
6.1 | Approved type 2cm thick terrazzo tile flooring | m2 | 14 | 280 | 3920 |  | 0
6.11 | Approved type10/2cm terrazzo tile skirting | m | 27 | 150 | 4050 |  | 0
6.16 | Terazo window cill Size 27/3 cm | m | 4 | 150 | 600 |  | 0
6.21 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 42 | 360 | 15120 | 29.05 | 10458
| Total to summary ………Birr |  |  |  | 39240 |  | 33598.7
7. PAINTING
7.1 | External rendered surface | m2 | 33 | 30 | 990 | 39.426 | 1182.78
7.1 | Internal plastered surfaceand external beams& | m2 | 47 | 25 | 1175 | 93.112 | 2327.8
7.3 | Chip wood ceiling surface | m2 | 14 | 27 | 378 | 16.3 | 440.1
| Total to summary ………Birr |  |  |  | 2543 |  | 3950.68
8. GLAZING
8.2 | 4mm thick frosted glass | m2 | 20 | 280 | 5600 |  | 0
| Total to summary ………Birr |  |  |  | 5600 |  | 0
8 | Electrical Installations
8.1 | Supply and install surface mounted sub distribution board | No | 1 | 1300 | 1300 |  | 0
8.2 | Light Points |  |  |  | 0 |  | 0
8.2.1 | Light points feed through PVC insulated cooper conductor | No | 6 | 250 | 1500 | 6 | 1500
8.2.2 | Extra over light points flush/surface mounted legrand |  |  |  | 0 |  | 0
| a) Single pole switch | No | 2 | 40 | 80 |  | 0
| b) Two circute switch | No | 1 | 40 | 40 |  | 0
| c) Two way switches | No | 2 | 40 | 80 |  | 0
8.3 | Socket Out Lets( Siements Shuko type) legrand mosaic plate |  |  |  | 0 |  | 0
8.3.1 | Flush mounted socket out let of 10/16 A ( 1- ph ) with | No | 3 | 300 | 900 | 1 | 300
| Tele phone system |  |  |  | 0 |  | 0
| and mechanism complete with clip on support frame and labling accessories. | No | 1 | 600 | 600 |  | 0
| b) Telephone point feed through pair of telephone cable | No | 1 | 200 | 200 |  | 0
8.4 | Light Fittings and Lamps( Specified or Equivalent). |  |  |  | 0 |  | 0
| Phillips TMS 012/118i MK ll 1*TL - D18W/840 | No | 1 | 400 | 400 |  | 0
| RZB 611010.002 + E27 PLE - T 20W | No | 4 | 400 | 1600 |  | 0
| RZB 31650.002. Q + A60 75W | No | 1 | 300 | 300 |  | 0
| Earthing System |  |  |  | 0 |  | 0
| a) Earthing rode of diametre 16mm | No | 2 | 2000 | 4000 |  | 0
| b) Earthing cable of 1*6mm2 | ml | 8 | 300 | 2400 |  | 0
| Total Carried to Summary |  |  |  | 13400 |  | 1800

## Meas Guard edted (hidden)
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise |  |  |  |  | Page No. :-
CONTRACTOR:-Trust Construction |  |  |  |  | Block : kitchen
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | executed
|  |  | Qty | Rate | amount | Qty | amount
A SUB STRUCTURE
1. Excavation & Earth Work
1.1 | Clear off site to remove top soil at an avg.depth of 30 cm | m2 | 39 | 8 | 312 |  |  | 0
1.2 | Bulk excavation in ordinary soil to a depth not exceeding 1.5m starting soil to a depth not exceeding 1.5m starting from reduced level | m3 | 58.5 | 70 | 4095 |  |  | 0
1.3 | Ditto but exceeding 1.5m less than 2m | m3 | 19.5 | 70 | 1365 |  |  | 0
1.4 | Selected borrowed fill brought from out side under hard core | m3 | 78 | 150 | 11700 |  |  | 0
1.5 | Cart away surplus excavated material to an appropriate tip | m3 | 78 | 70 | 5460 |  |  | 0
1.6 | 25 cm thick basaltic or equivalent stone hard core well ralled consoliated and blinded withcrushed stones. | m2 | 14 | 200 | 2800 |  |  | 0
Total carried to summary |  |  |  |  | 25732 |  |  | 0
| 2. CONCRETE WORKS | [6 empty] | 0
2.1 | 5cm thick lean concrete class C-7 with a minimum cement content of 150kg/m3 under masonry foundation | m2 | 8 | 150 | 1200 |  |  | 0
2.2 | 10cm thick reinforced concrete floor slab class C-20, with minimum cement content of 320kg/m3 well spread and leveled steel bar m. separately) | m2 | 14 | 400 | 5600 |  |  | 0
| Reinforced concrete class C-25 with minimum cement content of 360kg/m3 filled into form work and vibrated around rod reinforcement. Steel bar and form work measured separately | [6 empty] | 0
2.3 | In grade beam & step | m3 | 2 | 3200 | 6400 |  |  | 0
| Provide, cut and fix in position swan zigzag wood form work or metal panel To:- | [6 empty] | 0
2.4 | In grade beam | m2 | 2 | 150 | 300 |  |  | 0
2.5 | Steps | m2 | [5 empty] | 0
| Reinforcement steel bar according to St. drawing price includes cutting bending placing in position and tying wires | [6 empty] | 0
2.6 | Dia. 14mm deformed bar | Kg | 122 | 36 | 4392 |  |  | 0
2.7 | Dia. 12mm deformed bar | Kg | 0 | 0 | 0 |  |  | 0
2.8 | Dia. 8 mm deformed bar | Kg | 115 | 36 | 4140 |  |  | 0
2.9 | 10/2 cm chip wood expansion joint between grade beam and slab painted with two coats of asphalt | m | 22 | 30 | 660 |  |  | 0
Total carried to summary |  |  |  |  | 22692 |  |  | 0
| 3. Masonry Work | [6 empty] | 0
3.1 | Trychltic or equivalent stone masonry foundation wall bedded in cement mortar 1:3 | m3 | 8 | 1000 | 8000 |  |  | 0
3.2 | Ditto but above natural ground level externally left for pointing (price includes pointing) | m3 | 3 | 1100 | 3300 |  |  | 0
Total carried to summary |  |  |  |  | 11300 |  |  | 0
| B. SUPER STRUCTURE | [6 empty] | 0
| 1. CONCRETE WORKS | [6 empty] | 0
| Reinforced concrete class C-25, with minimum cement content of 360kg/m3 filled into form work and vibrated around rod reinforcement steel bar and form work measured separately | [6 empty] | 0
1.1 | In elevation column | m3 | 0.5 | 3200 | 1600 | 0.4368 |  | 0
1.2 | In beams & steps | m3 | 1 | 3200 | 3200 | 1.068 |  | 0
| Provide, cut and fix in position swan zigzag wood form work or metal panel To:- | [6 empty] | 0
1.3 | In elevation column | m2 | 8 | 130 | 1040 | 8.736 |  | 0
1.4 | In beams | m2 | 16 | 130 | 2080 | 14.08 |  | 0
| Reinforcement steel bars according to structural drawing. Price includes cutting, bending, placing in position and tying wires. |  |  |  | 0 |  |  | 0
1.5 | Dia. 14mm deformed bar | Kg | 66 | 36 | 2376 |  |  | 0
1.6 | Dia. 12mm deformed bar | Kg | 55 | 36 | 1980 | 169.5014 |  | 0
1.7 | Dia. 8 mm deformed bar | Kg | 3 | 36 | 108 | 52.7325 |  | 0
Total carried to summary |  |  |  |  | 12384 |  |  | 0
| 2. Block Work | [6 empty] | 0
2.1 | 20 cm thick | m2 | 51 | 350 | 17850 | 60.982 |  | 0
2.2 | 15 cm thick | m2 | 14 | 320 | 4480 |  |  | 0
Total carried to summary |  |  |  |  | 22330 |  |  | 0
| 3- Roofing | [6 empty] | 0
3.1 | G-28 C.I.S roof covering (roof cover measured in horizontal projection & purlin measured separately | m2 | 30 | 360 | 10800 | 23.78 |  | 0
3.2 | G-28 Ribbed Sheet ceiling under eave nailed to zigba purlins price shall include 40x50mm Zigba wood | m2 | 20 | 160 | 3200 | 2.9 |  | 0
3.3 | Supply and fix G-28 flat metal sheet gutter as per the detail drawing. Price shall include metal bracket | m | 11 | 110 | 1210 | 5.8 |  | 0
3.4 | Flashing in flat metal sheet fixed as shown development length 33cm | m | 22 | 120 | 2640 | 9.35 |  | 0
Total carried to summary |  |  |  |  | 17850 |  |  | 0
| 4. Carpentry and Joinery | [6 empty] | 0
4.1 | Upper and lower chord size diameter 10-12 | m | 44 | 23 | 1012 | 40 |  | 0
4.2 | Diagonal &vertical member size diameter 8-10 cm | m | 27 | 16 | 432 | 31.2 |  | 0
4.3 | purlin zigba size 5\7 cm thick | m | 47 | 33 | 1551 | 36 |  | 0
4.4 | Zigba wooden Fascia board price includes three coats of weather resistance paint supply & fix 40mm thick wood | m | 11 | 71 | 781 | 7 |  | 0
Total carried to summary |  |  |  |  | 3776 |  |  | 0
| 6. Finishing | [6 empty] | 0
6.1 | Apply two coats of plastering and one coat of rendering to external walls | m2 | 30 | 140 | 4200 | 39.426 |  | 0
6.2 | Apply three coats of plastering to internal walls & external columns and beams. | m2 | 47 | 150 | 7050 | 93.112 |  | 0
6.3 | Chip wood ceiling nailed on & including 4/5cm zigba batten on both ways at c/c 60cm | m2 | 14 | 310 | 4340 | 16.3 |  | 0
6.5 | Approved type 2mm thick terrazzo tile flooring bedded on and including 3cm thick cement mortar | m2 | 14 | 370 | 5180 |  |  | 0
6.5 | Approved type 10/2cm terrazzo tile skirting bedded on and including cement mortar backing | m | 27 | 35 | 945 |  |  | 0
6.16 | Approved type Terrazzo window cill bedded on cement mortar Size 27/3cm | ml | 4 | 150 | 600 |  |  | 0
6.21 | 10cm thick C-20 RC 1.2m wide pavement (including 4Ø 8 deformed bar mesh, expansion joint at every 1.2m length, 80cm | ml | 42 | 530 | 22260 | 29.05 |  | 0
Total carried to summary |  |  |  |  | 44575 |  |  | 0
0

## Gua. Sub TOS
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Guard Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
T | D | S | Item No. and Description | T | D | S | Item No. and Description
#REF!

## Gua. Super TOS
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Guard House
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 1 | 5.8
|  |  | 1.CONCRETE WORK |  | 0.2 | 1.16
1.1)In elevation column
4 | 2.73 |  | C1=4Pcs | 2 | 3.5 |  | Axis y
| 0.2 |  |  |  | 0.73 | 5.11
0.2
|  | 0.4368 | m3 net area item 1.1 | 1 | 0.8 |  | W1(1Pcs)
[5 empty] | 1.63 | -1.304
1.2)In beam & step
2 | 5.8 |  | TTB1=2Pcs | 2 | 0.7
| 0.3 |  | Axis x/01 & x/02 from (y/01 - y/02) |  | 2.73 | -3.822
| 0.2 | 0.696
[6 empty] | 60.982 | m2 net area item 2.1
2 | 3.1 |  | TTB2=2Pcs
| 0.3 |  | Axis y/01 & y/02 from ( y/01 - y/02) |  |  |  | 3)ROOFING WORK
| 0.2 | 0.372 |  |  |  |  | 3.1)G-28 CIS Roof covering
|  |  |  | 1 | 5.8 |  | W=5.80mt
|  | 1.068 | m3 net area item 1.2 |  | 4.1 |  | L=3.50+0.60=4.10mt
[6 empty] | 23.78 | m2 net area item 3.1
FORM WORK
|  |  | 1.3)Elevation column |  |  |  | 3.2)G-28 Ribbed sheet ceiling
4 | 2.73 |  | C1 =4PCS | 1 | 5.8
| 0.8 |  |  |  | 0.5
|  | 8.736 | m3 net area item 1.3 |  |  | 2.9 | m2 net area item 3.2
|  |  | 1.4)In beam |  |  |  | 3.3)Supply & fix G-28 gutter dev.
2 | 5.4 |  | TTB1=2Pcs | 1 | 5.8
| 0.8 | 8.64 | Axis x/01 & x/02 from (y/01 - y/06) |  |  | 5.8 | m2 net area item 3.3
2 | 3.1 |  | TTB2=2Pcs |  |  |  | 3.4)Flashing in metal sheet
| 0.8 | 4.96 | Axis x/02 & x/03 from ( y/01 - y/06) | 1 | 3.55
3.55
8 | 0.2
| 0.3 | 0.48 |  | 1 | 5.8
5.8
|  | 14.08 | m3 net area item 1.4
[6 empty] | 9.35 | m2 net area item 3.4
1.6)ф12mm deformed bar
|  | 169.5014 | kg net weight item 1.6 |  |  |  | 4)CARPENTRY
4.1)Uper & lower chord size 10-12cm
|  |  | 1.7)ф8mm deformed bar |  |  |  | L=4.20+3.8=8.00ml
|  | 52.7325 | kg net weight item 1.7 | 5 | 8 |  | No. truss=6.00/1.33+1=5pcs
[6 empty] | 40 | m net length item 4.1
2)BLOCK WORK
|  |  | 2.1)20cm thick HCB wall | 5 | 6.24 |  | 4.2)Vertical & Diagonal member
2 | 5.4 |  | Axis x |  |  | 31.2 | m net length item 4.2
| 2.73 | 29.484
4.3)Purlin zigba 5/7cm
2 | 3.1 |  | Axis y | 6 | 6 |  | No .pur =4.2/0.9+1=6mt
| 2.73 | 16.926 |  |  |  | 36 | m net length item 4.3
1 | 2 | [5 empty] | 4.4)Zigba wooden fascia board
| 3.06 | 6.12 |  | 1 | 5.8
|  |  | above top tie beam |  |  | 5.8
1 | 5.8 |  | Axis x | 2 | 0.6
| 1.26 | 7.308 |  |  |  | 1.2
[6 empty] | 7 | m net length item 4.4
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 6.1)Apply two coats of plastering & |  |  |  | 6.4)Chipwood ceiling
|  |  | one coat rendering | 1 | 2.75
1 | 5.6 |  | Axis x/01 from (y/01 - y/02) |  | 2 | 5.5
| 2.73 | 15.288
|  |  |  | 1 | 2.6
1 | 5.8 |  | Axis x/02 from (y/01 - y/02) |  | 2 | 5.2
| 1.26 | 7.308
|  |  |  | 1 | 1
2 | 3.1 |  | W1(1Pcs) |  | 5.6 | 5.6
| 2.73 | 16.926
[6 empty] | 16.3 | m2 net area item 6.1
2 | 3.5 |  | D1(2Pcs)
| 0.73 | 5.11 |  |  |  |  | 6.21)10cm thick C-20 RC 1.2mt wide
|  |  |  | 1 | 7
1 | 0.8 |  |  |  | 1.2 | 8.4
| 1.73 | -1.384
|  |  |  | 1 | 7
2 | 0.7 |  |  |  | 2.35 | 16.45
| 2.73 | -3.822
|  |  |  | 1 | 3.5
|  | 39.426 | m2 net area item 6.1 |  | 1.2 | 4.2
|  |  | 6.2)Apply three coats of plastering |  |  | 29.05 | m2 net area item 6.21
to internal wall & external beam & colu.
1 | 7.8 |  | L=1.10X2+5.60=7.80mt |  |  |  | 7)PAINTING
| 3.06 | 23.868 |  |  |  |  | 7.1)External rendered surface
|  |  |  | 1 | 39.426 |  | Ditto Item no 6.1
1 | 9.5 |  | L=2.75X2+2.0X2.0=9.50mt |  |  | 39.426 | m2 net area item 7.3
| 3.06 | 29.07
7.1)Internal plastered surface & external beam & column
1 | 9.2 |  | L=2.60X2+2.0X2.0=9.20mt | 1 | 93.112 |  | Ditto Item no 6.2
| 3.06 | 28.152 |  |  |  | 93.112 | m2 net area item 7.1
2 | 0.7 |  | D1(2Pcs) |  |  |  | 7.3)Chip wood ceiling surface
| 2.73 | -3.822 |  | 1 | 16.3 |  | Ditto Item no 6.4
[6 empty] | 16.3 | m2 net area item 7.2
1 | 0.8 |  | W1(Pcs)
| 1.73 | -1.384 |  |  |  |  | 10. Electrical Installation
2.Light point
2 | 5.8 |  | GRADE BEAM |  |  |  | 2.1)points conduti of 16mm 3*2.5mm2
| 0.4 | 4.64 |  | 6 | 1
[6 empty] | 6 | no net number item 2.01
2 | 3.5 |  | "
| 0.4 | 2.8 |  |  |  |  | 4.)Socket outlet point
4.01)Socket outlet point 3x2.5mm2
2 | 5.8 |  |  | 1 | 1
| 0.3 | 3.48 | TOP TIE BEAM |  |  | 1 | no net number item 4.01
2 | 3.5
| 0.3 | 2.1
8 | 2.63 |  | COLUMN
| 0.2 | 4.208
|  | 93.112 | m2 net area item 6.2

## Gua. Reinf
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Guard house
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 | 12 | 6.45 | 2 | 3 | 6 | - | - | - | 38.7
|  |  | 12 | 5.75 | 2 | 3 | 6 | - | - | - | 34.5
|  | st | 8 | 1.2 | 2 | 28 | 56 | - | 67.2 | - | -
|  | GB2 | 12 | 4.15 | 2 | 3 | 6 | - | - | - | 24.9
|  |  | 12 | 3.45 | 2 | 3 | 6 | - | - | - | 20.7
|  | st | 8 | 1.2 | 2 | 17 | 34 | - | 40.8 | - | -
[7 empty] | 0 | - | - | - | -
| Ground mesh |  | 8 | 5.27 | 1 | 16 | 16 | - | 84.32
|  |  | 8 | 2.97 | 1 | 27 | 27 |  | 80.19
[10 empty] | - | -
0
0
0
|  |  |  | TOTAL LENGTH |  |  |  |  | 272.51 | 0 | 118.8
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 107.6415 | 0 | 105.4944 | 0
| CONTRACTOR | [8 empty] | SUPERVISOR
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| COLUMN (C1) |  | 12 | 3.58 | 4 | 4 | 16 |  |  |  | 57.28
|  |  | 8 | 0.7 | 4 | 14 | 56 |  | 39.2
| TTB1 |  | 12 | 6.45 | 2 | 3 | 6 |  |  |  | 38.7
|  |  | 12 | 5.75 | 2 | 3 | 6 |  |  |  | 34.5
|  |  | 8 | 0.9 | 2 | 28 | 56 |  | 50.4
| TTB2 |  | 12 | 4.15 | 2 | 3 | 6 |  |  |  | 24.9
|  |  | 12 | 3.45 | 2 | 3 | 6 |  |  |  | 20.7
|  |  | 8 | 0.9 | 2 | 17 | 34 |  | 30.6
| W1 |  | 12 | 1.45 | 1 | 2 | 2 |  |  |  | 2.9
|  |  | 12 | 1.15 | 1 | 2 | 2 |  |  |  | 2.3
|  |  | 8 | 0.7 | 1 | 7 | 7 |  | 4.9
| D1 |  | 12 | 1.35 | 2 | 2 | 4 |  |  |  | 5.4
|  |  | 12 | 1.05 | 2 | 2 | 4 |  |  |  | 4.2
|  |  | 8 | 0.7 | 2 | 6 | 12 |  | 8.4
0
0
0
0
0
|  |  |  | TOTAL LENGTH |  |  |  |  | 133.5 |  | 190.88
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 52.7325 | 0 | 169.5014 | 0
| CONTRACTOR | [8 empty] | SUPERVISOR
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15
0.40
0..15
0.150
0.15

## Mor. Sum.
Summary of Statement
Project :- Wegeda Primary Hospital
Client :-ANRS Health Bureau |  |  |  | Page - ___
Location : Wegeda
Contractor :- Trust Consteraction
Block:-Mourge
Details of Works executed
Bill No. | Description | Sub Total Birr |  | Total Birr
|  | የውለታ | የተሠራው | የውለታ | የተሠራው
|  | Contract | Executed | Contract | Executed
A. Sub structure
1 | Excavation and Earth work | 34778 | 4754.28 | 34778 | 4754.28
2 | Concrete Work | 136220 | 17064.7056 | 136220 | 17064.7056
3 | Masonry work | 33700 | 6727.5 | 33700 | 6727.5
| sub total A | 204698 | 28546.4856 | 204698 | 28546.4856
| B. Super Structure |  |  | 0 | 0
1 | Concrete Work | 29237 | 15138.3184 | 29237 | 15138.3184
2 | Block work | 42000 | 12174.9 | 42000 | 12174.9
3 | Roofing | 27000 | 14852.8 | 27000 | 14852.8
4 | Carpentary & Joinery | 6850.2 | 7599 | 6850.2 | 7599
5 | Metal work | 18738 | 6000 | 18738 | 6000
6 | Finishing | 131540 | 25422.6 | 131540 | 25422.6
7 | Painting | 7560 | 1157.49 | 7560 | 1157.49
8 | Glazing | 4380 | 0 | 4380 | 0
9 | Sanitory Installation | 18815 | 0 | 18815 | 0
10 | Electrical Installation | 0 | 0 | 0 | 0
| sub total B | 286120.2 | 82345.1084 | 286120.2 | 82345.1084
| Total A+B | 490818.2 | 110891.594 | 490818.2 | 110891.594
I/We ____________________here by certify that the above figures/are corrected and the total
value of work executed and/or materials supplied to date is Birr
Contractor :- _________________ |  |  |  | Consultant:- _____________

## mor. Mea.
Project :Wegeda Primary Hospital
CONSULTANT:-Amhara Design & Supervision Works Enterprise |  |  |  |  | Page No. :-
CONTRACTOR:-Trust Construction |  |  |  |  | Block : Morgue House
CLIENT:-ANRS Health Bureau
Item | Description | Unit | Contract |  |  | Executed
|  |  | qty | Rate | amount | Qty | Amount
A. SUB- STRUCTURE
1. EXCAVATION & EARTH WORK
1.1 | Clear off site to remove top soil to an average | m2 | 42 | 8 | 336 | 35.28 | 282.24
1.2 | Bulk excavation in ordinary | m3 | 63 | 70 | 4410 | 25.676 | 1797.32
1.3 |  | m3 | 21 | 70 | 1470 | 1.696 | 118.72
1.3 | Selected borrowed fill brought from out side | m3 | 84 | 150 | 12600 | 1.04 | 156
1.4 | Cart away surplus excavated material to an | m3 | 96.6 | 70 | 6762 | 0 | 0
1.5 | 25cm thick basaltic or equivalent stone hard | m2 | 46 | 200 | 9200 | 12 | 2400
| Total to summary ………Birr |  |  |  | 34778 |  | 4754.28
2. CONCRETE WORK
2.1 | 5cm thick lean concrete class C-7, with | m2 | 14 | 150 | 2100 | 7.5 | 1125
2.2 | Ditto but under footing pad | m2 | 8 | 150 | 1200 |  | 0
2.3 | 10cm thick reinforced concrete floor slab class | m2 | 46 | 400 | 18400 | 2.94 | 1176
2.4 | In grade beam & steps | m3 | 6 | 3200 | 19200 | 1.56 | 4992
2.5 | In footing pad | m3 | 1.8 | 3200 | 5760 |  | 0
2.6 | In footing coloumn | m3 | 1.4 | 3200 | 4480 |  | 0
Provide cut and fix in position swan zigba wood
2.7 | Grade beam | m2 | 32 | 120 | 3840 | 12.48 | 1497.6
2.8 | In footing pad | m2 | 7 | 120 | 840 |  | 0
2.9 | In footing coloumn | m2 | 27 | 120 | 3240 |  | 0
2.1 | Steps | m2 | 2 | 120 | 240 |  | 0
| Reinforcement steel bar according to St.drawing |  |  |  | 0 |  | 0
2.11 | Dia 16 mm deformed bar | kg | 675 | 36 | 24300 |  | 0
2.12 | Dia. 12mm deformed bar | kg | 235 | 36 | 8460 | 94.8384 | 3414.1824
2.13 | Dia 8 mm deformed bar | kg | 1120 | 36 | 40320 | 86.3312 | 3107.9232
2.14 | Dia 6 mm plain bar | kg | 5 | 36 | 180 |  | 0
2.16 | 10/2 cm chip wood expansion joint between | m | 120 | 120 | 14400 | 14.6 | 1752
| Total to summary ………Birr |  |  |  | 146960 |  | 17064.7056
3. MASONRY WORK
3.1 | Trychitic or equivalent stone masonry foundation | m3 | 20 | 1250 | 25000 | 3.41 | 4262.5
3.2 | Ditto but well dressed stone above natural ground | m3 | 6 | 1450 | 8700 | 1.7 | 2465
| Total to summary ………Birr |  |  |  | 33700 |  | 6727.5
B. SUPER - STRUCTURE
1.CONCRETE WORK
Reinforced concrete class C -25, with minimum
1.1 | In elevation column | m3 | 0.9 | 2400 | 2160 | 0.4368 | 1048.32
1.2 | In beams | m3 | 1.98 | 2400 | 4752 | 0.948 | 2275.2
Provide cut and fix in position swan zigzag wood
1.3 | Elevation column | m2 | 17.92 | 150 | 2688 | 8.736 | 1310.4
1.4 | Beam | m2 | 25.32 | 150 | 3798 | 12.97 | 1945.5
| Reinforcement steel bar according to St.drawing | [5 empty] | 0
1.5 | Dia 14mm deformed bar | kg |  |  |  |  | 0
1.6 | Dia 12mm deformed bar | kg | 305 | 35 | 10675 | 172.0766 | 6022.6824
1.7 | Dia 8mm deformed bar | kg | 130 | 40 | 5200 | 63.4054 | 2536.216
1.8 | Dia 6 mm plain bar | kg
| Total to summary ………Birr |  |  |  | 29273 |  | 15138.3184
2. BLOCK WORK
Concrete block wall class "C" bedded in cement
mortar both sides left for plastering
2.1 | 20cm thick | m2 | 120 | 300 | 36000 | 40.583 | 12174.9
2.2 | 15cm thick | m2 | 0
| Total to summary ………Birr |  |  |  | 36000 |  | 12174.9
3.ROOFING
3.1 | G - 28 Roof covering in galvanized corrugated | m2 | 60 | 300 | 18000 | 27.06 | 8118
3.2 | G - 28ribbed sheet ceiling under eave | m2 | 7 | 320 | 2240 | 9.41 | 3011.2
3.3 | Supply and fix G-28 flat metal sheet gutter | m | 16 | 200 | 3200 | 13.2 | 2640
3.2 | Flushing in flat metal sheet fixed as shown | m | 21 | 90 | 1890 | 12.04 | 1083.6
| Total to summary ………Birr |  |  |  | 25330 |  | 14852.8
4. CARPENTRY & JOINERY
4.1 | Upper & lower chord size-diameter 10 - 12 cm | m | 100 | 25 | 2500 | 59 | 1475
4.2 | Diagonal & vertical members size-diameter 8 - 10cm | m | 70 | 20 | 1400 | 33.2 | 664
4.3 | Purlin zigba size 5/7cm | m | 82 | 70 | 5740 | 52.8 | 3696
4.4 | Ziba wooden fascia board price includes three coats | m | 10.2 | 70 | 714 | 25.2 | 1764
Doors
4.5 | Type D2 size-90/280cm | Nº | 0
| Total to summary ………Birr |  |  |  | 10354 |  | 7599
5. METAL WORK
Windows
5.1 | Type W1 size-138/180cm | Nº | 3 | 2000 | 6000 |  | 0
| W1 size-110/63cm | Nº |  | 2000 |  | 3 | 6000
| Doors |  |  |  | 0 |  | 0
5.4 | Type D3 size - 90/280 cm | Nº | 2 | 2000 | 4000 |  | 0
| Total to summary ………Birr |  |  |  | 10000 |  | 6000
6. FINISHING
6.1 | Apply two coats of plastering and one coat of ren | m2 | 95 | 150 | 14250 | 38.583 | 5787.45
6.2 | Apply three coats of plastering to internal walls & | m2 | 130 | 150 | 19500 | 21.801 | 3270.15
6.3 | Chip wood ceiling nailed on & including | m2 | 45 | 250 | 11250 | 12.5 | 3125
6.4 | Approved type 6mm thick glazed ceramic wall tile bedded on & including cement mortar backing and joints grouted in white cement. | m2 | 64 | 320 | 20480 |  | 0
6.5 | 9mm thick non slippery ceramic tile floor | m2 | 12 | 350 | 4200 |  | 0
6.1 | Approved type 2cm thick terrazzo tile flooring | m2 | 35 | 250 | 8750 |  | 0
6.11 | Approved type10/2cm terrazzo tile skirting | m | 42 | 180 | 7560 |  | 0 | 32
6.16 | Approved type Terrazo window cill | m | 4.5 | 200 | 900 |  | 0
6.21 | 10 cm thick C-20 RC 1.2 m wide pavement | m2 | 51 | 400 | 20400 | 19.8 | 7920
| storm water concrete pipes of half diameter 30cm | ml | 53 | 200 | 10600 | 26.6 | 5320
| Construction of 10x40 cm curb stone | ml | 53 | 250 | 13250 |  | 0
| Total to summary ………Birr |  |  |  | 131140 |  | 25422.6
7. PAINTING
7.1 | External rendered surface | m2 | 95 | 30 | 2850 | 38.583 | 1157.49
7.1 | Internal plastered surfaceand external beams& | m2 | 130 | 27 | 3510 |  | 0
7.3 | Chip wood ceiling surface | m2 | 45 | 25 | 1125 |  | 0
| Total to summary ………Birr |  |  |  | 7485 |  | 1157.49
8. GLAZING
8.1 | 4mm thick frosted glass | m2 | 12 | 280 | 3360 |  | 0
| Total to summary ………Birr |  |  |  | 3360 |  | 0
9. SANITARY INSTALLATION
9.1 | Supply & install PP-R water pipes for water
| 15mm diameter ;internal | LM | 10 | 30 | 300 |  | 0
| 20mm diameter ;internal | LM | 25 | 35 | 875 |  | 0
9.2 | Supply & fix chrome angle valves complete with |  |  |  | 0 |  | 0
| 15mm diameter | No | 15 | 90 | 1350 |  | 0
9.3 | Supply & fix bronze gate valves complete with |  |  |  | 0 |  | 0
| 20mm diameter | No | 2 | 120 | 240 |  | 0
9.4 | Ditto item 3,but chrome plated 15mm water tap | No | 1 | 130 | 130 |  | 0
9.5 | Supply & install waste water pipes made of rigid |  |  |  | 0 |  | 0
| 50mm diameter of min. wall thickness=2mm | LM | 5 | 40 | 200 |  | 0
| 75mm diameter of min. wall thickness=3mm | LM | 8 | 45 | 360 |  | 0
| 100 mm diameter of min. wall thickness=3.2mm | LM | 12 | 50 | 600 |  | 0
9.6 | Supply & fix 500x400 mm colored vitreous china | No | 1 | 900 | 900 |  | 0
9.7 | Suply & fix low flush colored vitreous china water | No | 1 | 1200 | 1200 |  | 0
9.9 | Supply & fix toilet paper holder made of metal | No | 1 | 150 | 150 |  | 0
9.1 | Supply & fix crystal glass mirror of | No | 2 | 400 | 800 |  | 0
9.11 | Supply & fix 600mm long towel hanger for | No | 2 | 150 | 300 |  | 0
9.12 | Supply & install shower units made of | No | 2 | 900 | 1800 |  | 0
9.13 | Supply & install electric water heater complete |  |  |  | 0 |  | 0
| 50 liters capacity | No | 1 | 2000 | 2000 |  | 0
9.15 | Supply & fix 50 mm diameter floor drain made of | No | 2 | 110 | 220 |  | 0
9.17 | Supply & fix 100mm 3.2mm thickness down pipes | LM | 32 | 80 | 2560 |  | 0
9.18 | Supply &B275 mount fire extingushers of class | No | 1 | 3000 | 3000 |  | 0
| Total to summary ………Birr |  |  |  | 16985 |  | 0
10. ELECTRICALL INSTALLATION
1 | Multi-core cable with copper conductors,XLPE
A | 3x6mm2 | m | 100 | 70 | 7000 |  | 0
C | 4x6mm2 | m | 200 | 90 | 18000 |  | 0
E | 4x10mm2 | m | 100 | 150 | 15000 |  | 0
2 | Distribution Boards |  |  |  | 0 |  | 0
| Distribution board, supplied, installed, connected |  |  |  | 0 |  | 0
A | Ditto, but SDB Rb2a | No. | 1 | 5000 | 5000 |  | 0
B | Ditto, but SDB Rb2a | No. | 1 | 5000 | 5000 |  | 0
C | Ditto, but SDB R | No. | 1 | 5000 | 5000 |  | 0
3 | Luminaires |  |  |  | 0 |  | 0
A | Ditto, but for item 8 | No. | 3 | 400 | 1200 |  | 0
B | Ditto, but for item 13 | No. | 6 | 300 | 1800 |  | 0
C | Ditto, but for item 16 | No. | 20 | 250 | 5000 |  | 0
D | Ditto, but for item 21 | No. | 12 | 300 | 3600 |  | 0
E | Ditto, but for item 22 | No. | 16 | 400 | 6400 |  | 0
F | Ditto, but for item 23 | No. | 4 | 400 | 1600 |  | 0
G | Ditto, but for item 24 | No. | 12 | 300 | 3600 |  | 0
I | Ditto, but for item 44 | No. | 12 | 300 | 3600 |  | 0
J | Ditto, but for item 45 | No. | 12 | 300 | 3600 |  | 0
| Wiring Devices |  |  |  | 0 |  | 0
4 | Switchs |  |  |  | 0 |  | 0
A | One way switch | No. | 12 | 100 | 1200 |  | 0
B | Ditto, two pole switch | No. | 26 | 40 | 1040 |  | 0
C | Ditto, but 10A and with pilot light | No. | 12 | 40 | 480 |  | 0
D | Ditto, but with two-way switch | No. | 40 | 40 | 1600 |  | 0
E | Ditto, but with dimmer switch | No. | 16 | 40 | 640 |  | 0
5 | Socket outlet |  |  |  | 0 |  | 0
A | 16A, 250V, 2 pole duplex socket outlet with | No. |  |  | 0 |  | 0
B | Ditto, but single socket outlet | No. | 46 | 100 | 4600 |  | 0
6 | Electrical Connections |  |  |  | 0 |  | 0
G | Refrigerator | No. | 6 | 1500 | 9000 |  | 0
J | Stove | No. | 6 | 2000 | 12000 |  | 0
K | Water heater | No. | 16 | 1000 | 16000 |  | 0
7 | Earthing Systems |  |  |  | 0 |  | 0
A | Earthing system | L.S. | 1 | 5000 | 5000 |  | 0
16 | Lightning Protection System |  |  |  | 0 |  | 0
A | Lightning protection system | L.S. | 1 | 7000 | 7000 |  | 0
8 | Telecommunication Systems |  |  |  | 0 |  | 0
A | Telephone outlets | No. | 19 | 3000 | 57000 |  | 0
| Note: Verify type of telephone outlets |  |  |  | 0 |  | 0
D | Ditto but 50 pair, TELE | No. | 1 | 20000 | 20000 |  | 0
| Total to summary ………Birr |  |  |  | 220960 |  | 0

## Mor. Sub TOS
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Morgue Sub-Structure
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | A) SUB-STRUCTURE |  |  |  | 2.3,10cmthick RC ground slab
|  |  | 1)Excavation & earth work |  |  |  | The same as item No 1.6
|  |  | 1.1) Clearoff sitr to remove |  | 2.1
|  |  | 5.4+1.0+1.0=7.4 | 1 | 1.4
|  |  | 2.9+1.0+1.0=4.9 |  |  | 2.94
1 | 7.2
| 4.9 | 35.28 |  |  |  |  | 2.4 a,(C-25) IN GRADE BEAM
axis x01-x02/Y01-Y02
|  |  | 1.2) Bulk excavation | 2 | 5.4 |  | L=5.2m W=0.25m
1 | 6.2 |  |  |  | 0.25 |  | D=0.40m
| 3.7 |  |  |  | 0.4
| 1 | 22.94 |  |  |  | 1.08
|  |  |  | 2 | 2.4 |  | axis x01-x02/Y01-Y02
|  |  | 1.3) Dittobut trench excavation |  | 0.25
2 | 5.7 |  |  |  | 0.4 |  | L=2.2m W=0.25m D=0.40m
| 0.9 |  |  |  |  | 0.48
| 0.2 | 2.052
1.56
2 | 1.9
| 0.9 | [5 empty] | Form work
| 0.2 | 0.684 |  |  |  |  | 2.7 a, Grade beam
|  |  |  | 2 | 5.4
|  | 2.736 | m² Total |  | 0.4 | 4.32
|  |  | 1.4) Selected fill under land core | 2 | 4.9
4 | 5.2 |  |  |  | 0.4 | 3.92
0.25
| 0.2 | 1.04 |  | 2 | 2.9
[5 empty] | 0.4 | 2.32
1.5) Cart away
| 7.4 |  |  | 2 | 2.4
| 4.9 |  |  |  | 0.4 | 1.92
| 0.3 | 10.878 | From item 1.1
|  | 7.02 | From item 1.2 |  |  | 12.48
|  | 10.04 | From item 1.3
2.14)10/2cm chipwoodexpantion joint
|  | 27.938 | G.total | 2 | 4.9
9.8
1.6) 25cm thick land core
| 2.4 |  |  | 2 | 2.4
| 5 | 12 | Total |  |  | 4.8
|  |  | 2. Concrete Work |  |  | 14.6
2.1-.Lean Concrete, C-7
Under masonery
2 | 5.5 |  | axis x01-x02/Y01-Y02
| 0.5 |  | L=5.0m W=0.50m
5.5
2 | 2 |  | axis y01-yx02/x01-x02
| 0.5 |  | L=2.7-.50=2.2m W=0.50m
2
7.5
T | D | S | Item No. and Description | T | D | S | Item No. and Description
#REF!

## Mor. Super TOS
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Morgue
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | B.SUPER STRUCTURE | 2 | 5 |  | "
|  |  | 1.CONCRETE WORK |  | 0.2 | 2
4 | 2.73 |  | 1.1)In elevation column
| 0.2 |  | C1=20Pcs & C2=4Pcs (0.2x0.2) | 4 | 1.1 |  | W1(4Pcs)
| 0.2 |  |  |  | 0.6 | -2.64
|  | 0.4368 | m3 net area item 1.1
|  |  |  | 1 | 0.9 |  | D1(1Pcs)
|  |  | 1.2)In beam |  | 2.73 | -2.457
2 | 5.4 |  | TTB1=2Pcs
| 0.3 |  | Axis x/01 & x/02 from (y/01 - y/02) |  |  | 40.583 | m2 net area item 2.1
| 0.2 | 0.648
3)ROOFING WORK
2 | 2.5 |  | TTB2=2Pcs |  |  |  | 3.1)G-28 CIS Roof covering
| 0.3 |  | Axis y/01 & y/02 from ( y/01 - y/02) | 1 | 6.6 |  | W=5.40+0.60X2=6.60mt
| 0.2 | 0.3 |  |  | 4.1 |  | L=2.9+0.60X2=4.10mt
[6 empty] | 27.06 | m2 net area item 3.1
|  | 0.948 | m3 net area item 1.2
3.2)G-28 Ribbed sheet ceiling
|  |  | FORM WORK | 2 | 6.4
|  |  | 1.3)Elevation column |  | 0.5
4 | 2.73 |  | C1 =4PCS |  |  | 6.4
| 0.8 |  |  | 2 | 3.01
|  | 8.736 | m3 net area item 1.3 |  | 0.5
3.01
1.4) Beam
2 | 5 |  | TTB1=2Pcs |  |  | 9.41 | m2 net area item 3.2
| 0.8 | 8 | Axis x/01 & x/02 from (y/01 - y/06)
3.3)Supply & fix G-28 gutter dev.
2 | 2.5 |  | TTB2=2Pcs | 2 | 6.6
| 0.8 | 4 | Axis x/02 & x/03 from ( y/01 - y/06) |  |  | 13.2 | m2 net area item 3.3
8 | 0.2 | [5 empty] | 3.4)Flashing in metal sheet
| 0.3 | 0.48 |  |  |  |  | l=5.20+1.2=6.60mt
l=3.01x2=6.02mt
1 | 2.1 |  |  | 4 | 3.01
| 0.1 | 0.21 | Morgue set |  |  | 12.04 | m2 net area item 3.4
2 | 1.4 | [5 empty] | 4)CARPENTRY
| 0.1 | 0.28 | " |  |  |  | 4.1)Uper & lower chord size 10-12cm
|  |  |  | 5 | 6.2 |  | Upper=3.10x2= 6.20ml
|  | 12.97 | m3 net area item 1.4 |  |  | 31 | Lower =2.80x2= 5.60mt
|  |  | 1.6)ф12mm deformed bar | 5 | 5.6
|  | 172.0766 | kg net weight item 1.6 |  |  | 28
|  |  | 1.7)ф8mm deformed bar |  |  | 59 | m net length item 4.1
|  | 63.4054 | kg net weight item 1.7
4.2)Vertical & Diagonal member
|  |  | 2)BLOCK WORK | 5 | 2.64 |  | V =2.64mt D=4.00mt
|  |  | 2.1)20cm thick HCB wall |  |  | 13.2
2 | 5 |  | Axis x/01 from (y/01 - y/02)
| 2.73 | 27.3 |  | 5 | 4
20
2 | 2.5 |  | Axis x/02 from (y/01 - y/02)
| 2.73 | 13.65 |  |  |  | 33.2 | m net length item 4.2
2 | 0.5 |  | Axis y/01 & y/02 from ( y/01 - y/02)
| 2.73 | 2.73
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 4.3)Purlin zigba 5/7cm | 2 | 2.9 |  | TOP TIE BEAM
|  |  | No .pur =2.3/0.9+1=4X2=8 |  | 0.3 | 1.74
8 | 6.6 |  | L=5.4+1.2=6.60mt
|  | 52.8 | m net length item 4.3 | 8 | 2.73 |  | COLUMNS
[5 empty] | 0.2 | 4.368
4.4)Zigba wooden fascia board
4 | 3.1 |  |  |  |  | 30.04 | DDT Ceramicc wall
12.4
[6 empty] | 21.801 | m2 net area item 6.2
2 | 6.4
|  | 12.8 |  |  |  |  | 6.4)Chipwood ceiling
|  |  |  | 1 | 5
|  | 25.2 | m net length item 4.4 |  | 2.5
[6 empty] | 12.5 | m2 net area item 6.4
5)METAL WORK
3 | 1 |  | 5.1)Type W7 ,Size 110/63 |  |  |  | 6.21)10cm thick C-20 RC 1.2mt wide
|  | 3 | no net number item 5.1 | 2 | 6.8
1.2
|  |  | 6.1)Apply two coats of plastering & |  |  | 16.32
|  |  | one coat rendering | 1 | 2.9
2 | 5 |  | Axis x/01 from (y/01 - y/02) |  | 1.2
| 2.73 | 27.3 |  |  |  | 3.48
2 | 2.5 |  | Axis x/02 from (y/01 - y/02) |  |  | 19.8 | m2 net area item 6.21
| 2.73 | 13.65
6.21)Supply & lay storm water
2 | 0.5 |  | Axis y/01 & y/02 from ( x/01 - x/02) |  |  |  | concrete pipe of 1/2 ф30cm
| 2.73 | 2.73 | Top tie beam | 2 | 7.4 |  | L=2.90+2.4+0.6=5.90mt
14.8
4 | 1.1 |  | W7(5Pcs)
| 0.6 | -2.64
|  |  |  | 2 | 5.9
1 | 0.9 |  | D3(1Pcs) |  |  | 11.8
| 2.73 | -2.457
[6 empty] | 26.6 | m2 net area item 6.22
|  | 38.583 | m2 net area item 6.1
7)PAINTING
|  |  | 6.2)Apply three coats of plastering |  |  |  | 7.1)External rendered surface
|  |  | to internal wall & external beam & colu. | 1 | 38.583 |  | Ditto Item no 6.1
1 | 15 |  | L=2.50X2+5.00X2=15.00mt |  |  | 38.583 | m2 net area item 7.3
| 2.73 | 40.95
4 | 1.1 |  | W1(4Pcs)
| 0.6 | -2.64
1 | 0.9 |  | D1(1Pcs)
| 2.73 | -2.457
2 | 5.4 |  | GRADE BEAM
| 0.4 | 4.32
2 | 2.9 |  | "
| 0.4 | 2.32
2 | 5.4 |  | TOP TIE BEAM
| 0.3 | 3.24

## Mor. Reinf
Project :Wegeda Primary Hospital | [9 empty] | Take off sheet no.:-
CONSULTANT:-Amhara Design & Supervision Works Enterprise | [9 empty] | Page No. :-
CONTRACTOR:-Trust Construction | [9 empty] | Block : Mourge
CLIENT:-ANRS Health Bureau
No | Location | Shape | Ømm | Length | No. of Members |  |  |  | TOTAL LENGTH IN METER
|  |  |  | ML | Membs. | b/memb. | T/bars | Ø6 | Ø8 | Ø10 | Ø12 | Ø14
| Grade beam | GB1 | 12 | 6.05 | 2 | 3 | 6 |  |  |  | 36.3
|  |  | 12 | 5.35 | 2 | 3 | 6 |  |  |  | 32.1
|  | st | 8 | 1.2 | 2 | 26 | 52 |  | 62.4
|  | GB2 | 12 | 3.55 | 2 | 3 | 6 |  |  |  | 21.3
|  |  | 12 | 2.85 | 2 | 3 | 6 |  |  |  | 17.1
|  | st | 8 | 1.2 | 2 | 14 | 28 |  | 33.6
GROUND FLOOR MESH
|  |  | 8 | 2.37 | 1 | 25 | 25 |  | 59.25
|  |  | 8 | 4.87 | 1 | 13 | 13 |  | 63.31
[7 empty] | 0 |  | 0
|  |  |  | TOTAL LENGTH |  |  |  |  | 218.56 | 0 | 106.8 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 | 0.617 | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 86.3312 | 0 | 94.8384 | 0
| COLUMN (C1) |  | 12 | 3.58 | 4 | 4 | 16 |  |  |  | 57.28
|  |  | 8 | 0.7 | 4 | 14 | 56 |  | 39.2
| TTB1 |  | 14 | 6.05 | 2 | 3 | 6 |  |  |  | 36.3
|  |  | 14 | 5.35 | 2 | 3 | 6 |  |  |  | 32.1
|  |  | 8 | 0.9 | 2 | 26 | 52 |  | 46.8
| TTB2 |  | 14 | 3.55 | 2 | 3 | 6 |  |  |  | 46.8
|  |  | 14 | 2.85 | 2 | 3 | 6 |  |  |  | 21.3
|  |  | 8 | 0.9 | 2 | 14 | 28 |  | 25.2
| Morgue set |  | 8 | 3.6 | 1 | 8 | 8 |  | 28.8
|  |  | 8 | 1.71 | 1 | 12 | 12 |  | 20.52
0
0
0
0
|  |  |  | TOTAL LENGTH |  |  |  |  | 160.52 |  | 193.78 | 0
|  |  |  | UINT WEIGHT in KG/ML |  |  |  |  | 0.395 |  | 0.888 | 1.21
|  |  |  | TOTAL WEIGHT IN KG |  |  |  |  | 63.4054 | 0 | 172.0766 | 0
| CONTRACTOR | [8 empty] | SUPERVISOR

## G Su Site
Block:-Site work
SUMMARY OF STATEMENT
Project -- Wegeda Primary Hospital
Location -- South Gonder/Wegeda
Contractor -- Trust Construction
¾}c^¨< Y^“/¨ÃU ¾k[u< °n­‹ ´`´`
Detail of works executed and / or material supplied
}.l Item No. | SÓKÝ Description | ÉU` uŸòM |  | ÉU`
|  | Sub total(Birr) |  | Sum
|  | ¾¨<K | ¾}W^¨< | ¾¨<K | ¾}W^¨<
|  | Contract | Executed | Contract | Executed
1 | GENERAL SITE WORK | 3935585 | 3192226.9048
2 | ELECTRICAL SITE WORK | 389895 | 358027.032
3 | UNCOVERED way /Fence work/ | 1345100 | 1312633.5
4 | RAMPS | 61650 | 194614.072
5 | Ash and Needle Pits | 150638 | 21773.0898
6 | Placenta Pit | 135501.25 | 58200.1813
7 | Incinanator | 77113.86 | 5250
8 | Covered walk way | 1051255.87 | 111549.7672
Total |  |  |  | 7146738.98 | 5254274.5471
’@/ — Ÿ²=I uLÃ ¾}²[²\ƒ H>dx‹ ƒ¡¡M SJ“†¨<”
¾}W^¨< Y^“ °n ÖpLL ªÒ w` |  |  | 5254274.5471 | SJ’<” “[ÒÓ×K”::
I/we here by certify that above figures are correct and that the total value of work executed
and/or materials supplied up to date is Birr |  |  | 5254274.5471
___________________ |  | ______________ |  | ______________
Contractor |  | Site Supervisor |  | Consultant
0

## Site Meas
Project:- WEGEDA PRIMARY HOSPITAL
Contractor:- TRUST CONSTRUCTION
Consultant:- ADSWE
Client:- ANRHB
Summary of Measurement for General Site Work
It. no | Description of Work | Unit | Rate | Contract Qty. | Contract Amt. | This payment | This payment Amt.
| Site Work |  |  |  |  | This payment
10.4 GENERAL SITE WORK
10.4.3 | Construct slab covered ditch as per the detail drawing. Price shall include excavation cart away and all civil assistance | m | 500 | 100 | 50000 |  | 0 | 0
10.4.4 | Supply and uPVC, PN-4 pipe for waste water drainage from the manhole to the septic tank with minimum slope as shown on the drawing or natural ground slop which ever is greater on a firm bed of sand a00mm thick below and 200mm thick above the crown of pipe in open ground. | [6 empty] | 0
| Excavation In hard rock | m3 | 684.97 |  | 0 | 20.595 | 14106.9572
| Dia 100mm | m | 120 | 303.1 | 36372 |  | 0 | 0
| Dia150mm | m | 200 | 63 | 12600 |  | 0 | 0
10.4.7 | Supply and fix approved quality garden taps, complete with gate valve and all other accessories and connecting pieces. Dia. 20mm | No | 200 | 1 | 200 |  | 0 | 0
10.4.8 | Construct manholes on a sanitary sewer drainage system as where shown on the drawing in single brick on 150mm both ways and 120mm thick reinforced cover slab in dia. 10c.c150mm both ways. Price shall include all assistance civil works and handle. | [5 empty] | 0 | 0
| a) size: 600x600mm average depth=850mm | No | 2500 | 23 | 57500 |  | 0 | 0
10.11 | Construct open ditch out of half precast concrete round pipes. Price shall include excavation, cart away and all civil works as shown on the detailed drawing. | [6 empty] | 0
| Ditch size 1/2 Diameter 300mm | m | 150 | 803.6 | 120540 |  | 0 | 0
10.4.14 | Supply and install water meter of approved quality price shall include gate valves after and before water meter | [5 empty] | 0 | 0
| Dia. 40mm | No | 15000 | 1 | 15000 |  | 0 | 0
| 10.4.15 WATER TANK | [5 empty] | 0 | 0
10.4.14.1 | Supply & install Elevated 5m3 water tank made of fiber glass as where shown on the drawing. The price include the construction cost for the water thank holder made of RC. | [6 empty] | 0
| Accessories | [6 empty] | 0
SUB- STRUCTURE
EXCAVATION & EARTH WORK
10.4.15.1 | Clear off site to remove top soil to an average | m2 | 8 | 0 | 0 | 41.6025 | 332.82
10.4.15.2 | Pit Excavation | m3 | 550 | 0 | 0 | 23.12 | 12716
10.4.15.3 | Back Fill around Footing | m3 | 150 | 0 | 0 | 9.216 | 1382.4
10.4.15.4 | Cartaway | m3 | 70 | 0 | 0 | 35.6007 | 2492.0525
10.4.15.5 | Lean Concrete | m2 | 150 | 0 | 0 | 9.76 | 1464
10.4.15.6 | C-25 16cm thick floor slab | m3 | 3200 | 0 | 0 | 1.44 | 4608
10.4.15.7 | In Grade Beams | m3 | 3200 | 0 | 0 | 10.8 | 34560
10.4.15.8 | In Footing Pad | m3 | 3200 | 0 | 0 | 2.304 | 7372.8
10.4.15.9 | In Footing Column | m3 | 3200 | 0 | 0 | 1.44 | 4608
10.4.15.10 | In Elevation Column | m3 | 3200 | 0 | 0 | 1.92 | 6144
10.4.15.11 | In Roof | m3 | 3200 | 0 | 0 | 0.28 | 896
Formwork
10.4.15.12 | C-25 16cm thick floor slab | m2 | 120 | 0 | 0 | 9 | 1080
10.4.15.13 | In Grade Beams | m2 | 120 | 0 | 0 | 30.33 | 3639.6
10.4.15.14 | In Footing Pad | m2 | 120 | 0 | 0 | 76.8 | 9216
10.4.15.15 | In Footing Column | m2 | 120 | 0 | 0 | 4.8 | 576
10.4.15.16 | In Elevation Column | m2 | 120 | 0 | 0 | 12 | 1440
10.4.15.17 | In Roof | m2 | 120 | 0 | 0 | 5.6 | 672
Reinforcement steel bar according to St.drawing
2.11 | Dia. 14 mm deformed bar | kg | 36 | 0 | 0 | 244.9824 | 8819.3664
2.12 | Dia. 12mm deformed bar | kg | 36 | 0 | 0 | 524.3652 | 18877.1488
2.13 | Dia 8 mm deformed bar | kg | 36 | 0 | 0 | 200.66 | 7223.76
| 10.4 50m3 ground reservoir | [6 empty] | 0
10.4.16 | Construct Septic tank as per the detail drawing | No | 294000 | 2 | 588000 | 2 | 588000 | 588000
| Capacity: 50m3 | [6 empty] | 0
10.4.18 | Construct soak away pit as per the detail drawing | No | 293000 | 4 | 1172000 | 4 | 1172000 | 1172000
10.4.19 | Construct Dry latrine as per the detail drawing | No | 430000 | 3 | 1290000 | 3 | 1290000 | 1290000
TOTAL CARRIED TO SUMMARY |  |  |  |  | 3342212 |  | 3192226.9048 | 0
ELECTRICAL SITE WORK
3 | manhole and ducts
3.1 | Manhole in brick or masonry, internally plastered including reinforced concrete cover with lifting lug of:
| 2.1.1 1200x1000x700mm | No | 5000 | 1 | 5000 |  | 0
| 2.1.2 Ditto, but with 1000x1000x700mm | No | 5000 | 9 | 45000 | 6 | 30000
| 2.1.2 Ditto, but with 600x600x500mm | No | 3500 | 9 | 31500 | 3 | 10500
3.2 | Cement pipe of dia. 110mm diameter to main power distribution. Price include digging and back fill | Ml | 754.97 | 16.8 | 12683.496 | 365.6 | 276017.032
4 | FEEDER CABLES (actual measurement to be deterimed | [5 empty] | 0
4.1 | 3x240/120mm2 from KWHM to CMDB (TENTATIVE) | Ml | 2000 | 17.5 | 35000 |  | 0
4.2 | 3x25/16mm2 | Ml | 1000 | 70 | 70000 |  | 0
4.3 | 5x16mm2 | Ml | 230 | 140 | 32200 |  | 0
4.4 | 5x10mm2 | Ml | 200 | 210 | 42000 |  | 0
4.5 | 4x6mm2 | Ml | 115 | 448 | 51520 |  | 0
4.6 | 3x50/25mm | Ml | 70 |  | 0 | 131 | 9170
4.7 | 4x10mm | Ml | 210 |  | 0 | 154 | 32340
TOTAL CARRIED TO SUMMARY |  |  |  |  | 6717115.496 |  | 358027.032 | 0
| 11- UNCOVERD WALK WAY /FENCE WORK/ | [6 empty] | 0
| 11.1 Excavation & Earth Work | [6 empty] | 0
11.1.1 | Bulk excavation for average depth of 600mm | m3 | 70 | 120 | 8400 | 671.6125 | 47012.875 | 47012.875
11.1.2 | Remove and spread surplus material | m3 | 70 | 120 | 8400 | 671.6125 | 47012.875 | 47012.875
| 11.2 Construction of sub base course | [5 empty] | 0 | 0
11.2.1 | The sub base course shall consist of selected material from quarry waste . Rolling shall be with 10-16ton roller to a finished thickness of 150mm. | m2 | 200 | 120 | 24000 | 1557.6875 | 311537.5 | 311537.5
| 11.3 Construction of bases course | [5 empty] | 0 | 0
11.3.1 | The bases consist of crushed aggregate 80/120mm well compacted and rolled with 10-16 ton roller to a finished thickness of 150mm. | m2 | 200 | 120 | 24000 |  | 0 | 0
| 11.4 Construction of surface course | [5 empty] | 0 | 0
11.4.1 | The surface course consists of 70mm thick wearing course size 20mm gravel (3/4) on the compacted base course and well compacted with 10-6 ton roller. The final level shall be topped with some kg/sq.m fine particles from quarry waste. 0/12 as a binding material and thoroughly rolled with sprinkling of water until fally sonsolidated, smoothed and leveled. | m2 | 200 | 120 | 24000 |  | 0 | 0
11.4.2 | Apply mass concrete | m2 | 260 | 120 | 31200 | 463.9375 | 120623.75 | 120623.75
| 11.5 Construction of Curbstone | [5 empty] | 0 | 0
11.5.1 | Construct curbstone bed on 12cm thick lean concrete in c-5 and joints pointed in cement sand mortar mix(1:3). Price includes excavation, caraway and lean concrete. Size 400*150mm | m | 265 | 220 | 58300 | 348 | 92220 | 92220
| 1. Fence | [5 empty] | 0 | 0
| 3. Front side masonry work | [5 empty] | 0 | 0
3.1 | Trench excavation for masonry foundation | m3 | 70 | 150 | 10500 | 131.5 | 9205 | 9205
3.2 | Caraway surplus | m3 | 70 | 150 | 10500 | 131.5 | 9205 | 9205
3.3 | 50cm thick masonry BGL | m3 | 1250 | 150 | 187500 | 62.5 | 78125 | 78125
3.4 | Ditto but well dressed stone above NGL (Price includes pointing and Copping) | m3 | 1450 | 150 | 217500 | 100 | 145000 | 145000
3.5 | 50cm thick well dressed masonry pillars (price includes pointing, copping and any related works) | m3 | 1450 | 190 | 275500 | 23.87 | 34611.5 | 34611.5
3.6 | Provide and fix fence grill out of RHS 40x40x3mm and RHS 20x20x2mm including one coat of anti rust paint and three coats of oil paint (size 200x120cm) | m2 | 1300 | 181 | 235300 | 151.2 | 196560 | 196560
3.7 | Supply and fix fence with 300cm high angle iron among which 50cm is bedded in foundation of size 40x40x2.5mm | m2 | 130 | 1400 | 182000 | 1704 | 221520 | 221520
TOTAL CARRIED TO SUMMARY |  |  |  |  | 1345100 |  | 1312633.5 | 0
| RAMPS | [6 empty] | 0
| 1.Excavation & Earth Work | [6 empty] | 0
1.1 | Excavation in 50cm from NGL | m3 | 70 | 10 | 700 | 43.064 | 3014.48 | 3014.48
1.2 | Stone masonry foundation wall with 50cm thick BNGL | m3 | 1250 | 10 | 12500 | 23.73 | 29662.5 | 29662.5
1.3 | Ditto but semi-dressed stone masonry 50cm thick ANGL | m3 | 1450 | 5 | 7250 | 22.14 | 32103 | 32103
1.4 | Caraway surplus excavated material | m3 | 150 | 10 | 1500 | 43.064 | 6459.6 | 6459.6
1.5 | Fill granular approved type selected | m3 | 150 | 5 | 750 | 13.882 | 2082.3 | 2082.3
1.6 | 15cm thick Hard core for ramps | m2 | 200 | 4 | 800 | 99.88 | 19976 | 19976
| 2 Concrete Work | [5 empty] | 0 | 0
2.1 | 5cm thick lean concrete | m2 | 150 | 5 | 750 | 69.1 | 10365 | 10365
2.2 | 10cm thick reinforced concrete slab | m2 | 400 | 25 | 10000 | 177.48 | 70992 | 70992
2.3 | Diam. 8mm | Kg | 36 |  |  | 554.422 | 19959.192
2.4 | 12.5cm thick reinforced concrete laid stone mass | m2 | 390 | 10 | 3900 |  | 0 | 0
TOTAL CARRIED TO SUMMARY |  |  |  |  | 38150 |  | 194614.072 | 0
| Ash and Needle Pits | [6 empty] | 0
| 1.Excavation & Earth Work | [6 empty] | 0
1.01 | Bulk excavation for average depth of 150mm | m3 | 337.53 | 84 | 28352.52 | 23.925 | 8075.4052 | 8075.4052
1.02 | Ditto but not exceeding a depth of 300cm | m3 | 337.53 | 84 | 28352.52 | 20.735 | 6998.6845 | 6998.6845
1.03 | Ditto but not exceeding a depth of 450cm | m3 | 70 | 84 | 5880 | 0 | 0 | 0
1.04 | Carteaway | m3 | 150 | 0 | 0 | 44.66 | 6699
| 2 Block Work | [5 empty] | 0 | 0
2.01 | 50cm thick hard trachytic or equivalent stone | m3 | 1450 | 80 | 116000 |  | 0 | 0
| 3 Concrete Work | [5 empty] | 0 | 0
3.01 | Reinforced concrete top slab class C-20 with thickness of 150mm | m3 | 2600 | 3.75 | 9750 |  | 0 | 0
3.02 | In top slab and manhold cover reinforcement-dim 8mm | Kg | 36 | 63 | 2268 |  | 0 | 0
3.02 | In top slab and manhole cover reinforcement -diam 12mm | Kg | 36 | 85 | 3060 |  | 0 | 0
3.03 | Provide, cut and fix in posiion zigba wood | m2 | 120 | 16 | 1920 |  | 0 | 0
TOTAL CARRIED TO SUMMARY |  |  |  |  | 195583.04 |  | 21773.0898 | 0
| Placenta Pit | [6 empty] | 0
| 1.Excavation & Earth Work | [6 empty] | 0
1.01 | Excavation for pit not exeeding 150cm | m2 | 669.75 | 73.983 | 49550.1143 | 45.375 | 30389.9062 | 30389.9062
1.02 | Ditto but over 150cm | m3 | 687.97 | 145 | 99755.65 | 32.5 | 22359.025 | 22359.025
1.03 | Back fill, around retaining wall | m3 | 70 | 37.856 | 2649.92 | 0 | 0 | 0
1.04 | Cartaway surplus | m3 | 70 | 116.246 | 8137.22 | 77.875 | 5451.25 | 5451.25
| 2 Concrete Work | [5 empty] | 0 | 0
2.01 | 5cm thick lean concrete | m2 | 150 | 49.322 | 7398.3 |  | 0 | 0
2.02 | Reinforced concrete in class C-20 | [5 empty] | 0 | 0
| a) in 15cm thick RC top slab | m2 | 2600 | 3 | 7800 |  | 0 | 0
2.03 | From work | [5 empty] | 0 | 0
| b) RC top slab | m2 | 120 | 20 | 2400 |  | 0 | 0
2.04 | Mild steel Reainforcement | [5 empty] | 0 | 0
| c) Diam. 8mm | Kg | 36 | 40 | 1440 |  | 0 | 0
| d) Diam. 10mm | Kg | 36 | 165 | 5940 |  | 0 | 0
| e) Diam. 12mm | Kg | 36 |  |  |  | 0 | 0
| 3 Masonry Work | [5 empty] | 0 | 0
3.01 | Trychitic or equivalents stone mortared masonry retaining wall | m2 | 1450 | 57.98 | 84071 |  | 0 | 0
| 4 Pipe Work | [5 empty] | 0 | 0
4.01 | Dia. 110mm PVC pipe with vent | ml | 120 | 2.8 | 336 |  | 0 | 0
TOTAL CARRIED TO SUMMARY |  |  |  |  | 269478.2043 |  | 58200.1813 | 0
Incinanator
1.Excavation & Earth Work
1.1 | Remove top soil | M 2 | 8 | 21.07 | 168.56 | 0 | 0
1.3 | Bulk Excavation with thickness of 75cm | M 2 | 70 | 4.95 | 346.5 | 37.5 | 2625
1.5 | Cart away | M 2 | 70 | 4.95 | 346.5 | 37.5 | 2625
1.6 | 25cm thick hard core | M 2 | 120 | 6.59 | 790.8 |  | 0
TOTAL CARRIED TO SUMMARY |  |  |  |  | 1652.36 |  | 5250 | 0
| 4- Covered walk way | [6 empty] | 0
| A. Sub structure | [6 empty] | 0
| 1.Excavation & Earth Work | [6 empty] | 0
1.1 | Removoval of top soil | m2 | 8 | 450.23 | 3601.84 | 102.5 | 820 | 820
1.2 | Excavation of black cottons soil up to 35cm | m3 | 70 | 162.08 | 11345.6 |  | 0 | 0
1.3 | Excavation of trench | m3 | 70 | 180.09 | 12606.3 |  | 0 | 0
1.4 | Selected material back fill | m3 | 150 | 108.05 | 16207.5 |  | 0 | 0
1.5 | Cart away | m3 | 70 | 477.24 | 33406.8 |  | 0 | 0
1.6 | Hard core | m2 | 120 | 360.18 | 43221.6 | 71.2 | 8544 | 8544
| 2 Concrete Work | [5 empty] | 0 | 0
2.1 | C-15 lean concrete | m2 | 150 | 180.09 | 27013.5 | 35.6 | 5340 | 5340
2.2 | C-25 RC Concrete in grade beam | m3 | 3200 | 18.01 | 57632 | 7.12 | 22784 | 22784
2.3 | C-15 concrete slab | m2 | 295 | 360.18 | 106253.1 | 71.2 | 21004 | 21004
2.4 | Form work | m2 | 120 | 180.09 | 21610.8 | 56.96 | 6835.2 | 6835.2
2.5 | Steel reinforcment | [5 empty] | 0 | 0
| a) Diameter 12 plain bars | Kg | 36 | 1320.66 | 47543.76 | 385.7472 | 13886.8992 | 13886.8992
| b) Diameter 8 deformed bars | Kg | 36 | 1500.75 | 54027 | 412.538 | 14851.368 | 14851.368
| c) Diameter 6 deformed bars | Kg | 36 | 324.16 | 11669.76 |  | 0 | 0
3.1 | Masonery wall below NGL | m3 | 1450 | 180.09 | 261130.5 |  | 0 | 0
| B. Super Structure | [5 empty] | 0 | 0
| 3 Steel structure | [5 empty] | 0 | 0
| Supply & fix steel structure fabricated according to drawing | [5 empty] | 0 | 0
3.1 | Diam 60mm CHS post 2.5mm | Kg | 30 | 1740.87 | 52226.1 | 52.74 | 1582.2 | 1582.2
3.2 | Plates (150mm*150mm) | No | 30 | 300 | 9000 | 26 | 780 | 780
3.3 | Ancher 'J' bolts | [5 empty] | 0 | 0
| a. diam 16mm length 30cm | No | 30 | 600 | 18000 | 104 | 3120 | 3120
3.4 | 40x60x2.5mm RHS | Kg | 30 | 1296.65 | 38899.5 | 313.2 | 9396 | 9396
3.5 | 40x30x2mm RHS for upper & lower trusses | Kg | 30 | 1476.74 | 44302.2 | 84.15 | 2524.5 | 2524.5
3.6 | Ditto but 30x20x2mm | Kg | 30 | 384.19 | 11525.7 | 2.72 | 81.6 | 81.6
| 4 Roofing | [5 empty] | 0 | 0
4.1 | Roof cover G-30 C-I-S including roof | m2 | 165 | 630.32 | 104002.8 |  | 0 | 0
| Eucalyptus truss | [5 empty] | 0 | 0
| 1. 5x7cm sawn zigba wood purlin wood | ml | 50 | 1320.66 | 66033 |  | 0 | 0
TOTAL CARRIED TO SUMMARY |  |  |  |  | 1051259.36 |  | 111549.7672 | 0
4722112.4183

## Site TOS
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Site Work
Client: - ANRS Health Bureau
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 10.4- General Site Work | 1 | 2.5
|  |  | 10.4.16- Septic Tank |  | 53.5
1 | 2 |  |  |  | 0.6 | 80.25
|  | 2 | No net number
|  |  |  | 1 | 60 |  | From main Gate to Emer.
|  |  | 10.4.18- Soak away pit |  | 6
1 | 4 |  |  |  | 0.31 | 111.6
|  | 4 | No net number
|  |  |  | 1 | 30 |  | curve area at Waiting
|  |  | 10.4.19- Dry latrine |  | 18
1 | 3 |  |  |  | 0.31 | 167.4
|  | 3 | No net number
|  |  |  | 1 | 20 |  | curve area at Emergency
|  |  | Electrical Site Work |  | 10
|  |  | 3- Manhole & Ducts |  | 0.59 | 118
3.1- Manhole in Masonary
|  |  | 3.1.2- 1000*1000*700mm |  |  | 671.6125 | m3 net volume
6 | 1 | 6 | No net number
11.1.2- Cart away
|  |  | 3.1.3- 600*600*500mm |  |  |  | Ditto item No 11.1.1
3 | 1 | 3 | No net number |  |  | 671.6125 | m3 net volume
|  |  | 4.00. FEEDER CABLES |  |  |  | 11.2- Sub base course
|  |  | 4.6. 3x50/25mm |  |  |  | 11.2.1 Sub Base Coarse
1 | 131 |  |  | 1 | 1.5
|  | 131 | m net length |  | 26.9 | 40.35
|  |  | 4.7. 4x10mm | 1 | 2.25
1 | 154 |  |  |  | 7.15 | 16.0875
|  | 154 | m net length
|  |  |  | 1 | 1.5
|  |  | Walk Way |  | 10.5 | 15.75
11.1- Excavation & Earth Work
|  |  | 11.1.1- Bulk Excavation | 1 | 2.5 |  | From IPD & Kitchen through
|  |  | From OR through Dry latrine |  | 17.7 | 44.25 | Morgue to Ash & Needle pit
to Generator House
1 | 1.5 |  |  | 1 | 2.5
| 26.9 |  |  |  | 51.5 | 128.75
| 0.6 | 24.21
|  |  |  | 1 | 2.5
1 | 2.25 |  |  |  | 31.5 | 78.75
7.15
| 0.6 | 9.6525 |  | 1 | 2.5
[5 empty] | 53.5 | 133.75
1 | 1.5
| 10.5 |  |  | 1 | 60 |  | From main Gate to Emer.
| 0.6 | 9.45 |  |  | 6 | 360
1 | 2.5 |  | From IPD & Kitchen through | 1 | 30 |  | curve area at Waiting
| 17.7 |  | Morgue to Ash & Needle pit |  | 18 | 540
| 0.6 | 26.55
1 | 2.5 |  |  | 1 | 20 |  | curve area at Emergency
| 51.5 |  |  |  | 10 | 200
| 0.6 | 77.25
1 | 2.5 |  |  |  |  | 1557.6875 | m3 net volume
31.5
| 0.6 | 47.25
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 11.4.2/ Apply mass concret |  |  |  | 3.06- Fence Grill
1 | 125.2 |  | from Ipd to morge to ash needle pit | 63 | 2
| 2.5 | 313 |  |  | 1.2
[6 empty] | 151.2 | m2 net arae
1 | 31.5
| 2.5 | 78.75 | from kitchen to morgue |  |  |  | 3.07 Supply and fix fence with 300cm high angle iron
|  |  |  | 1 | 310 |  | Rear Side
1 | 37.4 |  | from or to generator |  | 3 | 930
| 1.5 | 56.1
|  |  |  | 1 | 144
1 | 7.15 |  | b/n drylatrines |  | 3 | 432
| 2.25 | 16.0875
|  |  |  | 1 | 114
|  | 463.9375 | Total item to 11.4.2 |  | 3 | 342
|  |  | 11.5/ constraction of curb stone |  |  | 1704 | m3 Total to item 3.07
1 | 147 | 147 | from entrance to emergency & waiting
RAMPS
1 | 178 | 178 | from Ipd to morge& from kitchen to morgue |  |  |  | 1/Excavation &masonary work
1.1/Excavation in 50cm from NGL
1 | 23 | 23 | from opd toilet | 2 | 7
0.8
|  | 348 | Total item to 11.5 |  | 0.35 | 3.92 | from Block OR&Delivery
|  |  | Fence Work | 2 | 10
|  |  | 1. Fence |  | 0.8
|  |  | 3.1. Excavation & Earth Work |  | 0.35 | 5.6 | Opd
1 | 263
| 1 |  |  | 2 | 12
| 0.5 |  |  |  | 0.8
|  | 131.5 |  |  | 0.35 | 6.72 | from Block Waiting to Opd
|  |  | 3.02 Cart away surplus material | 2 | 11
|  | 131.5 |  |  | 0.8
[5 empty] | 0.35 | 6.16 | Waiting Blockinterance side
1 | 263 |  | Back Fill around Masonery Work
| 1 |  |  | 2 | 7
| 0.5 |  |  |  | 0.8
|  | 131.5 |  |  | 0.35 | 3.92 | from Block morge
|  |  | 3.03. Stone Masonery | 2 | 7.6
1 | 250 |  | BNGL |  | 0.8
| 0.5 |  |  |  | 0.35 | 4.256 | from Block Emergancy
| 0.5 | 62.5 | Total item to 3.03
|  |  |  | 3 | 5
|  |  | 3.04. Stone Masonery |  | 0.8
1 | 250 |  | ANGL |  | 0.35 | 4.2 | from Block Emergancy Verenda
0.8
| 0.5 | 100 | Total item to 3.04 | 10 | 2
0.8
|  |  | 3.05) 50cm thick dressd masonary pilars |  | 0.35 | 5.6 | from Block Kitchen
77 | 1.24
| 0.5 |  |  | 2 | 4.8
| 0.5 |  |  |  | 0.8
|  | 23.87 | Total item to 3.05 |  | 0.35 | 2.688 | from Block Generator
[6 empty] | 43.064 | Total item 1.1
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 1.2/stone masonary | 2 | 7
|  |  | foundation 50cm thick below NGL |  | 0.5
2 | 7 |  |  |  | 0.3 | 2.1 | from Block morge
0.5
| 0.3 | 2.1 | from Block OR&Delivery | 2 | 4.8
0.5
2 | 10 |  |  |  | 0.3 | 1.44 | from Block Generator
0.5
| 0.3 | 3 | from Block Opd | 2 | 7
0.5
2 | 12 |  |  |  | 0.2 | 1.4 | from block Emergancy
0.5
| 0.3 | 3.6 | from block waiting | 3 | 5
0.5
2 | 11 |  |  |  | 0.3 | 2.25 | Emeregency verenda ramp
0.5
| 0.3 | 3.3 | Waiting but interance side | 4 | 2
0.5
2 | 7 |  |  |  | 0.3 | 1.2 | from Block kitchen
0.5
| 0.3 | 2.1 | from Block morge | 6 | 2
0.5
2 | 7 |  |  |  | 0.2 | 1.2 | from Block kitchen
0.5
| 0.3 | 2.1 | from Block Generator |  |  | 22.14 | Total item to 1.3
2 | 7.6 | [5 empty] | 1.4/ Cartaway
| 0.5 | [5 empty] | Ditto item no 1.10
| 0.3 | 2.28 | from Block Emergancy |  |  | 43.064 | Total item to 1.4
3 | 5 | [5 empty] | 1.5/fill under hard core
| 0.5 |  |  | 1 | 7 |  | 25cm ave.depth - 15 cm hard core
| 0.3 | 2.25 | emergency verenda ramp |  | 1.4
[5 empty] | 0.1 | 0.98 | from Block OR&Delivery
10 | 2
| 0.5 |  |  | 1 | 10 |  | 40cm ave.depth - 15 cm hard core
| 0.3 | 3 | from Block kitchen |  | 1.4
[5 empty] | 0.25 | 3.5 | from Block OPD
|  | 23.73 | Total item to 1.2
|  |  |  | 1 | 12 |  | 20cm ave.depth - 15 cm hard core
|  |  | 1.3/Ditto above but semi dressed masonary Above NGL |  | 2
|  |  | Masonary above NGL |  | 0.05 | 1.2 | from Block Opd to waiting
2 | 7
| 0.5 |  |  | 1 | 11 |  | 40cm ave.depth - 15 cm hard core
| 0.25 | 1.75 | from Block OR&Delivery |  | 1.4
[5 empty] | 0.25 | 3.85 | Waiting block
2 | 10
| 0.5 |  |  | 1 | 7 |  | 30cm ave.depth - 15 cm hard core
| 0.4 | 4 | from Block Opd |  | 1
[5 empty] | 0.15 | 1.05 | from Block morge
2 | 12
| 0.5 |  |  | 1 | 7.6
| 0.2 | 2.4 | from Block Waiting To Opd |  | 1.8
[5 empty] | 0.15 | 2.052 | from Block Emergancy
2 | 11
0.5
| 0.4 | 4.4 | Waiting Blockbut interance side
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 5 | [5 empty] | 2.2/10cm thick reinforced concrete slab
| 5 |  |  | 1 | 7
| 0.05 | 1.25 | emergency verenda ramp |  | 2.4 | 16.8 | from Block OR&Delivery
|  | 13.882 | Total item to 1.5 | 1 | 10
[5 empty] | 2.4 | 24 | from Block OPD
1.6/ 15cm thick hard core
1 | 7 |  |  | 1 | 12
| 1.4 | 9.8 | from Block OR&Delivery |  | 3 | 36 | from Block Opd to waiting
1 | 10 |  |  | 1 | 11
| 1.4 | 14 | from Block Opd |  | 2.4 | 26.4 | Ditto above but interance side
1 | 12 |  |  | 1 | 7
| 2 | 24 | from Block Opd to waiting |  | 2 | 14 | from Block morge
1 | 11 |  |  | 1 | 7
| 1.4 | 15.4 | ditto above |  | 2.4 | 14 | from Generator block
1 | 7 |  |  | 1 | 5
| 1 | 7 | from Block morge |  | 5 | 25 | from Block Emergancy
1 | 7.6 |  |  | 1 | 7.6
| 1.8 | 13.68 | from Block Emergancy |  | 2.8 | 21.28 | from Block Emergancy
1 | 4 |  |  |  |  | 177.48 | Total item to 2.2
| 4 | 16 | Ditto above
ASH AND NEEDLE PIT
|  | 99.88 | Total item to 1.6 |  |  |  | 1) Excavation and Earth Work
1.01) Bulk Excavation on ordinary soil 150 cm
|  |  | 2/concrete work | 1 | 5.5 |  | Soft Rock
|  |  | 2.1) 5cm thick lean concrete for masonary work |  | 2.9
2 | 7 |  |  |  | 1.5
| 0.5 | 7 | from Block OR&Delivery |  |  | 23.925 | Total item to 1.01
2 | 10 |  |  | 1 | 5.5 |  | 1.2) Ditto but not exceeding a depth of 300 cm
| 0.5 | 10 | from Block OPD |  | 2.9 |  | Soft Rock
1.3
2 | 12 |  |  |  |  | 20.735 | Total item to 1.02
| 0.5 | 12 | from Block Opd to waiting
|  |  |  | 1 | 5 |  | 1.3) Ditto but not exceeding a depth of 450 cm
2 | 11 |  |  |  | 5
| 0.5 | 11 | Ditto above but interance side |  | 0
[6 empty] | 0 | Total item to 1.03
2 | 7
| 0.5 | 7 | from Block morge |  |  |  | 1.04) Cartaway
2 | 7 |  |  |  |  | 44.66 | Total item to 1.04
| 0.5 | 7 | from Generator block
PLACENTAL PIT
3 | 5 | [5 empty] | 1) Excavation and Earth Work
| 0.5 | 7.5 | from Block Emergancy | 1 | 5.5 |  | 1.01) Bulk Excavation on ordinary soil 150 cm
[5 empty] | 5.5 |  | Hard Rock
2 | 7.6 |  |  |  | 1.5
| 0.5 | 7.6 | from Block Emergancy |  |  | 45.375 | Total item to 1.01
|  | 69.1 | Total item to 2.1
T | D | S | Item No. and Description | T | D | S | Item No. and Description
1 | 5 |  | 1.2) Ditto but not exceeding a depth of 300 cm |  |  |  | 2.4- Formwork
| 5 |  | Hard Rock | 4 | 35.6
| 1.3 |  |  |  | 0.4
|  | 32.5 | Total item to 1.02 |  |  | 56.96 | m2 net area
1 | 5 |  | 1.3) Ditto but not exceeding a depth of 450 cm |  |  |  | 3- Steel Structure
| 5 | [5 empty] | 3.1- Dia. 6omm CHS Post
| 0 |  |  | 6 | 3
|  | 0 | Total item to 1.03 |  |  | 52.74 | kg net weight
|  |  | 1.04) Cartaway |  |  |  | 3.2 plate
|  |  |  | 26 | 1
|  | 77.875 | Total item to 1.04 |  |  | 26 | No net number
|  |  | INCINANATOR |  |  |  | 3.3- Ancher J bolt
|  |  | 1) Excavation and Earth Work | 26 | 4
1 |  |  | 1.1) Removal of Top Soil |  |  | 104 | No net number
|  | 0 | Total item to 1.01 |  |  |  | 3.4- 40*60*2.5mm RHS
|  |  |  | 2 | 43.5
1 | 5 |  | 1.3) Bulk Excavation on ordinary soil 750 cm |  |  | 87 | ml
5
| 1.5 |  |  |  |  | 313.2 | kg net weight
|  | 37.5 | Total item to 1.02
3.5.-40x30x2mm RHS
|  |  | 1.05) Cartaway | 5 | 5.1
[6 empty] | 25.5 | ml
|  | 37.5 | Total item to 1.05
[6 empty] | 84.15 | kg net weight
4- Covered Walk Way
|  |  | A- Sub Structure |  |  |  | 3.5.-40x30x2mm RHS
|  |  | 1- Excavation & Earth Work | 5 | 0.4
|  |  | 1.1- Removal of Top Soil |  |  | 2 | ml
1 | 41
| 2.5 |  |  |  |  | 2.72 | kg net weight
|  | 102.5 | m2 net area
1.6- Hard Core
1 | 35.6
2
|  | 71.2 | m2 net area
2- Concrete Work
2.1- Lean Concrete
2 | 0.5
35.6
|  | 35.6 | m2 net area
2.2- C-25 in Grade Beams
2 | 35.6
0.25
0.4
|  | 7.12 | m3 net volume
2.3- Concrete Slab
1 | 35.6
2
|  | 71.2 | m2 net area

## Ramp & Covered Way Rein.
Project:- WEGEDA PRIMARY HOSPITAL
Contractor:- TRUST CONSTRUCTION
Consultant:- ADSWE
Client:- ANRHB
[5 empty] | Block :- |  | Ramp
Location | Dia. (mm) | Length(m) | No of bars | Members | Diameter of RC Bar
[5 empty] | 6 | 8 | 10 | 12 | 14
OPD | 8 | 12 | 13 | 1 | " | 156 | " | " | "
| 8 | 2.4 | 61 | 1 | " | 146.4 | " | " | "
[5 empty] | " | " | " | " | "
OR & Delivery | 8 | 7 | 13 | 1 | " | 91 | " | " | "
| 8 | 2.4 | 36 | 1 | " | 86.4 | " | " | "
[5 empty] | " | " | " | " | "
Waiting | 8 | 11 | 13 | 1 | " | 143 | " | " | "
| 8 | 2.4 | 56 | 1 | " | 134.4 | " | " | "
[5 empty] | " | " | " | " | "
Wating to OPD | 8 | 12 | 16 | 1 | " | 192 | " | " | "
| 8 | 3 | 61 | 1 | " | 183 | " | " | "
[5 empty] | " | " | " | " | "
Morgue | 8 | 7 | 11 | 1 | " | 77 | " | " | "
| 8 | 2 | 36 | 1 | " | 72 | " | " | "
[5 empty] | " | " | " | " | "
Generator House | 8 | 4.8 | 13 | 1 | " | 62.4 | " | " | "
| 8 | 2.4 | 25 | 1 | " | 60 | " | " | "
[5 empty] | " | " | " | " | "
|  | Total Length |  |  | 0 | 1403.6 | 0 | 0 | 0
|  | Unit Wt.(kg/mL) |  |  | 0.22 | 0.395 | 0.617 | 0.888 | 1.208
|  | Total Weight |  |  | 0 | 554.422 | 0 | 0 | 0
[6 empty] | Block:- | Covered Walk Way
Location | Dia. (mm) | Length(m) | No of bars | Members | Diameter of RC Bar
[5 empty] | 6 | 8 | 10 | 12 | 14
GRADE BEAM
From Diagno. To IPD | 12 | 13.4 | 3 | 2 | " | " | " | 80.4 | "
| 12 | 12.8 | 3 | 2 | " | " | " | 76.8 | "
[5 empty] | " | " | " | " | "
Strriup | 8 | 1.2 | 65 | 2 | " | 156 | " | " | "
[5 empty] | " | " | " | " | "
From IPD to Kitchen | 12 | 23.4 | 3 | 2 | " | " | " | 140.4 | "
| 12 | 22.8 | 3 | 2 | " | " | " | 136.8 | "
[5 empty] | " | " | " | " | "
Stirrup | 8 | 1.2 | 115 | 2 | " | 276 | " | " | "
[5 empty] | " | " | " | " | "
SLAB |  |  |  |  | " | " | " | " | "
[5 empty] | " | " | " | " | "
From Diagno. To IPD | 8 | 12.8 | 9 | 1 | " | 115.2 | " | " | "
| 8 | 2 | 53 | 1 | " | 106 | " | " | "
[5 empty] | " | " | " | " | "
From IPD to Kitchen | 8 | 22.8 | 9 | 1 | " | 205.2 | " | " | "
| 8 | 2 | 93 | 1 | " | 186 | " | " | "
[5 empty] | " | " | " | " | "
[5 empty] | " | " | " | " | "
|  | Total Length |  |  | 0 | 1044.4 | 0 | 434.4 | 0
|  | Unit Wt.(kg/mL) |  |  | 0.22 | 0.395 | 0.617 | 0.888 | 1.208
|  | Total Weight |  |  | 0 | 412.538 | 0 | 385.7472 | 0

## Variation
Project: - Wogeda Primary Hospital | [5 empty] | Date: - | 2016-02-23
Contractor: - Trust Construction
Consultant: - Amhara Design & Supervision Works Enterprise | [5 empty] | Block: - Site Work
Client: - ANRS Health Bureau | [5 empty] | Variation Work
T | D | S | Item No. and Description | T | D | S | Item No. and Description
|  |  | 10.4- General Site Work |  |  |  | C-25 Concrete
|  | 10.4.4 | Hard Rock Excavation for uPVC, PN-4 pipe for waste water drinage from the manhole to the septic tank. |  |  |  | 10.4.15.6. 16cm thick floor slab
1 | 38.6 |  | From OPD Through Lattrin to Septic Tank | 1 | 3
| 0.5 |  | Avg Depth 0.5m |  | 3
| 0.3 | 5.79 |  |  | 0.16
[6 empty] | 1.44 | m3 net volume item 10.4.15.6
1 | 33.8 |  | IPD Block
| 0.6 |  | Avg Depth 0.6m |  |  |  | 10.4.15.7. In Grade Beams
| 0.3 | 6.084 |  | 4 | 3
3
1 | 44.3 |  | OR Block |  | 0.3
| 0.4 |  | Avg Depth 0.4m |  |  | 10.8 | m3 net volume item 10.4.15.7
| 0.3 | 5.316
10.4.15.8. In Footing Pad
1 | 22.7 |  | From Emer. through Lattrin to Septic Tank | 4 | 1.2
| 0.5 |  | Avg Depth 0.5m |  | 1.2
| 0.3 | 3.405 |  |  | 0.4
[6 empty] | 2.304 | m3 net volume item 10.4.15.8
|  | 20.595 | m3 net volume
10.4.15.9. In Footing Column
|  |  | 10.4.15. Elevated Water Tank | 4 | 1.2
|  |  | Excvation & Earth Work |  | 1.2
|  |  | 10.4.15.1. Site Clearance |  | 0.25
1 | 6.45 |  |  |  |  | 1.44 | m3 net volume item 10.4.15.9
6.45
|  | 41.6025 | m2 net area item 10.4.15.1 |  |  |  | 10.4.15.10. In Elevation Column
|  |  |  | 12 | 0.2
|  |  | 10.4.15.2. Pit Excavation |  | 0.2
4 | 1.7 |  |  |  | 4
| 1.7 |  |  |  |  | 1.92 | m3 net volume item 10.4.15.10
2
|  | 23.12 | m3 net Volume Item 10.4.15.2 |  |  |  | 10.4.15.11. In Roof
|  |  |  | 2 | 3.5
|  |  | 10.4.15.3. Back Fill around Footing |  | 0.1
4 | 1.2 |  |  |  | 0.4
| 1.2 |  |  |  |  | 0.28 | m3 net volume item 10.4.15.11
1.6
|  | 9.216 | m3 net Volume Item 10.4.15.3 |  |  |  | Form work
10.4.15.12. 16cm thick floor slab
|  |  | 10.4.15.4. Cartaway | 1 | 3
1 | 41.6025 |  | Item 10.4.15.1 |  | 3
| 0.3 | 12.4807 |  |  |  | 9 | m2 net area item 10.4.15.12
1 | 23.12 |  | Item 10.4.15.2 |  |  |  | 10.4.15.13. In Grade Beams
|  | 23.12 |  | 2 | 3
[5 empty] | 0.4 | 2.4
|  | 35.6007 | m3 net Volume Item 10.4.15.4
|  |  |  | 1 | 3
|  |  | Concrete Work |  | 0.25 | 0.75
10.4.15.5. Lean Concrete
4 | 1.3 |  | Under Footing Pad | 20 | 3
| 1.3 | 6.76 |  |  | 0.3 | 18
4 | 3 |  | Under Grade Beam | 4 | 3
| 0.25 | 3 |  |  | 0.14 | 1.68
|  | 9.76 | m2 net area item 10.4.15.5
T | D | S | Item No. and Description | T | D | S | Item No. and Description
10 | 3 | [5 empty] | 3.2- Concrete Pipe dai. 10cm
| 0.25 | 7.5 |  |  |  |  | Right side of OR
|  |  |  | 2 | 31.8
|  | 30.33 | m2 net area item 10.4.15.13 |  |  | 63.6
around fence and to morgue
|  |  | 10.4.15.14. In Footing Pad | 1 | 211
16 | 12 |  |  |  |  | 211
| 0.4 | [5 empty] | staff to generator
|  | 76.8 | m2 net area item 10.4.15.14 | 1 | 91
91
10.4.15.15. In Footing Column
16 | 1.2 |  |  |  |  | 365.6 | m net length
0.25
|  | 4.8 | m2 net area item 10.4.15.15
10.4.15.16. In Elevation Column
12 | 4
0.25
|  | 12 | m2 net area item 10.4.15.16
10.4.15.17. In Roof
4 | 3.5
0.4
|  | 5.6 | m2 net area item 10.4.15.17

## Elev. Water Tank Rein.
Project:- WEGEDA PRIMARY HOSPITAL
Contractor:- TRUST CONSTRUCTION
Consultant:- ADSWE
Client:- ANRHB
[5 empty] | Block :- |  | Elevated Water Tank
Location | Dia. (mm) | Length (m) | No of bars | Members | Diameter of RC Bar
[5 empty] | 6 | 8 | 10 | 12 | 14
Footing Pad | 12 | 1.3 | 6 | 4 | " | " | " | 31.2 | "
| 12 | 1.3 | 6 | 4 | " | " | " | 31.2 | "
In Footing Column | 14 | 3 | 4 | 4 | " | " | " | " | 48
Sttriup | 8 | 1 | 12 | 4 | " | 48 | " | " | "
In Grade Beam | 12 | 4 | 6 | 4 | " | " | " | 96 | "
| 12 | 3.85 | 6 | 8 | " | " | " | 184.8 | "
| 14 | 3.85 | 6 | 4 | " | " | " | " | 92.4
Sttriup | 8 | 1.5 | 16 | 16 | " | 384 | " | " | "
In Elevation Column | 14 | 4 | 4 | 3 | " | " | " | " | 48
| 14 | 3.6 | 4 | 1 | " | " | " | " | 14.4
Sttriup | 8 | 1 | 19 | 4 | " | 76 | " | " | "
Roof Slab | 12 | 5.49 | 21.43 | 1 | " | " | " | 117.6507 | "
| 12 | 5.49 | 21.43 | 1 | " | " | " | 117.6507 | "
| 12 | 3 | 2 | 2 | " | " | " | 12 | "
[5 empty] | " | " | " | " | "
[5 empty] | " | " | " | " | "
[5 empty] | " | " | " | " | "
[5 empty] | " | " | " | " | "
[5 empty] | " | " | " | " | "
|  | Total Length |  |  | 0 | 508 | 0 | 590.5014 | 202.8
|  | Unit Wt.(kg/mL) |  |  | 0.22 | 0.395 | 0.617 | 0.888 | 1.208
|  | Total Weight |  |  | 0 | 200.66 | 0 | 524.3652 | 244.9824